## Open Action Items
Action Item List - Open Items |  |  | Start new: | 2005-05-24
OSG WebPortal |  |  | Updated: | 2005-06-07
|  |  | PC= | Penelope Constanta | JF= | Jim Fromm
|  |  | MH = | Mari Herrera | MM= | Marc Mengel
|  |  | RP= | Ruth Pordes
|  |  | MT = | Marcia Teckenbrock
|  |  | KY= | Katie Yurkewicz
*****ONE TIME TASKS*****
Action Item | By Whom | Current Date | Target date | Status/Actions/Issues | Effort
Write Project Definition | MT |  | 6.10.05 | not done. New target | 1/4 day
Catalog pages to get a feel for types of information that is out there. | MT, MH |  | 6.10.05 | Marcia will make a list, Mari will review | 1/4 day
MailLists - define for project plan and send to Marcia | MH |  | 6.10.05 |  | 1/4 day
Meet with Indiana folks to discuss deliverables for this Project. | PC, MH, RP, MT |  |  | Monday, June 13th proposed. Marcia cannot make it. | 1 day
New web template | MT |  | 7.20.05 | new template approved with some modifications; Marcia will transfer to Plone site | 2 weeks
Encourage CSS to revamp Plone help pages | PC |  | 6.30.05 | Jim Fromm and Marc Mengel are working on this. Target date is for the documentation to be complete.
Document Views for Each Technical Group with Query Results | MT |  | 7.10.05 |  | < 1 day?
Test Eric's API | PC/MT |  | 7.17.05
*****OPERATIONS (ONGOING ITEMS)*****
Action Item | By Whom |  |  | Status/Actions/Issues | Effort
OSG/Plone Web Maintenance | MH/MT |  |  |  | MT: 40%, MH: 30-50%
MailList Support | MH |  |  |  | 5-10%
Determine Document Views Needed and give to Marcia | RP, PC

## Closed Action Items
Action Item List - Closed Items
<project name>
ID | Action Item | By Whom | Finished | Status/Actions Taken

## WBS
WBS for <project name>
|  | Last Update: | <date>
Date to
ID | WBS Item/Subitems | Status | Complete | Team Involved
1 | <WBS Item>
1.1 | <sub item>
1.2 | <sub item>
1.3 | <sub item>
1.4 | <sub item>
1.5 | <sub item>
2 | <WBS Item>
<etc>

## Top Risks
| Top Risks Chart | <project name>
| Last Update: | date>
ID | Risk Statement |  | Prob | Loss | Exp | Risk Handling Action | Who | Date
| Condition | Consequence
1
2
3
4
5
6
7
8
9
10