## PART Qs & Section Scoring
OMB Program Assessment Rating Tool (PART)
Capital Assets & Service Acquisition Programs
Name of Program: Flood Damage Reduction
Section I: Program Purpose & Design (Yes,No)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Is the program purpose clear? | Yes | Reduce flood damages to the nation through structural, non-structural, Flood Plain Mgt, Planning Assistance and other technical assistance programs. | 1936 Flood Control Act. Supplemented by other various Flood Control, Rivers and Harbors, and Water Resource Dev. Acts over the years | 20% | 0.2
2 | Does the program address a specific interest, problem or need? | Yes | Flood damage reduction projects requested by sponsors comprise the program with each project defining a solution to a need. Program focuses on (1) reducing risk of flood damage to existing development and (2) providing technical assistance to state and local governments to prevent future flood damage. | Formal study investigations and Project Reports. Congress shows interest and need through authorizations (regular and contingent). | 20% | 0.2
3 | Is the program designed to have a significant impact in addressing the interest, problem or need? | Yes | Program is designed to reduce flood damages by means of authorized and justified projects or through technical assistance programs. | Letters, and authorizing (Water Resources Development Act) and appropriations documents. Feasibility studies are authorized in response to actual flooding or new conditions expected to lead to flooding. Projects are planned, jointly with a local sponsor to reduce damages so long as economically justified. Studies include inputs from affected Federal and State agencies and individuals. After study, projects are authorized and project reports published in Congressional Committee Reports. | 20% | 0.2
4 | Is the program designed to make a unique contribution in addressing the interest, problem or need (i.e., not needlessly redundant of any other Federal, state, local or private efforts)? | Yes | Other agencies address the same issue, but generally each has a different focus and/or different program tools, such as insurance and hazard mitigation programs. | FEMA provides hazard mitigation and insurance; Natural Resources Conversation Service used to provide small watershed projects. The Corps program is comprehensive through holistic, basin-wide, watershed-centered studies and projects. The Galloway Report called for more State involvement with the Corps and FEMA. | 20% | 0.2
5 | Is the program optimally designed to address the interest, problem or need? | No | The Corps program provides for applying solutions that (1) directly address reducing existing flood damages and (2) utilize Corps technical assistance to support other Federal and non-Federal agencies devoted to preventing flood damages. The program is a good program, but not optimal. The Corps should put more emphasis on non-structural solutions and avoid designing projects to provide 100-year protection when it may not be economically justified, but allow property owners to avoid flood insurance, and more closely coordinate its general approach with FEMA. | Recent program improvements include Corps regulation 1105-2-100 that stipulates that communities participating in a flood damage reduction project must prepare and publicize throughout the region a flood plain management plan to reduce the impact of future flood events in the project area and to make citizens aware of remaining flood risks. Also, the local sponsor is asked to ensure the level of protection provided by by the Corps projects. | 20% | 0
Total Section Score |  |  |  |  | 100% | 80%
Section II: Strategic Planning (Yes,No, N/A)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Does the program have a limited number of specific, ambitious long-term performance goals that focus on outcomes and meaningfully reflect the purpose of the program? | No | The Corps broad goal is to reduce flood and storm damage reduction in the nation. | Basically, this goal is to maintain the status quo. The Corps is working with OMB to develop specific, long-term goals that focus on outcomes. | 11.12% | 0
2 | Does the program have a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals? | Yes | The Corps' annual goals are to make flood damage reduction investments where benefits exceed costs and to ensure that projects operate as designed. Two investment performance measures include #1 the net annual benefits of flood project investments and #2 ratio of expected project benefits to actual construction costs, with a target of completing projects within their estimated costs so that actual costs are less than estimated benefits, thus maintaining a benefit-cost ratio >1. Two operating measures are the % of time flood projects carry out their purpose, with a target >95% and the % of time that projects are not operable due to maintenance needs, where the target has not yet been established. | Investment measure #1 (net benefits), should have a goal attached to it, such as maximizing program net benefits. Investment measure#2 (ratio of expected benefits to actual costs) is a cost monitoring issue. This Corps should be concerned with how are costs are managed. Even if a project remains justified (Benefit/Cost>1), the Corps should find out why costs increased. Regarding operational goal #2, the Corps uses % time storm damage infrastructure sustains its purpose as a measure and proposes to add the % of projects not operable at design level due to maintenance needs. A more outcome oriented goal for consideration would be to allocate maintenance funds where they will be most effective in preventing loss of life and damages to public and private property. | 11.11% | 0.1111
3 | Do all partners (grantees, sub-grantees, contractors, etc.) support program planning efforts by committing to the annual and/or long-term goals of the program? | Yes | Sponsors (e.g, flood control districts) make inputs and participate financially in flood studies and projects. | Reflected in cost sharing agreements for each study and project whereby sponsors participate in studies, contribute 50% of study funds, and cash, and contribute lands, easements and rights of way to project construction (up to 35%). | 11.11% | 0.1111
4 | Does the program collaborate and coordinate effectively with related programs that share similar goals and objectives? | No | The Corps cooperates on a project by project basis with related programs, as well as coordinating operating rules and regulations prior to publication with interested parties. The Corps collaborates with technical assistance program clients. However, the Corps does not meet routinely, with FEMA NRCS, and TVA to compare notes or share lessons learned about their respective programs. | Continued coordination, especially with FEMA is needed to work towards reduction in national flood damages particularly to those areas not yet protected. Evacuation plans should be effected in a comprehensive multi-agency fashion. The Corps is moving towards examining interrelated problems on a watershed basis. This approach should encourage useful collaboration. | 11.11% | 0
5 | Are independent and quality evaluations of sufficient scope conducted on a regular basis or as needed to fill gaps in performance information to support program improvements and evaluate effectiveness? | No | Project by project review with further evolution of the process with input from the National Academy of Sciences report on independent review and other Corps reviews conducted on an as needed basis. However, external reviews are not a regular part of the process. | Review process for each project requires coordination with other Federal, State and local agencies and interested parties and outside reviews are conducted on an as needed, but not a regular basis. The NAS did review the Corp's probability based flood model. | 11.11% | 0
6 | Is the program budget aligned with the program goals in such a way that the impact of funding, policy, and legislative changes on performance is readily known? | Yes | The budget is built in increments and the impact of varying increments of funding is displayed both in terms of the appropriation accounts(general investigations, construction, and operation and maintenance) as well as the impacts on each business program in the business breakout in the Program Memorandum that explains the Corps Annual Budget Request to OMB. | Each (program level) defines what is achievable with additional increments/decrements of funding for each business program, which is presented in its annual budget request. | 11.11% | 0.1111
7 | Has the program taken meaningful steps to address its strategic planning deficiencies? | Yes | The Strategic Plan is continually reviewed and revised. It includes all interested parties in the mix of commentators through publication on the "WEB." | The Corps meets with interested parties including principals from other agencies & develops specialized training to improve project development processes. The Corps needs to respond to studies like the National Wildlife Federation Frequently Flooded Lands. | 11.11% | 0.1111
8 (Cap 1.) | Are acquisition program plans adjusted in response to performance data and changing conditions? | Yes | Program development is highly dynamic with levels changing in response to varying priorities. Flood project plans and operations are based on the latest hydrographs. | ` | 11.11% | 0.1111
9 (Cap 2.) | Has the agency/program conducted a recent, meaningful, credible analysis of alternatives that includes trade-offs between cost, schedule and performance goals? | Yes | The program is based on participation by non-Federal project sponsors so it can only address food damage problems where sponsors are willing to participate. Within that universe of problem areas, the tradeoffs of cost and benefits are conducted within the project development process. | Each increment (program level) defines what is achievable with each additional increment and/or decrement of funding. | 11.11% | 0.1111
Total Section Score |  |  |  |  | 100% | 66.66%
Section III: Program Management (Yes,No, N/A)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
Questions | Does the agency regularly collect timely and credible performance information, including information from key program partners, and use it to manage the program and improve performance? | Yes | The annual Flood Damages Prevented report displays the damages prevented by project, by state and by area throughout the country. | Annual Flood Damage Prevention reports; Project delivery process includes a formal reporting on "meeting Project Sponsor commitments" which are negotiated with local sponsor each fiscal year. | 9% | 0.09
2 | Are Federal managers and program partners (grantees, subgrantees, contractors, etc.) held accountable for cost, schedule and performance results? | Yes | Corps accomplishes much of its studies and all of its construction activities by contract. Fixed price contracts tightly specify performance requirements. ER 4115-1-17 prescribes "Construction Contractor Performance Evaluations" and record of performance is recorded in the Construction Contractor Appraisal Support System (CCAS) AIS and used for future construction contract bidder qualification. | Performance requirements of Federal Agency, non-Federal project sponsor and contractors performing project study and project construction activities are governed by Project Cooperation Agreements; Feasibility Cost sharing Agreements; PED Agreements; Construction Contractor Performance Evaluations, and formal reporting on "meeting project sponsor commitments." | 9.1% | 0.091
3 | Are all funds (Federal and partners’) obligated in a timely manner and spent for the intended purpose? | Yes | A major concern of the Corps within the Flood Damage reduction program (and others) is the efficient obligation and expending of funds and the Corps is most diligent in the tracking of such expenditures. | Project Review Boards & Resource Management Boards Monitor Performance measures as dictated by consolidated command guidance and other directives. 87% of available funds are obligated. | 9.1% | 0.091
4 | Does the program have incentives and procedures (e.g., competitive sourcing/cost comparisons, IT improvements) to measure and achieve efficiencies and cost effectiveness in program execution? | Yes | (1) Each project undergoes value engineering analysis to identify ways to construct project at less cost and more efficiently. (2) The principle of cost sharing with non-Federal project sponsors results in a strong incentive to achieve cost efficiencies and an effective project. | (a) Cost sharing agreements for all phases of work. (b) Value engineering evaluation prior to project construction which is done to assure the a project responds to the need in the most efficient and cost-effective manner. | 9.1% | 0.091
5 | Does the agency estimate and budget for the full annual costs of operating the program (including all administrative costs and allocated overhead) so that program performance changes are identified with changes in funding levels? | Yes | Project costs are budgeted incrementally (both studies and construction) with the full costs budgeted over a period of years. This procedure is pursuant to 33 US Code 621 and authorized in the River and Harbors Act of 1922. | The Corps does not use the count retirement costs funded through the Office of Personnel Management, but has consistently allocated costs among construction projects. The Corps absorbs executive direction (headquarters, etc) in the general expenses account. All other costs are allocated to projects. | 9.1% | 0.091
6 | Does the program use strong financial management practices? | Yes | The Corps has a real time database (CEFMS) which tracks appropriated, scheduled, and expended funds. Projects which are behind schedule may have funds reprogrammed to other projects. The Corps has been making substantial progress in producing sound annual financial statements. Its major obstacle is in determining the original cost of existing plant, property, and equipment, which affects its balance sheet. Funds are distributed by HQUSACE under the appropriate class/category for a given activity as outlined in ER 11-1-320. | HQUSACE continually monitors the status of distributed FCCE funds and recalls any unobligated balances on a periodic basis. Funds for the repair of damaged FCW are distributed by phases, as outlined in all Project Information Reports (PIR) (i.e. investigation, engineering and design, construction). ER500-1-1 states that repairs to FCW under this program requires local/federal cost share and a positive benefit/cost ratio and assistance provided during emergency operations are supplemental to state/local efforts. Funds for inspections of FCW in this program are budgeted and distributed every other year based on inspection schedules. |  | #VALUE!
7 | Has the program taken meaningful steps to address its management deficiencies? | Yes | The Corps uses yearly evaluations at the national, regional, and field operations levels to identify and correct management deficiencies. | Management deficiencies are identified through a proven internal control procedure developed by the Corps management audit program and governed by and Engineer Regulation. This management control system is common to all business programs in the Corps. This program and yearly evaluation is applied at the national program level, the regional level, and the field operations level. There are mandatory corrective actions as a result of this program. | 9.1% | 0.091
8 (Cap 1.) | Does the program define the required quality, capability, and performance objectives of deliverables? | Yes | Done on a project by project basis. Examples of defining documents that contain the relevant elements can be provided | Project by project, these factors are defined in the Feasibility Cost Sharing Agreements, Project Cost Sharing Agreements, and Design Agreements signed by the Corps and Non-Federal project cost sharing partners. Detailed Plans and Specifications specify the scope of construction performance requirements which govern contractor performance. | 9.1% | 0.091
9 (Cap 2.) | Has the program established appropriate, credible, cost and schedule goals? | No | When formulating proposed investments, the Corps assumes schedules that do not reflect likely funding constraints. Where total project costs exceed estimates by 20% in real terms, the Corps will examine the discrepancy. The Corps may estimate costs well, but does not routinely collect data that would support an assessment of the overall quality of its cost estimates. | Corps FY budget data contains overall expenditure and completion schedules. Internal “operating budget” at each District breaks out expenditure schedules by month. Recently, the Corps has adopted a performance measure where it compares the estimated costs of completed projects with the projected benefits to ensure that the project's benefit cost ratio is maintained. This is another way of monitoring costs and should prove useful. | 9.1% | 0
10 (Cap 3.) | Has the program conducted a recent, credible, cost-benefit analysis that shows a net benefit? | Yes | Done on a project by project basis and summed across the entire program | Project by project and kept current in that the economic analysis can be no more than 3 years old at the time a project is being considered for construction.. | 9.1% | 0.091
11 (Cap 4.) | Does the program have a comprehensive strategy for risk management that appropriately shares risk between the government and contractor? | No | The Corps does not use performance-based contracts as often as it should. The way in which it uses "continuing" contracts can constrain the ability of the government to allocate available funds the following year to a higher-priority project or purpose. | The Corps mostly uses fixed-price contracts that include safeguards to cover unsatisfactory performance. | 9.1% | 0
Total Section Score |  |  |  |  | ERROR | #VALUE!
Section IV: Program Results (Yes, Large Extent, Small Extent, No)
Questions |  | Ans. | Explanation | Evidence/Data | Weighting | Weighted Score
1 | Has the program demonstrated adequate progress in achieving its long-term outcome goal's)? | Small Extent | Some progress towards the general goal can be seen by the damages prevented by existing projects and additional benefits provided by completed new projects. | The Corps estimates that from 1991 to 2000 its projects prevented roughly $20.8 billion in flood damages. Projects under construction will yield another $1.5 billion per year in avoided damages. Despite Corps efforts, actual annual damages to the nation are increasing each year due to development in unprotected floodplains and increased runoff in protected areas due to development in upstream areas and other reasons. | 16.67% | 0.055011
| Long-Term Goal I: | Reduce flood and storm damages in Nation's flood hazard areas.
| Target: | Measures are under development
Actual Progress achieved toward goal:
Long-Term Goal II:
Target:
Actual Progress achieved toward goal:
Long-Term Goal III:
Target:
Actual Progress achieved toward goal:
2 | Does the program (including program partners) achieve its annual performance goals? | Small extent |  |  | 16.67% | 0.055011
| Key Goal I: | Investment Goal: net annual benefits association with flood program (no maximizing objective.)
| Performance Target: | no target, goal is under discussion.
Actual Performance:
| Key Goal II: | Operation and Maintenance Goal: Projects not available due to maintenance needs
| Performance Target: | 0%
| Actual Performance: | this goal is under discussion.
| Key Goal III: | Operation and Maintenance Goal: Ensure that flood protection infrastructure will function properly.
| Performance Target: | Maintain flood protection infrastructure performance through inspections and repair of any deficiencies.
| Actual Performance: | FY 00 & FY 01 all projects performed as intended when subjected to flooding, according to situational reports.
Footnote: Performance targets should reference the performance baseline and years, e.g. achieve a 5% increase over base of X in 2000.
3 | Does the program demonstrate improved efficiencies and cost effectiveness in achieving program goals each year? | Large Extent |  | Justified projects formulated based on maximizing net benefits operate to increase damages prevented each year. Corps strives to minimize operations costs. | 16.67% | 0.11169
4 | Does the performance of this program compare favorably to other programs with similar purpose and goals? | Large Extent | The Corps is unique in its mission as shown in Sec I - Q#4, but we are working to develop common inter-agency measures of performance for comparison purposes. | The Corps is working with other Federal Agencies (FEMA & NCRS) to develop common inter-agency measures. Net benefits per dollar invested is one of these. | 16.67% | 0.11169
5 | Do independent and quality evaluations of this program indicate that the program is effective and achieving results? | Yes | Corps has employed the National Academy of Sciences to do a comprehensive review of its study program procedures with the goal of improving the planning procedures. | The Corps has employed the NAS in the past to assess its planning process and has been found to be an effective process. Flood projects have not been plagued by same problems as navigation projects. | 16.66% | 0.1666
6 (Cap 1.) | Were program goals achieved within budgeted costs and established schedules? | Yes | See actual performance discussed in Key Goal II above. | Projects completed in FY 00 & FY 01 reflect reasonable performance in terms of cost management. | 16.66% | 0.1666
Total Section Score |  |  |  |  | 100% | 66.66%
Note on C4: This section examines the clarity of program purpose and related program design and looks at all factors including those the program or agency may not directly control but which are within the influence of the program or agency such as legislation and market factors. A clear understanding of program purpose is essential to setting program goals, maintaining focus, and managing the program. Potential source documents and evidence for answering questions in this section include authorizing legislation, agency strategic plans, annual performance plans, and other agency reports. Options for answers are Yes, No or Not Applicable.
Note on B6: 1. Is the program purpose clear? Purpose of the question: to determine whether the program has a focused and well-defined mission. Elements of a Yes answer: a Yes answer would require a consensus of program purpose among interested parties (e.g., Congress, Administration, public) and a clear and unambiguous mission. Considerations can include whether the program purpose can be stated succinctly. A No answer would be appropriate if the program has multiple conflicting purposes. Evidence/Data: evidence can include program authorizing legislation, program documentation or mission statement.
Note on B7: 2. Does the program address a specific interest, problem or need? Purpose of the question: to determine whether the program addresses a specific interest, problem or need that can be clearly defined and presently exists. Elements of a Yes answer: A Yes answer would require the existence of a relevant and clearly defined interest, problem or need that the program is designed to address. A Yes answer would also require that the program purpose is still relevant to current conditions (i.e., that the problem the program was created to address still exists). Considerations could include, for example, whether the program addresses a specific market failure. For research and development programs, a Yes answer would require identification of relevance to specific national needs, agency missions, fields of science or technology, or other “customer” needs. A customer may be another program at the same or another agency, an interagency initiative or partnership, or a firm or other organization from another sector or country. Evidence/Data: evidence can include documentation of the problem, interest or need that the program is designed to address. An example could be the number and income levels of uninsured individuals for a program that provides care to those without health insurance. For research and development programs, relevance to agency mission should be based on specific ways that the program addresses an important aspect of the agency mission. This question corresponds to Relevance criteria I.C and I.D of the R&D criteria.
Note on B8: 3. Is the program designed to have a significant impact in addressing the interest, problem or need? Purpose of the question: to determine whether the program is designed to have a significant impact that is reasonably known and can be measured. Elements of a Yes answer: a Yes answer would require that the Federal contribution and impact of the program are known and that increasing or reducing the Federal funding or intervention would have a significant impact in the context of all other factors. Important considerations include the role of state and local governments and the private and non-profit sectors and whether the program extends its impact or reach by leveraging funds and contributions from other parties. For credit programs, a consideration can include the extent to which a large number of borrowers would otherwise not have access to financial resources. Evidence/Data: evidence can include the percentage of total resources and requirements directed at the problem that come from the program and the relative impact of those resources and requirements, or the resources and behavior that the Federal contribution leverages.
Note on B9: 4. Is the program designed to make a unique contribution in addressing the interest, problem or need (i.e., is not needlessly redundant of any other Federal, state, local or private effort)? Purpose of the question: to determine whether the program is designed to fill a defensible gap or whether it instead duplicates or even competes with other Federal or non-federal programs. Elements of a Yes answer: a Yes answer would require that the program is not redundant or duplicative of other Federal or non-federal efforts, including the efforts of state and local governments or the private and non-profit sectors. A consideration can include whether the program serves a population not served by other programs. For credit programs, a Yes answer would require evidence of the market failure/absence or unwillingness of private sector participation and an overview of the market, including all international, Federal, local, and private sector participants. For research and development programs, a Yes answer would require justification that the program provides value beyond that of any similar efforts at the agency, efforts at other agencies, or efforts funded by state and local government, private and non-profit sectors, or other counties. Justification first requires due diligence in identifying similar efforts in the past or ongoing. Evidence/Data: evidence can include the number of separate programs and total expenditures or efforts supported by those programs that address a similar problem in a similar way as the program being evaluated. For research and development programs, this question corresponds to one aspect of Relevance criterion I.B of the R&D criteria.
Note on B10: 5. Is the program optimally designed to address the interest, problem or need? Purpose of the question: to determine whether the program design is logical given the current conditions and nature of the problem and whether the design is likely to yield the intended outcomes. This question addresses many elements. Elements of a Yes answer: in this question, the burden of proof is generally on selecting a No answer since it would not be feasible to consider all possible program design alternatives. A Yes answer would require that there be no conclusive evidence that another approach would be more efficient/effective to achieve the intended purpose. A consideration could be whether the government would get the same or better outcome expending fewer total resources through a different mechanism. For example, there may be evidence that a regulatory program to ensure public safety would be more effective as a grant program. There may be evidence that a research program to improve energy efficiency would be more effective as a tax incentive. The assessment should take into account whether the program funding and activity are roughly proportionate to the scope of the problem. This element includes whether funds are divided among so many purposes or recipients that the program is unable to use or target them effectively. In the case of formula grants and loan programs, the assessment should also consider how well funds are targeted to meet the program purpose and whether funds are protected against supplantation. The examination should also consider whether the program is optimally designed in its current form or whether the design no longer makes sense due to changes in the problem. For example, if a weapons system program was intended to combat a specific threat, the assessment should ask whether the design remains optimal when the nature or magnitude of the threat has changed. This question may also address legislative factors. For example, a mandatory program assessment could consider whether the program targets the intended beneficiaries to achieve the program goal. Evidence/Data: evidence can include cost effectiveness studies comparing alternative mechanisms such as a regulation versus a grant or data on the current form of the problem.
Note on C14: This section focuses on program planning, priority setting, and allocation of resources. Key elements in this section include an assessment of whether the program has a limited number of goals that are ambitious, yet achievable, to ensure planning is strategic and focused. Whether the program incorporates flexibility in the planning process to address problems identified through performance data and periodic monitoring is also an important element of this section. Potential source documents and evidence for answering questions include strategic planning documents, agency performance plans and reports, reports and submissions from program partners, evaluation plans, budget submissions and other documents. Options for answers are Yes, No or Not Applicable.
Note on B16: 1. Does the program have a limited number of specific, ambitious long-term performance goals that focus on outcomes and meaningfully reflect the purpose of the program? Purpose of the question: to determine if focused, long-term performance planning is used to guide program management and performance. This question seeks to assess whether the program goals used are salient, meaningful, and capture the most important aspects of program purpose and mission. Elements of a Yes answer: a Yes answer would require identifying a limited number (e.g., two or three) of specific, easily understood program outcome goals that directly and meaningfully support the program's mission and purpose. This question relates to Section 1, Question 1 in Program Purpose and Design. The goals should focus on outcomes and may or may not be those developed to comply with the Government Performance and Results Act (GPRA). While most programs have GPRA goals, many of these goals do not meet the standards of a Yes. A Yes answer can also be given, if OMB and the agency have reached agreement on a limited number of long-term outcome goals that will be added to the FY 2004 GPRA plan. Output goals would only meet the standards of a Yes answer, if the program can produce sound justification for not adopting outcome goals. Goals should be set relative to an established baseline, have clear time frames and targets, and challenge program managers to continuously improve program performance. Programs should have at least one efficiency goal. In evaluating the goals, considerations can also include whether the program is serving the right clients, such as with certain mandatory programs. A No answer would be given for long-term goals that do not directly and meaningfully relate to the program’s mission, do not have clear time frames and targets, or are focused on outputs and lack adequate justification. In some instances, a program may have multiple or even competing goals. In these cases, there may be a problem in the program design or the articulation of the program, which may require more focused program goals or a realignment of a program through management or legislative changes. Agency goals should be listed in the evidence/data section of the PART. For credit programs, customer service benchmarks for timeliness and quality of service and utilization or participation rates may be appropriate long-term outcome goals. Evidence/Data: evidence will include the long-term outcome goals established by the program either in the GPRA plan or other program document or as agreed to by OMB and to be included in FY 2004 GPRA documents. For research and development programs, this question corresponds in part to Performance criterion III.B of the R&D criteria.
Note on B17: 2. Does the program have a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals? Purpose of the question: to determine whether a limited number of annual performance goals have been identified that directly support the long-term goals evaluated in Question 1 of Section II above. Elements of a Yes answer: a Yes answer would require annual performance goals that are discrete, quantifiable, and measurable. Most importantly, these annual goals should measure the program's progress towards reaching the long-term goals evaluated in Question 1 of Section II above. The annual performance goals may focus on outputs and may or may not be those developed by the agency to comply with GPRA. A Yes answer can also be given, if OMB and the agency have reached agreement on a limited number of annual goals that will be included in the FY 2004 GPRA plan. Programs are encouraged to have at least one efficiency goal. If the program received a No in Question 1 of Section II above, an explanation of how annual performance goals contribute to desired long-term outcomes and purpose of the program must be provided to receive a Yes for this question. Agency goals should be listed in the evidence/data section of the PART. For credit programs, customer service benchmarks for timeliness and quality of service and utilization or participation rates may be appropriate annual goals. For research and development programs, a Yes answer would require that the program provides single- and multi-year R&D objectives, with annual performance outputs, to track how the program will improve scientific understanding and its application. Programs must provide schedules with annual milestones for future competitions, decisions, and termination points, highlighting changes from previous schedules. Program proposals must define what would be a minimally effective program and a successful program. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence will include the annual goals established by the program either in a GPRA Annual Performance Plan or other program document or as agreed to by OMB and to be included in FY 2004 GPRA documents. For research and development programs, this question corresponds in part to Performance criterion III.B of the R&D criteria.
Note on B18: 3. Do all partners (grantees, sub-grantees, contractors, etc.) support program planning efforts by committing to the annual and/or long-term goals of the program? Purpose of the question: to determine whether program efforts carried out by program partners also support the annual and long-term goals of the program. Elements of a Yes answer: a Yes answer would require that program managers strive to ensure that partners support the overall goals of the program and measure and report on their performance as it relates to accomplishing those goals. For example, a program that requires all grant applications to include performance measures that will help the program achieve its goals and monitor those measures would receive a Yes. If, however, a program does not through a requirement or some other means get program grantees to link their activities to the program’s goals, a No would be appropriate. The most obvious example of a partner is an entity receiving program funding. While a program cannot always control the activities of their partners, it can exert influence through a number of mechanisms. If the program received a No for both Questions 1 and 2 of Section II above, the program must receive a No for this question. In the case of regulatory programs, all regulated entities are not necessarily defined as program partners. Evidence/Data: evidence can include procedures the program uses to get partners to commit to, measure, and report on performance related to the program's goals.
Note on B19: 4. Does the program collaborate and coordinate effectively with related programs that share similar goals and objectives? Purpose of the question: to determine whether a Federal program that shares a common purpose or goal with another programs) collaborates with the other programs) in a meaningful way. Elements of a Yes answer: the question does not apply to every Federal program, but to programs that have interrelated, but separately budgeted for efforts. An example of interrelated Federal programs could include the shared efforts of Veterans Affairs and Medicare to provide care for aging veterans. A Yes answer would require the program collaborate with related Federal programs, and, to the extent appropriate or possible, with state, local and private programs that share a common purpose or goal as well. A Yes answer would require that the program show evidence of collaboration leading to meaningful actions in management and resource allocation. For example, the existence of a coordinating council would not by itself constitute meaningful collaboration. Evidence/Data: evidence of meaningful collaboration could include joint grant announcements, planning documents, or referral systems.
Note on B20: 5. Are independent and quality evaluations of sufficient scope conducted on a regular basis or as needed to fill gaps in performance information to support program improvements and evaluate effectiveness? Purpose of the question: to ensure program planning is informed by non-biased evaluations that are either conducted regularly or on an as needed basis to fill gaps in performance information. These evaluations should be of sufficient scope to inform program improvements and influence program planning. Elements of a Yes answer: a Yes answer would require regularly scheduled objective, independent evaluations that examine how well the program is accomplishing its mission and meeting its long-term goals. In cases where a comprehensive evaluation is unnecessary based on the known effectiveness of an intervention and performance data on the program, evaluations that fill gaps in performance information can meet the elements of a Yes answer. In addition to evaluating whether the program has achieved its goals on schedule, evaluations should include recommendations on how to improve the program's performance. To ensure the program continues to meet its goals, an evaluation may be scheduled on a periodic basis, such as every two to five years or whatever time schedule is reasonable based on the specific program, its mission, and goals. To be independent, non-biased parties with no conflict of interest would conduct the evaluation. A No answer would be appropriate for a program that has no independent evaluation or (except perhaps for basic research programs) the evaluations address process and not performance. Evidence/Data: evidence can include a plan or schedule of program evaluations and program documentation describing the type of evaluation and criteria for selecting an independent evaluator. For research and development programs, this question corresponds in part to Quality criterion II.B of the R&D criteria.
Note on B21: 6. Is the program budget aligned with the program goals in such a way that the impact of funding, policy, and legislative changes on performance is readily known? Purpose of the question: to establish whether or not the budget planning and performance planning processes are integrated. Elements of a Yes answer: a Yes answer would require effective program budgeting based on a determination of the level of financial resources needed to obtain annual and long-term goals. For mandatory programs, this question would assess whether the impact of specific legislative or policy changes on likely performance is readily known. If a program budget structure varies markedly from program goals, the impact of funding, policy, or legislative decisions on actual performance of a program is very difficult to estimate. A program fitting this description would receive a No. A program with budget planning that is not tied to performance or strategic planning would also receive a No. A Yes response indicates the budget reflects program goals and that annual budget requests are clearly derived by estimating what is needed to accomplish the annual performance measures and long-term goals. For capital assets and services acquisition programs, programs should be able to identify impacts of changes in quantities on performance. Evidence/Data: evidence can include documentation of how the budget structure reflects program goals or how the cost accounting system aligns the budget with program goals. Evidence could also include how budget requests clearly and directly support achieving performance measures and long-term goals.
Note on B22: 7. Has the program taken meaningful steps to address its strategic planning deficiencies? Purpose of the question: to determine whether the program has developed a system of evaluating the effectiveness of its strategic planning efforts and to correct deficiencies when they are identified. Elements of a Yes answer: a Yes answer would require that the program has a system for identifying and correcting deficiencies in its strategic planning process and whether the program has taken meaningful steps to eliminate the deficiencies. A program that does not review planning efforts or does not make corrections to eliminate identified deficiencies would receive a No. The question addresses any deficiencies identified in this section. However, particular emphasis should be placed on whether the program is working to adopt a limited number of specific, ambitious long-term performance goals and a limited number of annual performance goals that demonstrate progress toward achieving the long-term goals, if they do not already have these goals. Evidence/Data: evidence can include a description of how deficiencies in the strategic planning of a program are identified and corrected as well as examples of such changes.
Note on B23: Cap. 1. Are acquisition program plans adjusted in response to performance data and changing conditions? Purpose of the question: to determine if acquisition planning routinely includes review of performance information and the consideration of mid-course adjustments in response to changing needs, the availability of more efficient or cost-effective alternatives, and other variables, and if program plans are adjusted accordingly. Elements of a Yes answer: a Yes answer would require that the program routinely use a systematic process for revising program plans based on performance data or a change in circumstances. If no process exists or if the process is not used, the program should receive a No. Evidence/Data: evidence can include program planning or other documentation that outlines the process to be used to make mid-course adjustments and examples of plans where such changes have been incorporated.
Note on B24: Cap 2. Has the agency/program conducted a recent, meaningful, credible analysis of alternatives that includes trade-offs between cost, schedule and performance goals? Purpose of the question: to determine whether the agency is investing in an asset or service that provides the best value to the government. Elements of a Yes answer: to receive a Yes rating, the agency should have conducted an analysis of alternatives (AoA). The analysis should include the status quo, non-material solutions (e.g., data compression in lieu of a new data cable), and trade-offs between cost, schedule, and performance goals. Program should be able to demonstrate that the analysis is credible (e.g., by having it reviewed and validated by an independent entity outside the program.) If an independent entity’s analysis differs from the program’s analysis, the program should defend differences Evidence/Data: evidence can include a summary of the AoA, and documentation of any independent reviews of the analysis. Capital Asset Plan and Business Case documentation may also be used as source of data or evidence.
Note on C28: This section is focused on a variety of elements related to whether the program is effectively managed to meet program goals and objectives. Key areas include financial oversight, evaluation of program improvements, performance data collection, and program manager accountability. Additionally, specific areas of importance for each program type are also explored. There are a wide range of potential source documents and evidence for answering questions in this section including financial statements, GAO reports, IG reports, performance plans, budget execution data, IT plans, and independent program evaluations. Options for answers are Yes, No or Not Applicable.
Note on B30: 1. Does the agency regularly collect timely and credible performance information, including information from key program partners, and use it to manage the program and improve performance? Purpose of the question: to determine whether the program collects and reports on performance and the performance of its partners and uses the data to inform program management, resource decisions, and program performance. Program partners are other agencies or intermediaries responsible for carrying out different aspects of the program and might include partner agencies, grant recipients, participating financial institutions, regulated bodies, and contractors. Timely performance information is information that provides an accurate picture of current performance and is current enough to be useful to manage the program. Credible performance information is information that is collected through a systematic and consistent process with periodic quality controls to confirm the validity of the data. Elements of a Yes answer: a Yes answer would require that the program agency regularly collect high quality performance data relating to key program goals and use that information to adjust program priorities, make resource reallocations, or take other appropriate management actions. When key program activities are carried out by other entities, such as grantees, agencies should also consider their performance as well. A Yes also requires that the agency has collected the baseline performance data necessary to set meaningful, ambitious performance targets. For capital assets and service acquisition programs, a consideration is whether the program uses an earned value management system or similar system. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence can include a description of how the agency uses performance information in managing the program, as well as illustrative examples of recent management actions based on performance information. Evidence can also include steps taken by a program to enact necessary improvements cited by a specific evaluation.
Note on B31: 2. Are Federal managers and program partners (grantees, sub-grantees, contractors, etc.) held accountable for cost, schedule and performance results? Purpose of the question: to determine whether the program managers and partners are accountable for achieving program results. Elements of a Yes answer: a Yes answer would require that the program agency identify the managers who are responsible for achieving key program results and establish performance standards for those managers. When program partners contribute to the achievement of program goals, a Yes would also require those partners to achieve specific performance standards. In the case of block and formula grant programs, elements of a Yes are not confined to complying with the law. Elements of a Yes can include the presence of incentives for managers and program partners that would encourage corrections in deficient programs. For capital assets and service acquisition programs, a consideration is whether contracts include minimum performance thresholds, incentives for good performance, or other mechanisms to increase accountability. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Evidence/Data: evidence can include the use of performance management contracts with program managers, or some other mechanism for incorporating program performance into personnel performance evaluation criteria. Evidence of partners’ accountability can include requiring grant and contract awards and renewals to consider past performance.
Note on B32: 3. Are all funds (Federal and partners’) obligated in a timely manner and spent for the intended purpose? Purpose of the question: to determine whether funds are administered efficiently and obligated in accordance with planned schedules and spent for the intended purposes. Elements of a Yes answer: a Yes answer would require that the program funds be obligated consistently with the overall program plan and that a limited amount of unobligated funds remain at the end of the year. A Yes answer would also require that programs and partners establish schedules for obligations that align with the overall program plan. In addition, a Yes answer requires that adequate procedures exist for reporting actual expenditures, comparing them against the intended use, and taking timely and appropriate action to correct single audit findings when funds are not spent as intended. An important consideration for this question is whether grantees take action to address any deficiencies raised in audit reports. Evidence/Data: evidence can include periodic and year-end spending reports from the program and its partners. Evidence on expenditures can include spending reports that draw intended purpose from the Congressional Justifications, Appropriations, and program operating plans and match them against actual spending. For grantees, evidence can include grantee audit reports under the Single Audit Act, including data captured in the Federal Audit Clearinghouse, and the existence of an established procedure for reviewing actual expenditures against budgets in grant awards or appropriate Federal guidelines.
Note on B33: 4. Does the program have incentives and procedures (e.g. competitive sourcing/cost comparisons, IT improvements) to measure and achieve efficiencies and cost effectiveness in program execution? Purpose of the question: to determine whether the program has effective management procedures in place to ensure the most efficient use of each dollar spent on program execution. Elements of a Yes answer: a Yes would require that the program’s performance plans include efficiency measures and targets, such as per unit cost of outputs, timing targets, and other efficiency and productivity indicators germane to the program. A de-layered management structure that empowers front line managers and that has undergone competitive sourcing (if necessary) would also contribute to a Yes answer. For mandatory programs, a Yes could require the program to seek policies that would reduce unit costs. Evidence/Data: evidence can include performance measurements for efficiency and IT improvement plans designed to produce tangible productivity and efficiency gains, or IT business cases that document how particular projects improve efficiency.
Note on B34: 5. Does the agency estimate and budget for the full annual costs of operating the program (including all administrative costs and allocated overhead) so that program performance changes are identified with changes in funding levels? Purpose of the question: to determine whether the full costs of the program are known and are budgeted. Elements of a Yes answer: a Yes answer would require the budget estimate for the program includes all direct and indirect costs borne by the program agency, including applicable agency overhead, retirement, and other costs that might be budgeted elsewhere. While having a financial management system that fully allocates program costs and associates those costs with specific performance measures is the optimal standard, a Yes can also be achieved by having a consistent, defensible way to display the full cost of achieving performance goals. Evidence/Data: evidence can include an agency program budget estimate that identified all spending categories in sufficient detail to demonstrate that all relevant costs had been included or a report that shows the allocation of overhead and other program costs to the program.
Note on B35: 6. Does the program use strong financial management practices? Purpose of the question: to determine whether the program uses effective financial management practices in administering program funds. Elements of a Yes answer: a Yes answer would require that the program be free of material internal control weaknesses reported by auditors. Additional criteria could include whether the program has procedures in place to ensure that payments are made properly for the intended purpose to minimize erroneous payments. Evidence/Data: evidence can include recent audit reports and existence of procedures to identify and measure improper payments.
Note on B36: 7. Has the program taken meaningful steps to address its management deficiencies? Purpose of the question: to determine whether the program has developed a system of evaluating program management effectiveness and means to correct deficiencies when they are identified. Elements of a Yes answer: a Yes answer would require that the program has a system for identifying and correcting deficiencies in the various aspects of program management and implements the system to make necessary corrections. A program that does not review program management activities or does not make corrections to eliminate identified deficiencies would receive a No. Evidence/Data (if available): evidence can include a description of how deficiencies in the program management are identified and corrected as well as examples of such changes.
Note on B37: Cap 1. Does the program define the required quality, capability, and performance objectives for deliverables? Purpose of the question: to determine whether the agency has clearly identified and defined the required quality, capability, and performance characteristics or objectives expected of the end product/result of the asset or service acquisition. This element is critical because it assures that all parties (government, contractor, etc) are working toward the same end-product and result. Elements of a Yes answer: if acquiring a capital asset, a Yes would require the program to document the capabilities or characteristics that are expected. For example, a weapon system that has defined key performance parameters and operational requirements would get a Yes, one that is proceeding without such definition should receive a No. For services, a Yes would require the program made adequate use of performance-based contracting methods. A program that acquires services through other than performance based contracts should receive a No, unless there is a legitimate reason for not using such contracts. Evidence/Data: evidence can include documentation from the program describing key performance characteristics and/or deliverables.
Note on B38: Cap 2. Has the program established appropriate, credible, cost and schedule goals? Purpose of the question: to determine whether all program costs are well understood, and whether a realistic schedule has been established. Elements of a Yes answer: a Yes answer would require that the program is able to estimate unit costs, annual costs, and life-cycle costs. Programs should also be able to lay out detailed schedules for development and delivery of assets and services. Program should be able to demonstrate that the cost and schedule estimates are credible (e.g., by having them reviewed and validated by an independent entity outside the program.). If an independent entity’s cost or schedule estimates differ from the program’s estimates, the program should defend differences. Evidence/Data: evidence can include unit cost, acquisition cost, and life cycle cost estimates, as well as development and/or delivery schedules.
Note on B39: Cap 3. Has the program conducted a recent, credible, cost-benefit analysis that shows a net benefit? Purpose of the question: to determine if the program has a net benefit. Elements of a Yes answer: a Yes would require the program conducted an analysis of the projects total life cycle costs and benefits consistent with OMB Circular A-94. The program should be able to demonstrate that the assessment is credible (e.g., by having it reviewed and validated by an independent entity.) If an independent entity’s analysis differs from the program’s analysis, the program should defend the differences. Evidence/Data: evidence should include a summary of any cost/benefit analysis and documentation of any independent reviews of the analysis.
Note on B40: Cap 4. Does the program have a comprehensive strategy for risk management that appropriately shares risk between the government and contractor? Purpose of the question: to help ensure that the risk associated with acquisition of the asset or service is analyzed and managed carefully. Failure to analyze risk in acquisition may contribute to cost overruns, schedule delays, and programs that do not perform as expected. Elements of a Yes answer: a Yes would require the program to have an comprehensive risk management plan that identifies technical, cost, and schedule risks, and describes how these risks will be isolated, minimized, monitored, and controlled. A Yes would also require the program to select contracts and pricing mechanisms that provide appropriate incentives for contractors to meet cost, schedule and performance goals. A program that did only one of these would receive a No. Evidence/Data: evidence can include use of a performance based system such as an earned value management system to monitor and control risk, and use of contract award fees to provide incentives to a contractor to initiate innovations, cost management, and cost reduction measures.
Note on D44: This section considers whether a program is meeting its long-term and annual goals. This section also assesses how well the program compares to similar programs and how effective the program is based on independent evaluations. Potential source documents and evidence for answering questions in this section include annual performance reports, evaluations, GAO reports, IG reports and other agency documents. Assessments of program results should be based on the most recent reporting cycle or other relevant data. Answers in this section are rated as Yes, Large Extent, Small Extent, and No. Like Sections I-III, the scoring system in this section remains on a 0 to 1 point scale. Scoring for this section differs by including the option of partial credit between 0 and 1 in increments of 0, .33, .67, and 1.
Note on B46: 1. Has the program demonstrated adequate progress in achieving its long-term outcome goal's)? Purpose of the question: to determine whether the program is meeting or making measurable progress toward meeting the goals evaluated in Question 1 of Section II. The question also seeks to determine whether the program's partners are meeting long-term outcome goals evaluated in Question 3 of Section II, if partner performance is critical to the program achieving its overall goals. Examples of partners can include grantees, participating financial institutions, regulated bodies, or suppliers. Elements of a Yes answer: a Yes answer (i.e., full credit) would require that the program meet all the goals evaluated in Question 1 of Section II. A Yes answer would not be met by simply meeting any one of its goals. A Yes answer would also require that, where applicable, partners commit to long-term outcome goals and achieve them as well. Partial credit such as Large Extent or Small Extent, should be given in cases where there is partial, but notable, achievement of goals. A program could receive a No if it received a Yes for achieving its annual goals (next question), but is not making progress toward meeting its long-term goals. Space is provided in the PART worksheet to list and document goals, targets and achieved results. If adequate goals are not available and a program received a No in Question 1 of Section II, the program must receive a No answer to this question. For research and development programs, some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Where appropriate, these considerations should be factored into Question 5 of this Section, which should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include data from the agency's GPRA performance report, a strategic plan, or other Administration goals and objectives. Reports detailing customer satisfaction with program performance, program reports detailing rates of utilization or participation, or independent evaluations of the program’s performance may also be considered as relevant evidence. In cases where goals are not met, additional evidence can include an explanation of the main reasons.
Note on B56: 2. Does the program (including program partners) achieve its annual performance goals? Purpose of the question: to determine whether the program is meeting the goals evaluated in Question 2 of Section II. The question also seeks to determine whether the program's partners are meeting annual goals evaluated in Question 3 of Section II, if partner performance is critical to the program achieving its overall goals. Examples of partners can include grantees, contractors, participating financial institutions, regulated bodies, or suppliers. Elements of a Yes answer: a Yes answer (i.e., full credit) would require that the program meet all the goals evaluated in Question 2 of Section II. A Yes answer would also require the program received a Yes for Questions 1 and 2 of Section II and a Yes or Not Applicable for Question 3 of Section II. A Yes answer would not be met by simply meeting any one of its goals. A Yes answer would also require that, where applicable, partners commit to annual goals and achieve them as well. Partial credit such as Large Extent or Small Extent, should be given in cases where there is partial, but notable, achievement of goals. Space is provided in the PART worksheet to list and document goals, targets and achieved results. If adequate goals are not available and a program received a No in Question 2 of Section II, the program must receive a No answer to this question. Some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. Where appropriate, these considerations should be factored into Question 5 of this Section, which should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include data from the agency's annual GPRA performance report, a strategic plan, or other Administration goals and objectives. In cases where goals are not met, additional evidence can include an explanation of the main reasons. For research and development programs, this question corresponds in part to Performance criterion III.C of the R&D criteria.
Note on B67: 3. Does the program demonstrate improved efficiencies and cost effectiveness in achieving program goals each year? Purpose of the question: to determine whether management practices have resulted in efficiency gains over the past year. Elements of a Yes answer: A Yes would require that the program demonstrate improved efficiency over the prior year. Program’s that have undergone a A-76 competitions would also be eligible for yes answer, independent of the outcome. A program would normally not be eligible for a Yes answer to this question if the program received a No in Question 4 of Section III. Evidence/Data: evidence can include meeting performance targets to reduce per unit costs, meeting production and schedule targets, or meeting other targets that result in tangible productivity and efficiency gains.
Note on B68: 4. Does the performance of this program compare favorably to other programs with similar purpose and goals? Purpose of the question: to determine how well the program performs relative to other Federal programs engaged in a similar activity. Elements of a Yes answer: a Yes answer would require the program compare favorably to other Federal programs in the common measures exercise. If none of the common measures relate to the program, the user should consider relevant evaluations that allow a comparison with other Federal programs with similar purpose and goals or comparable private sector activities. If no common measures relate to the program and there are no other similar Federal programs, a Not Applicable rating would be appropriate. For capital assets and service acquisition programs, review of performance should include cost/schedule adherence, quality, and quantity of deliverables. Evidence/Data: evidence can include evaluations and documentation comparing similar programs, including, if applicable, the six common measures. For research and development programs, this question corresponds in part to Performance criterion III.C of the R&D criteria.
Note on B69: 5. Do independent and quality evaluations of this program indicate that the program is effective and achieving results? Purpose of the question: to determine whether the program is effective based on independent and comprehensive evaluations. Elements of a Yes answer: a Yes answer would require that quality program evaluations such as those measured in Question 4 of Section II indicate that the program is effective. If a program is taking necessary steps to correct deficiencies uncovered by the evaluation, the user should address this effort in Question 1 of Section III, Program Management. Relevant evaluations would be at the national program level, rather than evaluations of one or more program partners, and would not focus only on process indicators such as the number of grants provided, or hits on a web site. Relevant evaluations would consider a program's impact, effectiveness, financial management, or other measurement of performance. For research and development programs, some long-term basic research programs may not be able to define meaningful annual outcome performance measures, aside from process measures. In such cases, these programs may use process-related measures, especially those that can be conceptually linked to long-term research goals. This question should be assessed in such a way to address the relative importance of an effective process or relevance to a field of science. Evidence/Data: evidence can include findings of an evaluation conducted by the General Accounting Office, Inspectors General, academic and research institutions, agency contracts or staffs, or other entities. For research and development programs, this question corresponds in part to Relevance criterion I.E and Performance criterion III.C of the R&D criteria.
Note on B70: Cap 1. Were program goals achieved within budgeted costs and established schedules? Purpose of the question: to determine whether valid program goals were achieved within budgeted costs and established schedules and whether the program spends funds as planned and budgeted. Elements of a Yes answer: a Yes answer would require that the program achieved the goals evaluated in Section II on budget and on schedule. An example of a program that could receive a No rating could be an acquisition program that has experienced 60 percent cost growth and is behind schedule. If a program’s cost and schedule targets were changed in the last 12 months specifically due to failure to achieve previous goals, the program should get a No. Evidence/Data: evidence can include a comparison of the contract schedule, deliverables, and costs with the final outcomes for that fiscal year.