## 1.2.1 Observations
Observations |  | WBS 1.2.1 Vacuum | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type
Project Start Date | 2004-10-01
Project Finish Date | 2010-06-23
Project Calendar | Kopio Standard | 220 work days per yr. (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Count Tasks | 60
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 33.33%
Successors | Missing | 51.67%
Task Type (Units,Work,Duration) | Mixed | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 5, (8%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | Used conventional coding
Hours/day | 7.1
Hours/week | 35.5
Hours/year | 1760
Days/month | 18 | ~220 work days /12 months (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Excessive Durations | 14 Tasks | 23%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 6 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg
| 1.2.1 | KOPIO Vacuum Subsystem | 1042.07 days | 2005-10-03 08:00 | 2010-06-23 09:32 | 1039.1618 | 1724.0639 | 3206406.8 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.8361 | 796347.508 | 4002754.308
| 1.2.1.1 | U/S Vacuum Decay Vessel | 650 days | 2005-10-03 08:00 | 2008-09-11 09:00 | 647.3676 | 1074.0417 | 1418439.2 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.9736 | 368420.2 | 1786859.4
| 1.2.1.1.1 | Phase 1 First Article | 380 days | 2005-10-03 08:00 | 2007-06-25 11:00 | 379.8014 | 630.125 | 730452.8 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7537 | 188118.4 | 918571.2
| 1.2.1.1.1.1 | Engineering | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 217.79 | 361.3333 | 83512 |  | 5FF,21SS,38 | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 20878 | 104390
| 1.2.1.1.1.2 | Design | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 217.79 | 361.3333 | 71420.8 | 4FF | 6 | Fixed Units |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 17855.2 | 89276
| 1.2.1.1.1.3 | Procurement | 160 days | 2006-10-02 08:00 | 2007-06-25 11:00 | 160.4041 | 266.125 | 550520 | 5 | 7FF | Fixed Duration |  |  | 4 | 2 | 8 | 8 | 2 | 1 | 0 | 26 | 143135.2 | 693655.2
| 1.2.1.1.1.4 | Acceptance Test | 10 days | 2007-06-08 08:00 | 2007-06-25 11:00 | 10.3219 | 17.125 | 25000 | 6FF | 9 | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 6250 | 31250
| 1.2.1.1.2 | Phase 2 Final Article | 270 days | 2007-06-25 11:00 | 2008-09-11 09:00 | 267.5662 | 443.9167 | 687986.4 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.2072 | 180301.8 | 868288.2
| 1.2.1.1.2.1 | Engineering | 110 days | 2007-06-25 11:00 | 2007-12-24 12:00 | 109.7237 | 182.0417 | 41756 | 7 | 10FF | Fixed Units |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 10439 | 52195
| 1.2.1.1.2.2 | Design | 110 days | 2007-06-25 11:00 | 2007-12-24 12:00 | 109.7237 | 182.0417 | 35710.4 | 9FF | 11 | Fixed Units |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 8927.6 | 44638
| 1.2.1.1.2.3 | Procurement | 160 days | 2007-12-26 08:00 | 2008-09-11 09:00 | 156.7374 | 260.0417 | 380520 | 10 | 12FF,14FF,15FF,16FF,17 | Fixed Units |  |  | 4 | 2 | 8 | 8 | 2 | 1 | 0 | 26 | 98935.2 | 479455.2
| 1.2.1.1.2.4 | Acceptance Test | 10 days | 2008-08-26 09:00 | 2008-09-11 09:00 | 9.6438 | 16 | 5000 | 11FF |  | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 1250 | 6250
| 1.2.1.1.2.5 | Fabrication | 110 days | 2008-03-18 14:00 | 2008-09-11 09:00 | 106.5594 | 176.7917 | 225000 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 60750 | 285750
| 1.2.1.1.2.5.1 | Feed-thru Support Rings | 110 days | 2008-03-18 14:00 | 2008-09-11 09:00 | 106.5594 | 176.7917 | 50000 | 11FF |  | Fixed Duration |  |  | 4 | 3 | 8 | 8 | 2 | 1 | 0 | 27 | 13500 | 63500
| 1.2.1.1.2.5.2 | Vessel Support System | 110 days | 2008-03-18 14:00 | 2008-09-11 09:00 | 106.5594 | 176.7917 | 100000 | 11FF |  | Fixed Duration |  |  | 4 | 3 | 8 | 8 | 2 | 1 | 0 | 27 | 27000 | 127000
| 1.2.1.1.2.5.3 | Installation Fixtures | 110 days | 2008-03-18 14:00 | 2008-09-11 09:00 | 106.5594 | 176.7917 | 75000 | 11FF | 17 | Fixed Duration |  |  | 4 | 3 | 8 | 8 | 2 | 1 | 0 | 27 | 20250 | 95250
| 1.2.1.1.3 | Deliver Vessel to BNL | 0 days | 2008-09-11 09:00 | 2008-09-11 09:00 | 0 | 0 | 0 | 11,16 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2 | Vacuum Transitions | 610 days | 2005-10-03 08:00 | 2008-07-08 16:00 | 608.3653 | 1009.3333 | 359475.2 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.2869 | 101684.272 | 461159.472
| 1.2.1.2.1 | Vacuum Transition Membrane | 460 days | 2005-10-03 08:00 | 2007-11-01 11:00 | 457.5548 | 759.125 | 227886.8 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.5266 | 67287.172 | 295173.972
| 1.2.1.2.1.1 | Phase 1 First Article | 240 days | 2005-10-03 08:00 | 2006-11-01 11:00 | 237.5548 | 394.125 | 118820 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.4208 | 34957.8 | 153777.8
| 1.2.1.2.1.1.1 | Engineering | 180 days | 2005-10-03 08:00 | 2006-07-27 16:00 | 179.2146 | 297.3333 | 34164 | 4SS | 22SS | Fixed Duration |  |  | 6 | 1 | 8 | 8 | 2 | 1 | 0 | 29 | 9907.56 | 44071.56
| 1.2.1.2.1.1.2 | Design | 110 days | 2005-10-03 08:00 | 2006-04-04 16:00 | 110.5023 | 183.3333 | 35710.4 | 21SS | 23 | Fixed Duration |  |  | 6 | 1 | 8 | 8 | 2 | 1 | 0 | 29 | 10356.016 | 46066.416
| 1.2.1.2.1.1.3 | Procurement | 110 days | 2006-04-05 08:00 | 2006-09-29 16:00 | 106.8858 | 177.3333 | 25000 | 22 | 24,26 | Fixed Duration |  |  | 6 | 3 | 8 | 8 | 2 | 1 | 0 | 31 | 7750 | 32750
| 1.2.1.2.1.1.4 | Assemble and Test | 20 days | 2006-10-02 08:00 | 2006-11-01 11:00 | 18.1575 | 30.125 | 23945.6 | 23 |  | Fixed Duration |  |  | 6 | 1 | 8 | 8 | 2 | 1 | 0 | 29 | 6944.224 | 30889.824
| 1.2.1.2.1.2 | Phase 2 Final Article | 240 days | 2006-10-02 08:00 | 2007-11-01 11:00 | 238.1575 | 395.125 | 109066.8 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.6418 | 32329.372 | 141396.172
| 1.2.1.2.1.2.1 | Engineering | 170 days | 2006-10-02 08:00 | 2007-07-12 12:00 | 170.6758 | 283.1667 | 32266 | 23 | 27SS,32 | Fixed Duration |  |  | 6 | 1 | 8 | 8 | 2 | 1 | 0 | 29 | 9357.14 | 41623.14
| 1.2.1.2.1.2.2 | Design | 110 days | 2006-10-02 08:00 | 2007-04-05 09:00 | 111.532 | 185.0417 | 17855.2 | 26SS | 28 | Fixed Duration |  |  | 6 | 1 | 8 | 8 | 2 | 1 | 0 | 29 | 5178.008 | 23033.208
| 1.2.1.2.1.2.3 | Procurement | 110 days | 2007-04-05 09:00 | 2007-10-01 17:00 | 108.0913 | 179.3333 | 35000 | 27 | 29,30 | Fixed Duration |  |  | 6 | 3 | 8 | 8 | 2 | 1 | 0 | 31 | 10850 | 45850
| 1.2.1.2.1.2.4 | Assemble and Test | 20 days | 2007-10-02 08:00 | 2007-11-01 11:00 | 18.1575 | 30.125 | 23945.6 | 28 |  | Fixed Duration |  |  | 6 | 1 | 8 | 8 | 2 | 1 | 0 | 29 | 6944.224 | 30889.824
| 1.2.1.2.2 | Deliver Membrane to BNL | 0 days | 2007-10-01 17:00 | 2007-10-01 17:00 | 0 | 0 | 0 | 28 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.2.3 | Vacuum Windows | 220 days | 2007-07-12 13:00 | 2008-07-08 16:00 | 218.2671 | 362.125 | 131588.4 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.1399 | 34397.1 | 165985.5
| 1.2.1.2.3.1 | Engineering | 110 days | 2007-07-12 13:00 | 2008-01-11 09:00 | 110.2009 | 182.8333 | 20878 | 26 | 33SS | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 5219.5 | 26097.5
| 1.2.1.2.3.2 | Design | 110 days | 2007-07-12 13:00 | 2008-01-11 09:00 | 110.2009 | 182.8333 | 35710.4 | 32SS | 34 | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 8927.6 | 44638
| 1.2.1.2.3.3 | Procurement | 110 days | 2008-01-11 09:00 | 2008-07-08 16:00 | 108.0662 | 179.2917 | 50000 | 33 | 35FF | Fixed Duration |  |  | 4 | 3 | 8 | 8 | 2 | 1 | 0 | 27 | 13500 | 63500
| 1.2.1.2.3.4 | Fabrication | 110 days | 2008-01-11 09:00 | 2008-07-08 16:00 | 108.0662 | 179.2917 | 25000 | 34FF | 36 | Fixed Duration |  |  | 4 | 3 | 8 | 8 | 2 | 1 | 0 | 27 | 6750 | 31750
| 1.2.1.2.4 | Deliver Vacuum Windows to BNL | 0 days | 2008-07-08 16:00 | 2008-07-08 16:00 | 0 | 0 | 0 | 35 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.3 | D4 Vacuum Box | 330 days | 2006-10-02 08:00 | 2008-04-02 14:00 | 330.4521 | 548.25 | 238176.8 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5745 | 63294.2 | 301471
| 1.2.1.3.1 | Engineering | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 219.6233 | 364.375 | 41756 | 4 | 39SS,44 | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 10439 | 52195
| 1.2.1.3.2 | Design | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 219.6233 | 364.375 | 71420.8 | 38SS | 40 | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 17855.2 | 89276
| 1.2.1.3.3 | Procurement | 110 days | 2007-10-02 08:00 | 2008-04-02 14:00 | 110.4521 | 183.25 | 100000 | 39 | 41FF | Fixed Duration |  |  | 4 | 4 | 8 | 8 | 2 | 1 | 0 | 28 | 28000 | 128000
| 1.2.1.3.4 | Fabrication | 110 days | 2007-10-02 08:00 | 2008-04-02 14:00 | 110.4521 | 183.25 | 25000 | 40FF | 42 | Fixed Duration |  |  | 4 | 4 | 8 | 8 | 2 | 1 | 0 | 28 | 7000 | 32000
| 1.2.1.3.5 | Deliver D-4 Vacuum Box to BNL | 0 days | 2008-04-02 14:00 | 2008-04-02 14:00 | 0 | 0 | 0 | 41 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.4 | Downstream Veto Vacuum Tank | 400 days | 2007-10-02 08:00 | 2009-07-24 12:00 | 398.5114 | 661.1667 | 393176.8 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.1364 | 106694.2 | 499871
| 1.2.1.4.1 | Engineering | 220 days | 2007-10-02 08:00 | 2008-09-26 12:00 | 217.0868 | 360.1667 | 41756 | 38 | 45SS | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 10439 | 52195
| 1.2.1.4.2 | Design | 220 days | 2007-10-02 08:00 | 2008-09-26 12:00 | 217.0868 | 360.1667 | 71420.8 | 44SS | 46 | Fixed Duration |  |  | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 17855.2 | 89276
| 1.2.1.4.3 | Procurement | 180 days | 2008-09-26 13:00 | 2009-07-24 12:00 | 181.3995 | 300.9583 | 250000 | 45 | 47FF | Fixed Duration |  |  | 4 | 4 | 8 | 8 | 2 | 1 | 0 | 28 | 70000 | 320000
| 1.2.1.4.4 | Fabrication | 180 days | 2008-09-26 13:00 | 2009-07-24 12:00 | 181.3995 | 300.9583 | 30000 | 46FF | 48 | Fixed Duration |  |  | 4 | 4 | 8 | 8 | 2 | 1 | 0 | 28 | 8400 | 38400
| 1.2.1.4.5 | Deliver Veto Vacuum Tank to BNL | 0 days | 2009-07-24 12:00 | 2009-07-24 12:00 | 0 | 0 | 0 | 47 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.5 | Vacuum Pumping Station | 395 days | 2007-06-29 11:00 | 2009-04-16 09:00 | 395.9498 | 656.9167 | 630114.8 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.1711 | 114498.636 | 744613.436
| 1.2.1.5.1 | Supervision | 40 days | 2008-07-23 15:00 | 2008-09-25 17:00 | 38.6256 | 64.0833 | 30368 |  |  | Fixed Duration | 2008-09-25 17:00 | Finish No Earlier Than | 2 | 1 | 4 | 8 | 2 | 1 | 0 | 17 | 5162.56 | 35530.56
| 1.2.1.5.2 | Engineering | 110 days | 2007-06-29 11:00 | 2008-01-01 17:00 | 112.2603 | 186.25 | 83512 |  | 52SS,53 | Fixed Duration | 2008-01-01 17:00 | Finish No Earlier Than | 2 | 1 | 4 | 8 | 2 | 1 | 0 | 17 | 14197.04 | 97709.04
| 1.2.1.5.3 | Design | 60 days | 2007-06-29 11:00 | 2007-10-05 12:00 | 59.0936 | 98.0417 | 38956.8 | 51SS |  | Fixed Duration |  |  | 2 | 1 | 4 | 8 | 2 | 1 | 0 | 17 | 6622.656 | 45579.456
| 1.2.1.5.4 | Procurement | 110 days | 2008-01-02 08:00 | 2008-06-27 10:00 | 106.7352 | 177.0833 | 292800 | 51 | 55,57 | Fixed Duration |  |  | 2 | 1 | 4 | 8 | 2 | 1 | 0 | 17 | 49776 | 342576
| 1.2.1.5.5 | Installation & Test | 175 days | 2008-06-27 10:00 | 2009-04-16 09:00 | 176.5776 | 292.9583 | 184478 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 38740.38 | 223218.38
| 1.2.1.5.5.1 | Assembly | 175 days | 2008-06-27 10:00 | 2009-04-16 09:00 | 176.5776 | 292.9583 | 104762 | 53 | 56FF | Fixed Duration |  |  | 2 | 1 | 8 | 8 | 2 | 1 | 0 | 21 | 22000.02 | 126762.02
| 1.2.1.5.5.2 | Test | 105 days | 2008-10-17 13:00 | 2009-04-16 09:00 | 108.9954 | 180.8333 | 79716 | 55FF |  | Fixed Duration |  |  | 2 | 1 | 8 | 8 | 2 | 1 | 0 | 21 | 16740.36 | 96456.36
| 1.2.1.5.6 | Deliver Equipment to BNL | 0 days | 2008-06-27 10:00 | 2008-06-27 10:00 | 0 | 0 | 0 | 53 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.1.6 | Management Activities | 1042.07 days | 2005-10-03 08:00 | 2010-06-23 09:32 | 1039.1618 | 1724.0639 | 167024 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 41756 | 208780
| 1.2.1.6.1 | Subsystem Manager | 880 days | 2005-10-03 08:00 | 2009-09-28 15:00 | 877.7648 | 1456.2917 | 0 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 0 | 0 | 0
| 1.2.1.6.2 | Subsystem Engineer | 1042.07 days | 2005-10-03 08:00 | 2010-06-23 09:32 | 1039.1618 | 1724.0639 | 167024 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 1 | 8 | 8 | 2 | 1 | 0 | 25 | 41756 | 208780
Count | 60 | [6 empty] | Count | 40 | 29 |  | 5
[8 empty] | Assigned | 0.66667 | 0.48333
[8 empty] | Missing | 0.33333 | 0.51667

## 1.2.1 Durations & Milestone
| Excessive Durations |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs
1.2.1.2.1.1 | Phase 1 First Article | 2005-10-03 08:00 | 2006-11-01 11:00 | 1.0798
1.2.1.2.1.2 | Phase 2 Final Article | 2006-10-02 08:00 | 2007-11-01 11:00 | 1.0825
1.2.1.1.2 | Phase 2 Final Article | 2007-06-25 11:00 | 2008-09-11 09:00 | 1.2162
1.2.1.3 | D4 Vacuum Box | 2006-10-02 08:00 | 2008-04-02 14:00 | 1.5021
1.2.1.1.1 | Phase 1 First Article | 2005-10-03 08:00 | 2007-06-25 11:00 | 1.7264
1.2.1.5 | Vacuum Pumping Station | 2007-06-29 11:00 | 2009-04-16 09:00 | 1.7998
1.2.1.4 | Downstream Veto Vacuum Tank | 2007-10-02 08:00 | 2009-07-24 12:00 | 1.8114
1.2.1.2.1 | Vacuum Transition Membrane | 2005-10-03 08:00 | 2007-11-01 11:00 | 2.0798
1.2.1.2 | Vacuum Transitions | 2005-10-03 08:00 | 2008-07-08 16:00 | 2.7653
1.2.1.1 | U/S Vacuum Decay Vessel | 2005-10-03 08:00 | 2008-09-11 09:00 | 2.9426
1.2.1.6.1 | Subsystem Manager | 2005-10-03 08:00 | 2009-09-28 15:00 | 3.9898
1.2.1 | KOPIO Vacuum Subsystem | 2005-10-03 08:00 | 2010-06-23 09:32 | 4.7235 | OK
1.2.1.6 | Management Activities | 2005-10-03 08:00 | 2010-06-23 09:32 | 4.7235
1.2.1.6.2 | Subsystem Engineer | 2005-10-03 08:00 | 2010-06-23 09:32 | 4.7235
|  |  | Count Excessive | 14
>1 year
23.33%
Sort by
WBS | Milestone | Start | Finish | Duration Days
1.2.1.2.2 | Deliver Membrane to BNL | 2007-10-01 17:00 | 2007-10-01 17:00 | 0 days
1.2.1.3.5 | Deliver D-4 Vacuum Box to BNL | 2008-04-02 14:00 | 2008-04-02 14:00 | 0 days
1.2.1.5.6 | Deliver Equipment to BNL | 2008-06-27 10:00 | 2008-06-27 10:00 | 0 days
1.2.1.2.4 | Deliver Vacuum Windows to BNL | 2008-07-08 16:00 | 2008-07-08 16:00 | 0 days
1.2.1.1.3 | Deliver Vessel to BNL | 2008-09-11 09:00 | 2008-09-11 09:00 | 0 days
1.2.1.4.5 | Deliver Veto Vacuum Tank to BNL | 2009-07-24 12:00 | 2009-07-24 12:00 | 0 days
|  |  | Count | 6

## 1.2.2 Observations
Observations |  | WBS 1.2.2 Preradiator | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg
Project Start Date | 2005-10-03
Project Finish Date | 2009-12-31
Project Calendar | Kopio Standard | 220 work days per yr. (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Count Tasks | 196
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 78.57%
Successors | Missing | 80.1%
Task Type (Units,Work,Duration) | All Duration | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 135, (69%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | Used conventional coding
Hours/day | 7.1
Hours/week | 35.5
Hours/year | 1760
Days/month | 18 | ~220 work days /12 months (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Excessive Durations | 130 Tasks | 66%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 17 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg
| 1.2.2 | Preradiator | 1106.38 days | 2005-01-03 08:00 | 2009-12-31 12:00 | 1098.895 | 1823.1667 | 17210424.83 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.906 | 5319051.1996 | 22204998.3996
| 1.2.2.1 | Chamber System | 957.75 days | 2005-03-01 08:00 | 2009-06-30 09:00 | 953.5594 | 1582.0417 | 2757707.51 |  |  | Fixed Duration |  |  | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 41.3013 | 1138968.7356 | 3896676.2456
| 1.2.2.1.1 | Chambers | 957.75 days | 2005-03-01 08:00 | 2009-06-30 09:00 | 953.5594 | 1582.0417 | 2341351.26 |  |  | Fixed Duration |  |  | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 42.244 | 989080.4856 | 3330431.7456
| 1.2.2.1.1.1 | Design | 152 days | 2005-03-01 08:00 | 2005-10-31 17:00 | 147.2945 | 244.375 | 0 |  |  | Fixed Duration | 2005-03-01 08:00 | Start No Earlier Than | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 0 | 0 | 0
| 1.2.2.1.1.2 | Prototype | 152 days | 2005-03-01 08:00 | 2005-10-31 17:00 | 147.2945 | 244.375 | 455172.37 |  | 6,8,9,10,11 | Fixed Duration | 2005-03-01 08:00 | Start No Earlier Than | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 44 | 200275.8428 | 655448.2128
|  | Chamber FDR/PRR Review | 0 days | 2005-10-31 17:00 | 2005-10-31 17:00 | 0 | 0 | 0 | 5 | 7 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.1.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 1886178.89 | 6 |  | Fixed Duration |  |  | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 41.8202 | 788804.6428 | 2674983.5328
| 1.2.2.1.1.3.1 | Cathode strips | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 42879.57 | 5 |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 8 | 6 | 8 | 8 | 4 | 2 | 1 | 60 | 25727.742 | 68607.312
| 1.2.2.1.1.3.2 | Frame assembly | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 1337929.32 | 5 |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 44 | 588688.9008 | 1926618.2208
| 1.2.2.1.1.3.3 | Stringing | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 342630 | 5 |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 2 | 1 | 32 | 109641.6 | 452271.6
| 1.2.2.1.1.3.4 | Chamber assembly | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 119870 | 5 |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 44 | 52742.8 | 172612.8
| 1.2.2.1.1.3.5 | Tests | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 42870 |  | 13 | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 28 | 12003.6 | 54873.6
|  | Chamber Production Complete | 0 days | 2009-06-30 09:00 | 2009-06-30 09:00 | 0 | 0 | 0 | 12 |  | Fixed Duration | 2009-06-30 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.2 | Gas System | 402 days | 2005-09-01 08:00 | 2007-06-29 10:00 | 401.4749 | 666.0833 | 416356.25 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 149888.25 | 566244.5
| 1.2.2.1.2.1 | Design | 106 days | 2005-09-01 08:00 | 2006-02-28 14:00 | 108.6438 | 180.25 | 23751.2 |  | 17 | Fixed Duration | 2005-09-01 | Start No Earlier Than | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 8550.432 | 32301.632
| 1.2.2.1.2.2 | Prototype | 106 days | 2005-09-01 08:00 | 2006-02-28 14:00 | 108.6438 | 180.25 | 115004.8 |  | 17 | Fixed Duration | 2005-09-01 | Start No Earlier Than | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 41401.728 | 156406.528
|  | Gas FDR | 0 days | 2006-03-01 08:00 | 2006-03-01 08:00 | 0 | 0 | 0 | 15,16 | 18,19,20,21,22,23 | Fixed Duration | 2006-03-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.1.2.3 | Fabrication/Procurement | 111 days | 2007-01-01 08:00 | 2007-06-29 10:00 | 107.9406 | 179.0833 | 277600.25 | 17 |  | Fixed Duration |  |  | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 99936.09 | 377536.34
| 1.2.2.1.2.3.1 | In module(tube,MFM x256) | 111 days | 2007-01-02 08:00 | 2007-06-29 10:00 | 107.3379 | 178.0833 | 61400 | 17 |  | Fixed Duration | 2007-01-01 | Start No Earlier Than | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 22104 | 83504
| 1.2.2.1.2.3.2 | Rec.system(MFC,pump x4) | 111 days | 2007-01-02 08:00 | 2007-06-29 10:00 | 107.3379 | 178.0833 | 96000 | 17 |  | Fixed Duration | 2007-01-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 34560 | 130560
| 1.2.2.1.2.3.3 | Assembly | 111 days | 2007-01-01 08:00 | 2007-06-29 10:00 | 107.9406 | 179.0833 | 96200.25 | 17 | 24 | Fixed Duration | 2007-01-01 | Start No Earlier Than | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 34632.09 | 130832.34
| 1.2.2.1.2.3.4 | Gas shack/plumbing | 111 days | 2007-01-02 08:00 | 2007-06-29 10:00 | 107.3379 | 178.0833 | 16000 | 17 | 24 | Fixed Duration | 2007-01-01 | Start No Earlier Than | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 5760 | 21760
| 1.2.2.1.2.3.5 | DAQ | 111 days | 2007-01-02 08:00 | 2007-06-29 10:00 | 107.3379 | 178.0833 | 8000 | 17 | 24 | Fixed Duration | 2007-01-01 | Start No Earlier Than | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 36 | 2880 | 10880
|  | Gas System Complete | 0 days | 2007-06-29 10:00 | 2007-06-29 10:00 | 0 | 0 | 0 | 21,22,23 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2 | Scintillator System | 958.5 days | 2005-03-01 08:00 | 2009-06-30 16:00 | 953.7352 | 1582.3333 | 2618014.81 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 22.5017 | 589097.546 | 3207112.356
| 1.2.2.2.1 | Scintillator Plates | 958.5 days | 2005-03-01 08:00 | 2009-06-30 16:00 | 953.7352 | 1582.3333 | 1410880.08 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.1484 | 397140.04 | 1808020.12
| 1.2.2.2.1.1 | Design | 152 days | 2005-03-01 08:00 | 2005-10-31 17:00 | 147.2945 | 244.375 | 33251.68 |  | 29 | Fixed Duration | 2005-03-01 | Start No Earlier Than | 8 | 6 | 4 | 4 | 2 | 1 | 1 | 30 | 9975.504 | 43227.184
| 1.2.2.2.1.2 | Prototype | 152 days | 2005-03-01 08:00 | 2005-10-31 17:00 | 147.2945 | 244.375 | 245065.62 |  | 29 | Fixed Duration | 2005-03-01 | Start No Earlier Than | 8 | 6 | 4 | 4 | 2 | 1 | 1 | 30 | 73519.686 | 318585.306
|  | Scintillator Plate FDR/PRR | 0 days | 2005-10-31 17:00 | 2005-10-31 17:00 | 0 | 0 | 0 | 27,28 | 30,31,32,33 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.1.3 | Fabrication/Procurement | 806.5 days | 2005-11-01 08:00 | 2009-06-30 16:00 | 806.0639 | 1337.3333 | 1132562.78 | 29 |  | Fixed Duration |  |  | 8 | 6 | 4 | 4 | 2 | 1 | 1 | 27.6934 | 313644.85 | 1446207.63
| 1.2.2.2.1.3.1 | Scintillator production | 253 days | 2005-11-01 08:00 | 2006-12-28 16:00 | 254.5571 | 422.3333 | 77612.4 | 29 |  | Fixed Duration | 2005-11-01 | Start No Earlier Than | 2 | 4 | 8 | 0 | 1 | 1 | 1 | 14 | 10865.736 | 88478.136
| 1.2.2.2.1.3.2 | Plane fabrication | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 712300.38 | 29 |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 8 | 6 | 4 | 4 | 2 | 1 | 1 | 30 | 213690.114 | 925990.494
| 1.2.2.2.1.3.3 | Fiber installation | 764 days | 2006-01-17 08:00 | 2009-06-30 16:00 | 759.653 | 1260.3333 | 342650 | 29 |  | Fixed Duration | 2006-01-15 | Start No Earlier Than | 6 | 6 | 4 | 4 | 2 | 1 | 1 | 26 | 89089 | 431739
| 1.2.2.2.1.3.4 | Tests | 764 days | 2006-01-17 08:00 | 2009-06-30 16:00 | 759.653 | 1260.3333 | 0 |  |  | Fixed Duration | 2006-01-15 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.2.2.2 | WLS fiber | 828.13 days | 2005-04-01 08:00 | 2008-12-31 16:00 | 825.9543 | 1370.3333 | 508242.73 |  |  | Fixed Duration |  |  | 4 | 6 | 4 | 4 | 2 | 1 | 1 | 20.24 | 102868.546 | 611111.276
| 1.2.2.2.2.2 | Prototype | 131 days | 2005-04-01 08:00 | 2005-10-31 14:00 | 128.5342 | 213.25 | 25000 |  | 37,39,40 | Fixed Duration | 2005-04-01 | Start No Earlier Than | 4 | 6 | 4 | 4 | 2 | 1 | 1 | 22 | 5500 | 30500
|  | WLS Fiber PRR | 0 days | 2005-10-31 14:00 | 2005-10-31 14:00 | 0 | 0 | 0 | 36 | 38 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.2.2.3 | Fabrication/Procurement | 663 days | 2006-01-02 08:00 | 2008-12-31 16:00 | 659.5982 | 1094.3333 | 483242.73 | 37 |  | Fixed Duration |  |  | 4 | 6 | 4 | 4 | 2 | 1 | 1 | 20.149 | 97368.546 | 580611.276
| 1.2.2.2.2.3.1 | Fiber | 663 days | 2006-01-02 08:00 | 2008-12-31 16:00 | 659.5982 | 1094.3333 | 447242.73 | 36 |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 89448.546 | 536691.276
| 1.2.2.2.2.3.2 | Coupler | 663 days | 2006-01-02 08:00 | 2008-12-31 16:00 | 659.5982 | 1094.3333 | 36000 | 36 |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 6 | 4 | 4 | 2 | 1 | 1 | 22 | 7920 | 43920
| 1.2.2.2.3 | Scintillator readout | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 698892 |  |  | Fixed Duration |  |  | 2 | 4 | 4 | 0 | 2 | 1 | 1 | 12.7472 | 89088.96 | 787980.96
| 1.2.2.2.3.1 | Photo Tube | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 276480 |  |  | Fixed Duration |  |  | 2 | 4 | 4 | 0 | 2 | 1 | 1 | 12 | 33177.6 | 309657.6
| 1.2.2.2.3.1.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 276480 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 2 | 4 | 4 | 0 | 2 | 1 | 1 | 12 | 33177.6 | 309657.6
| 1.2.2.2.3.2 | MU Metal Shield/Bases | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 172800 |  |  | Fixed Duration |  |  | 4 | 8 | 4 | 4 | 2 | 1 | 1 | 24 | 41472 | 214272
| 1.2.2.2.3.2.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 172800 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 8 | 4 | 4 | 2 | 1 | 1 | 24 | 41472 | 214272
| 1.2.2.2.3.3 | Cables | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 72196.8 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 14439.36 | 86636.16
| 1.2.2.2.3.3.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 72196.8 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 14439.36 | 86636.16
| 1.2.2.2.3.4 | Preampifier | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 34565.2 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0 | 0 | 34565.2
| 1.2.2.2.3.4.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 34565.2 |  |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34565.2
| 1.2.2.2.3.5 | LV-HV converter | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 142850 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142850
| 1.2.2.2.3.5.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 142850 |  |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142850
| 1.2.2.3 | Electronics | 1106.38 days | 2005-01-03 08:00 | 2009-12-31 12:00 | 1098.895 | 1823.1667 | 6530263.9 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.871 | 1428236.886 | 7634023.156
| 1.2.2.3.1 | Anode Electronics | 994.38 days | 2005-01-03 08:00 | 2009-06-30 09:00 | 987.9155 | 1639.0417 | 2372514.54 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 17.2647 | 409607.382 | 2457644.292
| 1.2.2.3.1.1 | Design | 188 days | 2005-01-03 08:00 | 2005-10-31 11:00 | 181.5 | 301.125 | 0 |  | 56 | Fixed Duration | 2005-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.2.3.1.2 | Prototype | 188 days | 2005-01-03 08:00 | 2005-10-31 11:00 | 181.5 | 301.125 | 249716.91 |  | 56 | Fixed Duration | 2005-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 49943.382 | 299660.292
|  | Anode PRR | 0 days | 2005-10-31 11:00 | 2005-10-31 11:00 | 0 | 0 | 0 | 54,55 | 57 | Fixed Duration | 2005-10-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.1.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 2122797.63 | 56 |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 16.9429 | 359664 | 2157984
| 1.2.2.3.1.3.1 | Adaptor Cards | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 500800 |  |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 100160 | 600960
| 1.2.2.3.1.3.2 | Readout Cards | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 827600 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 165520 | 993120
| 1.2.2.3.1.3.3 | Cables | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 469920 |  |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 93984 | 563904
| 1.2.2.3.2 | Cathode Electronics | 994.38 days | 2005-01-03 08:00 | 2009-06-30 09:00 | 987.9155 | 1639.0417 | 2096844.8 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 419368.96 | 2516213.76
| 1.2.2.3.2.1 | Design | 188 days | 2005-01-03 08:00 | 2005-10-31 11:00 | 181.5 | 301.125 | 0 |  | 64 | Fixed Duration | 2005-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.2.3.2.2 | Prototype | 188 days | 2005-01-03 08:00 | 2005-10-31 11:00 | 181.5 | 301.125 | 138204.8 |  | 64 | Fixed Duration | 2005-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 27640.96 | 165845.76
|  | Cathode PRR | 0 days | 2005-10-31 11:00 | 2005-10-31 11:00 | 0 | 0 | 0 | 62,63 | 65 | Fixed Duration | 2005-10-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.2.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 1958640 | 64 |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 391728 | 2350368
| 1.2.2.3.2.3.1 | Adaptor Cards | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 255200 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 51040 | 306240
| 1.2.2.3.2.3.2 | Readout Cards | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 1233520 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 246704 | 1480224
| 1.2.2.3.2.3.3 | Cables | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 469920 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 93984 | 563904
| 1.2.2.3.3 | HV | 957.75 days | 2005-03-01 08:00 | 2009-06-30 09:00 | 953.5594 | 1582.0417 | 288805.76 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 57761.152 | 346566.912
| 1.2.2.3.3.1 | Design | 185 days | 2005-03-01 08:00 | 2005-12-29 09:00 | 182.6553 | 303.0417 | 0 |  | 72 | Fixed Duration | 2005-03-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.2.3.3.2 | Prototype | 185 days | 2005-03-01 08:00 | 2005-12-29 09:00 | 182.6553 | 303.0417 | 138005.76 |  | 72 | Fixed Duration | 2005-03-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 27601.152 | 165606.912
|  | HV PRR | 0 days | 2005-12-29 09:00 | 2005-12-29 09:00 | 0 | 0 | 0 | 70,71 | 73 | Fixed Duration | 2005-12-29 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.3.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 150800 | 72 |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 30160 | 180960
| 1.2.2.3.3.3.1 | HV source | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 67600 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 13520 | 81120
| 1.2.2.3.3.3.2 | HV cards | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 83200 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 16640 | 99840
| 1.2.2.3.4 | Crate Assembly | 957.75 days | 2005-03-01 08:00 | 2009-06-30 09:00 | 953.5594 | 1582.0417 | 414280 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 82856 | 497136
| 1.2.2.3.4.2 | Prototype | 185 days | 2005-03-01 08:00 | 2005-12-29 09:00 | 182.6553 | 303.0417 | 15200 |  |  | Fixed Duration | 2005-03-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 3040 | 18240
| 1.2.2.3.4.3 | Production | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 399080 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 79816 | 478896
| 1.2.2.3.4.3.1 | Mechanical | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 84760 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 16952 | 101712
| 1.2.2.3.4.3.2 | LV source | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 314320 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 62864 | 377184
| 1.2.2.3.5 | Controller cards | 899.88 days | 2005-06-01 08:00 | 2009-06-30 09:00 | 898.1073 | 1490.0417 | 475884.8 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 44 | 209389.312 | 685274.112
| 1.2.2.3.5.1 | Design | 127 days | 2005-06-01 08:00 | 2005-12-28 16:00 | 126.7763 | 210.3333 | 0 |  | 84 | Fixed Duration | 2005-06-01 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.2.3.5.2 | Prototype | 127 days | 2005-06-01 08:00 | 2005-12-28 16:00 | 126.7763 | 210.3333 | 99004.8 |  | 84 | Fixed Duration | 2005-06-01 | Start No Earlier Than | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 44 | 43562.112 | 142566.912
|  | Controller PRR | 0 days | 2005-12-28 16:00 | 2005-12-28 16:00 | 0 | 0 | 0 | 82,83 | 85 | Fixed Duration | 2005-12-28 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.5.3 | Fabrication/Procurement | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 376880 | 84 |  | Fixed Duration |  |  | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 44 | 165827.2 | 542707.2
| 1.2.2.3.5.3.1 | Chamber collector cards | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 263440 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 44 | 115913.6 | 379353.6
| 1.2.2.3.5.3.2 | Module collector cards | 772 days | 2006-01-02 08:00 | 2009-06-30 09:00 | 768.5183 | 1275.0417 | 113440 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 44 | 49913.6 | 163353.6
| 1.2.2.3.6 | Scintillator Electronics | 680.13 days | 2006-12-01 08:00 | 2009-12-31 12:00 | 678.7854 | 1126.1667 | 881934 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 28.2622 | 249254.08 | 1131188.08
| 1.2.2.3.6.1 | HV Control System | 236.75 days | 2006-12-01 08:00 | 2007-12-31 11:00 | 238.1575 | 395.125 | 100000 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 28 | 28000 | 128000
| 1.2.2.3.6.1.1 | VME Carriers | 145 days | 2006-12-01 08:00 | 2007-07-31 11:00 | 145.9384 | 242.125 | 13000 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 28 | 3640 | 16640
| 1.2.2.3.6.1.2 | IP Modules | 145 days | 2006-12-01 08:00 | 2007-07-31 11:00 | 145.9384 | 242.125 | 67000 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 28 | 18760 | 85760
| 1.2.2.3.6.1.3 | VME/VXI Mainframes | 53 days | 2007-10-02 08:00 | 2007-12-31 11:00 | 54.3219 | 90.125 | 20000 |  |  | Fixed Duration | 2007-10-02 08:00 | Start No Earlier Than | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 28 | 5600 | 25600
| 1.2.2.3.6.2 | Monitoring & Calibration System | 423.38 days | 2007-01-03 08:00 | 2008-11-25 15:00 | 417.2717 | 692.2917 | 56666 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 28 | 15866.48 | 72532.48
| 1.2.2.3.6.2.1 | Design | 202 days | 2007-01-03 08:00 | 2007-11-29 15:00 | 199.0799 | 330.2917 | 0 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.3.6.2.2 | Prototype | 202 days | 2007-01-03 08:00 | 2007-11-29 15:00 | 199.0799 | 330.2917 | 0 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.3.6.2.3 | Fabrication/Procurement | 237 days | 2007-11-01 08:00 | 2008-11-25 15:00 | 235.2443 | 390.2917 | 56666 |  |  | Fixed Duration | 2007-11-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 28 | 15866.48 | 72532.48
| 1.2.2.3.6.3 | Readout Electronics | 552.75 days | 2007-01-02 08:00 | 2009-06-30 16:00 | 548.6941 | 910.3333 | 626206 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 29.6348 | 185575.2 | 811781.2
| 1.2.2.3.6.3.1 | WFD Boards | 474.88 days | 2007-01-03 08:00 | 2009-02-27 10:00 | 473.8037 | 786.0833 | 500256 |  |  | Fixed Duration |  |  | 8 | 4 | 4 | 4 | 2 | 2 | 1 | 31.0535 | 155347.2 | 655603.2
| 1.2.2.3.6.3.1.3 | Fabrication/Procurement | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 460800 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 8 | 4 | 4 | 4 | 2 | 2 | 1 | 32 | 147456 | 608256
| 1.2.2.3.6.3.1.5 | Test | 420 days | 2007-04-03 08:00 | 2009-02-27 10:00 | 419.5571 | 696.0833 | 39456 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 7891.2 | 47347.2
| 1.2.2.3.6.3.2 | Crate Data-Collection Boards | 475.63 days | 2007-01-02 08:00 | 2009-02-27 09:00 | 474.3813 | 787.0417 | 50380 |  |  | Fixed Duration |  |  | 8 | 4 | 8 | 4 | 2 | 2 | 1 | 36 | 18136.8 | 68516.8
| 1.2.2.3.6.3.2.3 | Fabrication/Procurement | 425 days | 2007-01-02 08:00 | 2008-11-26 15:00 | 418.4772 | 694.2917 | 50380 |  |  | Fixed Duration | 2007-01-02 08:00 | Start No Earlier Than | 8 | 4 | 8 | 4 | 2 | 2 | 1 | 36 | 18136.8 | 68516.8
| 1.2.2.3.6.3.2.5 | Test | 309 days | 2007-10-01 08:00 | 2009-02-27 09:00 | 310.4361 | 515.0417 | 0 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.3.6.3.3 | VXI Mainframes & Controller | 419 days | 2007-04-03 08:00 | 2009-02-26 09:00 | 418.9292 | 695.0417 | 75570 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 0 | 2 | 2 | 1 | 16 | 12091.2 | 87661.2
| 1.2.2.3.6.3.4 | System tests | 162 days | 2008-10-02 08:00 | 2009-06-30 16:00 | 163.5434 | 271.3333 | 0 |  |  | Fixed Duration | 2008-10-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.3.6.4 | Electronic Racks & LV Power Supplies | 369 days | 2007-04-03 08:00 | 2008-11-26 12:00 | 363.5525 | 603.1667 | 6050 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 1210 | 7260
| 1.2.2.3.6.4.1 | LV Power Supplies | 369 days | 2007-04-03 08:00 | 2008-11-26 12:00 | 363.5525 | 603.1667 | 6050 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 1210 | 7260
| 1.2.2.3.6.4.2 | Electronic Racks | 369 days | 2007-04-03 08:00 | 2008-11-26 12:00 | 363.5525 | 603.1667 | 0 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.3.6.5 | Cabling | 387 days | 2008-04-02 08:00 | 2009-12-31 12:00 | 384.6484 | 638.1667 | 93012 |  |  | Fixed Duration |  |  | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 18602.4 | 111614.4
| 1.2.2.3.6.5.1 | LV-PS Cables | 148 days | 2008-04-02 08:00 | 2008-11-26 15:00 | 143.6279 | 238.2917 | 23012 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 4602.4 | 27614.4
| 1.2.2.3.6.5.2 | HV Control Cables | 148 days | 2008-04-02 08:00 | 2008-11-26 15:00 | 143.6279 | 238.2917 | 6006 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 1201.2 | 7207.2
| 1.2.2.3.6.5.3 | Signal Cables | 148 days | 2008-04-02 08:00 | 2008-11-26 15:00 | 143.6279 | 238.2917 | 25000 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 5000 | 30000
| 1.2.2.3.6.5.4 | Assembly & Installation | 387 days | 2008-04-02 08:00 | 2009-12-31 12:00 | 384.6484 | 638.1667 | 38994 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 7798.8 | 46792.8
| 1.2.2.3.6.5.5 | Technical Support & Test | 387 days | 2008-04-02 08:00 | 2009-12-31 12:00 | 384.6484 | 638.1667 | 0 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.4 | Mechanical | 900.13 days | 2005-09-01 08:00 | 2009-09-30 11:00 | 898.1575 | 1490.125 | 2065783.26 |  |  | Fixed Duration |  |  | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 1322101.2864 | 3387884.5464
| 1.2.2.4.1 | Module assembly | 843.5 days | 2005-09-01 08:00 | 2009-06-30 14:00 | 842.7808 | 1398.25 | 1155105.56 |  |  | Fixed Duration |  |  | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 739267.5584 | 1894373.1184
| 1.2.2.4.1.1 | Design | 71 days | 2005-09-01 08:00 | 2005-12-29 16:00 | 71.9269 | 119.3333 | 80754.08 |  | 119 | Fixed Duration | 2005-09-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 51682.6112 | 132436.6912
| 1.2.2.4.1.2 | Prototype | 71 days | 2005-09-01 08:00 | 2005-12-29 16:00 | 71.9269 | 119.3333 | 114200.25 |  | 119 | Fixed Duration | 2005-09-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 73088.16 | 187288.41
|  | Module Assembly PRR | 0 days | 2005-12-29 16:00 | 2005-12-29 16:00 | 0 | 0 | 0 | 117,118 | 120 | Fixed Duration | 2005-12-29 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4.1.3 | Fabrication/Procurement | 737.25 days | 2006-03-01 08:00 | 2009-06-30 14:00 | 733.6849 | 1217.25 | 960151.23 | 119 |  | Fixed Duration |  |  | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 614496.7872 | 1574648.0172
| 1.2.2.4.1.3.1 | L-unit assembly | 737 days | 2006-03-01 08:00 | 2009-06-30 11:00 | 733.6096 | 1217.125 | 766388.63 |  |  | Fixed Duration | 2006-03-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 490488.7232 | 1256877.3532
| 1.2.2.4.1.3.2 | Detector unit Assembly | 737 days | 2006-03-01 08:00 | 2009-06-30 11:00 | 733.6096 | 1217.125 | 78606.47 |  |  | Fixed Duration | 2006-03-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 50308.1408 | 128914.6108
| 1.2.2.4.1.3.3 | PR Module Assembly | 699 days | 2006-05-01 08:00 | 2009-06-30 14:00 | 696.9178 | 1156.25 | 115156.13 |  |  | Fixed Duration | 2006-05-01 08:00 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 73699.9232 | 188856.0532
| 1.2.2.4.2 | Support structure | 331 days | 2006-01-02 08:00 | 2007-06-29 10:00 | 327.3379 | 543.0833 | 532956.25 |  |  | Fixed Duration |  |  | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 341092 | 874048.25
| 1.2.2.4.2.1 | Design | 220 days | 2006-01-02 08:00 | 2006-12-29 15:00 | 217.7648 | 361.2917 | 95004.8 |  | 127 | Fixed Duration | 2006-01-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 60803.072 | 155807.872
| 1.2.2.4.2.2 | Prototype | 220 days | 2006-01-02 08:00 | 2006-12-29 15:00 | 217.7648 | 361.2917 | 137951.45 |  | 127 | Fixed Duration | 2006-01-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 88288.928 | 226240.378
|  | Support Structure FDR/PRR | 0 days | 2006-12-29 15:00 | 2006-12-29 15:00 | 0 | 0 | 0 | 125,126 | 128 | Fixed Duration | 2006-12-29 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4.2.3 | Fabrication/Procurement | 111 days | 2007-01-02 08:00 | 2007-06-29 10:00 | 107.3379 | 178.0833 | 300000 | 127 | 186 | Fixed Duration | 2007-01-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 192000 | 492000
| 1.2.2.4.3 | Transport/storage | 829.13 days | 2006-01-02 08:00 | 2009-09-30 11:00 | 824.0205 | 1367.125 | 377721.45 |  |  | Fixed Duration |  |  | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 241741.728 | 619463.178
| 1.2.2.4.3.1 | Design | 112 days | 2006-01-02 08:00 | 2006-06-30 10:00 | 107.9406 | 179.0833 | 71253.6 |  | 132 | Fixed Duration | 2006-01-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 45602.304 | 116855.904
| 1.2.2.4.3.2 | Prototype | 112 days | 2006-01-02 08:00 | 2006-06-30 10:00 | 107.9406 | 179.0833 | 60449.05 |  | 132 | Fixed Duration | 2006-01-01 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 38687.392 | 99136.442
|  | Transport FDR | 0 days | 2006-06-30 10:00 | 2006-06-30 10:00 | 0 | 0 | 0 | 130,131 | 133 | Fixed Duration | 2006-06-30 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.4.3.3 | Fabrication/Procurement | 516 days | 2007-06-01 08:00 | 2009-09-30 11:00 | 513.6096 | 852.125 | 246018.8 | 132 |  | Fixed Duration | 2007-06-01 08:00 | Start No Earlier Than | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 64 | 157452.032 | 403470.832
|  | Start Shipping to BNL | 0 days | 2007-06-01 08:00 | 2007-06-01 08:00 | 0 | 0 | 0 |  | 192,194 | Fixed Duration | 2007-06-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5 | External PV | 884 days | 2006-01-02 08:00 | 2009-12-31 12:00 | 879.4977 | 1459.1667 | 2349644.43 |  |  | Fixed Duration |  |  | 4 | 10 | 8 | 15 | 4 | 2 | 1 | 25.1022 | 589813.1104 | 2939457.5404
| 1.2.2.5.1 | PMT - Instrumented Modules | 477.25 days | 2006-10-02 08:00 | 2008-11-26 14:00 | 473.9041 | 786.25 | 1449186 |  |  | Fixed Duration |  |  | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 25.5517 | 370291.92 | 1819477.92
| 1.2.2.5.1.1 | Modules | 477.25 days | 2006-10-02 08:00 | 2008-11-26 14:00 | 473.9041 | 786.25 | 778730 |  |  | Fixed Duration |  |  | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 155746 | 934476
| 1.2.2.5.1.1.1 | Scintillator Tiles | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 166496 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 33299.2 | 199795.2
| 1.2.2.5.1.1.2 | Lead Tiles | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 216522 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 43304.4 | 259826.4
| 1.2.2.5.1.1.3 | WLS Fiber | 370 days | 2007-01-03 08:00 | 2008-08-29 15:00 | 364.2306 | 604.2917 | 141700 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 28340 | 170040
| 1.2.2.5.1.1.4 | Assembly | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 187772 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 37554.4 | 225326.4
| 1.2.2.5.1.1.5 | Test | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 41472 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 8294.4 | 49766.4
| 1.2.2.5.1.1.6 | Packing | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 24768 |  | 176SS | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 4953.6 | 29721.6
|  | Start Module Shipping | 0 days | 2007-01-16 08:00 | 2007-01-16 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-01-16 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.1.2 | Module Instrumentation | 477.25 days | 2006-10-02 08:00 | 2008-11-26 14:00 | 473.9041 | 786.25 | 657496 |  |  | Fixed Duration |  |  | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 210398.72 | 867894.72
| 1.2.2.5.1.2.1 | Phototube | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 233860 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 74835.2 | 308695.2
| 1.2.2.5.1.2.2 | Preamplifier | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 34560 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 11059.2 | 45619.2
| 1.2.2.5.1.2.3 | LV-HV Converter | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 148610 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 47555.2 | 196165.2
| 1.2.2.5.1.2.4 | Mechanics | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 144000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 46080 | 190080
| 1.2.2.5.1.2.5 | Assembly | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 84098 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 26911.36 | 111009.36
| 1.2.2.5.1.2.6 | Test | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 5184 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 1658.88 | 6842.88
| 1.2.2.5.1.2.7 | Packing | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 7184 |  | 176SS | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 2298.88 | 9482.88
| 1.2.2.5.1.3 | Cosmic Ray Test of Module/PMT | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 12960 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 10 | 8 | 0 | 2 | 2 | 1 | 32 | 4147.2 | 17107.2
|  | Start Shipping Instrumentation | 0 days | 2007-01-16 08:00 | 2007-01-16 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-01-16 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.2 | Instrumentation | 568.88 days | 2006-12-01 08:00 | 2009-06-30 16:00 | 567.9817 | 942.3333 | 457617.02 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 26.186 | 119831.764 | 577448.784
| 1.2.2.5.2.1 | HV Control System | 236.75 days | 2006-12-01 08:00 | 2007-12-31 11:00 | 238.1575 | 395.125 | 100000 |  |  | Fixed Duration |  |  | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 16000 | 116000
| 1.2.2.5.2.1.1 | VME Carriers | 145 days | 2006-12-01 08:00 | 2007-07-31 11:00 | 145.9384 | 242.125 | 13000 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 2080 | 15080
| 1.2.2.5.2.1.2 | IP Modules | 145 days | 2006-12-01 08:00 | 2007-07-31 11:00 | 145.9384 | 242.125 | 67000 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 10720 | 77720
| 1.2.2.5.2.1.3 | VME/VXI Mainframes | 53 days | 2007-10-02 08:00 | 2007-12-31 11:00 | 54.3219 | 90.125 | 20000 |  |  | Fixed Duration | 2007-10-02 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 3200 | 23200
| 1.2.2.5.2.2 | Monitoring & Calibration System | 423.38 days | 2007-01-03 08:00 | 2008-11-25 15:00 | 417.2717 | 692.2917 | 56666 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 2 | 2 | 2 | 1 | 26 | 14733.16 | 71399.16
| 1.2.2.5.2.2.1 | Design | 202 days | 2007-01-03 08:00 | 2007-11-29 15:00 | 199.0799 | 330.2917 | 0 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.5.2.2.2 | Prototype | 202 days | 2007-01-03 08:00 | 2007-11-29 15:00 | 199.0799 | 330.2917 | 0 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 2 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.5.2.2.3 | Fabrication/Procurement | 237 days | 2007-11-01 08:00 | 2008-11-25 15:00 | 235.2443 | 390.2917 | 56666 |  |  | Fixed Duration | 2007-11-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 2 | 2 | 2 | 1 | 26 | 14733.16 | 71399.16
| 1.2.2.5.2.3 | Readout Electronics | 552.75 days | 2007-01-02 08:00 | 2009-06-30 16:00 | 548.6941 | 910.3333 | 275331.02 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 4 | 2 | 2 | 1 | 30.4995 | 83974.604 | 359305.624
| 1.2.2.5.2.3.1 | WFD Boards | 474.88 days | 2007-01-03 08:00 | 2009-02-27 10:00 | 473.8037 | 786.0833 | 243841.02 |  |  | Fixed Duration |  |  | 8 | 4 | 4 | 4 | 2 | 2 | 1 | 31.3385 | 76416.204 | 320257.224
| 1.2.2.5.2.3.1.3 | Fabrication/Procurement | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 230400 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 8 | 4 | 4 | 4 | 2 | 2 | 1 | 32 | 73728 | 304128
| 1.2.2.5.2.3.1.5 | Test | 420 days | 2007-04-03 08:00 | 2009-02-27 10:00 | 419.5571 | 696.0833 | 13441.02 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 2688.204 | 16129.224
| 1.2.2.5.2.3.2 | Crate Data-Collection Boards | 475.63 days | 2007-01-02 08:00 | 2009-02-27 09:00 | 474.3813 | 787.0417 | 12600 |  |  | Fixed Duration |  |  | 8 | 4 | 8 | 4 | 2 | 2 | 1 | 36 | 4536 | 17136
| 1.2.2.5.2.3.2.3 | Fabrication/Procurement | 424 days | 2007-01-02 08:00 | 2008-11-25 12:00 | 417.7991 | 693.1667 | 12600 |  |  | Fixed Duration | 2007-01-02 08:00 | Start No Earlier Than | 8 | 4 | 8 | 4 | 2 | 2 | 1 | 36 | 4536 | 17136
| 1.2.2.5.2.3.2.5 | Test | 309 days | 2007-10-01 08:00 | 2009-02-27 09:00 | 310.4361 | 515.0417 | 0 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.5.2.3.3 | VXI Mainframes & Controller | 420 days | 2007-04-03 08:00 | 2009-02-27 10:00 | 419.5571 | 696.0833 | 18890 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 0 | 2 | 2 | 1 | 16 | 3022.4 | 21912.4
| 1.2.2.5.2.3.4 | System tests | 162 days | 2008-10-02 08:00 | 2009-06-30 16:00 | 163.5434 | 271.3333 | 0 |  |  | Fixed Duration | 2008-10-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.5.2.4 | Electronic Racks & LV Power Supplies | 369 days | 2007-04-03 08:00 | 2008-11-26 12:00 | 363.5525 | 603.1667 | 25620 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 5124 | 30744
| 1.2.2.5.2.4.1 | LV Power Supplies | 369 days | 2007-04-03 08:00 | 2008-11-26 12:00 | 363.5525 | 603.1667 | 12810 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 2562 | 15372
| 1.2.2.5.2.4.2 | Electronic Racks | 369 days | 2007-04-03 08:00 | 2008-11-26 12:00 | 363.5525 | 603.1667 | 12810 |  |  | Fixed Duration | 2007-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 2562 | 15372
| 1.2.2.5.3 | Shipping | 424 days | 2007-02-01 08:00 | 2008-12-31 12:00 | 421.4155 | 699.1667 | 80000 | 143SS,152SS |  | Fixed Duration | 2007-02-01 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 19200 | 99200
| 1.2.2.5.4 | Assembly & Test | 440 days | 2007-03-02 08:00 | 2009-02-27 15:00 | 438.9703 | 728.2917 | 198028.61 |  |  | Fixed Duration |  |  | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 47526.8664 | 245555.4764
| 1.2.2.5.4.1 | Mechanical & Optical Test | 440 days | 2007-03-02 08:00 | 2009-02-27 15:00 | 438.9703 | 728.2917 | 131045.48 |  |  | Fixed Duration | 2007-03-02 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 31450.9152 | 162496.3952
| 1.2.2.5.4.2 | Cosmic Ray Test | 440 days | 2007-03-02 08:00 | 2009-02-27 15:00 | 438.9703 | 728.2917 | 66983.13 |  |  | Fixed Duration | 2007-03-02 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 16075.9512 | 83059.0812
| 1.2.2.5.4.3 | Technical Support | 440 days | 2007-03-02 08:00 | 2009-02-27 15:00 | 438.9703 | 728.2917 | 0 |  |  | Fixed Duration | 2007-03-02 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 0 | 0 | 0
| 1.2.2.5.5 | Cabling | 884 days | 2006-01-02 08:00 | 2009-12-31 12:00 | 879.4977 | 1459.1667 | 164812.8 |  |  | Fixed Duration |  |  | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 32962.56 | 197775.36
| 1.2.2.5.5.1 | Signal/HV cables inside module | 754 days | 2006-01-02 08:00 | 2009-06-01 15:00 | 751.1895 | 1246.2917 | 72196.8 |  |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 14439.36 | 86636.16
| 1.2.2.5.5.2 | LV-PS Cables | 148 days | 2008-04-02 08:00 | 2008-11-26 15:00 | 143.6279 | 238.2917 | 22616 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 4523.2 | 27139.2
| 1.2.2.5.5.3 | HV Control Cables | 148 days | 2008-04-02 08:00 | 2008-11-26 15:00 | 143.6279 | 238.2917 | 6006 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 1201.2 | 7207.2
| 1.2.2.5.5.4 | Signal Cables | 148 days | 2008-04-02 08:00 | 2008-11-26 15:00 | 143.6279 | 238.2917 | 25000 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 5000 | 30000
| 1.2.2.5.5.5 | Assembly & Installation | 387 days | 2008-04-02 08:00 | 2009-12-31 12:00 | 384.6484 | 638.1667 | 38994 | 128 |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 7798.8 | 46792.8
| 1.2.2.5.5.6 | Technical Support & Test | 387 days | 2008-04-02 08:00 | 2009-12-31 12:00 | 384.6484 | 638.1667 | 0 |  |  | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.2.6 | Work at BNL | 883.75 days | 2006-01-02 08:00 | 2009-12-31 10:00 | 879.4475 | 1459.0833 | 413986.92 |  |  | Fixed Duration |  |  | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 56 | 231832.6752 | 645819.5952
| 1.2.2.6.1 | Pre-installation work at BNL | 848.75 days | 2006-01-02 08:00 | 2009-10-30 11:00 | 842.1027 | 1397.125 | 301423.61 |  |  | Fixed Duration |  |  | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 56 | 168797.2216 | 470220.8316
| 1.2.2.6.1.1 | Design | 220 days | 2006-01-02 08:00 | 2006-12-29 15:00 | 217.7648 | 361.2917 | 0 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 0 | 0 | 0
| 1.2.2.6.1.2 | Prototype | 220 days | 2006-01-02 08:00 | 2006-12-29 15:00 | 217.7648 | 361.2917 | 0 |  |  | Fixed Duration | 2006-01-01 | Start No Earlier Than | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 0 | 0 | 0
|  | Start Module Pre-Install Work at BNL | 0 days | 2007-07-02 08:00 | 2007-07-02 08:00 | 0 | 0 | 0 | 134 |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.2.6.1.3 | Fabrication/Procurement | 517 days | 2007-07-02 08:00 | 2009-10-30 11:00 | 513.0068 | 851.125 | 301423.61 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 56 | 168797.2216 | 470220.8316
| 1.2.2.6.2 | Installation monitoring | 552 days | 2007-07-02 08:00 | 2009-12-31 10:00 | 550.3516 | 913.0833 | 112563.31 | 134 |  | Fixed Duration |  |  | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 56 | 63035.4536 | 175598.7636
| 1.2.2.6.2.3 | Fabrication/Procurement | 552 days | 2007-07-02 08:00 | 2009-12-31 10:00 | 550.3516 | 913.0833 | 112563.31 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 56 | 63035.4536 | 175598.7636
| 1.2.2.10 | Management | 1106 days | 2005-01-03 08:00 | 2009-12-31 09:00 | 1098.8196 | 1823.0417 | 475024 |  |  | Fixed Duration | 2005-01-01 | Start No Earlier Than | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 4 | 19000.96 | 494024.96
| Count All | 196 | [5 empty] | Count | 42 | 39 |  | 135
[8 empty] | Assigned | 0.21429 | 0.19898
[8 empty] | Missing | 0.78571 | 0.80102

## 1.2.2 Durations & Milestone
| Excessive Durations |  |  | Sort by |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration
1.2.2.3.6.2.3 | Fabrication/Procurement | 2007-11-01 08:00 | 2008-11-25 15:00 | 1.0693 |  | Anode PRR | 2005-10-31 11:00 | 2005-10-31 11:00 | 0 days
1.2.2.5.2.2.3 | Fabrication/Procurement | 2007-11-01 08:00 | 2008-11-25 15:00 | 1.0693 |  | Cathode PRR | 2005-10-31 11:00 | 2005-10-31 11:00 | 0 days
1.2.2.3.6.1 | HV Control System | 2006-12-01 08:00 | 2007-12-31 11:00 | 1.0825 |  | WLS Fiber PRR | 2005-10-31 14:00 | 2005-10-31 14:00 | 0 days
1.2.2.5.2.1 | HV Control System | 2006-12-01 08:00 | 2007-12-31 11:00 | 1.0825 |  | Chamber FDR/PRR Review | 2005-10-31 17:00 | 2005-10-31 17:00 | 0 days
1.2.2.2.1.3.1 | Scintillator production | 2005-11-01 08:00 | 2006-12-28 16:00 | 1.1571 |  | Scintillator Plate FDR/PRR | 2005-10-31 17:00 | 2005-10-31 17:00 | 0 days
1.2.2.3.6.3.2.5 | Test | 2007-10-01 08:00 | 2009-02-27 09:00 | 1.4111 |  | Controller PRR | 2005-12-28 16:00 | 2005-12-28 16:00 | 0 days
1.2.2.5.2.3.2.5 | Test | 2007-10-01 08:00 | 2009-02-27 09:00 | 1.4111 |  | HV PRR | 2005-12-29 09:00 | 2005-12-29 09:00 | 0 days
1.2.2.4.2 | Support structure | 2006-01-02 08:00 | 2007-06-29 10:00 | 1.4879 |  | Module Assembly PRR | 2005-12-29 16:00 | 2005-12-29 16:00 | 0 days
1.2.2.3.6.4 | Electronic Racks & LV Power Supplies | 2007-04-03 08:00 | 2008-11-26 12:00 | 1.6525 |  | Gas FDR | 2006-03-01 08:00 | 2006-03-01 08:00 | 0 days
1.2.2.3.6.4.1 | LV Power Supplies | 2007-04-03 08:00 | 2008-11-26 12:00 | 1.6525 |  | Transport FDR | 2006-06-30 10:00 | 2006-06-30 10:00 | 0 days
1.2.2.3.6.4.2 | Electronic Racks | 2007-04-03 08:00 | 2008-11-26 12:00 | 1.6525 |  | Support Structure FDR/PRR | 2006-12-29 15:00 | 2006-12-29 15:00 | 0 days
1.2.2.5.2.4 | Electronic Racks & LV Power Supplies | 2007-04-03 08:00 | 2008-11-26 12:00 | 1.6525 |  | Start Module Shipping | 2007-01-16 08:00 | 2007-01-16 08:00 | 0 days
1.2.2.5.2.4.1 | LV Power Supplies | 2007-04-03 08:00 | 2008-11-26 12:00 | 1.6525 |  | Start Shipping Instrumentation | 2007-01-16 08:00 | 2007-01-16 08:00 | 0 days
1.2.2.5.2.4.2 | Electronic Racks | 2007-04-03 08:00 | 2008-11-26 12:00 | 1.6525 |  | Start Shipping to BNL | 2007-06-01 08:00 | 2007-06-01 08:00 | 0 days
1.2.2.5.1.1.3 | WLS Fiber | 2007-01-03 08:00 | 2008-08-29 15:00 | 1.6556 |  | Gas System Complete | 2007-06-29 10:00 | 2007-06-29 10:00 | 0 days
1.2.2.3.6.5 | Cabling | 2008-04-02 08:00 | 2009-12-31 12:00 | 1.7484 |  | Start Module Pre-Install Work at BNL | 2007-07-02 08:00 | 2007-07-02 08:00 | 0 days
1.2.2.3.6.5.4 | Assembly & Installation | 2008-04-02 08:00 | 2009-12-31 12:00 | 1.7484 |  | Chamber Production Complete | 2009-06-30 09:00 | 2009-06-30 09:00 | 0 days
1.2.2.3.6.5.5 | Technical Support & Test | 2008-04-02 08:00 | 2009-12-31 12:00 | 1.7484 |  | Count | 17
1.2.2.5.5.5 | Assembly & Installation | 2008-04-02 08:00 | 2009-12-31 12:00 | 1.7484
1.2.2.5.5.6 | Technical Support & Test | 2008-04-02 08:00 | 2009-12-31 12:00 | 1.7484
1.2.2.1.2 | Gas System | 2005-09-01 08:00 | 2007-06-29 10:00 | 1.8249
1.2.2.3.6.2 | Monitoring & Calibration System | 2007-01-03 08:00 | 2008-11-25 15:00 | 1.8967
1.2.2.5.2.2 | Monitoring & Calibration System | 2007-01-03 08:00 | 2008-11-25 15:00 | 1.8967
1.2.2.5.2.3.2.3 | Fabrication/Procurement | 2007-01-02 08:00 | 2008-11-25 12:00 | 1.8991
1.2.2.3.6.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.1.1.4 | Assembly | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.1.1.5 | Test | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.1.1.6 | Packing | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.1.2.5 | Assembly | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.1.2.6 | Test | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.1.2.7 | Packing | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.1.3 | Cosmic Ray Test of Module/PMT | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.5.2.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993
1.2.2.3.6.3.2.3 | Fabrication/Procurement | 2007-01-02 08:00 | 2008-11-26 15:00 | 1.9022
1.2.2.3.6.3.3 | VXI Mainframes & Controller | 2007-04-03 08:00 | 2009-02-26 09:00 | 1.9042
1.2.2.3.6.3.1.5 | Test | 2007-04-03 08:00 | 2009-02-27 10:00 | 1.9071
1.2.2.5.2.3.1.5 | Test | 2007-04-03 08:00 | 2009-02-27 10:00 | 1.9071
1.2.2.5.2.3.3 | VXI Mainframes & Controller | 2007-04-03 08:00 | 2009-02-27 10:00 | 1.9071
1.2.2.5.1.1.1 | Scintillator Tiles | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.2.5.1.1.2 | Lead Tiles | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.2.5.1.2.1 | Phototube | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.2.5.1.2.2 | Preamplifier | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.2.5.1.2.3 | LV-HV Converter | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.2.5.1.2.4 | Mechanics | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.2.5.3 | Shipping | 2007-02-01 08:00 | 2008-12-31 12:00 | 1.9155
1.2.2.5.4 | Assembly & Test | 2007-03-02 08:00 | 2009-02-27 15:00 | 1.9953
1.2.2.5.4.1 | Mechanical & Optical Test | 2007-03-02 08:00 | 2009-02-27 15:00 | 1.9953
1.2.2.5.4.2 | Cosmic Ray Test | 2007-03-02 08:00 | 2009-02-27 15:00 | 1.9953
1.2.2.5.4.3 | Technical Support | 2007-03-02 08:00 | 2009-02-27 15:00 | 1.9953
1.2.2.3.6.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-02-27 10:00 | 2.1537
1.2.2.5.2.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-02-27 10:00 | 2.1537
1.2.2.5.1 | PMT - Instrumented Modules | 2006-10-02 08:00 | 2008-11-26 14:00 | 2.1541
1.2.2.5.1.1 | Modules | 2006-10-02 08:00 | 2008-11-26 14:00 | 2.1541
1.2.2.5.1.2 | Module Instrumentation | 2006-10-02 08:00 | 2008-11-26 14:00 | 2.1541
1.2.2.3.6.3.2 | Crate Data-Collection Boards | 2007-01-02 08:00 | 2009-02-27 09:00 | 2.1563
1.2.2.5.2.3.2 | Crate Data-Collection Boards | 2007-01-02 08:00 | 2009-02-27 09:00 | 2.1563
1.2.2.6.1.3 | Fabrication/Procurement | 2007-07-02 08:00 | 2009-10-30 11:00 | 2.3318
1.2.2.4.3.3 | Fabrication/Procurement | 2007-06-01 08:00 | 2009-09-30 11:00 | 2.3346
1.2.2.3.6.3 | Readout Electronics | 2007-01-02 08:00 | 2009-06-30 16:00 | 2.4941
1.2.2.5.2.3 | Readout Electronics | 2007-01-02 08:00 | 2009-06-30 16:00 | 2.4941
1.2.2.6.2 | Installation monitoring | 2007-07-02 08:00 | 2009-12-31 10:00 | 2.5016
1.2.2.6.2.3 | Fabrication/Procurement | 2007-07-02 08:00 | 2009-12-31 10:00 | 2.5016
1.2.2.5.2 | Instrumentation | 2006-12-01 08:00 | 2009-06-30 16:00 | 2.5817
1.2.2.2.2.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2008-12-31 16:00 | 2.9982
1.2.2.2.2.3.1 | Fiber | 2006-01-02 08:00 | 2008-12-31 16:00 | 2.9982
1.2.2.2.2.3.2 | Coupler | 2006-01-02 08:00 | 2008-12-31 16:00 | 2.9982
1.2.2.3.6 | Scintillator Electronics | 2006-12-01 08:00 | 2009-12-31 12:00 | 3.0854
1.2.2.4.1.3.3 | PR Module Assembly | 2006-05-01 08:00 | 2009-06-30 14:00 | 3.1678
1.2.2.4.1.3.1 | L-unit assembly | 2006-03-01 08:00 | 2009-06-30 11:00 | 3.3346
1.2.2.4.1.3.2 | Detector unit Assembly | 2006-03-01 08:00 | 2009-06-30 11:00 | 3.3346
1.2.2.4.1.3 | Fabrication/Procurement | 2006-03-01 08:00 | 2009-06-30 14:00 | 3.3349
1.2.2.5.5.1 | Signal/HV cables inside module | 2006-01-02 08:00 | 2009-06-01 15:00 | 3.4145
1.2.2.2.1.3.3 | Fiber installation | 2006-01-17 08:00 | 2009-06-30 16:00 | 3.453
1.2.2.2.1.3.4 | Tests | 2006-01-17 08:00 | 2009-06-30 16:00 | 3.453
1.2.2.1.1.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.1.1.3.1 | Cathode strips | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.1.1.3.2 | Frame assembly | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.1.1.3.3 | Stringing | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.1.1.3.4 | Chamber assembly | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.1.1.3.5 | Tests | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.1.3.2 | Plane fabrication | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3 | Scintillator readout | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.1 | Photo Tube | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.1.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.2 | MU Metal Shield/Bases | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.2.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.3 | Cables | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.3.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.4 | Preampifier | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.4.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.5 | LV-HV converter | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.3.5.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.1.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.1.3.1 | Adaptor Cards | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.1.3.2 | Readout Cards | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.1.3.3 | Cables | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.2.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.2.3.1 | Adaptor Cards | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.2.3.2 | Readout Cards | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.2.3.3 | Cables | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.3.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.3.3.1 | HV source | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.3.3.2 | HV cards | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.4.3 | Production | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.4.3.1 | Mechanical | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.4.3.2 | LV source | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.5.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.5.3.1 | Chamber collector cards | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.3.5.3.2 | Module collector cards | 2006-01-02 08:00 | 2009-06-30 09:00 | 3.4933
1.2.2.2.1.3 | Fabrication/Procurement | 2005-11-01 08:00 | 2009-06-30 16:00 | 3.6639
1.2.2.4.3 | Transport/storage | 2006-01-02 08:00 | 2009-09-30 11:00 | 3.7455
1.2.2.2.2 | WLS fiber | 2005-04-01 08:00 | 2008-12-31 16:00 | 3.7543
1.2.2.6.1 | Pre-installation work at BNL | 2006-01-02 08:00 | 2009-10-30 11:00 | 3.8277
1.2.2.4.1 | Module assembly | 2005-09-01 08:00 | 2009-06-30 14:00 | 3.8308
1.2.2.6 | Work at BNL | 2006-01-02 08:00 | 2009-12-31 10:00 | 3.9975
1.2.2.5 | External PV | 2006-01-02 08:00 | 2009-12-31 12:00 | 3.9977
1.2.2.5.5 | Cabling | 2006-01-02 08:00 | 2009-12-31 12:00 | 3.9977
1.2.2.3.5 | Controller cards | 2005-06-01 08:00 | 2009-06-30 09:00 | 4.0823
1.2.2.4 | Mechanical | 2005-09-01 08:00 | 2009-09-30 11:00 | 4.0825
1.2.2.1 | Chamber System | 2005-03-01 08:00 | 2009-06-30 09:00 | 4.3344
1.2.2.1.1 | Chambers | 2005-03-01 08:00 | 2009-06-30 09:00 | 4.3344
1.2.2.3.3 | HV | 2005-03-01 08:00 | 2009-06-30 09:00 | 4.3344
1.2.2.3.4 | Crate Assembly | 2005-03-01 08:00 | 2009-06-30 09:00 | 4.3344
1.2.2.2 | Scintillator System | 2005-03-01 08:00 | 2009-06-30 16:00 | 4.3352
1.2.2.2.1 | Scintillator Plates | 2005-03-01 08:00 | 2009-06-30 16:00 | 4.3352
1.2.2.3.1 | Anode Electronics | 2005-01-03 08:00 | 2009-06-30 09:00 | 4.4905
1.2.2.3.2 | Cathode Electronics | 2005-01-03 08:00 | 2009-06-30 09:00 | 4.4905
1.2.2.10 | Management | 2005-01-03 08:00 | 2009-12-31 09:00 | 4.9946
1.2.2 | Preradiator | 2005-01-03 08:00 | 2009-12-31 12:00 | 4.995 | OK
1.2.2.3 | Electronics | 2005-01-03 08:00 | 2009-12-31 12:00 | 4.995
|  |  | Count Excessive | 130
>1 year
66.33%

## 1.2.3 Observations
Observations |  | WBS 1.2.3 Calorimeter | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
Project Start Date | 2004-10-04
Project Finish Date | 2011-09-30
Project Calendar | Kopio Standard | 220 work days per yr. (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Count Tasks | 116
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 81.03%
Successors | Missing | 87.93%
Task Type (Units,Work,Duration) | Mostly Duration | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 90, (78%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 7.1
Hours/week | 35.5
Hours/year | 1760
Days/month | 18 | ~220 work days /12 months (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Excessive Durations | 43 Tasks | 37%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 16 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
| 1.2.3 | Calorimeter System | 1325 days | 2005-10-03 08:00 | 2011-09-30 12:00 | 1318.895 | 2188.1667 | 5293037.28 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.1314 | 1065560.5384 | 6358597.8184
| 1.2.3.1 | System Prototype | 624.75 days | 2005-10-03 08:00 | 2008-07-31 15:00 | 622.2032 | 1032.2917 | 550712.48 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.4424 | 118085.8448 | 668798.3248
| 1.2.3.1.1 | Modules | 165 days | 2005-10-03 08:00 | 2006-06-30 16:00 | 162.9406 | 270.3333 | 87496 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 2 | 2 | 0 | 2 | 1 | 1 | 12 | 10499.52 | 97995.52
| 1.2.3.1.2 | Modules Instrumentation | 164.25 days | 2005-10-03 08:00 | 2006-06-30 09:00 | 162.7648 | 270.0417 | 165302 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 33060.4 | 198362.4
| 1.2.3.1.2.1 | Design of APD-unit | 52 days | 2005-10-03 08:00 | 2005-12-29 12:00 | 52.5388 | 87.1667 | 13536 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 2707.2 | 16243.2
|  | APD Design Review | 0 days | 2005-12-15 08:00 | 2005-12-15 08:00 | 0 | 0 | 0 |  | 8 | Fixed Duration | 2005-12-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.2.2 | Prototyping of APD-unit | 52 days | 2005-10-03 08:00 | 2005-12-29 12:00 | 52.5388 | 87.1667 | 20162 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 4032.4 | 24194.4
| 1.2.3.1.2.3 | Fabrication of 100 APD-unit | 111 days | 2006-01-03 08:00 | 2006-06-30 09:00 | 107.3128 | 178.0417 | 131604 | 6 |  | Fixed Duration | 2006-01-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 26320.8 | 157924.8
|  | Fabrication Complete | 0 days | 2006-06-30 08:00 | 2006-06-30 08:00 | 0 | 0 | 0 |  | 26 | Fixed Duration | 2006-06-30 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.3 | Mechanics | 91 days | 2006-07-03 08:00 | 2006-11-30 15:00 | 90.5868 | 150.2917 | 30004 |  | 27 | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 7801.04 | 37805.04
| 1.2.3.1.4 | Cooling System | 91 days | 2006-07-03 08:00 | 2006-11-30 15:00 | 90.5868 | 150.2917 | 16759.6 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 4357.496 | 21117.096
| 1.2.3.1.5 | HV Control System | 72 days | 2006-01-03 08:00 | 2006-04-28 11:00 | 69.3904 | 115.125 | 16000 |  | 28 | Fixed Duration | 2006-01-03 08:00 | Start No Earlier Than | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 4160 | 20160
|  | HV Design Review | 0 days | 2006-02-28 08:00 | 2006-02-28 08:00 | 0 | 0 | 0 |  | 76 | Fixed Duration | 2006-02-28 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.6 | Cosmic Ray Pre-Calibration System | 51 days | 2006-10-03 08:00 | 2006-12-29 10:00 | 52.4886 | 87.0833 | 9996 |  |  | Fixed Duration | 2006-10-03 08:00 | Start No Earlier Than | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 2598.96 | 12594.96
| 1.2.3.1.7 | LED Monitoring System | 164.25 days | 2005-10-03 08:00 | 2006-06-30 09:00 | 162.7648 | 270.0417 | 29968 |  |  | Fixed Duration |  |  | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 20 | 5993.6 | 35961.6
| 1.2.3.1.7.1 | Design | 52 days | 2005-10-03 08:00 | 2005-12-29 12:00 | 52.5388 | 87.1667 | 10560 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 2112 | 12672
|  | LED Design Review | 0 days | 2005-12-15 08:00 | 2005-12-15 08:00 | 0 | 0 | 0 |  | 18,19,81 | Fixed Duration | 2005-12-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.7.2 | Prototyping | 55 days | 2006-01-03 08:00 | 2006-03-31 17:00 | 52.6644 | 87.375 | 14984 | 17 |  | Fixed Duration | 2006-01-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 2996.8 | 17980.8
| 1.2.3.1.7.3 | Fabrication & Test | 56 days | 2006-04-03 08:00 | 2006-06-30 09:00 | 53.0662 | 88.0417 | 4424 | 17 |  | Fixed Duration | 2006-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 884.8 | 5308.8
| 1.2.3.1.8 | WFD Readout | 239.13 days | 2005-10-03 08:00 | 2006-10-31 12:00 | 236.9772 | 393.1667 | 138498.88 |  |  | Fixed Duration |  |  | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 36009.7088 | 174508.5888
| 1.2.3.1.8.1 | Design Modifications | 108 days | 2005-10-03 08:00 | 2006-03-31 15:00 | 108.0662 | 179.2917 | 37914.8 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 9857.848 | 47772.648
|  | WFD Design Review | 0 days | 2006-03-31 17:00 | 2006-03-31 17:00 | 0 | 0 | 0 |  | 23FS-60 days,24,84 | Fixed Duration | 2006-03-31 17:00 | Finish No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.1.8.2 | Prototyping | 111 days | 2006-01-03 08:00 | 2006-06-30 09:00 | 107.3128 | 178.0417 | 62049.44 | 22FS-60 days |  | Fixed Duration | 2006-01-03 08:00 | Start No Earlier Than | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 16132.8544 | 78182.2944
| 1.2.3.1.8.3 | Fabrication & Test | 74 days | 2006-07-05 08:00 | 2006-10-31 12:00 | 71.2237 | 118.1667 | 38534.64 | 22 |  | Fixed Duration | 2006-07-05 08:00 | Start No Earlier Than | 4 | 4 | 2 | 4 | 4 | 1 | 1 | 26 | 10019.0064 | 48553.6464
| 1.2.3.1.9 | Shipping | 125.25 days | 2006-07-05 08:00 | 2007-01-31 11:00 | 126.6507 | 210.125 | 10000 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 2400 | 12400
| 1.2.3.1.9.1 | Shipping #1 | 16 days | 2006-07-05 08:00 | 2006-07-31 10:00 | 15.7215 | 26.0833 | 5000 | 9 |  | Fixed Duration | 2006-07-05 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 1200 | 6200
| 1.2.3.1.9.2 | Shipping #2 | 18 days | 2007-01-02 08:00 | 2007-01-31 11:00 | 17.5548 | 29.125 | 5000 | 10 |  | Fixed Duration | 2007-01-02 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 1200 | 6200
| 1.2.3.1.10 | Test & Study | 443 days | 2006-08-01 08:00 | 2008-07-31 15:00 | 440.1758 | 730.2917 | 46688 | 12 |  | Fixed Duration | 2006-08-01 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 11205.12 | 57893.12
| 1.2.3.2 | Photon Calorimeter | 697.38 days | 2005-10-03 08:00 | 2008-11-26 15:00 | 693.3265 | 1150.2917 | 3151285.6 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.2967 | 576579.98 | 3727865.58
| 1.2.3.2.1 | Design | 181.25 days | 2005-10-03 08:00 | 2006-07-31 11:00 | 181.5 | 301.125 | 49992 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 12498 | 62490
| 1.2.3.2.1.1 | Conceptual Design | 52 days | 2005-10-03 08:00 | 2005-12-29 12:00 | 52.5388 | 87.1667 | 13992 |  | 33 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 3 | 3 | 8 | 8 | 2 | 1 | 1 | 25 | 3498 | 17490
|  | Calorimeter Design Review | 0 days | 2006-07-05 08:00 | 2006-07-05 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-07-05 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.1.2 | Technical Design | 128 days | 2006-01-03 08:00 | 2006-07-31 11:00 | 126.0479 | 209.125 | 36000 | 31 | 37,45 | Fixed Duration | 2006-01-03 08:00 | Start No Earlier Than | 3 | 3 | 8 | 8 | 2 | 1 | 1 | 25 | 9000 | 45000
| 1.2.3.2.2 | Tools & Test Equipment Modification | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 124006 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 24801.2 | 148807.2
| 1.2.3.2.2.1 | Cosmic Ray Setup | 87 days | 2006-10-02 08:00 | 2007-02-28 10:00 | 89.8584 | 149.0833 | 30004 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 6000.8 | 36004.8
| 1.2.3.2.2.2 | Molding Forms and Stamps | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 94002 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 18800.4 | 112802.4
| 1.2.3.2.3 | Module Production | 477.25 days | 2006-10-02 08:00 | 2008-11-26 14:00 | 473.9041 | 786.25 | 1148200 | 33 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 229640 | 1377840
| 1.2.3.2.3.1 | Scintillator Tiles | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 257660 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 51532 | 309192
| 1.2.3.2.3.2 | Lead Tiles | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 321354 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 64270.8 | 385624.8
| 1.2.3.2.3.3 | WLS Fiber | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 211398 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 42279.6 | 253677.6
| 1.2.3.2.3.4 | Assembly | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 272608 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 54521.6 | 327129.6
|  | Assembly Complete | 0 days | 2008-11-26 08:00 | 2008-11-26 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-11-26 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.3.5 | Module Test | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 52704 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 10540.8 | 63244.8
| 1.2.3.2.3.6 | Module Packing | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 32476 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 6495.2 | 38971.2
| 1.2.3.2.4 | Module Instrumentation | 477.25 days | 2006-10-02 08:00 | 2008-11-26 14:00 | 473.9041 | 786.25 | 1335816 | 33 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7687 | 197283.12 | 1533099.12
| 1.2.3.2.4.1 | APD | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 945402 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 132356.28 | 1077758.28
| 1.2.3.2.4.2 | Preamplifier | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 39100 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 7038 | 46138
| 1.2.3.2.4.3 | LV-HV Converter | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 130562 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 18278.68 | 148840.68
| 1.2.3.2.4.4 | Mechanics & PC Boards | 423 days | 2006-10-02 08:00 | 2008-08-29 12:00 | 420.21 | 697.1667 | 67250 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 12105 | 79355
| 1.2.3.2.4.5 | APD Units Assembly | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 129366 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 23285.88 | 152651.88
|  | APD Assembly Complete | 0 days | 2008-11-26 08:00 | 2008-11-26 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-11-26 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.4.6 | APD Units Test | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 14004 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 2800.8 | 16804.8
| 1.2.3.2.4.7 | APD Units Packing | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 10132 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 1418.48 | 11550.48
| 1.2.3.2.5 | Cosmic Ray Test of Module/APD | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 12999.6 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 2599.92 | 15599.52
| 1.2.3.2.6 | Beam Liner Module's Production | 167 days | 2008-03-03 08:00 | 2008-11-26 09:00 | 161.5594 | 268.0417 | 65254 |  |  | Fixed Duration | 2008-03-03 08:00 | Start No Earlier Than | 4 | 4 | 2 | 15 | 4 | 2 | 1 | 41 | 26754.14 | 92008.14
| 1.2.3.2.7 | Photon Calorimeter Mechanics | 424.13 days | 2007-01-03 08:00 | 2008-11-26 15:00 | 417.8744 | 693.2917 | 415018 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 83003.6 | 498021.6
| 1.2.3.2.7.1 | Support Frame | 312.88 days | 2007-01-03 08:00 | 2008-05-30 11:00 | 309.2808 | 513.125 | 194986 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 38997.2 | 233983.2
| 1.2.3.2.7.1.1 | Production Dwgs | 110 days | 2007-01-03 08:00 | 2007-06-29 09:00 | 106.71 | 177.0417 | 19992 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 3998.4 | 23990.4
|  | Support Frame Design Review | 0 days | 2007-06-29 08:00 | 2007-06-29 08:00 | 0 | 0 | 0 |  | 60 | Fixed Duration | 2007-06-29 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.7.1.2 | Fabrication/Procurement | 202 days | 2007-07-02 08:00 | 2008-05-30 11:00 | 200.7877 | 333.125 | 174994 | 59 |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 34998.8 | 209992.8
| 1.2.3.2.7.2 | Cooling System | 258.88 days | 2007-07-02 08:00 | 2008-08-29 12:00 | 255.6621 | 424.1667 | 120012 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 24002.4 | 144014.4
| 1.2.3.2.7.2.1 | Production Dwgs | 54 days | 2007-07-02 08:00 | 2007-09-27 16:00 | 52.6393 | 87.3333 | 10008 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 2001.6 | 12009.6
|  | Cooling Design Review | 0 days | 2007-09-27 08:00 | 2007-09-27 08:00 | 0 | 0 | 0 |  | 64 | Fixed Duration | 2007-09-27 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.7.2.2 | Fabrication/Procurement | 204 days | 2007-10-01 08:00 | 2008-08-29 12:00 | 200.8128 | 333.1667 | 110004 | 63 |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 22000.8 | 132004.8
| 1.2.3.2.7.3 | Railway System | 204.5 days | 2007-10-01 08:00 | 2008-08-29 17:00 | 200.9384 | 333.375 | 40006 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 8001.2 | 48007.2
| 1.2.3.2.7.3.1 | Production Dwgs | 54 days | 2007-10-01 08:00 | 2007-12-31 11:00 | 54.9247 | 91.125 | 10008 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 2001.6 | 12009.6
|  | Railway Design Review | 0 days | 2007-12-31 08:00 | 2007-12-31 08:00 | 0 | 0 | 0 |  | 68 | Fixed Duration | 2007-12-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.7.3.2 | Fabrication/Procurement | 149 days | 2008-01-03 08:00 | 2008-08-29 17:00 | 144.2808 | 239.375 | 29998 | 67 |  | Fixed Duration | 2008-01-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 5999.6 | 35997.6
| 1.2.3.2.7.4 | Assembly & Service Tools | 202.88 days | 2008-01-03 08:00 | 2008-11-26 15:00 | 197.8744 | 328.2917 | 60014 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12002.8 | 72016.8
| 1.2.3.2.7.4.1 | Production Dwgs | 53 days | 2008-01-03 08:00 | 2008-03-31 09:00 | 53.0662 | 88.0417 | 10008 |  |  | Fixed Duration | 2008-01-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 2001.6 | 12009.6
|  | Assembly and Service Tools Design Review | 0 days | 2008-03-31 08:00 | 2008-03-31 08:00 | 0 | 0 | 0 |  | 72 | Fixed Duration | 2008-03-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.7.4.2 | Fabrication/Procurement | 149 days | 2008-04-01 08:00 | 2008-11-26 15:00 | 144.2306 | 239.2917 | 50006 | 71 |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 2 | 1 | 20 | 10001.2 | 60007.2
|  | Mechanics Fabrication Complete | 0 days | 2008-11-26 08:00 | 2008-11-26 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-11-26 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.2.7.5 | Supervision & Technical Control | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 0 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3 | Calorimeter Instrumentation | 605.13 days | 2006-10-02 08:00 | 2009-06-30 16:00 | 604.1461 | 1002.3333 | 592224.4 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.417 | 150525.936 | 742750.336
| 1.2.3.3.1 | HV Control System | 273.13 days | 2006-10-02 08:00 | 2007-12-31 12:00 | 274.347 | 455.1667 | 113240 | 13 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18118.4 | 131358.4
| 1.2.3.3.1.1 | VME Carriers | 145 days | 2006-12-01 08:00 | 2007-07-31 11:00 | 145.9384 | 242.125 | 15340 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 2454.4 | 17794.4
| 1.2.3.3.1.2 | DA Converters | 145 days | 2006-12-01 08:00 | 2007-07-31 11:00 | 145.9384 | 242.125 | 82500 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 13200 | 95700
| 1.2.3.3.1.3 | VME/VXI Mainframe | 52 days | 2006-10-02 08:00 | 2006-12-29 11:00 | 53.1164 | 88.125 | 15400 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 2464 | 17864
| 1.2.3.3.1.4 | Test | 109 days | 2007-07-02 08:00 | 2007-12-31 12:00 | 109.7991 | 182.1667 | 0 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3.2 | LED Monitoring System | 220 days | 2007-01-03 08:00 | 2007-12-31 14:00 | 218.3425 | 362.25 | 56984 | 17 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 11396.8 | 68380.8
| 1.2.3.3.2.1 | Fabrication of 52 Units | 220 days | 2007-01-03 08:00 | 2007-12-31 14:00 | 218.3425 | 362.25 | 53870 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 10774 | 64644
| 1.2.3.3.2.3 | Test & Packing of 52 Units | 220 days | 2007-01-03 08:00 | 2007-12-31 14:00 | 218.3425 | 362.25 | 3114 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 622.8 | 3736.8
| 1.2.3.3.3 | WFD Readout Electronics | 551.88 days | 2007-01-03 08:00 | 2009-06-30 16:00 | 548.0913 | 909.3333 | 409866.4 | 22 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.9323 | 118583.936 | 528450.336
| 1.2.3.3.3.1 | WFD Boards | 475 days | 2007-01-03 08:00 | 2009-02-27 11:00 | 473.8288 | 786.125 | 347066.4 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.6343 | 109791.936 | 456858.336
| 1.2.3.3.3.1.3 | Fabrication/Procurement | 424 days | 2007-01-03 08:00 | 2008-11-26 14:00 | 417.8493 | 693.25 | 331200 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 8 | 4 | 4 | 4 | 2 | 2 | 1 | 32 | 105984 | 437184
| 1.2.3.3.3.1.5 | Test | 421 days | 2007-04-02 08:00 | 2009-02-27 11:00 | 420.1849 | 697.125 | 15866.4 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than | 4 | 4 | 8 | 0 | 2 | 2 | 1 | 24 | 3807.936 | 19674.336
| 1.2.3.3.3.2 | Crate Data-Collection Boards | 313 days | 2007-07-02 08:00 | 2008-11-26 12:00 | 309.3059 | 513.1667 | 24800 |  |  | Fixed Units | 2007-07-02 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 3472 | 28272
| 1.2.3.3.3.3 | VME64x-9U/400 crates | 109 days | 2007-07-02 08:00 | 2007-12-31 12:00 | 109.7991 | 182.1667 | 38000 |  |  | Fixed Units | 2007-07-02 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 5320 | 43320
| 1.2.3.3.3.4 | System Test | 163 days | 2008-10-01 08:00 | 2009-06-30 16:00 | 164.1461 | 272.3333 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.3.4 | LV Power Supplies | 47.25 days | 2007-07-02 08:00 | 2007-09-05 10:00 | 39.2283 | 65.0833 | 12134 |  |  | Fixed Units | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 2426.8 | 14560.8
| 1.2.3.4 | Shipping | 439.5 days | 2007-06-01 08:00 | 2009-05-29 10:00 | 438.8447 | 728.0833 | 96600 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 23184 | 119784
| 1.2.3.4.1 | Shipment #1 | 36 days | 2007-06-01 08:00 | 2007-07-31 14:00 | 36.3151 | 60.25 | 16100 |  |  | Fixed Duration | 2007-06-01 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 3864 | 19964
| 1.2.3.4.2 | Shipment #2 | 16 days | 2007-11-01 08:00 | 2007-11-30 10:00 | 17.5297 | 29.0833 | 16100 |  |  | Fixed Duration | 2007-11-01 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 3864 | 19964
| 1.2.3.4.3 | Shipment #3 | 18 days | 2008-05-01 08:00 | 2008-05-30 10:00 | 17.5297 | 29.0833 | 16100 |  |  | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 3864 | 19964
| 1.2.3.4.4 | Shipment #4 | 14 days | 2008-11-03 08:00 | 2008-11-26 09:00 | 13.8881 | 23.0417 | 16100 |  |  | Fixed Duration | 2008-11-03 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 3864 | 19964
| 1.2.3.4.5 | Shipment #5 | 17 days | 2009-05-01 08:00 | 2009-05-29 10:00 | 16.9269 | 28.0833 | 32200 |  |  | Fixed Duration | 2009-05-01 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 7728 | 39928
|  | Shipping Complete | 0 days | 2009-05-29 08:00 | 2009-05-29 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-05-29 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.5 | Assembly & Test | 532.88 days | 2007-07-02 08:00 | 2009-11-30 11:00 | 531.6918 | 882.125 | 197520 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 47404.8 | 244924.8
| 1.2.3.5.1 | Modules Assy | 460 days | 2007-07-02 08:00 | 2009-07-31 10:00 | 458.1324 | 760.0833 | 130968 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 31432.32 | 162400.32
| 1.2.3.5.2 | Cosmic Ray Test | 478 days | 2007-10-01 08:00 | 2009-11-30 11:00 | 476.8425 | 791.125 | 66552 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 0 | 10 | 4 | 0 | 0 | 2 | 1 | 24 | 15972.48 | 82524.48
| 1.2.3.6 | Installation | 145.63 days | 2009-08-03 08:00 | 2010-03-31 16:00 | 144.8584 | 240.3333 | 113033.92 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 22606.784 | 135640.704
|  | Mechanics Installation Complete | 0 days | 2009-08-03 08:00 | 2009-08-03 08:00 | 0 | 0 | 0 |  | 104,105,106,111 | Fixed Duration | 2009-08-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.6.1 | Modules into Frame | 145 days | 2009-08-03 08:00 | 2010-03-31 10:00 | 144.7078 | 240.0833 | 35988 | 103 |  | Fixed Duration | 2009-08-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 7197.6 | 43185.6
| 1.2.3.6.2 | Led Based Monitoring System | 127 days | 2009-09-01 08:00 | 2010-03-31 16:00 | 127.379 | 211.3333 | 24996 | 103 |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 4999.2 | 29995.2
| 1.2.3.6.3 | WFD Read-out Electronics | 127 days | 2009-09-01 08:00 | 2010-03-31 16:00 | 127.379 | 211.3333 | 52049.92 | 103 |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 10409.984 | 62459.904
| 1.2.3.7 | Cabling | 442.13 days | 2008-04-01 08:00 | 2010-03-31 16:00 | 439.5982 | 729.3333 | 115290 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 23058 | 138348
| 1.2.3.7.1 | Production of LV-PS Cables | 149 days | 2008-04-01 08:00 | 2008-11-26 15:00 | 144.2306 | 239.2917 | 34032 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 6806.4 | 40838.4
| 1.2.3.7.2 | Production of HV-Control Cables | 149 days | 2008-04-01 08:00 | 2008-11-26 15:00 | 144.2306 | 239.2917 | 7996 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 1599.2 | 9595.2
| 1.2.3.7.3 | Production of Signal Cables | 257 days | 2008-04-01 08:00 | 2009-05-29 14:00 | 255.1096 | 423.25 | 37490 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 7498 | 44988
| 1.2.3.7.4 | Assembly and Installation | 127 days | 2009-09-01 08:00 | 2010-03-31 16:00 | 127.379 | 211.3333 | 35772 | 103 |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 7154.4 | 42926.4
|  | Subsystem Installation Complete | 0 days | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2010-03-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.3.8 | Commissioning of Photon Calorimeter | 57 days | 2010-06-01 08:00 | 2010-08-31 09:00 | 54.8744 | 91.0417 | 34320 |  |  | Fixed Duration | 2010-06-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 6864 | 41184
| 1.2.3.9 | Scientific & Technical Support | 1325 days | 2005-10-03 08:00 | 2011-09-30 12:00 | 1318.895 | 2188.1667 | 442050.88 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 97251.1936 | 539302.0736
| 1.2.3.9.1 | Scientific Support | 1325 days | 2005-10-03 08:00 | 2011-09-30 12:00 | 1318.895 | 2188.1667 | 322050.88 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 0 | 10 | 2 | 0 | 0 | 2 | 1 | 22 | 70851.1936 | 392902.0736
| 1.2.3.9.2 | Technical Support | 1325 days | 2005-10-03 08:00 | 2011-09-30 12:00 | 1318.895 | 2188.1667 | 120000 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 0 | 10 | 2 | 0 | 0 | 2 | 1 | 22 | 26400 | 146400
| Count All | 116 | [5 empty] | Count | 22 | 14 | 116 | 90 | 90
[8 empty] | Assigned | 0.18966 | 0.12069
[8 empty] | Missing | 0.81034 | 0.87931

## 1.2.3 Durations & Milestone
| Excessive Durations |  |  | Sort by |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration Days
1.2.3.1.8 | WFD Readout | 2005-10-03 08:00 | 2006-10-31 12:00 | 1.0772 |  | APD Design Review | 2005-12-15 08:00 | 2005-12-15 08:00 | 0 days
1.2.3.7.3 | Production of Signal Cables | 2008-04-01 08:00 | 2009-05-29 14:00 | 1.1596 |  | LED Design Review | 2005-12-15 08:00 | 2005-12-15 08:00 | 0 days
1.2.3.2.7.2 | Cooling System | 2007-07-02 08:00 | 2008-08-29 12:00 | 1.1621 |  | HV Design Review | 2006-02-28 08:00 | 2006-02-28 08:00 | 0 days
1.2.3.3.1 | HV Control System | 2006-10-02 08:00 | 2007-12-31 12:00 | 1.247 |  | WFD Design Review | 2006-03-31 17:00 | 2006-03-31 17:00 | 0 days
1.2.3.2.7.1 | Support Frame | 2007-01-03 08:00 | 2008-05-30 11:00 | 1.4058 |  | Fabrication Complete | 2006-06-30 08:00 | 2006-06-30 08:00 | 0 days
1.2.3.3.3.2 | Crate Data-Collection Boards | 2007-07-02 08:00 | 2008-11-26 12:00 | 1.4059 |  | Calorimeter Design Review | 2006-07-05 08:00 | 2006-07-05 08:00 | 0 days
1.2.3.2.3.3 | WLS Fiber | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Support Frame Design Review | 2007-06-29 08:00 | 2007-06-29 08:00 | 0 days
1.2.3.2.3.4 | Assembly | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Cooling Design Review | 2007-09-27 08:00 | 2007-09-27 08:00 | 0 days
1.2.3.2.3.5 | Module Test | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Railway Design Review | 2007-12-31 08:00 | 2007-12-31 08:00 | 0 days
1.2.3.2.3.6 | Module Packing | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Assembly and Service Tools Design Review | 2008-03-31 08:00 | 2008-03-31 08:00 | 0 days
1.2.3.2.4.5 | APD Units Assembly | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Assembly Complete | 2008-11-26 08:00 | 2008-11-26 08:00 | 0 days
1.2.3.2.4.6 | APD Units Test | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | APD Assembly Complete | 2008-11-26 08:00 | 2008-11-26 08:00 | 0 days
1.2.3.2.4.7 | APD Units Packing | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Mechanics Fabrication Complete | 2008-11-26 08:00 | 2008-11-26 08:00 | 0 days
1.2.3.2.5 | Cosmic Ray Test of Module/APD | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Shipping Complete | 2009-05-29 08:00 | 2009-05-29 08:00 | 0 days
1.2.3.2.7.5 | Supervision & Technical Control | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Mechanics Installation Complete | 2009-08-03 08:00 | 2009-08-03 08:00 | 0 days
1.2.3.3.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-11-26 14:00 | 1.8993 |  | Subsystem Installation Complete | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 days
1.2.3.2.7 | Photon Calorimeter Mechanics | 2007-01-03 08:00 | 2008-11-26 15:00 | 1.8994 |  | Count | 16
1.2.3.3.3.1.5 | Test | 2007-04-02 08:00 | 2009-02-27 11:00 | 1.9099
1.2.3.2.2 | Tools & Test Equipment Modification | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.2.2.2 | Molding Forms and Stamps | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.2.3.1 | Scintillator Tiles | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.2.3.2 | Lead Tiles | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.2.4.1 | APD | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.2.4.2 | Preamplifier | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.2.4.3 | LV-HV Converter | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.2.4.4 | Mechanics & PC Boards | 2006-10-02 08:00 | 2008-08-29 12:00 | 1.91
1.2.3.4 | Shipping | 2007-06-01 08:00 | 2009-05-29 10:00 | 1.9947
1.2.3.7 | Cabling | 2008-04-01 08:00 | 2010-03-31 16:00 | 1.9982
1.2.3.1.10 | Test & Study | 2006-08-01 08:00 | 2008-07-31 15:00 | 2.0008
1.2.3.5.1 | Modules Assy | 2007-07-02 08:00 | 2009-07-31 10:00 | 2.0824
1.2.3.3.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-02-27 11:00 | 2.1538
1.2.3.2.3 | Module Production | 2006-10-02 08:00 | 2008-11-26 14:00 | 2.1541
1.2.3.2.4 | Module Instrumentation | 2006-10-02 08:00 | 2008-11-26 14:00 | 2.1541
1.2.3.5.2 | Cosmic Ray Test | 2007-10-01 08:00 | 2009-11-30 11:00 | 2.1675
1.2.3.5 | Assembly & Test | 2007-07-02 08:00 | 2009-11-30 11:00 | 2.4168
1.2.3.3.3 | WFD Readout Electronics | 2007-01-03 08:00 | 2009-06-30 16:00 | 2.4913
1.2.3.3 | Calorimeter Instrumentation | 2006-10-02 08:00 | 2009-06-30 16:00 | 2.7461
1.2.3.1 | System Prototype | 2005-10-03 08:00 | 2008-07-31 15:00 | 2.8282
1.2.3.2 | Photon Calorimeter | 2005-10-03 08:00 | 2008-11-26 15:00 | 3.1515
1.2.3 | Calorimeter System | 2005-10-03 08:00 | 2011-09-30 12:00 | 5.995 | OK
1.2.3.9 | Scientific & Technical Support | 2005-10-03 08:00 | 2011-09-30 12:00 | 5.995
1.2.3.9.1 | Scientific Support | 2005-10-03 08:00 | 2011-09-30 12:00 | 5.995
1.2.3.9.2 | Technical Support | 2005-10-03 08:00 | 2011-09-30 12:00 | 5.995
|  |  | Count Excessive | 43
>1 year
37.07%

## 1.2.4 Observations
Observations |  | WBS 1.2.4 Charged Particle | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
Project Start Date | 2005-10-03
Project Finish Date | 2010-03-31
Project Calendar | Standard | 260 work days per yr. (No adj'd for Holidays, pd. abs or vacation)
Count Tasks | 115
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 57.39%
Successors | Missing | 57.39%
Task Type (Units,Work,Duration) | All Fixed Duration | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 74, (64%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 8
Hours/week | 40
Hours/year | 2080 | Equals 260 days x 8 hours.
Days/month | 21.7 | Equals 260 days / 12 months.
Excessive Durations | 25 Tasks | 22%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 12 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
| 1.2.4 | Charged Particle Veto | 1173 days | 2005-10-03 08:00 | 2010-03-31 17:00 | 1168.4863 | 1640.375 | 2631266.68 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.1269 | 713782.1536 | 3345048.8336
| 1.2.4.1 | Barrel Charged PV | 848 days | 2005-10-03 08:00 | 2008-12-31 17:00 | 844.3767 | 1185.375 | 1390128.24 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.7963 | 344700.928 | 1734829.168
| 1.2.4.1.1 | Overall Design | 129 days | 2005-10-03 08:00 | 2006-03-30 17:00 | 127.0616 | 178.375 | 0 |  | 22SS,5SS | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 4 | 2 | 1 | 0 | 0 | 0
| 1.2.4.1.2 | Scintillator Plates | 86 days | 2005-10-03 08:00 | 2006-01-30 17:00 | 85.0342 | 119.375 | 92000 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.3913 | 24280 | 116280
| 1.2.4.1.2.1 | Prototype | 64 days | 2005-10-03 08:00 | 2005-12-29 17:00 | 62.2397 | 87.375 | 18000 | 3SS | 6 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 8 | 2 | 2 | 1 | 28 | 5040 | 23040
|  | Complete scintillator prototype studies | 0 days | 2005-12-29 17:00 | 2005-12-29 17:00 | 0 | 0 | 0 | 5 | 7 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.1.2.2 | Fabrication/Procurement | 21 days | 2006-01-02 08:00 | 2006-01-30 17:00 | 20.2123 | 28.375 | 74000 | 6 |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 3 | 4 | 8 | 8 | 2 | 1 | 1 | 26 | 19240 | 93240
| 1.2.4.1.3 | Detector Modules | 435 days | 2005-10-03 08:00 | 2007-06-01 17:00 | 431.9384 | 606.375 | 248086.08 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.3478 | 67846.1856 | 315932.2656
| 1.2.4.1.3.1 | Design | 65.3 days | 2005-10-03 08:00 | 2006-01-02 10:24 | 64.8932 | 91.1 | 0 |  | 11FS-1 day | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.4.1.3.2 | Prototype | 174 days | 2005-10-03 08:00 | 2006-06-01 17:00 | 171.9384 | 241.375 | 5000 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 2 | 1 | 32 | 1600 | 6600
| 1.2.4.1.3.3 | Fabrication/Procurement | 370 days | 2006-01-02 08:00 | 2007-06-01 17:00 | 367.1164 | 515.375 | 40784 | 9FS-1 day |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 1 | 28 | 11419.52 | 52203.52
| 1.2.4.1.3.4 | PMT assembly | 109 days | 2006-01-02 08:00 | 2006-06-01 17:00 | 107.1164 | 150.375 | 113000 | 14SS |  | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 1 | 8 | 8 | 2 | 1 | 1 | 25 | 28250 | 141250
| 1.2.4.1.3.5 | On Detector Electronics | 262 days | 2006-01-02 08:00 | 2007-01-02 17:00 | 260.2671 | 365.375 | 89302.08 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7604 | 26576.6656 | 115878.7456
| 1.2.4.1.3.5.1 | Prototype | 109 days | 2006-01-02 08:00 | 2006-06-01 17:00 | 107.1164 | 150.375 | 39302.08 |  | 12SS,15 | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 2 | 1 | 32 | 12576.6656 | 51878.7456
|  | selection of tube/base complete | 0 days | 2006-06-01 17:00 | 2006-06-01 17:00 | 0 | 0 | 0 | 14 | 16FS-1 day | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.1.3.5.2 | Fabrication/Procurement | 154 days | 2006-06-01 08:00 | 2007-01-02 17:00 | 153.4178 | 215.375 | 50000 | 15FS-1 day |  | Fixed Duration | 2006-06-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 1 | 28 | 14000 | 64000
| 1.2.4.1.4 | Monitor System | 325 days | 2005-10-03 08:00 | 2006-12-29 17:00 | 322.2397 | 452.375 | 79878.08 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79878.08
| 1.2.4.1.5 | Detector Support Structure | 390 days | 2005-10-03 08:00 | 2007-03-30 17:00 | 387.0616 | 543.375 | 134853.44 |  | 19SS | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 2 | 1 | 32 | 43153.1008 | 178006.5408
| 1.2.4.1.6 | Detector Module Assembly | 390 days | 2005-10-03 08:00 | 2007-03-30 17:00 | 387.0616 | 543.375 | 95853.44 | 18SS | 22SS+60 days,23SS+120 days | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 2 | 4 | 8 | 8 | 2 | 1 | 1 | 24 | 23004.8256 | 118858.2656
| 1.2.4.1.7 | Vacuum System Integration | 260 days | 2006-01-02 08:00 | 2006-12-29 17:00 | 257.4178 | 361.375 | 333225.2 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 93303.056 | 426528.256
| 1.2.4.1.7.1 | Design | 195 days | 2006-01-02 08:00 | 2006-09-29 17:00 | 192.5959 | 270.375 | 88255.2 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24711.456 | 112966.656
| 1.2.4.1.7.1.1 | Overall Design | 195 days | 2006-01-02 08:00 | 2006-09-29 17:00 | 192.5959 | 270.375 | 88255.2 | 19SS+60 days,3SS | 24SS | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 28 | 24711.456 | 112966.656
| 1.2.4.1.7.1.2 | Vacuum Flange Design | 128 days | 2006-04-03 08:00 | 2006-09-27 17:00 | 126.3493 | 177.375 | 0 | 19SS+120 days |  | Fixed Duration | 2006-04-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.4.1.7.2 | Prototype | 85 days | 2006-01-02 08:00 | 2006-04-28 17:00 | 82.8973 | 116.375 | 6000 | 22SS | 25 | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 28 | 1680 | 7680
|  | completion of vacuum prototype | 0 days | 2006-04-28 17:00 | 2006-04-28 17:00 | 0 | 0 | 0 | 24 | 26 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.1.7.3 | Fabrication/Procurement | 175 days | 2006-05-01 08:00 | 2006-12-29 17:00 | 172.6507 | 242.375 | 238970 | 25 | 27FS+60 days | Fixed Duration | 2006-05-01 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 28 | 66911.6 | 305881.6
| 1.2.4.1.8 | Assembly of complete Detector | 130 days | 2007-04-02 08:00 | 2007-09-28 17:00 | 127.774 | 179.375 | 257488 | 26FS+60 days | 30,28 | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 61797.12 | 319285.12
|  | assemby complete | 0 days | 2007-09-28 17:00 | 2007-09-28 17:00 | 0 | 0 | 0 | 27 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.1.9 | Detector Test | 153 days | 2007-10-01 08:00 | 2008-04-30 17:00 | 151.2808 | 212.375 | 91960 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 16552.8 | 108512.8
| 1.2.4.1.9.1 | Laboratory Test | 66 days | 2007-10-01 08:00 | 2007-12-31 17:00 | 65.089 | 91.375 | 91960 | 27 |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 4 | 2 | 8 | 2 | 1 | 1 | 18 | 16552.8 | 108512.8
| 1.2.4.1.9.2 | Beam Test | 86 days | 2008-01-02 08:00 | 2008-04-30 17:00 | 85.0342 | 119.375 | 0 |  | 32 | Fixed Duration | 2008-01-02 08:00 | Start No Earlier Than | 2 | 4 | 2 | 8 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.4.1.10 | Shipping | 22 days | 2008-05-01 08:00 | 2008-05-30 17:00 | 20.9247 | 29.375 | 20000 | 31 | 33 | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 4 | 4 | 2 | 8 | 2 | 2 | 1 | 26 | 5200 | 25200
|  | arrival at BNL | 0 days | 2008-05-30 17:00 | 2008-05-30 17:00 | 0 | 0 | 0 | 32 | 34 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.1.11 | Installation at BNL | 133 days | 2008-06-30 08:00 | 2008-12-31 17:00 | 131.3356 | 184.375 | 36784 | 33 |  | Fixed Duration | 2008-06-30 08:00 | Start No Earlier Than | 4 | 4 | 2 | 8 | 2 | 2 | 1 | 26 | 9563.84 | 46347.84
| 1.2.4.2 | Downstream Charged PV | 716 days | 2005-10-03 08:00 | 2008-06-30 17:00 | 713.3082 | 1001.375 | 804554.59 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.7111 | 255133.3636 | 1059687.9536
| 1.2.4.2.1 | Design | 130 days | 2005-10-03 08:00 | 2006-03-31 17:00 | 127.774 | 179.375 | 48696 |  | 44,65,66 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 15095.76 | 63791.76
| 1.2.4.2.2 | Scintillator Plates | 390 days | 2005-10-03 08:00 | 2007-03-30 17:00 | 387.0616 | 543.375 | 111312.57 |  | 68 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6764 | 14110.3899 | 125422.9599
| 1.2.4.2.2.1 | Prototype | 129 days | 2005-10-03 08:00 | 2006-03-30 17:00 | 127.0616 | 178.375 | 64714.4 |  | 65,66 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6782 | 6263.184 | 70977.584
| 1.2.4.2.2.1.1 | Test Equipment | 65 days | 2005-10-03 08:00 | 2005-12-30 17:00 | 62.9521 | 88.375 | 14786.4 |  | 51SS,53SS | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 1 | 1 | 16 | 2365.824 | 17152.224
| 1.2.4.2.2.1.2 | Procurement | 65 days | 2005-10-03 08:00 | 2005-12-30 17:00 | 62.9521 | 88.375 | 5030 |  | 41 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 1 | 1 | 4 | 8 | 2 | 1 | 1 | 15 | 754.5 | 5784.5
| 1.2.4.2.2.1.3 | Evaluation | 64 days | 2006-01-02 08:00 | 2006-03-30 17:00 | 62.2397 | 87.375 | 44898 | 40 | 55,56,42 | Fixed Duration | 2006-01-02 08:00 | Start No Earlier Than | 1 | 1 | 4 | 0 | 2 | 1 | 1 | 7 | 3142.86 | 48040.86
|  | scintillator evaluation complete | 0 days | 2006-03-30 17:00 | 2006-03-30 17:00 | 0 | 0 | 0 | 41 | 44 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.2.2.2 | Procurement | 67 days | 2006-10-02 08:00 | 2007-01-02 17:00 | 65.8014 | 92.375 | 39190 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.9196 | 5847 | 45037
| 1.2.4.2.2.2.1 | Raw Material | 67 days | 2006-10-02 08:00 | 2007-01-02 17:00 | 65.8014 | 92.375 | 33080 | 36,42 | 45SS | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 1 | 1 | 4 | 8 | 2 | 1 | 1 | 15 | 4962 | 38042
| 1.2.4.2.2.2.2 | Machining | 67 days | 2006-10-02 08:00 | 2007-01-02 17:00 | 65.8014 | 92.375 | 5480 | 44SS | 46FS-1 day | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 1 | 1 | 4 | 8 | 2 | 1 | 1 | 15 | 822 | 6302
| 1.2.4.2.2.2.3 | Shipping to BNL | 1 day | 2007-01-02 08:00 | 2007-01-02 17:00 | 0.26712 | 0.375 | 630 | 45FS-1 day | 47 | Fixed Duration | 2007-01-02 08:00 | Start No Earlier Than | 1 | 4 | 4 | 0 | 2 | 1 | 1 | 10 | 63 | 693
| 1.2.4.2.2.3 | Acceptance Test at BNL | 42 days | 2007-02-01 08:00 | 2007-03-30 17:00 | 40.8699 | 57.375 | 7408.17 | 46 | 48 | Fixed Duration | 2007-02-01 08:00 | Start No Earlier Than | 2 | 4 | 4 | 15 | 2 | 1 | 1 | 27 | 2000.2059 | 9408.3759
|  | scintillator acceptance complete | 0 days | 2007-03-30 17:00 | 2007-03-30 17:00 | 0 | 0 | 0 | 47 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.2.3 | ON Detector Electronics | 456 days | 2005-10-03 08:00 | 2007-07-02 17:00 | 454.0205 | 637.375 | 247211.63 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.2503 | 94559.1255 | 341770.7555
| 1.2.4.2.3.1 | Prototype | 66 days | 2005-10-03 08:00 | 2006-01-02 17:00 | 65.089 | 91.375 | 17340.4 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.1375 | 5399.364 | 22739.764
| 1.2.4.2.3.1.1 | Base Circuit and Preamp | 66 days | 2005-10-03 08:00 | 2006-01-02 17:00 | 65.089 | 91.375 | 12310.4 | 39SS | 55,56,52 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 8 | 6 | 4 | 15 | 2 | 1 | 1 | 41 | 5047.264 | 17357.664
|  | base/preamp prototype complete | 0 days | 2006-01-02 17:00 | 2006-01-02 17:00 | 0 | 0 | 0 | 51 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.2.3.1.2 | Phototube | 2 days | 2005-10-03 08:00 | 2005-10-04 17:00 | 0.97945 | 1.375 | 5030 | 39SS | 65,66 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 1 | 1 | 4 | 0 | 2 | 1 | 1 | 7 | 352.1 | 5382.1
| 1.2.4.2.3.2 | Procurement | 64 days | 2007-02-01 08:00 | 2007-05-01 17:00 | 63.6644 | 89.375 | 223810 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.7018 | 88856.7 | 312666.7
| 1.2.4.2.3.2.1 | Base Circuit and Preamp | 64 days | 2007-02-01 08:00 | 2007-05-01 17:00 | 63.6644 | 89.375 | 67150 | 51,41 |  | Fixed Duration | 2007-02-01 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 4 | 2 | 1 | 81 | 54391.5 | 121541.5
| 1.2.4.2.3.2.2 | Phototube | 64 days | 2007-02-01 08:00 | 2007-05-01 17:00 | 63.6644 | 89.375 | 156660 | 51,41 |  | Fixed Duration | 2007-02-01 08:00 | Start No Earlier Than | 1 | 1 | 4 | 15 | 2 | 1 | 1 | 22 | 34465.2 | 191125.2
| 1.2.4.2.3.3 | Acceptance Test at BNL | 44 days | 2007-05-02 08:00 | 2007-07-02 17:00 | 43.7192 | 61.375 | 6061.23 |  | 58 | Fixed Duration | 2007-05-02 08:00 | Start No Earlier Than | 1 | 1 | 2 | 0 | 2 | 1 | 1 | 5 | 303.0615 | 6364.2915
|  | base/pmt acceptance complete | 0 days | 2007-07-02 17:00 | 2007-07-02 17:00 | 0 | 0 | 0 | 57 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.2.4 | Monitor Design | 325 days | 2005-10-03 08:00 | 2006-12-29 17:00 | 322.2397 | 452.375 | 54439.76 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.3511 | 21422.628 | 75862.388
| 1.2.4.2.4.1 | Design | 88 days | 2005-10-03 08:00 | 2006-02-01 17:00 | 86.4589 | 121.375 | 32532.4 |  | 62,65,66 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 8 | 6 | 4 | 15 | 2 | 1 | 1 | 41 | 13338.284 | 45870.684
| 1.2.4.2.4.2 | LED System | 237 days | 2006-02-02 08:00 | 2006-12-29 17:00 | 235.3356 | 330.375 | 21907.36 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.9024 | 8084.344 | 29991.704
| 1.2.4.2.4.2.1 | Fiber Optics, LED | 172 days | 2006-02-02 08:00 | 2006-09-29 17:00 | 170.5137 | 239.375 | 7540 | 60 | 63 | Fixed Duration | 2006-02-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 2337.4 | 9877.4
| 1.2.4.2.4.2.2 | Construct Harnesses | 65 days | 2006-10-02 08:00 | 2006-12-29 17:00 | 62.9521 | 88.375 | 14367.36 | 62 | 79 | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 3 | 15 | 4 | 15 | 2 | 1 | 1 | 40 | 5746.944 | 20114.304
| 1.2.4.2.5 | Mount Phototube Hardware | 109 days | 2007-05-02 08:00 | 2007-10-01 17:00 | 108.5411 | 152.375 | 33470 |  | 71SS | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.0899 | 8732.3 | 42202.3
| 1.2.4.2.5.1 | Magnetic Shields | 109 days | 2007-05-02 08:00 | 2007-10-01 17:00 | 108.5411 | 152.375 | 18260 | 36,38,53,60 |  | Fixed Duration | 2007-05-02 08:00 | Start No Earlier Than | 2 | 6 | 4 | 8 | 2 | 1 | 1 | 22 | 4017.2 | 22277.2
| 1.2.4.2.5.2 | Delrin Clamps | 109 days | 2007-05-02 08:00 | 2007-10-01 17:00 | 108.5411 | 152.375 | 15210 | 36,38,53,60 |  | Fixed Duration | 2007-05-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 4715.1 | 19925.1
| 1.2.4.2.6 | Strips of Counters, Assy | 217 days | 2007-06-01 08:00 | 2008-03-31 17:00 | 216.8151 | 304.375 | 82892.7 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.842 | 28881.441 | 111774.141
| 1.2.4.2.6.1 | Scintillator, Machine Recess | 196 days | 2007-07-02 08:00 | 2008-03-31 17:00 | 194.7329 | 273.375 | 15210 | 37 | 69SS | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 2 | 15 | 4 | 15 | 2 | 1 | 1 | 38 | 5779.8 | 20989.8
| 1.2.4.2.6.2 | Wrap Scintillator | 196 days | 2007-07-02 08:00 | 2008-03-31 17:00 | 194.7329 | 273.375 | 21274.5 | 68SS | 71SS | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 8 | 1 | 4 | 15 | 2 | 1 | 1 | 36 | 7658.82 | 28933.32
| 1.2.4.2.6.3 | Assemble Strip | 154 days | 2007-06-01 08:00 | 2008-01-02 17:00 | 153.4178 | 215.375 | 28367.3 |  | 75SS | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.3792 | 8901.425 | 37268.725
| 1.2.4.2.6.3.1 | Couple Scintillator to Phototube | 133 days | 2007-07-02 08:00 | 2008-01-02 17:00 | 131.3356 | 184.375 | 17959.2 | 69SS,73SS,64SS |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 5567.352 | 23526.552
| 1.2.4.2.6.3.2 | Silastic Cookie Mfg. | 21 days | 2007-06-01 08:00 | 2007-06-29 17:00 | 20.2123 | 28.375 | 5030 |  | 73 | Fixed Duration | 2007-06-01 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 1559.3 | 6589.3
| 1.2.4.2.6.3.3 | Construct Cookies | 133 days | 2007-07-02 08:00 | 2008-01-02 17:00 | 131.3356 | 184.375 | 5378.1 | 72 | 71SS | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 6 | 4 | 15 | 2 | 1 | 1 | 33 | 1774.773 | 7152.873
| 1.2.4.2.6.4 | Assembly Process | 133 days | 2007-07-02 08:00 | 2008-01-02 17:00 | 131.3356 | 184.375 | 18040.9 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.2587 | 6541.396 | 24582.296
| 1.2.4.2.6.4.1 | Strips of Counters to Holders Assy | 133 days | 2007-07-02 08:00 | 2008-01-02 17:00 | 131.3356 | 184.375 | 14217.7 | 70SS,76SS,77SS |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 4407.487 | 18625.187
| 1.2.4.2.6.4.2 | Glue Jig | 7 days | 2007-07-02 08:00 | 2007-07-10 17:00 | 5.9658 | 8.375 | 2874.9 |  | 75SS,79 | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 15 | 15 | 4 | 15 | 2 | 1 | 1 | 64 | 1839.936 | 4714.836
| 1.2.4.2.6.4.3 | Transport Fixtures | 7 days | 2007-07-02 08:00 | 2007-07-10 17:00 | 5.9658 | 8.375 | 948.3 |  | 75SS,79,78 | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 293.973 | 1242.273
|  | assembly complete | 0 days | 2007-07-10 17:00 | 2007-07-10 17:00 | 0 | 0 | 0 | 77 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.2.7 | Strip Test | 123 days | 2007-07-11 08:00 | 2007-12-28 17:00 | 121.363 | 170.375 | 14217.7 | 76,77,63 |  | Fixed Duration | 2007-07-11 08:00 | Start No Earlier Than | 2 | 4 | 4 | 15 | 2 | 1 | 1 | 27 | 3838.779 | 18056.479
| 1.2.4.2.8 | Mount Detector | 522 days | 2006-06-01 08:00 | 2008-05-30 17:00 | 519.5548 | 729.375 | 89035.53 |  | 86SS | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.4452 | 28887.7272 | 117923.2572
| 1.2.4.2.8.1 | Construct Support Structure | 155 days | 2006-06-01 08:00 | 2007-01-03 17:00 | 154.1301 | 216.375 | 28920 |  | 90 | Fixed Duration | 2006-06-01 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 2 | 1 | 1 | 50 | 14460 | 43380
| 1.2.4.2.8.2 | Mount Strips on Support Structure | 218 days | 2007-08-01 08:00 | 2008-05-30 17:00 | 216.1027 | 303.375 | 7108.85 |  |  | Fixed Duration | 2007-08-01 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 1706.124 | 8814.974
| 1.2.4.2.8.3 | Construct Transfer Jigs | 11 days | 2007-07-02 08:00 | 2007-07-16 17:00 | 10.2397 | 14.375 | 3717.28 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 892.1472 | 4609.4272
| 1.2.4.2.8.4 | Secure Cables to Support Structure | 218 days | 2007-08-01 08:00 | 2008-05-30 17:00 | 216.1027 | 303.375 | 49289.4 |  |  | Fixed Duration | 2007-08-01 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 11829.456 | 61118.856
| 1.2.4.2.9 | Test | 65 days | 2008-03-03 08:00 | 2008-05-30 17:00 | 62.9521 | 88.375 | 36222 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.0168 | 9061.572 | 45283.572
| 1.2.4.2.9.1 | Overall Bench Test | 44 days | 2008-04-01 08:00 | 2008-05-30 17:00 | 42.2945 | 59.375 | 23945.6 | 87,80SS | 88 | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 5746.944 | 29692.544
| 1.2.4.2.9.2 | Prepare Darkroom | 20 days | 2008-03-03 08:00 | 2008-03-28 17:00 | 18.0753 | 25.375 | 12276.4 |  | 86,94 | Fixed Duration | 2008-03-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 15 | 2 | 1 | 1 | 27 | 3314.628 | 15591.028
|  | completion of bench tests | 0 days | 2008-05-30 17:00 | 2008-05-30 17:00 | 0 | 0 | 0 | 86 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.2.10 | Install in Vacuum Vessel | 543 days | 2006-06-01 08:00 | 2008-06-30 17:00 | 541.637 | 760.375 | 87056.7 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.0848 | 30543.641 | 117600.341
| 1.2.4.2.10.1 | Trolley System | 65 days | 2008-01-02 08:00 | 2008-04-01 17:00 | 64.3767 | 90.375 | 19219.2 | 81 | 94 | Fixed Duration | 2008-01-02 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 2 | 1 | 1 | 50 | 9609.6 | 28828.8
| 1.2.4.2.10.2 | Prepare Vacuum Vessel | 65 days | 2008-01-02 08:00 | 2008-04-01 17:00 | 64.3767 | 90.375 | 7246.4 |  | 94 | Fixed Duration | 2008-01-02 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 2 | 1 | 1 | 50 | 3623.2 | 10869.6
| 1.2.4.2.10.3 | Electrical Feed-throughs | 132 days | 2006-06-01 08:00 | 2006-12-01 17:00 | 130.6233 | 183.375 | 16360 |  | 93,94 | Fixed Duration | 2006-06-01 08:00 | Start No Earlier Than | 1 | 1 | 4 | 15 | 2 | 1 | 1 | 22 | 3599.2 | 19959.2
| 1.2.4.2.10.4 | Convert Output to Normal BNC Cables | 130 days | 2007-07-02 08:00 | 2007-12-28 17:00 | 127.774 | 179.375 | 37733 | 92 |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 11697.23 | 49430.23
| 1.2.4.2.10.5 | Complete Assy to AGS Floor | 21 days | 2008-06-02 08:00 | 2008-06-30 17:00 | 20.2123 | 28.375 | 6498.1 | 91,90,92,87 | 95 | Fixed Duration | 2008-06-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 2014.411 | 8512.511
|  | ready for installation | 0 days | 2008-06-30 17:00 | 2008-06-30 17:00 | 0 | 0 | 0 | 94 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.3 | Front-End Electronics & Cabling | 913 days | 2006-10-02 08:00 | 2010-03-31 17:00 | 909.1986 | 1276.375 | 436583.85 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.0999 | 113947.862 | 550531.712
| 1.2.4.3.1 | HV Control System | 326 days | 2006-10-02 08:00 | 2007-12-31 17:00 | 324.3767 | 455.375 | 44870 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7179.2 | 52049.2
| 1.2.4.3.1.1 | VME Carriers | 173 days | 2006-12-01 08:00 | 2007-07-31 17:00 | 172.6507 | 242.375 | 6200 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 992 | 7192
| 1.2.4.3.1.2 | D/A Converters | 173 days | 2006-12-01 08:00 | 2007-07-31 17:00 | 172.6507 | 242.375 | 32170 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 5147.2 | 37317.2
| 1.2.4.3.1.3 | VME/VXI Mainframe | 66 days | 2006-10-02 08:00 | 2007-01-01 17:00 | 65.089 | 91.375 | 6500 |  |  | Fixed Duration | 2006-10-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 1040 | 7540
| 1.2.4.3.1.4 | Test | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 0 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.3.2 | LED Monitoring System | 281 days | 2007-01-03 08:00 | 2008-01-30 17:00 | 279.5 | 392.375 | 0 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.3.3 | WFD Readout Electronics | 650 days | 2007-01-03 08:00 | 2009-06-30 17:00 | 647.774 | 909.375 | 302322.3 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.4025 | 88890.352 | 391212.652
| 1.2.4.3.3.1 | WFD Boards | 563 days | 2007-01-03 08:00 | 2009-02-27 17:00 | 560.1575 | 786.375 | 264052.3 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.6349 | 83532.552 | 347584.852
| 1.2.4.3.3.1.1 | Fabrication/Procurement | 498 days | 2007-01-03 08:00 | 2008-11-28 17:00 | 495.3356 | 695.375 | 252000 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 8 | 4 | 4 | 4 | 2 | 2 | 0 | 32 | 80640 | 332640
| 1.2.4.3.3.1.2 | Test | 500 days | 2007-04-02 08:00 | 2009-02-27 17:00 | 496.7603 | 697.375 | 12052.3 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than | 4 | 4 | 8 | 0 | 2 | 2 | 0 | 24 | 2892.552 | 14944.852
| 1.2.4.3.3.2 | Crate Data-Collection Boards | 370 days | 2007-07-02 08:00 | 2008-11-28 17:00 | 367.1164 | 515.375 | 15110 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 0 | 14 | 2115.4 | 17225.4
| 1.2.4.3.3.3 | VME Mainframes & Controller | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 23160 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 0 | 14 | 3242.4 | 26402.4
| 1.2.4.3.3.4 | System Test | 195 days | 2008-10-01 08:00 | 2009-06-30 17:00 | 194.0205 | 272.375 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.4.3.4 | LV Power Supplies | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 6037.35 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 0 | 20 | 1207.47 | 7244.82
| 1.2.4.3.5 | Cabling Outside Vacuum | 522 days | 2008-04-01 08:00 | 2010-03-31 17:00 | 519.5548 | 729.375 | 83354.2 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16670.84 | 100025.04
| 1.2.4.3.5.1 | LV PS Cable Production | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 18959.26 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 3791.852 | 22751.112
| 1.2.4.3.5.2 | HV Control Cable production | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 6049.8 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 1209.96 | 7259.76
| 1.2.4.3.5.3 | Signal Cable Production | 304 days | 2008-04-01 08:00 | 2009-05-29 17:00 | 301.5822 | 423.375 | 14300 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 2860 | 17160
| 1.2.4.3.5.4 | Assembly & Installation | 152 days | 2009-09-01 08:00 | 2010-03-31 17:00 | 150.5685 | 211.375 | 44045.14 |  |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 8809.028 | 52854.168
| Count All | 115 | [5 empty] | Count | 49 | 49 | 115 | 74 | 74
[8 empty] | Assigned | 0.42609 | 0.42609
[8 empty] | Missing | 0.57391 | 0.57391

## 1.2.4 Durations & Milestone
| Excessive Durations |  |  | Sort by |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration Days
1.2.4.3.2 | LED Monitoring System | 2007-01-03 08:00 | 2008-01-30 17:00 | 1.075 |  | Complete scintillator prototype studies | 2005-12-29 17:00 | 2005-12-29 17:00 | 0 days
1.2.4.3.5.3 | Signal Cable Production | 2008-04-01 08:00 | 2009-05-29 17:00 | 1.1599 |  | base/preamp prototype complete | 2006-01-02 17:00 | 2006-01-02 17:00 | 0 days
1.2.4.1.4 | Monitor System | 2005-10-03 08:00 | 2006-12-29 17:00 | 1.2394 |  | scintillator evaluation complete | 2006-03-30 17:00 | 2006-03-30 17:00 | 0 days
1.2.4.2.4 | Monitor Design | 2005-10-03 08:00 | 2006-12-29 17:00 | 1.2394 |  | completion of vacuum prototype | 2006-04-28 17:00 | 2006-04-28 17:00 | 0 days
1.2.4.3.1 | HV Control System | 2006-10-02 08:00 | 2007-12-31 17:00 | 1.2476 |  | selection of tube/base complete | 2006-06-01 17:00 | 2006-06-01 17:00 | 0 days
1.2.4.1.3.3 | Fabrication/Procurement | 2006-01-02 08:00 | 2007-06-01 17:00 | 1.412 |  | scintillator acceptance complete | 2007-03-30 17:00 | 2007-03-30 17:00 | 0 days
1.2.4.3.3.2 | Crate Data-Collection Boards | 2007-07-02 08:00 | 2008-11-28 17:00 | 1.412 |  | base/pmt acceptance complete | 2007-07-02 17:00 | 2007-07-02 17:00 | 0 days
1.2.4.1.5 | Detector Support Structure | 2005-10-03 08:00 | 2007-03-30 17:00 | 1.4887 |  | assembly complete | 2007-07-10 17:00 | 2007-07-10 17:00 | 0 days
1.2.4.1.6 | Detector Module Assembly | 2005-10-03 08:00 | 2007-03-30 17:00 | 1.4887 |  | assemby complete | 2007-09-28 17:00 | 2007-09-28 17:00 | 0 days
1.2.4.2.2 | Scintillator Plates | 2005-10-03 08:00 | 2007-03-30 17:00 | 1.4887 |  | completion of bench tests | 2008-05-30 17:00 | 2008-05-30 17:00 | 0 days
1.2.4.1.3 | Detector Modules | 2005-10-03 08:00 | 2007-06-01 17:00 | 1.6613 |  | arrival at BNL | 2008-05-30 17:00 | 2008-05-30 17:00 | 0 days
1.2.4.2.3 | ON Detector Electronics | 2005-10-03 08:00 | 2007-07-02 17:00 | 1.7462 |  | ready for installation | 2008-06-30 17:00 | 2008-06-30 17:00 | 0 days
1.2.4.3.3.1.1 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-11-28 17:00 | 1.9051 |  | Count | 12
1.2.4.3.3.1.2 | Test | 2007-04-02 08:00 | 2009-02-27 17:00 | 1.9106
1.2.4.2.8 | Mount Detector | 2006-06-01 08:00 | 2008-05-30 17:00 | 1.9983
1.2.4.3.5 | Cabling Outside Vacuum | 2008-04-01 08:00 | 2010-03-31 17:00 | 1.9983
1.2.4.2.10 | Install in Vacuum Vessel | 2006-06-01 08:00 | 2008-06-30 17:00 | 2.0832
1.2.4.3.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-02-27 17:00 | 2.1545
1.2.4.3.3 | WFD Readout Electronics | 2007-01-03 08:00 | 2009-06-30 17:00 | 2.4914
1.2.4.2 | Downstream Charged PV | 2005-10-03 08:00 | 2008-06-30 17:00 | 2.7435
1.2.4.1 | Barrel Charged PV | 2005-10-03 08:00 | 2008-12-31 17:00 | 3.2476
1.2.4.3 | Front-End Electronics & Cabling | 2006-10-02 08:00 | 2010-03-31 17:00 | 3.4969
1.2.4 | Charged Particle Veto | 2005-10-03 08:00 | 2010-03-31 17:00 | 4.4942 | OK
|  |  | Count Excessive | 23
>1 year
20%

## 1.2.5 Observations
Observations |  | WBS 1.2.5 Photon Veto | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type
Project Start Date | 2005-10-03
Project Finish Date | 2010-10-01
Project Calendar | MS Project Standard | 260 work days per yr. (No adj'd for Holidays, pd. abs or vacation)
Count Tasks | 289
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 93.43%
Successors | Missing | 95.16%
Task Type (Units,Work,Duration) | All Fixed Duration | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 211, (73%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 8
Hours/week | 40
Hours/year | 2080 | Equals 260 days x 8 hours.
Days/month | 21.7 | Equals 260 days / 12 months.
Excessive Durations | 166 Tasks | 57%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 44 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
| 1.2.5 | Photon Veto | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 7194379.23 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.1269 | 713782.1536 | 3345048.8336
|  | LED Design Review (Calorimeter) | 0 days | 2005-12-15 08:00 | 2005-12-15 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2005-12-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.7963 | 344700.928 | 1734829.168
|  | HV Design Review (Calorimeter) | 0 days | 2006-02-28 08:00 | 2006-02-28 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-02-28 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 4 | 2 | 1 | 0 | 0 | 0
|  | Readout Design Review (Calorimeter) | 0 days | 2006-03-31 08:00 | 2006-03-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-03-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.3913 | 24280 | 116280
| 1.2.5.1 | Upstream Photon Veto | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 1493676 |  |  | Fixed Duration |  |  | 2 | 4 | 8 | 8 | 2 | 2 | 1 | 28 | 5040 | 23040
|  | UPV Design Review | 0 days | 2005-10-17 08:00 | 2005-10-17 08:00 | 0 | 0 | 0 |  | 7,18 | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.1 | Log Module | 913 days | 2005-10-17 08:00 | 2009-04-15 17:00 | 909.1986 | 1276.375 | 693304 | 6 |  | Fixed Duration |  |  | 3 | 4 | 8 | 8 | 2 | 1 | 1 | 26 | 19240 | 93240
| 1.2.5.1.1.1 | WLS Fibers | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 127432 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.3478 | 67846.1856 | 315932.2656
| 1.2.5.1.1.2 | Scintillator | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 131472 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 1 | 0 | 0 | 0
| 1.2.5.1.1.3 | Reflective Covering/Gluing | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 155678 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 2 | 1 | 32 | 1600 | 6600
| 1.2.5.1.1.4 | Lead | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 60402 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 1 | 28 | 11419.52 | 52203.52
| 1.2.5.1.1.5 | Assembly & Test | 567 days | 2006-10-16 08:00 | 2008-12-16 17:00 | 564.4315 | 792.375 | 175440 |  |  | Fixed Duration | 2006-10-16 08:00 | Start No Earlier Than | 4 | 1 | 8 | 8 | 2 | 1 | 1 | 25 | 28250 | 141250
|  | Production Complete | 0 days | 2008-12-16 08:00 | 2008-12-16 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-12-16 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7604 | 26576.6656 | 115878.7456
| 1.2.5.1.1.6 | Shipping | 327 days | 2008-01-15 08:00 | 2009-04-15 17:00 | 325.089 | 456.375 | 42880 |  |  | Fixed Duration | 2008-01-15 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 2 | 1 | 32 | 12576.6656 | 51878.7456
| 1.2.5.1.2 | UpstreamVeto Assembling | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 365560 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.2.1 | Preinstallation/Test/Support | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 305560 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 1 | 28 | 14000 | 64000
| 1.2.5.1.2.2 | Travel | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 60000 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79878.08
| 1.2.5.1.3 | Module Instrumentation | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 95314 | 6 |  | Fixed Duration |  |  | 4 | 4 | 8 | 8 | 2 | 2 | 1 | 32 | 43153.1008 | 178006.5408
| 1.2.5.1.3.1 | PMT Unit | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 29306 |  |  | Fixed Duration |  |  | 2 | 4 | 8 | 8 | 2 | 1 | 1 | 24 | 23004.8256 | 118858.2656
| 1.2.5.1.3.1.1 | PMT | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 1188 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 93303.056 | 426528.256
| 1.2.5.1.3.1.2 | Voltage Divider | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 3038 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 24711.456 | 112966.656
| 1.2.5.1.3.1.3 | Mu metal shielding | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 25080 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 28 | 24711.456 | 112966.656
| 1.2.5.1.3.2 | Preamplifier | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 6600 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 0 | 0 | 0
| 1.2.5.1.3.3 | LV-HV Converter | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 22048 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 28 | 1680 | 7680
| 1.2.5.1.3.4 | Mechanics & PC Boards | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 11350 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3.5 | PMT Units Assembly | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 21916 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 2 | 1 | 28 | 66911.6 | 305881.6
|  | PMT Assembly Complete | 0 days | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-12-01 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 61797.12 | 319285.12
| 1.2.5.1.3.6 | PMT Units Test | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 2376 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.3.7 | PMT Units Packing | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 1718 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 16552.8 | 108512.8
| 1.2.5.1.4 | Mechanics | 990 days | 2005-10-17 08:00 | 2009-07-31 17:00 | 985.4178 | 1383.375 | 221920 |  |  | Fixed Duration |  |  | 2 | 4 | 2 | 8 | 2 | 1 | 1 | 18 | 16552.8 | 108512.8
| 1.2.5.1.4.1 | Design | 435 days | 2005-10-17 08:00 | 2007-06-15 17:00 | 431.9384 | 606.375 | 44160 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 2 | 4 | 2 | 8 | 2 | 1 | 1 | 0 | 0 | 0
|  | Mechanics Design Review | 0 days | 2007-06-01 08:00 | 2007-06-01 08:00 | 0 | 0 | 0 |  | 33 | Fixed Duration | 2007-06-01 08:00 | Start No Earlier Than | 4 | 4 | 2 | 8 | 2 | 2 | 1 | 26 | 5200 | 25200
| 1.2.5.1.4.3 | Fabrication/Procurement | 328 days | 2007-06-15 08:00 | 2008-09-16 17:00 | 327.226 | 459.375 | 120000 | 32 | 36FS-2 days | Fixed Duration | 2007-06-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.4.4 | Assembly/Support | 78 days | 2009-04-15 08:00 | 2009-07-31 17:00 | 76.4863 | 107.375 | 34880 | 36 |  | Fixed Duration | 2009-04-15 08:00 | Start No Earlier Than | 4 | 4 | 2 | 8 | 2 | 2 | 1 | 26 | 9563.84 | 46347.84
|  | Mechanics Assembly Complete | 0 days | 2009-07-31 08:00 | 2009-07-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-07-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.7111 | 255133.3636 | 1059687.9536
| 1.2.5.1.4.6 | Shipping | 130 days | 2008-09-15 08:00 | 2009-03-13 17:00 | 127.774 | 179.375 | 22880 | 33FS-2 days | 34 | Fixed Duration | 2008-09-15 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 15095.76 | 63791.76
| 1.2.5.1.5 | Instrumentation | 717 days | 2006-10-02 08:00 | 2009-06-30 17:00 | 714.0205 | 1002.375 | 100264 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6764 | 14110.3899 | 125422.9599
| 1.2.5.1.5.1 | HV Control System | 326 days | 2006-10-02 08:00 | 2007-12-31 17:00 | 324.3767 | 455.375 | 18970 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6782 | 6263.184 | 70977.584
| 1.2.5.1.5.1.1 | VME Carriers | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 2950 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 4 | 4 | 4 | 2 | 1 | 1 | 16 | 2365.824 | 17152.224
| 1.2.5.1.5.1.2 | DA Converters | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 14030 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 1 | 1 | 4 | 8 | 2 | 1 | 1 | 15 | 754.5 | 5784.5
| 1.2.5.1.5.1.3 | VME/VXI Mainframe | 65 days | 2006-10-02 08:00 | 2006-12-29 17:00 | 62.9521 | 88.375 | 1990 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 1 | 1 | 4 | 0 | 2 | 1 | 1 | 7 | 3142.86 | 48040.86
| 1.2.5.1.5.1.4 | Test | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 0 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.5.2 | LED Monitoring System | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 9880 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.9196 | 5847 | 45037
| 1.2.5.1.5.2.1 | Fabrication | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 9232 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 1 | 1 | 4 | 8 | 2 | 1 | 1 | 15 | 4962 | 38042
|  | Fabrication Complete | 0 days | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-01-01 08:00 | Start No Earlier Than | 1 | 1 | 4 | 8 | 2 | 1 | 1 | 15 | 822 | 6302
| 1.2.5.1.5.2.2 | Test & Packing | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 648 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 1 | 4 | 4 | 0 | 2 | 1 | 1 | 10 | 63 | 693
| 1.2.5.1.5.3 | Readout Electronics | 650 days | 2007-01-03 08:00 | 2009-06-30 17:00 | 647.774 | 909.375 | 68978 |  |  | Fixed Duration |  |  | 2 | 4 | 4 | 15 | 2 | 1 | 1 | 27 | 2000.2059 | 9408.3759
| 1.2.5.1.5.3.1 | WFD Boards | 564 days | 2007-01-03 08:00 | 2009-03-02 17:00 | 562.2945 | 789.375 | 61128 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.5.3.1.3 | Fabrication/Procurement | 499 days | 2007-01-03 08:00 | 2008-12-01 17:00 | 497.4726 | 698.375 | 60120 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.2503 | 94559.1255 | 341770.7555
| 1.2.5.1.5.3.1.5 | Test | 501 days | 2007-04-02 08:00 | 2009-03-02 17:00 | 498.8973 | 700.375 | 1008 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.1375 | 5399.364 | 22739.764
|  | Fabrication Complete | 0 days | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-03-02 08:00 | Start No Earlier Than | 8 | 6 | 4 | 15 | 2 | 1 | 1 | 41 | 5047.264 | 17357.664
| 1.2.5.1.5.3.2 | Crate Data-Collection Boards | 370 days | 2007-07-02 08:00 | 2008-11-28 17:00 | 367.1164 | 515.375 | 3100 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.5.3.3 | VME Mainframes & Controller | 130 days | 2007-07-02 08:00 | 2007-12-28 17:00 | 127.774 | 179.375 | 4750 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 1 | 1 | 4 | 0 | 2 | 1 | 1 | 7 | 352.1 | 5382.1
| 1.2.5.1.5.3.4 | System Test | 195 days | 2008-10-01 08:00 | 2009-06-30 17:00 | 194.0205 | 272.375 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.7018 | 88856.7 | 312666.7
|  | Fabrication Complete | 0 days | 2009-06-30 08:00 | 2009-06-30 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-06-30 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 4 | 2 | 1 | 81 | 54391.5 | 121541.5
| 1.2.5.1.5.4 | LV Power Supplies & Electronic Racks | 130 days | 2007-07-02 08:00 | 2007-12-28 17:00 | 127.774 | 179.375 | 2436 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 1 | 1 | 4 | 15 | 2 | 1 | 1 | 22 | 34465.2 | 191125.2
| 1.2.5.1.6 | Cabling | 522 days | 2008-04-01 08:00 | 2010-03-31 17:00 | 519.5548 | 729.375 | 17314 |  |  | Fixed Duration |  |  | 1 | 1 | 2 | 0 | 2 | 1 | 1 | 5 | 303.0615 | 6364.2915
| 1.2.5.1.6.1 | Production of LV-PS Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 5628 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.1.6.2 | Production of HV-Control Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 1364 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.3511 | 21422.628 | 75862.388
| 1.2.5.1.6.3 | Production of Signal Cables | 304 days | 2008-04-01 08:00 | 2009-05-29 17:00 | 301.5822 | 423.375 | 6200 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 8 | 6 | 4 | 15 | 2 | 1 | 1 | 41 | 13338.284 | 45870.684
| 1.2.5.1.6.4 | Assembly and Installation | 152 days | 2009-09-01 08:00 | 2010-03-31 17:00 | 150.5685 | 211.375 | 4122 |  |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.9024 | 8084.344 | 29991.704
|  | Subsystem Installation Compllete | 0 days | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2010-03-31 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 2337.4 | 9877.4
| 1.2.5.2 | Barrel Photon Veto | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 3599472.3 |  |  | Fixed Duration |  |  | 3 | 15 | 4 | 15 | 2 | 1 | 1 | 40 | 5746.944 | 20114.304
|  | BPV Design Review | 0 days | 2005-10-17 08:00 | 2005-10-17 08:00 | 0 | 0 | 0 |  | 65,76 | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.0899 | 8732.3 | 42202.3
| 1.2.5.2.1 | Shashlyk Module | 913 days | 2005-10-17 08:00 | 2009-04-15 17:00 | 909.1986 | 1276.375 | 1596490 | 64 |  | Fixed Duration |  |  | 2 | 6 | 4 | 8 | 2 | 1 | 1 | 22 | 4017.2 | 22277.2
| 1.2.5.2.1.1 | WLS Fibers | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 395050 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 4715.1 | 19925.1
| 1.2.5.2.1.2 | Scintillator | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 263340 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.842 | 28881.441 | 111774.141
| 1.2.5.2.1.3 | Reflective Covering | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 114240 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 2 | 15 | 4 | 15 | 2 | 1 | 1 | 38 | 5779.8 | 20989.8
| 1.2.5.2.1.4 | Lead Sheet | 827 days | 2005-10-17 08:00 | 2008-12-16 17:00 | 823.7192 | 1156.375 | 361260 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 8 | 1 | 4 | 15 | 2 | 1 | 1 | 36 | 7658.82 | 28933.32
| 1.2.5.2.1.5 | Assembly & Test | 567 days | 2006-10-16 08:00 | 2008-12-16 17:00 | 564.4315 | 792.375 | 376840 |  |  | Fixed Duration | 2006-10-16 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.3792 | 8901.425 | 37268.725
|  | Production Complete | 0 days | 2008-12-16 08:00 | 2008-12-16 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-12-16 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 5567.352 | 23526.552
| 1.2.5.2.1.6 | Shipping | 413 days | 2007-09-17 08:00 | 2009-04-15 17:00 | 410.5685 | 576.375 | 85760 |  |  | Fixed Duration | 2007-09-17 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 1559.3 | 6589.3
| 1.2.5.2.2 | Barrel Veto Assemby | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 653200 |  |  | Fixed Duration |  |  | 4 | 6 | 4 | 15 | 2 | 1 | 1 | 33 | 1774.773 | 7152.873
| 1.2.5.2.2.1 | Preinstallation/Test/Support | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 525200 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.2587 | 6541.396 | 24582.296
| 1.2.5.2.2.2 | Travel | 1295 days | 2005-10-17 08:00 | 2010-10-01 17:00 | 1289.5822 | 1810.375 | 128000 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 4407.487 | 18625.187
| 1.2.5.2.3 | Module Instrumentation | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 303240 | 64 |  | Fixed Duration |  |  | 15 | 15 | 4 | 15 | 2 | 1 | 1 | 64 | 1839.936 | 4714.836
| 1.2.5.2.3.1 | PMT Unit | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 93240 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 293.973 | 1242.273
| 1.2.5.2.3.1.1 | PMT | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 3780 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.3.1.2 | Voltage Divider | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 9660 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 2 | 4 | 4 | 15 | 2 | 1 | 1 | 27 | 3838.779 | 18056.479
| 1.2.5.2.3.1.3 | Mu metal shielding | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 79800 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.4452 | 28887.7272 | 117923.2572
| 1.2.5.2.3.2 | Preamplifier | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 21000 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 2 | 1 | 1 | 50 | 14460 | 43380
| 1.2.5.2.3.3 | LV-HV Converter | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 70140 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 1706.124 | 8814.974
| 1.2.5.2.3.4 | Mechanics & PC Boards | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 36120 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 892.1472 | 4609.4272
| 1.2.5.2.3.5 | PMT Units Assembly | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 69720 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 11829.456 | 61118.856
|  | PMT Assembly Complete | 0 days | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-12-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.0168 | 9061.572 | 45283.572
| 1.2.5.2.3.6 | PMT Units Test | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 7560 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 5746.944 | 29692.544
| 1.2.5.2.3.7 | PMT Units Packing | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 5460 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 4 | 4 | 15 | 2 | 1 | 1 | 27 | 3314.628 | 15591.028
| 1.2.5.2.4 | Mechanics | 1087 days | 2005-10-17 08:00 | 2009-12-15 17:00 | 1083.0068 | 1520.375 | 686260 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.4.1 | Design | 390 days | 2005-10-17 08:00 | 2007-04-13 17:00 | 387.0616 | 543.375 | 105180 |  |  | Fixed Duration | 2005-10-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.0848 | 30543.641 | 117600.341
|  | Mechanics Design Review | 0 days | 2007-04-13 08:00 | 2007-04-13 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-04-13 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 2 | 1 | 1 | 50 | 9609.6 | 28828.8
| 1.2.5.2.4.3 | Fabrication/Procurement | 414 days | 2008-05-15 08:00 | 2009-12-15 17:00 | 412.7055 | 579.375 | 435000 |  |  | Fixed Duration | 2008-05-15 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 2 | 1 | 1 | 50 | 3623.2 | 10869.6
| 1.2.5.2.4.4 | Assembly/Support | 326 days | 2007-05-15 08:00 | 2008-08-12 17:00 | 324.3767 | 455.375 | 60320 |  |  | Fixed Duration | 2007-05-15 08:00 | Start No Earlier Than | 1 | 1 | 4 | 15 | 2 | 1 | 1 | 22 | 3599.2 | 19959.2
|  | Mechanics Assembly Complete | 0 days | 2008-08-12 08:00 | 2008-08-12 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-08-12 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 11697.23 | 49430.23
| 1.2.5.2.4.6 | Shipping | 281 days | 2008-02-15 08:00 | 2009-03-13 17:00 | 279.5 | 392.375 | 85760 |  |  | Fixed Duration | 2008-02-15 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 2014.411 | 8512.511
| 1.2.5.2.5 | Instrumentation | 717 days | 2006-10-02 08:00 | 2009-06-30 17:00 | 714.0205 | 1002.375 | 305378.3 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.5.1 | HV Control System | 326 days | 2006-10-02 08:00 | 2007-12-31 17:00 | 324.3767 | 455.375 | 59170 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.0999 | 113947.862 | 550531.712
| 1.2.5.2.5.1.1 | VME Carriers | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 7740 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 7179.2 | 52049.2
| 1.2.5.2.5.1.2 | DA Converters | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 43730 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 992 | 7192
| 1.2.5.2.5.1.3 | VME/VXI Mainframe | 65 days | 2006-10-02 08:00 | 2006-12-29 17:00 | 62.9521 | 88.375 | 7700 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 5147.2 | 37317.2
| 1.2.5.2.5.1.4 | Test | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 0 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 1040 | 7540
| 1.2.5.2.5.2 | LED Monitoring System | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 29612 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.5.2.1 | Fabrication | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 27668 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fabrication Complete | 0 days | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-01-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.4025 | 88890.352 | 391212.652
| 1.2.5.2.5.2.3 | Test & Packing | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 1944 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.6349 | 83532.552 | 347584.852
| 1.2.5.2.5.3 | Readout Electronics | 650 days | 2007-01-03 08:00 | 2009-06-30 17:00 | 647.774 | 909.375 | 211784.3 |  |  | Fixed Duration |  |  | 8 | 4 | 4 | 4 | 2 | 2 | 0 | 32 | 80640 | 332640
| 1.2.5.2.5.3.1 | WFD Boards | 564 days | 2007-01-03 08:00 | 2009-03-02 17:00 | 562.2945 | 789.375 | 188234.3 |  |  | Fixed Duration |  |  | 4 | 4 | 8 | 0 | 2 | 2 | 0 | 24 | 2892.552 | 14944.852
| 1.2.5.2.5.3.1.3 | Fabrication/Procurement | 499 days | 2007-01-03 08:00 | 2008-12-01 17:00 | 497.4726 | 698.375 | 179640 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 0 | 14 | 2115.4 | 17225.4
| 1.2.5.2.5.3.1.5 | Test | 501 days | 2007-04-02 08:00 | 2009-03-02 17:00 | 498.8973 | 700.375 | 8594.3 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 0 | 14 | 3242.4 | 26402.4
|  | Fabrication Complete | 0 days | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-03-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.5.2.5.3.2 | Crate Data-Collection Boards | 370 days | 2007-07-02 08:00 | 2008-11-28 17:00 | 367.1164 | 515.375 | 9300 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 0 | 20 | 1207.47 | 7244.82
| 1.2.5.2.5.3.3 | VME Mainframes & Controller | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 14250 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 16670.84 | 100025.04
| 1.2.5.2.5.3.4 | System Test | 195 days | 2008-10-01 08:00 | 2009-06-30 17:00 | 194.0205 | 272.375 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 3791.852 | 22751.112
| 1.2.5.2.5.4 | LV Power Supplies & Electronic Racks | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 4812 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 1209.96 | 7259.76
| 1.2.5.2.6 | Cabling | 522 days | 2008-04-01 08:00 | 2010-03-31 17:00 | 519.5548 | 729.375 | 54904 |  |  | Fixed Duration |  |  | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 2860 | 17160
| 1.2.5.2.6.1 | Production of LV-PS Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 17868 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 8809.028 | 52854.168
| 1.2.5.2.6.2 | Production of HV-Control Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 4244 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.2.6.3 | Production of Signal Cables | 304 days | 2008-04-01 08:00 | 2009-05-29 17:00 | 301.5822 | 423.375 | 19670 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.2.6.4 | Assembly and Installation | 152 days | 2009-09-01 08:00 | 2010-03-31 17:00 | 150.5685 | 211.375 | 13122 |  |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than
|  | Subsystem Installation Compllete | 0 days | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2010-03-31 08:00 | Start No Earlier Than
| 1.2.5.3 | Magnet Photon Veto | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 678998.25 |  |  | Fixed Duration
|  | MPV Design Review | 0 days | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 | 0 | 0 |  | 122,133 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.5.3.1 | Log Module | 640 days | 2005-10-03 08:00 | 2008-03-14 17:00 | 636.3767 | 893.375 | 327294 | 121 |  | Fixed Duration
| 1.2.5.3.1.1 | WLS Fibers | 335 days | 2005-10-03 08:00 | 2007-01-12 17:00 | 332.2123 | 466.375 | 107794 |  |  | Fixed Duration
| 1.2.5.3.1.2 | Scintillator | 621 days | 2005-10-03 08:00 | 2008-02-18 17:00 | 618.5685 | 868.375 | 50640 |  |  | Fixed Duration
| 1.2.5.3.1.3 | Reflective Covering/Gluing | 621 days | 2005-10-03 08:00 | 2008-02-18 17:00 | 618.5685 | 868.375 | 72320 |  |  | Fixed Duration
| 1.2.5.3.1.4 | Lead | 621 days | 2005-10-03 08:00 | 2008-02-18 17:00 | 618.5685 | 868.375 | 48780 |  |  | Fixed Duration
| 1.2.5.3.1.5 | Assembly & Test | 481 days | 2006-04-17 08:00 | 2008-02-18 17:00 | 478.9521 | 672.375 | 35040 |  |  | Fixed Duration | 2006-04-17 08:00 | Start No Earlier Than
|  | Production Complete | 0 days | 2008-02-18 08:00 | 2008-02-18 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-02-18 08:00 | Start No Earlier Than
| 1.2.5.3.1.6 | Shipping | 65 days | 2007-12-17 08:00 | 2008-03-14 17:00 | 62.9521 | 88.375 | 12720 |  |  | Fixed Duration | 2007-12-17 08:00 | Start No Earlier Than
| 1.2.5.3.2 | Magnet Veto Assemby | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 99000 |  |  | Fixed Duration
| 1.2.5.3.2.1 | Preinstallation/Test/Support | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 79800 |  |  | Fixed Duration
| 1.2.5.3.2.2 | Travel | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 19200 |  |  | Fixed Duration
| 1.2.5.3.3 | Module Instrumentation | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 83360 | 121 |  | Fixed Duration
| 1.2.5.3.3.1 | PMT Unit | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 43360 |  |  | Fixed Duration
| 1.2.5.3.3.1.1 | PMT | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 26320 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.3.3.1.2 | Voltage Divider | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 1840 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.3.3.1.3 | Mu metal shielding | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 15200 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.3.3.2 | Preamplifier | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 4000 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.3.3.3 | LV-HV Converter | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 13360 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.3.3.4 | Mechanics & PC Boards | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 6880 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.3.3.5 | PMT Units Assembly | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 13280 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
|  | PMT Assembly Complete | 0 days | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-12-01 08:00 | Start No Earlier Than
| 1.2.5.3.3.6 | PMT Units Test | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 1440 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.3.3.7 | PMT Units Packing | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 1040 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.3.4 | Mechanics | 631 days | 2005-11-15 08:00 | 2008-04-15 17:00 | 628.5411 | 882.375 | 92000 |  |  | Fixed Duration
| 1.2.5.3.4.1 | Design | 284 days | 2005-11-15 08:00 | 2006-12-15 17:00 | 281.637 | 395.375 | 21120 |  |  | Fixed Duration | 2005-11-15 08:00 | Start No Earlier Than
|  | Mechanics Design Review | 0 days | 2006-12-15 08:00 | 2006-12-15 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-12-15 08:00 | Start No Earlier Than
| 1.2.5.3.4.3 | Fabrication/Procurement | 110 days | 2007-01-15 08:00 | 2007-06-15 17:00 | 107.8288 | 151.375 | 44000 |  |  | Fixed Duration | 2007-01-15 08:00 | Start No Earlier Than
| 1.2.5.3.4.4 | Assembly/Support | 152 days | 2007-09-17 08:00 | 2008-04-15 17:00 | 150.5685 | 211.375 | 15440 |  |  | Fixed Duration | 2007-09-17 08:00 | Start No Earlier Than
|  | Mechanics Assembly Complete | 0 days | 2008-04-15 08:00 | 2008-04-15 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-04-15 08:00 | Start No Earlier Than
| 1.2.5.3.4.6 | Shipping | 45 days | 2007-06-15 08:00 | 2007-08-16 17:00 | 44.4315 | 62.375 | 11440 |  |  | Fixed Duration | 2007-06-15 08:00 | Start No Earlier Than
| 1.2.5.3.5 | Instrumentation | 717 days | 2006-10-02 08:00 | 2009-06-30 17:00 | 714.0205 | 1002.375 | 66902.25 |  |  | Fixed Duration
| 1.2.5.3.5.1 | HV Control System | 326 days | 2006-10-02 08:00 | 2007-12-31 17:00 | 324.3767 | 455.375 | 11700 |  |  | Fixed Duration
| 1.2.5.3.5.1.1 | VME Carriers | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 1480 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than
| 1.2.5.3.5.1.2 | DA Converters | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 8250 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than
| 1.2.5.3.5.1.3 | VME/VXI Mainframe | 65 days | 2006-10-02 08:00 | 2006-12-29 17:00 | 62.9521 | 88.375 | 1970 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.3.5.1.4 | Test | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 0 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.3.5.2 | LED Monitoring System | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 5478 |  |  | Fixed Duration
| 1.2.5.3.5.2.1 | Fabrication | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 5118 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
|  | Fabrication Complete | 0 days | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-01-01 08:00 | Start No Earlier Than
| 1.2.5.3.5.2.3 | Test & Packing | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 360 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
| 1.2.5.3.5.3 | Readout Electronics | 650 days | 2007-01-03 08:00 | 2009-06-30 17:00 | 647.774 | 909.375 | 45654.97 |  |  | Fixed Duration
| 1.2.5.3.5.3.1 | WFD Boards | 564 days | 2007-01-03 08:00 | 2009-03-02 17:00 | 562.2945 | 789.375 | 39504.97 |  |  | Fixed Duration
| 1.2.5.3.5.3.1.3 | Fabrication/Procurement | 499 days | 2007-01-03 08:00 | 2008-12-01 17:00 | 497.4726 | 698.375 | 37720 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
| 1.2.5.3.5.3.1.5 | Test | 501 days | 2007-04-02 08:00 | 2009-03-02 17:00 | 498.8973 | 700.375 | 1784.97 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than
|  | Fabrication Complete | 0 days | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-03-02 08:00 | Start No Earlier Than
| 1.2.5.3.5.3.2 | Crate Data-Collection Boards | 370 days | 2007-07-02 08:00 | 2008-11-28 17:00 | 367.1164 | 515.375 | 3180 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.3.5.3.3 | VME Mainframes & Controller | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 2970 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.3.5.3.4 | System Test | 195 days | 2008-10-01 08:00 | 2009-06-30 17:00 | 194.0205 | 272.375 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.5.3.5.4 | LV Power Supplies & Electronic Racks | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 4069.28 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.3.6 | Cabling | 522 days | 2008-04-01 08:00 | 2010-03-31 17:00 | 519.5548 | 729.375 | 10442 |  |  | Fixed Duration
| 1.2.5.3.6.1 | Production of LV-PS Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 3398 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.3.6.2 | Production of HV-Control Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 796 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.3.6.3 | Production of Signal Cables | 304 days | 2008-04-01 08:00 | 2009-05-29 17:00 | 301.5822 | 423.375 | 3740 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.3.6.4 | Assembly and Installation | 152 days | 2009-09-01 08:00 | 2010-03-31 17:00 | 150.5685 | 211.375 | 2508 |  |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than
|  | Subsytem Installation Complete | 0 days | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2010-03-31 08:00 | Start No Earlier Than
| 1.2.5.4 | DS Photon Veto | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 1038172.12 |  |  | Fixed Duration
|  | DSPV Design Review | 0 days | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 | 0 | 0 |  | 190,179 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.5.4.1 | Log Module | 705 days | 2005-10-03 08:00 | 2008-06-13 17:00 | 701.1986 | 984.375 | 332074 | 178 |  | Fixed Duration
| 1.2.5.4.1.1 | WLS Fibers | 335 days | 2005-10-03 08:00 | 2007-01-12 17:00 | 332.2123 | 466.375 | 102760 |  |  | Fixed Duration
| 1.2.5.4.1.2 | Scintillator | 641 days | 2005-10-03 08:00 | 2008-03-17 17:00 | 638.5137 | 896.375 | 52200 |  |  | Fixed Duration
| 1.2.5.4.1.3 | Reflective Covering/Gluing | 641 days | 2005-10-03 08:00 | 2008-03-17 17:00 | 638.5137 | 896.375 | 69860 |  |  | Fixed Duration
| 1.2.5.4.1.4 | Lead | 641 days | 2005-10-03 08:00 | 2008-03-17 17:00 | 638.5137 | 896.375 | 48474 |  |  | Fixed Duration
| 1.2.5.4.1.5 | Assembly & Test | 480 days | 2006-06-15 08:00 | 2008-04-16 17:00 | 478.2397 | 671.375 | 46060 |  |  | Fixed Duration | 2006-06-15 08:00 | Start No Earlier Than
|  | Production Complete | 0 days | 2008-04-16 08:00 | 2008-04-16 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-04-16 08:00 | Start No Earlier Than
| 1.2.5.4.1.6 | Shipping | 130 days | 2007-12-17 08:00 | 2008-06-13 17:00 | 127.774 | 179.375 | 12720 |  |  | Fixed Duration | 2007-12-17 08:00 | Start No Earlier Than
| 1.2.5.4.2 | DS Veto Assembly | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 302800 |  |  | Fixed Duration
| 1.2.5.4.2.1 | Preinstallation/Test/Support | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 278800 |  |  | Fixed Duration
| 1.2.5.4.2.2 | Travel | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 24000 |  |  | Fixed Duration
| 1.2.5.4.3 | Module Instrumentation | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 145880 | 178 |  | Fixed Duration
| 1.2.5.4.3.1 | PMT Unit | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 75880 |  |  | Fixed Duration
| 1.2.5.4.3.1.1 | PMT | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 46060 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.4.3.1.2 | Voltage Divider | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 3220 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.4.3.1.3 | Mu metal shielding | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 26600 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.4.3.2 | Preamplifier | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 7000 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.4.3.3 | LV-HV Converter | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 23380 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.4.3.4 | Mechanics & PC Boards | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 12040 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.4.3.5 | PMT Units Assembly | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 23240 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
|  | PMT Assembly Complete | 0 days | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-12-01 08:00 | Start No Earlier Than
| 1.2.5.4.3.6 | PMT Units Test | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 2520 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.4.3.7 | PMT Units Packing | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 1820 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.4.5 | Mechanics | 696 days | 2005-11-15 08:00 | 2008-07-15 17:00 | 693.363 | 973.375 | 134720 |  |  | Fixed Duration
| 1.2.5.4.5.1 | Design | 348 days | 2005-11-15 08:00 | 2007-03-15 17:00 | 345.7466 | 485.375 | 21120 |  |  | Fixed Duration | 2005-11-15 08:00 | Start No Earlier Than
|  | Mechanics Design Review | 0 days | 2007-03-01 08:00 | 2007-03-01 08:00 | 0 | 0 | 0 |  | 205 | Fixed Duration | 2007-03-01 08:00 | Start No Earlier Than
| 1.2.5.4.5.3 | Fabrication/Procurement | 196 days | 2007-03-15 08:00 | 2007-12-13 17:00 | 194.7329 | 273.375 | 80000 | 204 | 208 | Fixed Duration | 2007-03-15 08:00 | Start No Earlier Than
| 1.2.5.4.5.4 | Assembly/Support | 87 days | 2008-03-17 08:00 | 2008-07-15 17:00 | 85.7466 | 120.375 | 22160 | 208 |  | Fixed Duration | 2008-03-17 08:00 | Start No Earlier Than
|  | Mechanics Assembly Complete | 0 days | 2008-07-15 08:00 | 2008-07-15 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-07-15 08:00 | Start No Earlier Than
| 1.2.5.4.5.6 | Shipping | 45 days | 2007-12-17 08:00 | 2008-02-15 17:00 | 43.0068 | 60.375 | 11440 | 205 | 206 | Fixed Duration | 2007-12-17 08:00 | Start No Earlier Than
| 1.2.5.4.6 | Instrumentation | 717 days | 2006-10-02 08:00 | 2009-06-30 17:00 | 714.0205 | 1002.375 | 104368.12 |  |  | Fixed Duration
| 1.2.5.4.6.1 | HV Control System | 326 days | 2006-10-02 08:00 | 2007-12-31 17:00 | 324.3767 | 455.375 | 19540 |  |  | Fixed Duration
| 1.2.5.4.6.1.1 | VME Carriers | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 2580 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than
| 1.2.5.4.6.1.2 | DA Converters | 174 days | 2006-12-01 08:00 | 2007-08-01 17:00 | 173.363 | 243.375 | 14850 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than
| 1.2.5.4.6.1.3 | VME/VXI Mainframe | 65 days | 2006-10-02 08:00 | 2006-12-29 17:00 | 62.9521 | 88.375 | 2110 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.4.6.1.4 | Test | 131 days | 2007-07-02 08:00 | 2007-12-31 17:00 | 129.911 | 182.375 | 0 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.4.6.2 | LED Monitoring System | 259 days | 2007-01-03 08:00 | 2007-12-31 17:00 | 258.1301 | 362.375 | 9880 |  |  | Fixed Duration
| 1.2.5.4.6.2.1 | Fabrication | 259 days | 2007-01-03 08:00 | 2007-12-31 17:00 | 258.1301 | 362.375 | 9232 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
|  | Fabrication Complete | 0 days | 2007-12-31 08:00 | 2007-12-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-12-31 08:00 | Start No Earlier Than
| 1.2.5.4.6.2.3 | Test & Packing | 259 days | 2007-01-03 08:00 | 2007-12-31 17:00 | 258.1301 | 362.375 | 648 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
| 1.2.5.4.6.3 | Readout Electronics | 650 days | 2007-01-03 08:00 | 2009-06-30 17:00 | 647.774 | 909.375 | 70878.84 |  |  | Fixed Duration
| 1.2.5.4.6.3.1 | WFD Boards | 564 days | 2007-01-03 08:00 | 2009-03-02 17:00 | 562.2945 | 789.375 | 63028.84 |  |  | Fixed Duration
| 1.2.5.4.6.3.1.3 | Fabrication/Procurement | 499 days | 2007-01-03 08:00 | 2008-12-01 17:00 | 497.4726 | 698.375 | 60120 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
| 1.2.5.4.6.3.1.5 | Test | 501 days | 2007-04-02 08:00 | 2009-03-02 17:00 | 498.8973 | 700.375 | 2908.84 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than
|  | Fabrication Complete | 0 days | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-03-02 08:00 | Start No Earlier Than
| 1.2.5.4.6.3.2 | Crate Data-Collection Boards | 370 days | 2007-07-02 08:00 | 2008-11-28 17:00 | 367.1164 | 515.375 | 3100 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.4.6.3.3 | VME Mainframes & Controller | 130 days | 2007-07-02 08:00 | 2007-12-28 17:00 | 127.774 | 179.375 | 4750 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.4.6.3.4 | System Test | 195 days | 2008-10-01 08:00 | 2009-06-30 17:00 | 194.0205 | 272.375 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.5.4.6.4 | LV Power Supplies & Electronic Racks | 132 days | 2007-07-02 08:00 | 2008-01-01 17:00 | 130.6233 | 183.375 | 4069.28 |  |  | Fixed Duration | 2007-07-01 08:00 | Start No Earlier Than
| 1.2.5.4.7 | Cabling | 522 days | 2008-04-01 08:00 | 2010-03-31 17:00 | 519.5548 | 729.375 | 18330 |  |  | Fixed Duration
| 1.2.5.4.7.1 | Production of LV-PS Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 5950 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.4.7.2 | Production of HV-Control Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 1440 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.4.7.3 | Production of Signal Cables | 304 days | 2008-04-01 08:00 | 2009-05-29 17:00 | 301.5822 | 423.375 | 6560 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.4.7.4 | Assembly and Installation | 152 days | 2009-09-01 08:00 | 2010-03-31 17:00 | 150.5685 | 211.375 | 4380 |  |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than
|  | Subsystem Installation Complete | 0 days | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2010-03-31 08:00 | Start No Earlier Than
| 1.2.5.5 | Magnet Charged Particle Veto | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 384060.56 |  |  | Fixed Duration
|  | MCPV Design Review | 0 days | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 | 0 | 0 |  | 236,246 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.5.5.1 | Plate Module | 640 days | 2005-10-03 08:00 | 2008-03-14 17:00 | 636.3767 | 893.375 | 100248 | 235 |  | Fixed Duration
| 1.2.5.5.1.1 | WLS Fibers | 335 days | 2005-10-03 08:00 | 2007-01-12 17:00 | 332.2123 | 466.375 | 6184 |  |  | Fixed Duration
| 1.2.5.5.1.2 | Scintillator | 621 days | 2005-10-03 08:00 | 2008-02-18 17:00 | 618.5685 | 868.375 | 60880 |  |  | Fixed Duration
| 1.2.5.5.1.4 | Reflective Covering/Gluing | 621 days | 2005-10-03 08:00 | 2008-02-18 17:00 | 618.5685 | 868.375 | 17824 |  |  | Fixed Duration
| 1.2.5.5.1.5 | Assembly & Test | 481 days | 2006-04-17 08:00 | 2008-02-18 17:00 | 478.9521 | 672.375 | 15360 |  |  | Fixed Duration | 2006-04-17 08:00 | Start No Earlier Than
|  | Production Complete | 0 days | 2008-02-18 08:00 | 2008-02-18 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-02-18 08:00 | Start No Earlier Than
| 1.2.5.5.1.6 | Shipping | 65 days | 2007-12-17 08:00 | 2008-03-14 17:00 | 62.9521 | 88.375 | 0 |  |  | Fixed Duration | 2007-12-17 08:00 | Start No Earlier Than
| 1.2.5.5.2 | Magnet Veto Assemby | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 46080 |  |  | Fixed Duration
| 1.2.5.5.2.1 | Preinstallation/Test/Support | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 46080 |  |  | Fixed Duration
| 1.2.5.5.2.2 | Travel | 1305 days | 2005-10-03 08:00 | 2010-10-01 17:00 | 1299.5548 | 1824.375 | 0 |  |  | Fixed Duration
| 1.2.5.5.3 | Module Instrumentation | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 89440 | 235 |  | Fixed Duration
| 1.2.5.5.3.1 | PMT Unit | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 49440 |  |  | Fixed Duration
| 1.2.5.5.3.1.1 | APD | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 32400 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.5.3.1.2 | Voltage Divider | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 1840 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.5.3.1.3 | Mu metal shielding | 703 days | 2006-07-03 08:00 | 2009-03-11 17:00 | 699.774 | 982.375 | 15200 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.5.3.2 | Preamplifier | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 4000 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.5.3.3 | LV-HV Converter | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 13360 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.5.3.4 | Mechanics & PC Boards | 566 days | 2006-07-03 08:00 | 2008-09-01 17:00 | 563.7192 | 791.375 | 6880 |  |  | Fixed Duration | 2006-07-03 08:00 | Start No Earlier Than
| 1.2.5.5.3.5 | PMT Units Assembly | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 13280 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
|  | PMT Assembly Complete | 0 days | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-12-01 08:00 | Start No Earlier Than
| 1.2.5.5.3.6 | PMT Units Test | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 1440 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.5.3.7 | PMT Units Packing | 566 days | 2006-10-02 08:00 | 2008-12-01 17:00 | 563.7192 | 791.375 | 1040 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.5.5 | Mechanics | 631 days | 2005-11-15 08:00 | 2008-04-15 17:00 | 628.5411 | 882.375 | 38080 |  |  | Fixed Duration
| 1.2.5.5.5.1 | Design | 284 days | 2005-11-15 08:00 | 2006-12-15 17:00 | 281.637 | 395.375 | 10560 |  |  | Fixed Duration | 2005-11-15 08:00 | Start No Earlier Than
|  | Mechanics Design Review | 0 days | 2006-12-01 08:00 | 2006-12-01 08:00 | 0 | 0 | 0 |  | 261 | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than
| 1.2.5.5.5.2 | Fabrication/Procurement | 110 days | 2007-01-15 08:00 | 2007-06-15 17:00 | 107.8288 | 151.375 | 16000 | 260 | 264FS-1 day | Fixed Duration | 2007-01-15 08:00 | Start No Earlier Than
| 1.2.5.5.5.4 | Assembly/Support | 152 days | 2007-09-17 08:00 | 2008-04-15 17:00 | 150.5685 | 211.375 | 11520 | 264 |  | Fixed Duration | 2007-09-17 08:00 | Start No Earlier Than
|  | Mechanics Assembly Complete | 0 days | 2008-04-15 08:00 | 2008-04-15 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-04-15 08:00 | Start No Earlier Than
| 1.2.5.5.5.6 | Shipping | 45 days | 2007-06-15 08:00 | 2007-08-16 17:00 | 44.4315 | 62.375 | 0 | 261FS-1 day | 262 | Fixed Duration | 2007-06-15 08:00 | Start No Earlier Than
| 1.2.5.5.6 | Instrumentation | 717 days | 2006-10-02 08:00 | 2009-06-30 17:00 | 714.0205 | 1002.375 | 99770.56 |  |  | Fixed Duration
| 1.2.5.5.6.1 | HV Control System | 327 days | 2006-10-02 08:00 | 2008-01-01 17:00 | 325.089 | 456.375 | 11700 |  |  | Fixed Duration
| 1.2.5.5.6.1.1 | VME Carriers | 172 days | 2006-12-01 08:00 | 2007-07-30 17:00 | 171.9384 | 241.375 | 1480 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than
| 1.2.5.5.6.1.2 | DA Converters | 172 days | 2006-12-01 08:00 | 2007-07-30 17:00 | 171.9384 | 241.375 | 8250 |  |  | Fixed Duration | 2006-12-01 08:00 | Start No Earlier Than
| 1.2.5.5.6.1.3 | VME/VXI Mainframe | 65 days | 2006-10-02 08:00 | 2006-12-29 17:00 | 62.9521 | 88.375 | 1970 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.5.5.6.1.4 | Test | 132 days | 2007-07-02 08:00 | 2008-01-01 17:00 | 130.6233 | 183.375 | 0 |  |  | Fixed Duration | 2007-07-01 08:00 | Start No Earlier Than
| 1.2.5.5.6.2 | LED Monitoring System | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 5478 |  |  | Fixed Duration
| 1.2.5.5.6.2.1 | Fabrication | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 5118 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
|  | Fabrication Complete | 0 days | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-01-01 08:00 | Start No Earlier Than
| 1.2.5.5.6.2.3 | Test & Packing | 260 days | 2007-01-03 08:00 | 2008-01-01 17:00 | 258.8425 | 363.375 | 360 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
| 1.2.5.5.6.3 | Readout Electronics | 650 days | 2007-01-03 08:00 | 2009-06-30 17:00 | 647.774 | 909.375 | 78523.28 |  |  | Fixed Duration
| 1.2.5.5.6.3.1 | WFD Boards | 564 days | 2007-01-03 08:00 | 2009-03-02 17:00 | 562.2945 | 789.375 | 69693.28 |  |  | Fixed Duration
| 1.2.5.5.6.3.1.3 | Fabrication/Procurement | 499 days | 2007-01-03 08:00 | 2008-12-01 17:00 | 497.4726 | 698.375 | 66520 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
| 1.2.5.5.6.3.1.5 | Test | 501 days | 2007-04-02 08:00 | 2009-03-02 17:00 | 498.8973 | 700.375 | 3173.28 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than
|  | Fabrication Complete | 0 days | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-03-02 08:00 | Start No Earlier Than
| 1.2.5.5.6.3.2 | Crate Data-Collection Boards | 370 days | 2007-07-02 08:00 | 2008-11-28 17:00 | 367.1164 | 515.375 | 3490 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.5.6.3.3 | VME Mainframes & Controller | 130 days | 2007-07-02 08:00 | 2007-12-28 17:00 | 127.774 | 179.375 | 5340 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.5.6.3.4 | System Test | 195 days | 2008-10-01 08:00 | 2009-06-30 17:00 | 194.0205 | 272.375 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.5.5.6.4 | LV Power Supplies & Electronic Racks | 130 days | 2007-07-02 08:00 | 2007-12-28 17:00 | 127.774 | 179.375 | 4069.28 |  |  | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.5.5.7 | Cabling | 522 days | 2008-04-01 08:00 | 2010-03-31 17:00 | 519.5548 | 729.375 | 10442 |  |  | Fixed Duration
| 1.2.5.5.7.1 | Production of LV-PS Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 3398 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.5.7.2 | Production of HV-Control Cables | 174 days | 2008-04-01 08:00 | 2008-11-28 17:00 | 171.9384 | 241.375 | 796 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.5.7.3 | Production of Signal Cables | 304 days | 2008-04-01 08:00 | 2009-05-29 17:00 | 301.5822 | 423.375 | 3740 |  |  | Fixed Duration | 2008-04-01 08:00 | Start No Earlier Than
| 1.2.5.5.7.4 | Assembly and Installation | 152 days | 2009-09-01 08:00 | 2010-03-31 17:00 | 150.5685 | 211.375 | 2508 |  |  | Fixed Duration | 2009-09-01 08:00 | Start No Earlier Than
|  | Subsystem Installation Complete | 0 days | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2010-03-31 08:00 | Start No Earlier Than
|  | 289 | [5 empty] | Count | 19 | 14 | 289 | 211 | 211
[8 empty] | Assigned | 6.574% | 4.844%
[8 empty] | Missing | 93.43% | 95.16%

## 1.2.5 Durations & Milestone
| Excessive Durations |  |  | Sort |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration Days
1.2.5.2.4.6 | Shipping | 2008-02-15 08:00 | 2009-03-13 17:00 | 1.075 |  | MPV Design Review | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 days
1.2.5.3.4.1 | Design | 2005-11-15 08:00 | 2006-12-15 17:00 | 1.0832 |  | DSPV Design Review | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 days
1.2.5.5.5.1 | Design | 2005-11-15 08:00 | 2006-12-15 17:00 | 1.0832 |  | MCPV Design Review | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 days
1.2.5.1.6.3 | Production of Signal Cables | 2008-04-01 08:00 | 2009-05-29 17:00 | 1.1599 |  | UPV Design Review | 2005-10-17 08:00 | 2005-10-17 08:00 | 0 days
1.2.5.2.6.3 | Production of Signal Cables | 2008-04-01 08:00 | 2009-05-29 17:00 | 1.1599 |  | BPV Design Review | 2005-10-17 08:00 | 2005-10-17 08:00 | 0 days
1.2.5.3.6.3 | Production of Signal Cables | 2008-04-01 08:00 | 2009-05-29 17:00 | 1.1599 |  | LED Design Review (Calorimeter) | 2005-12-15 08:00 | 2005-12-15 08:00 | 0 days
1.2.5.4.7.3 | Production of Signal Cables | 2008-04-01 08:00 | 2009-05-29 17:00 | 1.1599 |  | HV Design Review (Calorimeter) | 2006-02-28 08:00 | 2006-02-28 08:00 | 0 days
1.2.5.5.7.3 | Production of Signal Cables | 2008-04-01 08:00 | 2009-05-29 17:00 | 1.1599 |  | Readout Design Review (Calorimeter) | 2006-03-31 08:00 | 2006-03-31 08:00 | 0 days
1.2.5.1.5.1 | HV Control System | 2006-10-02 08:00 | 2007-12-31 17:00 | 1.2476 |  | Mechanics Design Review | 2006-12-01 08:00 | 2006-12-01 08:00 | 0 days
1.2.5.2.4.4 | Assembly/Support | 2007-05-15 08:00 | 2008-08-12 17:00 | 1.2476 |  | Mechanics Design Review | 2006-12-15 08:00 | 2006-12-15 08:00 | 0 days
1.2.5.2.5.1 | HV Control System | 2006-10-02 08:00 | 2007-12-31 17:00 | 1.2476 |  | Mechanics Design Review | 2007-03-01 08:00 | 2007-03-01 08:00 | 0 days
1.2.5.3.5.1 | HV Control System | 2006-10-02 08:00 | 2007-12-31 17:00 | 1.2476 |  | Mechanics Design Review | 2007-04-13 08:00 | 2007-04-13 08:00 | 0 days
1.2.5.4.6.1 | HV Control System | 2006-10-02 08:00 | 2007-12-31 17:00 | 1.2476 |  | Mechanics Design Review | 2007-06-01 08:00 | 2007-06-01 08:00 | 0 days
1.2.5.1.1.6 | Shipping | 2008-01-15 08:00 | 2009-04-15 17:00 | 1.2503 |  | Fabrication Complete | 2007-12-31 08:00 | 2007-12-31 08:00 | 0 days
1.2.5.5.6.1 | HV Control System | 2006-10-02 08:00 | 2008-01-01 17:00 | 1.2503 |  | Fabrication Complete | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 days
1.2.5.1.4.3 | Fabrication/Procurement | 2007-06-15 08:00 | 2008-09-16 17:00 | 1.2586 |  | Fabrication Complete | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 days
1.2.5.3.1.1 | WLS Fibers | 2005-10-03 08:00 | 2007-01-12 17:00 | 1.2777 |  | Fabrication Complete | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 days
1.2.5.4.1.1 | WLS Fibers | 2005-10-03 08:00 | 2007-01-12 17:00 | 1.2777 |  | Fabrication Complete | 2008-01-01 08:00 | 2008-01-01 08:00 | 0 days
1.2.5.5.1.1 | WLS Fibers | 2005-10-03 08:00 | 2007-01-12 17:00 | 1.2777 |  | Production Complete | 2008-02-18 08:00 | 2008-02-18 08:00 | 0 days
1.2.5.4.5.1 | Design | 2005-11-15 08:00 | 2007-03-15 17:00 | 1.3298 |  | Production Complete | 2008-02-18 08:00 | 2008-02-18 08:00 | 0 days
1.2.5.1.5.3.2 | Crate Data-Collection Boards | 2007-07-02 08:00 | 2008-11-28 17:00 | 1.412 |  | Mechanics Assembly Complete | 2008-04-15 08:00 | 2008-04-15 08:00 | 0 days
1.2.5.2.5.3.2 | Crate Data-Collection Boards | 2007-07-02 08:00 | 2008-11-28 17:00 | 1.412 |  | Mechanics Assembly Complete | 2008-04-15 08:00 | 2008-04-15 08:00 | 0 days
1.2.5.3.5.3.2 | Crate Data-Collection Boards | 2007-07-02 08:00 | 2008-11-28 17:00 | 1.412 |  | Production Complete | 2008-04-16 08:00 | 2008-04-16 08:00 | 0 days
1.2.5.4.6.3.2 | Crate Data-Collection Boards | 2007-07-02 08:00 | 2008-11-28 17:00 | 1.412 |  | Mechanics Assembly Complete | 2008-07-15 08:00 | 2008-07-15 08:00 | 0 days
1.2.5.5.6.3.2 | Crate Data-Collection Boards | 2007-07-02 08:00 | 2008-11-28 17:00 | 1.412 |  | Mechanics Assembly Complete | 2008-08-12 08:00 | 2008-08-12 08:00 | 0 days
1.2.5.2.4.1 | Design | 2005-10-17 08:00 | 2007-04-13 17:00 | 1.4887 |  | PMT Assembly Complete | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 days
1.2.5.2.1.6 | Shipping | 2007-09-17 08:00 | 2009-04-15 17:00 | 1.5791 |  | PMT Assembly Complete | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 days
1.2.5.2.4.3 | Fabrication/Procurement | 2008-05-15 08:00 | 2009-12-15 17:00 | 1.5873 |  | PMT Assembly Complete | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 days
1.2.5.1.4.1 | Design | 2005-10-17 08:00 | 2007-06-15 17:00 | 1.6613 |  | PMT Assembly Complete | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 days
1.2.5.4.1.5 | Assembly & Test | 2006-06-15 08:00 | 2008-04-16 17:00 | 1.8394 |  | PMT Assembly Complete | 2008-12-01 08:00 | 2008-12-01 08:00 | 0 days
1.2.5.3.1.5 | Assembly & Test | 2006-04-17 08:00 | 2008-02-18 17:00 | 1.8421 |  | Production Complete | 2008-12-16 08:00 | 2008-12-16 08:00 | 0 days
1.2.5.5.1.5 | Assembly & Test | 2006-04-17 08:00 | 2008-02-18 17:00 | 1.8421 |  | Production Complete | 2008-12-16 08:00 | 2008-12-16 08:00 | 0 days
1.2.5.1.5.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-12-01 17:00 | 1.9134 |  | Fabrication Complete | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 days
1.2.5.2.5.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-12-01 17:00 | 1.9134 |  | Fabrication Complete | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 days
1.2.5.3.5.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-12-01 17:00 | 1.9134 |  | Fabrication Complete | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 days
1.2.5.4.6.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-12-01 17:00 | 1.9134 |  | Fabrication Complete | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 days
1.2.5.5.6.3.1.3 | Fabrication/Procurement | 2007-01-03 08:00 | 2008-12-01 17:00 | 1.9134 |  | Fabrication Complete | 2009-03-02 08:00 | 2009-03-02 08:00 | 0 days
1.2.5.1.5.3.1.5 | Test | 2007-04-02 08:00 | 2009-03-02 17:00 | 1.9188 |  | Fabrication Complete | 2009-06-30 08:00 | 2009-06-30 08:00 | 0 days
1.2.5.2.5.3.1.5 | Test | 2007-04-02 08:00 | 2009-03-02 17:00 | 1.9188 |  | Mechanics Assembly Complete | 2009-07-31 08:00 | 2009-07-31 08:00 | 0 days
1.2.5.3.5.3.1.5 | Test | 2007-04-02 08:00 | 2009-03-02 17:00 | 1.9188 |  | Subsystem Installation Complete | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 days
1.2.5.4.6.3.1.5 | Test | 2007-04-02 08:00 | 2009-03-02 17:00 | 1.9188 |  | Subsystem Installation Complete | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 days
1.2.5.5.6.3.1.5 | Test | 2007-04-02 08:00 | 2009-03-02 17:00 | 1.9188 |  | Subsytem Installation Complete | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 days
1.2.5.1.6 | Cabling | 2008-04-01 08:00 | 2010-03-31 17:00 | 1.9983 |  | Subsystem Installation Complete | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 days
1.2.5.2.6 | Cabling | 2008-04-01 08:00 | 2010-03-31 17:00 | 1.9983 |  | Subsystem Installation Complete | 2010-03-31 08:00 | 2010-03-31 08:00 | 0 days
1.2.5.3.6 | Cabling | 2008-04-01 08:00 | 2010-03-31 17:00 | 1.9983 |  | Count | 44
1.2.5.4.7 | Cabling | 2008-04-01 08:00 | 2010-03-31 17:00 | 1.9983
1.2.5.5.7 | Cabling | 2008-04-01 08:00 | 2010-03-31 17:00 | 1.9983
1.2.5.1.5.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-03-02 17:00 | 2.1627
1.2.5.2.5.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-03-02 17:00 | 2.1627
1.2.5.3.5.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-03-02 17:00 | 2.1627
1.2.5.4.6.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-03-02 17:00 | 2.1627
1.2.5.5.6.3.1 | WFD Boards | 2007-01-03 08:00 | 2009-03-02 17:00 | 2.1627
1.2.5.1.3.2 | Preamplifier | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.1.3.3 | LV-HV Converter | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.1.3.4 | Mechanics & PC Boards | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.1.3.5 | PMT Units Assembly | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.1.3.6 | PMT Units Test | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.1.3.7 | PMT Units Packing | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.2.3.2 | Preamplifier | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.2.3.3 | LV-HV Converter | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.2.3.4 | Mechanics & PC Boards | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.2.3.5 | PMT Units Assembly | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.2.3.6 | PMT Units Test | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.2.3.7 | PMT Units Packing | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.3.3.2 | Preamplifier | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.3.3.3 | LV-HV Converter | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.3.3.4 | Mechanics & PC Boards | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.3.3.5 | PMT Units Assembly | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.3.3.6 | PMT Units Test | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.3.3.7 | PMT Units Packing | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.4.3.2 | Preamplifier | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.4.3.3 | LV-HV Converter | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.4.3.4 | Mechanics & PC Boards | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.4.3.5 | PMT Units Assembly | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.4.3.6 | PMT Units Test | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.4.3.7 | PMT Units Packing | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.5.3.2 | Preamplifier | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.5.3.3 | LV-HV Converter | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.5.3.4 | Mechanics & PC Boards | 2006-07-03 08:00 | 2008-09-01 17:00 | 2.1682
1.2.5.5.3.5 | PMT Units Assembly | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.5.3.6 | PMT Units Test | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.5.3.7 | PMT Units Packing | 2006-10-02 08:00 | 2008-12-01 17:00 | 2.1682
1.2.5.1.1.5 | Assembly & Test | 2006-10-16 08:00 | 2008-12-16 17:00 | 2.1709
1.2.5.2.1.5 | Assembly & Test | 2006-10-16 08:00 | 2008-12-16 17:00 | 2.1709
1.2.5.3.1.2 | Scintillator | 2005-10-03 08:00 | 2008-02-18 17:00 | 2.3791
1.2.5.3.1.3 | Reflective Covering/Gluing | 2005-10-03 08:00 | 2008-02-18 17:00 | 2.3791
1.2.5.3.1.4 | Lead | 2005-10-03 08:00 | 2008-02-18 17:00 | 2.3791
1.2.5.5.1.2 | Scintillator | 2005-10-03 08:00 | 2008-02-18 17:00 | 2.3791
1.2.5.5.1.4 | Reflective Covering/Gluing | 2005-10-03 08:00 | 2008-02-18 17:00 | 2.3791
1.2.5.3.4 | Mechanics | 2005-11-15 08:00 | 2008-04-15 17:00 | 2.4175
1.2.5.5.5 | Mechanics | 2005-11-15 08:00 | 2008-04-15 17:00 | 2.4175
1.2.5.3.1 | Log Module | 2005-10-03 08:00 | 2008-03-14 17:00 | 2.4476
1.2.5.5.1 | Plate Module | 2005-10-03 08:00 | 2008-03-14 17:00 | 2.4476
1.2.5.4.1.2 | Scintillator | 2005-10-03 08:00 | 2008-03-17 17:00 | 2.4558
1.2.5.4.1.3 | Reflective Covering/Gluing | 2005-10-03 08:00 | 2008-03-17 17:00 | 2.4558
1.2.5.4.1.4 | Lead | 2005-10-03 08:00 | 2008-03-17 17:00 | 2.4558
1.2.5.1.5.3 | Readout Electronics | 2007-01-03 08:00 | 2009-06-30 17:00 | 2.4914
1.2.5.2.5.3 | Readout Electronics | 2007-01-03 08:00 | 2009-06-30 17:00 | 2.4914
1.2.5.3.5.3 | Readout Electronics | 2007-01-03 08:00 | 2009-06-30 17:00 | 2.4914
1.2.5.4.6.3 | Readout Electronics | 2007-01-03 08:00 | 2009-06-30 17:00 | 2.4914
1.2.5.5.6.3 | Readout Electronics | 2007-01-03 08:00 | 2009-06-30 17:00 | 2.4914
1.2.5.4.5 | Mechanics | 2005-11-15 08:00 | 2008-07-15 17:00 | 2.6668
1.2.5.1.3 | Module Instrumentation | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.1.3.1 | PMT Unit | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.1.3.1.1 | PMT | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.1.3.1.2 | Voltage Divider | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.1.3.1.3 | Mu metal shielding | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.2.3 | Module Instrumentation | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.2.3.1 | PMT Unit | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.2.3.1.1 | PMT | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.2.3.1.2 | Voltage Divider | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.2.3.1.3 | Mu metal shielding | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.3.3 | Module Instrumentation | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.3.3.1 | PMT Unit | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.3.3.1.1 | PMT | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.3.3.1.2 | Voltage Divider | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.3.3.1.3 | Mu metal shielding | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.4.3 | Module Instrumentation | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.4.3.1 | PMT Unit | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.4.3.1.1 | PMT | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.4.3.1.2 | Voltage Divider | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.4.3.1.3 | Mu metal shielding | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.5.3 | Module Instrumentation | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.5.3.1 | PMT Unit | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.5.3.1.1 | APD | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.5.3.1.2 | Voltage Divider | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.5.3.1.3 | Mu metal shielding | 2006-07-03 08:00 | 2009-03-11 17:00 | 2.6914
1.2.5.4.1 | Log Module | 2005-10-03 08:00 | 2008-06-13 17:00 | 2.6969
1.2.5.1.5 | Instrumentation | 2006-10-02 08:00 | 2009-06-30 17:00 | 2.7462
1.2.5.2.5 | Instrumentation | 2006-10-02 08:00 | 2009-06-30 17:00 | 2.7462
1.2.5.3.5 | Instrumentation | 2006-10-02 08:00 | 2009-06-30 17:00 | 2.7462
1.2.5.4.6 | Instrumentation | 2006-10-02 08:00 | 2009-06-30 17:00 | 2.7462
1.2.5.5.6 | Instrumentation | 2006-10-02 08:00 | 2009-06-30 17:00 | 2.7462
1.2.5.1.1.1 | WLS Fibers | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.1.1.2 | Scintillator | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.1.1.3 | Reflective Covering/Gluing | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.1.1.4 | Lead | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.2.1.1 | WLS Fibers | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.2.1.2 | Scintillator | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.2.1.3 | Reflective Covering | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.2.1.4 | Lead Sheet | 2005-10-17 08:00 | 2008-12-16 17:00 | 3.1682
1.2.5.1.1 | Log Module | 2005-10-17 08:00 | 2009-04-15 17:00 | 3.4969
1.2.5.2.1 | Shashlyk Module | 2005-10-17 08:00 | 2009-04-15 17:00 | 3.4969
1.2.5.1.4 | Mechanics | 2005-10-17 08:00 | 2009-07-31 17:00 | 3.7901
1.2.5.2.4 | Mechanics | 2005-10-17 08:00 | 2009-12-15 17:00 | 4.1654
1.2.5.1 | Upstream Photon Veto | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5.1.2 | UpstreamVeto Assembling | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5.1.2.1 | Preinstallation/Test/Support | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5.1.2.2 | Travel | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5.2 | Barrel Photon Veto | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5.2.2 | Barrel Veto Assemby | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5.2.2.1 | Preinstallation/Test/Support | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5.2.2.2 | Travel | 2005-10-17 08:00 | 2010-10-01 17:00 | 4.9599
1.2.5 | Photon Veto | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983 | OK
1.2.5.3 | Magnet Photon Veto | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.3.2 | Magnet Veto Assemby | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.3.2.1 | Preinstallation/Test/Support | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.3.2.2 | Travel | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.4 | DS Photon Veto | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.4.2 | DS Veto Assembly | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.4.2.1 | Preinstallation/Test/Support | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.4.2.2 | Travel | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.5 | Magnet Charged Particle Veto | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.5.2 | Magnet Veto Assemby | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.5.2.1 | Preinstallation/Test/Support | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
1.2.5.5.2.2 | Travel | 2005-10-03 08:00 | 2010-10-01 17:00 | 4.9983
|  |  | Count Excessive | 166
>1 year
57.44%

## 1.2.6 Observations
Observations |  | WBS 1.2.6 Catcher | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type
Project Start Date | 2005-11-01
Project Finish Date | 2009-07-30
Project Calendar | Standard | 260 work days per yr. (No adj'd for Holidays, pd. abs or vacation)
Count Tasks | 80
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 27.5%
Successors | Missing | 43.75%
Task Type (Units,Work,Duration) | All Fixed Duration | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 49, (61%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 8
Hours/week | 40
Hours/year | 2080 | Equals 260 days x 8 hours.
Days/month | 21.7 | Equals 260 days / 12 months.
Excessive Durations | 16 Tasks | 20%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 18 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
| 1.2.6 | Catcher | 794 days | 2006-07-17 08:00 | 2009-07-30 17:00 | 790.2397 | 1109.375 | 3151187.42 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.9287 | 659502.8808 | 3810690.3008
| 1.2.6.1 | Aerogel Counter | 577 days | 2006-07-17 08:00 | 2008-09-30 17:00 | 574.4041 | 806.375 | 2265800 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.076 | 386908.8 | 2652708.8
| 1.2.6.1.1 | Modules | 577 days | 2006-07-17 08:00 | 2008-09-30 17:00 | 574.4041 | 806.375 | 2219800 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.0154 | 377708.8 | 2597508.8
| 1.2.6.1.1.1 | Aerogel Tile | 358 days | 2007-02-15 08:00 | 2008-06-30 17:00 | 357.1438 | 501.375 | 860000 |  | 6FF,5 | Fixed Duration | 2007-02-15 | Start No Earlier Than | 2 | 8 | 8 | 0 | 2 | 1 | 1 | 20 | 172000 | 1032000
|  | Complete Fabrication | 0 days | 2008-06-30 17:00 | 2008-06-30 17:00 | 0 | 0 | 0 | 4 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.1.1.2 | Lead Plate | 132 days | 2007-12-28 08:00 | 2008-06-30 17:00 | 132.0479 | 185.375 | 7000 | 4FF |  | Fixed Duration | 2008-06-30 17:00 | Finish No Earlier Than | 2 | 4 | 8 | 0 | 2 | 1 | 1 | 16 | 1120 | 8120
| 1.2.6.1.1.3 | PMT | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 1005000 |  |  | Fixed Duration |  |  | 1 | 1 | 8 | 0 | 2 | 1 | 1 | 13.3711 | 134380 | 1139380
| 1.2.6.1.1.3.1 | Purchase PMT - 5 inch | 314 days | 2006-07-17 08:00 | 2007-09-27 17:00 | 311.5548 | 437.375 | 735000 |  | 10FF,9 | Fixed Duration | 2006-07-15 | Start No Earlier Than | 2 | 3 | 4 | 0 | 2 | 1 | 1 | 11 | 80850 | 815850
|  | Complete Procurement | 0 days | 2007-09-27 17:00 | 2007-09-27 17:00 | 0 | 0 | 0 | 8 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.1.1.3.2 | Voltage Divider | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 11000 | 8FF | 11FF | Fixed Duration | 2006-07-15 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 2640 | 13640
| 1.2.6.1.1.3.3 | Mu Shield | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 41000 | 10FF | 12FF | Fixed Duration | 2006-07-17 08:00 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 12710 | 53710
| 1.2.6.1.1.3.4 | Preamplifier | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 14000 | 11FF | 13FF | Fixed Duration | 2006-07-17 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 2520 | 16520
| 1.2.6.1.1.3.5 | LV-HV Convertor | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 52000 | 12FF | 14FF | Fixed Duration | 2006-07-17 08:00 | Start No Earlier Than | 1 | 3 | 8 | 0 | 2 | 2 | 0 | 16 | 8320 | 60320
| 1.2.6.1.1.3.6 | Mechanics & PC-Boards | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 24000 | 13FF | 15FF | Fixed Duration | 2006-07-17 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 4320 | 28320
| 1.2.6.1.1.3.7 | PMT_Units Assembly | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 105000 | 14FF | 16FF | Fixed Duration | 2006-07-17 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 18900 | 123900
| 1.2.6.1.1.3.8 | PMT-Units Test | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 15000 | 15FF | 17FF | Fixed Duration | 2006-07-17 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 3000 | 18000
| 1.2.6.1.1.3.9 | PMT-Units Packing | 315 days | 2006-07-17 08:00 | 2007-09-28 17:00 | 312.2671 | 438.375 | 8000 | 16FF | 21SS | Fixed Duration | 2006-07-17 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 1120 | 9120
| 1.2.6.1.1.4 | Mirrors | 252 days | 2007-04-16 08:00 | 2008-04-01 17:00 | 250.2945 | 351.375 | 115000 |  | 19FF | Fixed Duration | 2007-04-15 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 1 | 1 | 15 | 17250 | 132250
| 1.2.6.1.1.5 | Funnels | 252 days | 2007-04-16 08:00 | 2008-04-01 17:00 | 250.2945 | 351.375 | 191000 | 18FF | 24FF,20 | Fixed Duration | 2007-04-15 | Start No Earlier Than | 4 | 3 | 8 | 4 | 2 | 1 | 1 | 23 | 43930 | 234930
|  | Complete Fabriction | 0 days | 2008-04-01 17:00 | 2008-04-01 17:00 | 0 | 0 | 0 | 19 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.1.1.6 | Element Tests | 534 days | 2006-07-17 08:00 | 2008-07-31 17:00 | 530.9521 | 745.375 | 16720 | 17SS | 22SS | Fixed Duration | 2006-07-15 | Start No Earlier Than | 4 | 4 | 8 | 0 | 2 | 2 | 1 | 24 | 4012.8 | 20732.8
| 1.2.6.1.1.7 | Assembly & Test | 382 days | 2007-04-16 08:00 | 2008-09-30 17:00 | 379.9384 | 533.375 | 25080 | 21SS | 23 | Fixed Duration | 2007-04-15 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 5016 | 30096
|  | Complete Assembly and Test | 0 days | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 | 0 | 0 | 22 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.1.2 | Support Frames | 58 days | 2008-01-11 08:00 | 2008-04-01 17:00 | 57.9658 | 81.375 | 46000 | 19FF |  | Fixed Duration | 2008-01-11 | Start No Earlier Than | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 20 | 9200 | 55200
| 1.2.6.2 | Guard Counter | 262 days | 2007-10-01 08:00 | 2008-09-30 17:00 | 260.2671 | 365.375 | 421020 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.6395 | 95317 | 516337
| 1.2.6.2.1 | Modules | 262 days | 2007-10-01 08:00 | 2008-09-30 17:00 | 260.2671 | 365.375 | 375020 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.982 | 82437 | 457457
| 1.2.6.2.1.1 | Acrylic Sheet | 132 days | 2007-10-01 08:00 | 2008-04-01 17:00 | 130.6233 | 183.375 | 9000 |  | 28SS | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 4 | 4 | 0 | 2 | 1 | 1 | 12 | 1080 | 10080
| 1.2.6.2.1.2 | Lead Plate | 132 days | 2007-10-01 08:00 | 2008-04-01 17:00 | 130.6233 | 183.375 | 5000 | 27SS | 29,31SS | Fixed Duration | 2007-10-01 | Start No Earlier Than | 2 | 4 | 4 | 0 | 2 | 1 | 1 | 12 | 600 | 5600
|  | Complete Fabrication | 0 days | 2008-04-01 17:00 | 2008-04-01 17:00 | 0 | 0 | 0 | 28 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.2.1.3 | PMT - 5 inch | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 344300 |  |  | Fixed Duration |  |  | 2 | 3 | 4 | 0 | 2 | 1 | 1 | 22.4842 | 77413 | 421713
| 1.2.6.2.1.3.1 | Purchase PMT - 5 inch | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 252000 | 28SS | 32SS | Fixed Duration | 2007-10-01 | Start No Earlier Than | 4 | 4 | 4 | 8 | 2 | 1 | 1 | 24 | 60480 | 312480
| 1.2.6.2.1.3.2 | Voltage Divider | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 3700 | 31SS | 33SS | Fixed Duration | 2007-10-01 | Start No Earlier Than | 4 | 4 | 4 | 15 | 2 | 1 | 1 | 31 | 1147 | 4847
| 1.2.6.2.1.3.3 | Mu Shield | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 14000 | 32SS | 34SS | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 2520 | 16520
| 1.2.6.2.1.3.4 | Preamplifier | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 4800 | 33SS | 35SS | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 672 | 5472
| 1.2.6.2.1.3.5 | LV-HV Convertor | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 17800 | 34SS | 36SS | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 3204 | 21004
| 1.2.6.2.1.3.6 | Mechanics & PC-Boards | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 8200 | 35SS | 38SS,37 | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 3 | 8 | 0 | 2 | 2 | 1 | 18 | 1476 | 9676
|  | Complete Procurement | 0 days | 2008-06-30 17:00 | 2008-06-30 17:00 | 0 | 0 | 0 | 36 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.2.1.3.7 | PMT_Units Assembly | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 36000 | 36SS | 39SS | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 7200 | 43200
| 1.2.6.2.1.3.8 | PMT-Units Test | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 5100 | 38SS | 40SS | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14 | 714 | 5814
| 1.2.6.2.1.3.9 | PMT-Units Packing | 196 days | 2007-10-01 08:00 | 2008-06-30 17:00 | 194.7329 | 273.375 | 2700 | 39SS | 41SS,44FF | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700
| 1.2.6.2.1.4 | Element Tests | 219 days | 2007-10-01 08:00 | 2008-07-31 17:00 | 216.8151 | 304.375 | 4180 | 40SS | 42SS | Fixed Duration | 2007-10-01 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 836 | 5016
| 1.2.6.2.1.5 | Assembly & Test | 262 days | 2007-10-01 08:00 | 2008-09-30 17:00 | 260.2671 | 365.375 | 12540 | 41SS | 43,45 | Fixed Duration | 2007-10-01 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 1 | 20 | 2508 | 15048
|  | Complete Assembly and Test | 0 days | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 | 0 | 0 | 42 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.2.2 | Support Frames | 57 days | 2008-04-11 08:00 | 2008-06-30 17:00 | 57.2534 | 80.375 | 46000 | 40FF |  | Fixed Duration | 2008-04-11 08:00 | Start No Earlier Than | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 28 | 12880 | 58880
|  | Complete Fabrication | 0 days | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 | 0 | 0 | 42 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3 | Front End Electronics | 209 days | 2008-04-15 08:00 | 2009-01-30 17:00 | 206.8425 | 290.375 | 422647.42 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.497 | 166933.0808 | 589580.5008
| 1.2.6.3.1 | HV Distribution System | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 42710 |  |  | Fixed Duration |  |  | 2 | 4 | 4 | 4 | 4 | 1 | 1 | 16 | 6833.6 | 49543.6
| 1.2.6.3.1.1 | VME Carriers | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 5310 |  | 49SS | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 849.6 | 6159.6
| 1.2.6.3.1.2 | D/A Converters | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 29700 | 48SS | 50SS | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 4752 | 34452
| 1.2.6.3.1.3 | VMV/VXI Mainframe | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 7700 | 49SS | 52SS,51 | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 2 | 2 | 8 | 0 | 2 | 2 | 1 | 16 | 1232 | 8932
|  | Complete Procurement | 0 days | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 | 0 | 0 | 50 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.1.4 | Test | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 0 | 50SS | 53 | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Complete Assembly and Test | 0 days | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 | 0 | 0 | 52 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.2 | LED Monitoring System | 121 days | 2008-04-15 08:00 | 2008-09-30 17:00 | 119.9384 | 168.375 | 36016.75 |  |  | Fixed Duration |  |  | 4 | 4 | 4 | 0 | 4 | 1 | 1 | 20 | 7203.35 | 43220.1
| 1.2.6.3.2.1 | Fabrication of Units | 121 days | 2008-04-15 08:00 | 2008-09-30 17:00 | 119.9384 | 168.375 | 32045.75 |  | 56SS | Fixed Duration | 2008-04-15 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 0 | 20 | 6409.15 | 38454.9
| 1.2.6.3.2.2 | Test & Packing of Units | 121 days | 2008-04-15 08:00 | 2008-09-30 17:00 | 119.9384 | 168.375 | 3971 | 55SS | 57 | Fixed Duration | 2008-04-15 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 0 | 20 | 794.2 | 4765.2
|  | Complete Assembly and Test | 0 days | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 | 0 | 0 | 56 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.3 | WFD Readout Electronics | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 280499.92 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.9865 | 140211.9808 | 420711.9008
| 1.2.6.3.3.1 | WFD Boards | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 249099.92 |  |  | Fixed Duration |  |  | 8 | 4 | 4 | 4 | 2 | 2 | 1 | 54.5227 | 135815.9808 | 384915.9008
| 1.2.6.3.3.1.1 | Fabrication/Procurement | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 237600 |  | 62SS,61 | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 10 | 4 | 4 | 4 | 4 | 2 | 1 | 56 | 133056 | 370656
|  | Complete Procurement | 0 days | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 | 0 | 0 | 60 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.3.1.2 | Test | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 11499.92 | 60SS | 64SS,63 | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 4 | 4 | 8 | 0 | 2 | 2 | 0 | 24 | 2759.9808 | 14259.9008
|  | Complete Tests | 0 days | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 | 0 | 0 | 62 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.3.2 | Crate Collector Boards | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 12400 | 62SS | 65SS | Fixed Duration | 2008-07-01 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 0 | 14 | 1736 | 14136
| 1.2.6.3.3.3 | VME Mainframes & Controller | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 19000 | 64SS | 66SS | Fixed Duration | 2008-07-01 | Start No Earlier Than | 1 | 2 | 8 | 0 | 2 | 2 | 0 | 14 | 2660 | 21660
| 1.2.6.3.3.4 | System Test | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 0 | 65SS | 68SS,67 | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Complete System Tests | 0 days | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 | 0 | 0 | 66 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.4 | LV Power Supplies | 154 days | 2008-07-01 08:00 | 2009-01-30 17:00 | 151.9932 | 213.375 | 5439.25 | 66SS | 69 | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 4 | 4 | 4 | 0 | 2 | 2 | 0 | 20 | 1087.85 | 6527.1
|  | Complete Procurement | 0 days | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 | 0 | 0 | 68 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.5 | Cabling | 21 days | 2008-05-01 08:00 | 2008-05-29 17:00 | 20.2123 | 28.375 | 57981.5 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 11596.3 | 69577.8
| 1.2.6.3.5.1 | LV-PS Cables Production | 21 days | 2008-05-01 08:00 | 2008-05-29 17:00 | 20.2123 | 28.375 | 17564.5 |  | 72SS | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 3512.9 | 21077.4
| 1.2.6.3.5.2 | HV Controls Cables Production | 21 days | 2008-05-01 08:00 | 2008-05-29 17:00 | 20.2123 | 28.375 | 5620 | 71SS | 73SS | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 1124 | 6744
| 1.2.6.3.5.3 | Signals Cables Production | 21 days | 2008-05-01 08:00 | 2008-05-29 17:00 | 20.2123 | 28.375 | 13240 | 72SS | 75SS,74 | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 2648 | 15888
|  | Complete Procurement and Test | 0 days | 2008-05-29 17:00 | 2008-05-29 17:00 | 0 | 0 | 0 | 73 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.3.5.4 | Assembly & Production | 21 days | 2008-05-01 08:00 | 2008-05-29 17:00 | 20.2123 | 28.375 | 21557 | 73SS | 76 | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 4311.4 | 25868.4
|  | Complete Assembly | 0 days | 2008-05-29 17:00 | 2008-05-29 17:00 | 0 | 0 | 0 | 75 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.4 | Shipping | 195 days | 2007-12-03 08:00 | 2008-08-29 17:00 | 192.5959 | 270.375 | 25000 |  | 78 | Fixed Duration | 2007-12-03 08:00 | Start No Earlier Than | 0 | 10 | 8 | 0 | 0 | 2 | 1 | 28 | 7000 | 32000
| 1.2.6.5 | Installation | 152 days | 2008-10-01 08:00 | 2009-04-30 17:00 | 150.5685 | 211.375 | 16720 | 77 | 80,79 | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 20 | 3344 | 20064
|  | Complete Installation | 0 days | 2009-04-30 17:00 | 2009-04-30 17:00 | 0 | 0 | 0 | 78 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.6.6 | Commissioning | 44 days | 2009-06-01 08:00 | 2009-07-30 17:00 | 42.2945 | 59.375 | 0 | 78 |  | Fixed Duration | 2009-06-01 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0
|  | 80 | [5 empty] | Count | 58 | 45 | 80 | 49 | 49
[8 empty] | Assigned | 72.5% | 56.25%
[8 empty] | Missing | 27.5% | 43.75%

## 1.2.6 Durations & Milestone
| Excessive Durations |  |  | Sort |  |  | Sort
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration
1.2.6.1.1.3.1 | Purchase PMT - 5 inch | 2006-07-17 08:00 | 2007-09-27 17:00 | 1.1983 |  | Complete Procurement | 2007-09-27 17:00 | 2007-09-27 17:00 | 0 days
1.2.6.1.1.3 | PMT | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Fabriction | 2008-04-01 17:00 | 2008-04-01 17:00 | 0 days
1.2.6.1.1.3.2 | Voltage Divider | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Fabrication | 2008-04-01 17:00 | 2008-04-01 17:00 | 0 days
1.2.6.1.1.3.3 | Mu Shield | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Procurement and Test | 2008-05-29 17:00 | 2008-05-29 17:00 | 0 days
1.2.6.1.1.3.4 | Preamplifier | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Assembly | 2008-05-29 17:00 | 2008-05-29 17:00 | 0 days
1.2.6.1.1.3.5 | LV-HV Convertor | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Fabrication | 2008-06-30 17:00 | 2008-06-30 17:00 | 0 days
1.2.6.1.1.3.6 | Mechanics & PC-Boards | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Procurement | 2008-06-30 17:00 | 2008-06-30 17:00 | 0 days
1.2.6.1.1.3.7 | PMT_Units Assembly | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Assembly and Test | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 days
1.2.6.1.1.3.8 | PMT-Units Test | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Assembly and Test | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 days
1.2.6.1.1.3.9 | PMT-Units Packing | 2006-07-17 08:00 | 2007-09-28 17:00 | 1.201 |  | Complete Fabrication | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 days
1.2.6.1.1.1 | Aerogel Tile | 2007-02-15 08:00 | 2008-06-30 17:00 | 1.3736 |  | Complete Assembly and Test | 2008-09-30 17:00 | 2008-09-30 17:00 | 0 days
1.2.6.1.1.7 | Assembly & Test | 2007-04-16 08:00 | 2008-09-30 17:00 | 1.4613 |  | Complete Procurement | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 days
1.2.6.1.1.6 | Element Tests | 2006-07-17 08:00 | 2008-07-31 17:00 | 2.0421 |  | Complete Assembly and Test | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 days
1.2.6.1 | Aerogel Counter | 2006-07-17 08:00 | 2008-09-30 17:00 | 2.2092 |  | Complete Procurement | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 days
1.2.6.1.1 | Modules | 2006-07-17 08:00 | 2008-09-30 17:00 | 2.2092 |  | Complete Tests | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 days
1.2.6 | Catcher | 2006-07-17 08:00 | 2009-07-30 17:00 | 3.0394 | OK | Complete System Tests | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 days
| 16 |  | Count Excessive | 16 |  | Complete Procurement | 2009-01-30 17:00 | 2009-01-30 17:00 | 0 days
|  |  |  | >1 year |  | Complete Installation | 2009-04-30 17:00 | 2009-04-30 17:00 | 0 days
|  |  |  | 20% |  | Count | 18

## 1.2.7 Observations
Observations |  | WBS 1.2.7 Trigger | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type
Project Start Date | 2004-11-01
Project Finish Date | 2009-10-08
Project Calendar | Standard | 260 work days per yr. (No adj'd for Holidays, pd. abs or vacation)
Count Tasks | 98
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 29.59%
Successors | Missing | 35.71%
Task Type (Units,Work,Duration) | Mixed | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 62, (63%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 8
Hours/week | 40
Hours/year | 2080 | Equals 260 days x 8 hours.
Days/month | 21.7 | Equals 260 days / 12 months.
Excessive Durations | 10 Tasks | 10%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 20 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
| 1.2.7 | Trigger | 1199 days | 2005-03-07 08:00 | 2009-10-08 17:00 | 1194.1301 | 1676.375 | 2622447.28 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.2026 | 1368985.9184 | 3991433.1984
| 1.2.7.1 | Architecture | 250 days | 2005-03-07 08:00 | 2006-02-17 17:00 | 247.4452 | 347.375 | 36542.4 |  | 12,19,27,39,46,54,7 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 10231.872 | 46774.272
| 1.2.7.1.1 | MC simulations | 100 days | 2005-03-07 08:00 | 2005-07-22 17:00 | 97.8562 | 137.375 | 0 |  | 5 | Fixed Duration | 2005-03-07 08:00 | Start No Earlier Than | 2 | 4 | 8 | 0 | 2 | 1 | 0 | 0 | 0 | 0
| 1.2.7.1.2 | Analysis of F.E.E. Performance | 20 days | 2005-10-03 08:00 | 2005-10-28 17:00 | 18.0753 | 25.375 | 12180.8 |  | 5 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 0 | 28 | 3410.624 | 15591.424
| 1.2.7.1.3 | Specification of Trigger Elements | 80 days | 2005-10-31 08:00 | 2006-02-17 17:00 | 77.911 | 109.375 | 12180.8 | 3,4 |  | Fixed Duration | 2005-10-31 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 0 | 28 | 3410.624 | 15591.424
| 1.2.7.1.4 | Interconnection Protocol | 80 days | 2005-10-31 08:00 | 2006-02-17 17:00 | 77.911 | 109.375 | 12180.8 |  | 9FS-25 days | Fixed Duration | 2005-10-31 08:00 | Start No Earlier Than | 4 | 4 | 8 | 8 | 2 | 1 | 0 | 28 | 3410.624 | 15591.424
|  | Trigger Design Review | 0 days | 2006-02-17 17:00 | 2006-02-17 17:00 | 0 | 0 | 0 | 2 | 15,21,29,41,48,56,67,73,79 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.2 | Interconnection Boards | 160 days | 2006-01-23 08:00 | 2006-09-01 17:00 | 157.6918 | 221.375 | 161117.6 |  | 54 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.7598 | 85005.256 | 246122.856
| 1.2.7.2.1 | Prototype | 100 days | 2006-01-23 08:00 | 2006-06-09 17:00 | 97.8562 | 137.375 | 90684.8 | 6FS-25 days | 10 | Fixed Duration | 2006-01-23 08:00 | Start No Earlier Than | 6 | 15 | 8 | 15 | 2 | 2 | 0 | 65 | 58945.12 | 149629.92
|  | Production Readiness Review | 0 days | 2006-06-09 17:00 | 2006-06-09 17:00 | 0 | 0 | 0 | 9 | 11 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.2.2 | Fabrication/Procurement | 60 days | 2006-06-12 08:00 | 2006-09-01 17:00 | 57.9658 | 81.375 | 70432.8 | 10 | 43,50 | Fixed Duration | 2006-06-12 08:00 | Start No Earlier Than | 4 | 10 | 4 | 15 | 2 | 1 | 0 | 37 | 26060.136 | 96492.936
| 1.2.7.3 | Module collector | 698 days | 2006-02-20 08:00 | 2008-10-22 17:00 | 694.7877 | 975.375 | 284369.6 | 2 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.1893 | 154097.968 | 438467.568
| 1.2.7.3.1 | Design | 40 days | 2006-02-20 08:00 | 2006-04-14 17:00 | 38.0205 | 53.375 | 24361.6 |  | 28,14 | Fixed Duration | 2006-02-20 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 11206.336 | 35567.936
|  | Design Review | 0 days | 2006-04-14 17:00 | 2006-04-14 17:00 | 0 | 0 | 0 | 13 | 15 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.3.2 | Prototype | 60 days | 2006-08-08 08:00 | 2006-10-30 17:00 | 59.3904 | 83.375 | 76104 | 7,14 | 30,32,35,16 | Fixed Duration | 2006-08-08 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 4 | 2 | 0 | 73 | 55555.92 | 131659.92
|  | Production Readiness Review | 0 days | 2006-10-30 17:00 | 2006-10-30 17:00 | 0 | 0 | 0 | 15 | 17 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.3.3 | Production | 61 days | 2008-01-23 08:00 | 2008-04-16 17:00 | 60.1027 | 84.375 | 164342.4 | 16 | 18,32FS-1 day | Fixed Duration | 2008-01-23 08:00 | Start No Earlier Than | 6 | 10 | 4 | 15 | 2 | 2 | 0 | 51 | 83814.624 | 248157.024
| 1.2.7.3.4 | Installation & Cabling | 40 days | 2008-08-28 08:00 | 2008-10-22 17:00 | 39.4452 | 55.375 | 19561.6 | 17,25FS-1 day,33 | 34 | Fixed Units | 2008-08-28 08:00 | Start No Earlier Than | 1 | 4 | 4 | 8 | 2 | 1 | 0 | 18 | 3521.088 | 23082.688
| 1.2.7.4 | Strip Routing Cards | 579 days | 2006-06-12 08:00 | 2008-08-28 17:00 | 575.8288 | 808.375 | 279666.8 | 2 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.4793 | 163547.188 | 443213.988
| 1.2.7.4.1 | Design | 40 days | 2006-06-12 08:00 | 2006-08-04 17:00 | 38.0205 | 53.375 | 24361.6 | 28 | 21 | Fixed Duration | 2006-06-12 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 11206.336 | 35567.936
|  | Design Review | 0 days | 2006-08-04 17:00 | 2006-08-04 17:00 | 0 | 0 | 0 | 20,7 |  | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.4.2 | Digitizer Crate Backplane (design and prototype) | 41 days | 2007-01-23 08:00 | 2007-03-20 17:00 | 40.1575 | 56.375 | 53923.2 | 30FS-1 day | 23FS-1 day,35 | Fixed Duration | 2007-01-23 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 2 | 0 | 61 | 32893.152 | 86816.352
| 1.2.7.4.3 | Prototype | 61 days | 2007-03-20 08:00 | 2007-06-12 17:00 | 60.1027 | 84.375 | 76104 | 22FS-1 day | 35FS-1 day,24 | Fixed Duration | 2007-03-20 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 4 | 2 | 0 | 73 | 55555.92 | 131659.92
|  | Production Readiness Review | 0 days | 2007-06-12 17:00 | 2007-06-12 17:00 | 0 | 0 | 0 | 23 | 25 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.4.4 | Production | 41 days | 2008-07-03 08:00 | 2008-08-28 17:00 | 40.1575 | 56.375 | 75561.6 | 33FS-1 day,24 | 18FS-1 day | Fixed Duration | 2008-07-03 08:00 | Start No Earlier Than | 6 | 10 | 4 | 15 | 2 | 2 | 0 | 51 | 38536.416 | 114098.016
| 1.2.7.4.5 | Custom Backplane (fabrication) | 31 days | 2008-05-15 08:00 | 2008-06-26 17:00 | 30.1849 | 42.375 | 49716.4 | 32FS-1 day | 33FS-1 day | Fixed Duration | 2008-05-15 08:00 | Start No Earlier Than | 6 | 10 | 4 | 15 | 2 | 2 | 0 | 51 | 25355.364 | 75071.764
| 1.2.7.5 | Strip Collector | 719 days | 2006-04-17 08:00 | 2009-01-15 17:00 | 715.4452 | 1004.375 | 122910.8 | 2 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.8964 | 56411.644 | 179322.444
| 1.2.7.5.1 | Design | 40 days | 2006-04-17 08:00 | 2006-06-09 17:00 | 38.0205 | 53.375 | 24361.6 | 13 | 20,29 | Fixed Duration | 2006-04-17 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 11206.336 | 35567.936
|  | Design Review | 0 days | 2006-06-09 17:00 | 2006-06-09 17:00 | 0 | 0 | 0 | 28,7 |  | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.5.2 | Firmware Development | 61 days | 2006-10-31 08:00 | 2007-01-23 17:00 | 60.1027 | 84.375 | 36542.4 | 15 | 22FS-1 day,35,31 | Fixed Duration | 2006-10-31 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 16809.504 | 53351.904
|  | Production Readiness Review | 0 days | 2007-01-23 17:00 | 2007-01-23 17:00 | 0 | 0 | 0 | 30 | 32 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.5.3 | Procurement & Test | 22 days | 2008-04-16 08:00 | 2008-05-15 17:00 | 20.9247 | 29.375 | 45780.8 | 15,17FS-1 day,31 | 26FS-1 day | Fixed Duration | 2008-04-16 08:00 | Start No Earlier Than | 6 | 10 | 4 | 15 | 2 | 2 | 0 | 51 | 23348.208 | 69129.008
| 1.2.7.5.4 | Custom Backplane (Fabrication) | 6 days | 2008-06-26 08:00 | 2008-07-03 17:00 | 5.2534 | 7.375 | 6445.2 | 26FS-1 day | 18,25FS-1 day | Fixed Duration | 2008-06-26 08:00 | Start No Earlier Than | 6 | 10 | 4 | 15 | 2 | 2 | 0 | 51 | 3287.052 | 9732.252
| 1.2.7.5.5 | Installation & Cabling | 21 days | 2008-12-18 08:00 | 2009-01-15 17:00 | 20.2123 | 28.375 | 9780.8 | 18 |  | Fixed Duration | 2008-12-18 08:00 | Start No Earlier Than | 1 | 4 | 4 | 8 | 2 | 1 | 0 | 18 | 1760.544 | 11541.344
| 1.2.7.6 | Digitizer's & Collectors Test | 161 days | 2007-06-12 08:00 | 2008-01-22 17:00 | 159.8288 | 224.375 | 68284.8 | 15,22,23FS-1 day,30 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.8488 | 29259.232 | 97544.032
| 1.2.7.6.1 | Set-up | 41 days | 2007-06-12 08:00 | 2007-08-07 17:00 | 40.1575 | 56.375 | 19561.6 |  | 37FS-1 day | Fixed Duration | 2007-06-12 08:00 | Start No Earlier Than | 4 | 15 | 4 | 8 | 2 | 1 | 0 | 35 | 6846.56 | 26408.16
| 1.2.7.6.2 | Online Software | 61 days | 2007-08-07 08:00 | 2007-10-30 17:00 | 60.1027 | 84.375 | 24361.6 | 36FS-1 day | 38FS-1 day | Fixed Duration | 2007-08-07 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 11206.336 | 35567.936
| 1.2.7.6.3 | Test & Analysis | 61 days | 2007-10-30 08:00 | 2008-01-22 17:00 | 60.1027 | 84.375 | 24361.6 | 37FS-1 day |  | Fixed Duration | 2007-10-30 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 11206.336 | 35567.936
| 1.2.7.7 | Pattern Card | 362 days | 2006-05-15 08:00 | 2007-10-02 17:00 | 359.9932 | 505.375 | 230673.6 | 2 | 53 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.257 | 143610.512 | 374284.112
| 1.2.7.7.1 | Design | 80 days | 2006-05-15 08:00 | 2006-09-01 17:00 | 77.911 | 109.375 | 48723.2 |  | 47,41 | Fixed Duration | 2006-05-15 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 2 | 1 | 0 | 50 | 24361.6 | 73084.8
|  | Design Review | 0 days | 2006-09-01 17:00 | 2006-09-01 17:00 | 0 | 0 | 0 | 40,7 | 42 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.7.2 | Generation of Test Data | 60 days | 2006-09-04 08:00 | 2006-11-24 17:00 | 57.9658 | 81.375 | 0 | 41 | 49,43 | Fixed Duration | 2006-09-04 08:00 | Start No Earlier Than | 4 | 15 | 4 | 15 | 2 | 1 | 0 | 0 | 0 | 0
| 1.2.7.7.3 | Prototype | 101 days | 2006-11-27 08:00 | 2007-04-16 17:00 | 99.9932 | 140.375 | 120246.4 | 11,42 | 50,44 | Fixed Duration | 2006-11-27 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 4 | 2 | 0 | 73 | 87779.872 | 208026.272
|  | Production Readiness Review | 0 days | 2007-04-16 17:00 | 2007-04-16 17:00 | 0 | 0 | 0 | 43 | 45 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.7.4 | Construction | 60 days | 2007-07-11 08:00 | 2007-10-02 17:00 | 59.3904 | 83.375 | 61704 | 44 | 52 | Fixed Duration | 2007-07-11 08:00 | Start No Earlier Than | 6 | 10 | 4 | 15 | 2 | 2 | 0 | 51 | 31469.04 | 93173.04
| 1.2.7.8 | Boolean Logic Card | 342 days | 2006-09-04 08:00 | 2007-12-25 17:00 | 340.0479 | 477.375 | 202131.2 | 2 | 53 | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7756 | 136995.632 | 339126.832
| 1.2.7.8.1 | Design | 60 days | 2006-09-04 08:00 | 2006-11-24 17:00 | 57.9658 | 81.375 | 36542.4 | 40 | 48 | Fixed Duration | 2006-09-04 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 16809.504 | 53351.904
|  | Design Review | 0 days | 2006-11-24 17:00 | 2006-11-24 17:00 | 0 | 0 | 0 | 47,7 | 50 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.8.2 | Generation of Test Data | 60 days | 2006-11-27 08:00 | 2007-02-16 17:00 | 57.9658 | 81.375 | 0 | 42 |  | Fixed Duration | 2006-11-27 08:00 | Start No Earlier Than | 4 | 15 | 4 | 15 | 2 | 1 | 0 | 0 | 0 | 0
| 1.2.7.8.3 | Prototype | 60 days | 2007-04-17 08:00 | 2007-07-09 17:00 | 59.3904 | 83.375 | 95884.8 | 43,11,48 | 51 | Fixed Duration | 2007-04-17 08:00 | Start No Earlier Than | 8 | 15 | 4 | 15 | 4 | 2 | 0 | 81 | 77666.688 | 173551.488
|  | Production Readiness Review | 0 days | 2007-07-09 17:00 | 2007-07-09 17:00 | 0 | 0 | 0 | 50 | 52 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.8.4 | Construction | 60 days | 2007-10-03 08:00 | 2007-12-25 17:00 | 59.3904 | 83.375 | 69704 | 45,51 |  | Fixed Duration | 2007-10-03 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 2 | 0 | 61 | 42519.44 | 112223.44
| 1.2.7.9 | LV1 Logic Crate Installation & Cabling | 20 days | 2007-12-26 08:00 | 2008-01-22 17:00 | 19.5 | 27.375 | 9780.8 | 39,46 |  | Fixed Units | 2007-12-26 08:00 | Start No Earlier Than | 1 | 4 | 4 | 8 | 2 | 1 | 0 | 18 | 1760.544 | 11541.344
| 1.2.7.10 | Supervision and Monitoring System | 502 days | 2006-09-04 08:00 | 2008-08-05 17:00 | 499.6096 | 701.375 | 499308.8 | 2,8 |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.0378 | 319746.288 | 819055.088
| 1.2.7.10.1 | Design | 120 days | 2006-09-04 08:00 | 2007-02-16 17:00 | 117.8014 | 165.375 | 60904 |  | 60,56 | Fixed Duration | 2006-09-04 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 28015.84 | 88919.84
|  | Design Review | 0 days | 2007-02-16 17:00 | 2007-02-16 17:00 | 0 | 0 | 0 | 55,7 | 57 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.10.2 | Alignment Board Develop. & Test | 80 days | 2007-02-20 08:00 | 2007-06-11 17:00 | 79.3356 | 111.375 | 98065.6 | 56 | 58,61 | Fixed Duration | 2007-02-20 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 4 | 2 | 0 | 73 | 71587.888 | 169653.488
| 1.2.7.10.3 | Formation Board Develop. & Test | 100 days | 2007-06-12 08:00 | 2007-10-29 17:00 | 99.2808 | 139.375 | 110246.4 | 57 | 59,61 | Fixed Duration | 2007-06-12 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 4 | 2 | 0 | 73 | 80479.872 | 190726.272
| 1.2.7.10.4 | Transmitter Develop. & Test | 100 days | 2007-10-30 08:00 | 2008-03-17 17:00 | 99.2808 | 139.375 | 110246.4 | 58 | 61 | Fixed Duration | 2007-10-30 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 4 | 2 | 0 | 73 | 80479.872 | 190726.272
| 1.2.7.10.5 | Scalers | 1 day | 2007-02-19 08:00 | 2007-02-19 17:00 | 0.26712 | 0.375 | 10400 | 55 | 61 | Fixed Duration | 2007-02-19 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 1 | 1 | 0 | 8 | 832 | 11232
|  | Production Readiness Review | 0 days | 2008-03-17 17:00 | 2008-03-17 17:00 | 0 | 0 | 0 | 57,58,59,60 | 62 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.10.6 | Production | 60 days | 2008-03-19 08:00 | 2008-06-10 17:00 | 59.3904 | 83.375 | 89884.8 | 61 | 63 | Fixed Duration | 2008-03-19 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 2 | 0 | 61 | 54829.728 | 144714.528
| 1.2.7.10.7 | Installation & Cabling | 40 days | 2008-06-11 08:00 | 2008-08-05 17:00 | 39.4452 | 55.375 | 19561.6 | 62 |  | Fixed Duration | 2008-06-11 08:00 | Start No Earlier Than | 1 | 4 | 4 | 8 | 2 | 1 | 0 | 18 | 3521.088 | 23082.688
| 1.2.7.11 | Clock System | 569 days | 2005-10-03 08:00 | 2007-12-06 17:00 | 565.8562 | 794.375 | 540537.68 |  |  | Fixed Duration |  |  | 6 | 4 | 4 | 15 | 2 | 1 | 0 | 42.2304 | 228271.1104 | 768808.7904
| 1.2.7.11.1 | Master Clock | 313 days | 2005-10-03 08:00 | 2006-12-13 17:00 | 310.8425 | 436.375 | 104895.44 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.0738 | 44133.4632 | 149028.9032
| 1.2.7.11.1.1 | Design | 89 days | 2005-10-03 08:00 | 2006-02-02 17:00 | 87.1712 | 122.375 | 54204.56 |  | 72,67 | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 2 | 1 | 0 | 37 | 20055.6872 | 74260.2472
|  | Design Review | 0 days | 2006-02-17 17:00 | 2006-02-17 17:00 | 0 | 0 | 0 | 66,7 | 68 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.11.1.2 | Prototype | 29 days | 2006-07-24 08:00 | 2006-08-31 17:00 | 27.3356 | 38.375 | 28508.72 | 67 | 74,69 | Fixed Duration | 2006-07-24 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 4 | 2 | 0 | 51 | 14539.4472 | 43048.1672
|  | Production Readiness Review | 0 days | 2006-08-31 17:00 | 2006-08-31 17:00 | 0 | 0 | 0 | 68 | 70 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.11.1.3 | Fabricate | 30 days | 2006-11-02 08:00 | 2006-12-13 17:00 | 29.4726 | 41.375 | 22182.16 | 69 | 76FS-1 day,83 | Fixed Duration | 2006-11-02 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 2 | 2 | 0 | 43 | 9538.3288 | 31720.4888
| 1.2.7.11.2 | Clock Drivers | 272 days | 2006-02-03 08:00 | 2007-02-19 17:00 | 271.6644 | 381.375 | 106525.04 |  |  | Fixed Duration |  |  | 6 | 4 | 4 | 15 | 2 | 1 | 0 | 43.0828 | 45893.9208 | 152418.9608
| 1.2.7.11.2.1 | Design | 60 days | 2006-02-03 08:00 | 2006-04-27 17:00 | 59.3904 | 83.375 | 36542.4 | 66 | 78,73 | Fixed Duration | 2006-02-03 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 2 | 1 | 0 | 37 | 13520.688 | 50063.088
|  | Design Review | 0 days | 2006-04-27 17:00 | 2006-04-27 17:00 | 0 | 0 | 0 | 72,7 |  | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.11.2.2 | Prototype | 30 days | 2006-09-01 08:00 | 2006-10-12 17:00 | 29.4726 | 41.375 | 28508.72 | 68 | 80FS-1 day,75 | Fixed Duration | 2006-09-01 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 4 | 2 | 0 | 51 | 14539.4472 | 43048.1672
|  | Production Readiness Review | 0 days | 2006-10-12 17:00 | 2006-10-12 17:00 | 0 | 0 | 0 | 74 | 76 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.11.2.3 | Fabricate | 49 days | 2006-12-13 08:00 | 2007-02-19 17:00 | 48.7055 | 68.375 | 41473.92 | 70FS-1 day,75 | 82FS-1 day,83 | Fixed Duration | 2006-12-13 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 2 | 2 | 0 | 43 | 17833.7856 | 59307.7056
| 1.2.7.11.3 | Clock Receivers | 402 days | 2006-04-28 08:00 | 2007-11-12 17:00 | 401.3082 | 563.375 | 314833.12 |  |  | Fixed Duration |  |  | 6 | 4 | 4 | 15 | 2 | 1 | 0 | 42.8213 | 134815.5472 | 449648.6672
| 1.2.7.11.3.1 | Design | 60 days | 2006-04-28 08:00 | 2006-07-20 17:00 | 59.3904 | 83.375 | 36542.4 | 72 | 79 | Fixed Duration | 2006-04-28 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 2 | 1 | 0 | 37 | 13520.688 | 50063.088
|  | Design Review | 0 days | 2006-07-20 17:00 | 2006-07-20 17:00 | 0 | 0 | 0 | 78,7 | 80 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.11.3.2 | Prototype | 15 days | 2006-10-12 08:00 | 2006-11-01 17:00 | 14.5137 | 20.375 | 20373.12 | 74FS-1 day,79 | 81 | Fixed Duration | 2006-10-12 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 4 | 2 | 0 | 51 | 10390.2912 | 30763.4112
|  | Production Readiness Review | 0 days | 2006-11-01 17:00 | 2006-11-01 17:00 | 0 | 0 | 0 | 80 | 82 | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.7.11.3.3 | Fabricate | 191 days | 2007-02-19 08:00 | 2007-11-12 17:00 | 189.7466 | 266.375 | 257917.6 | 76FS-1 day,81 | 83FS-1 day | Fixed Duration | 2007-02-19 08:00 | Start No Earlier Than | 4 | 6 | 8 | 15 | 2 | 2 | 0 | 43 | 110904.568 | 368822.168
| 1.2.7.11.4 | Assembly, Test & Installation | 19 days | 2007-11-12 08:00 | 2007-12-06 17:00 | 17.363 | 24.375 | 14284.08 | 70,76,82FS-1 day |  | Fixed Duration | 2007-11-12 08:00 | Start No Earlier Than | 2 | 4 | 8 | 8 | 2 | 1 | 0 | 24 | 3428.1792 | 17712.2592
| 1.2.7.12 | Infrastructure | 1 day | 2008-10-01 08:00 | 2008-10-01 17:00 | 0.26712 | 0.375 | 138400 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.7428 | 17636 | 156036
| 1.2.7.12.1 | 9U Crates | 1 day | 2008-10-01 08:00 | 2008-10-01 17:00 | 0.26712 | 0.375 | 45000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 0 | 1 | 1 | 0 | 4 | 1800 | 46800
| 1.2.7.12.2 | 6 U Crate | 1 day | 2008-10-01 08:00 | 2008-10-01 17:00 | 0.26712 | 0.375 | 20000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 0 | 1 | 1 | 0 | 4 | 800 | 20800
| 1.2.7.12.3 | Crate Interfaces | 1 day | 2008-10-01 08:00 | 2008-10-01 17:00 | 0.26712 | 0.375 | 14400 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 0 | 1 | 1 | 0 | 4 | 576 | 14976
| 1.2.7.12.4 | Cables | 1 day | 2008-10-01 08:00 | 2008-10-01 17:00 | 0.26712 | 0.375 | 39000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 1 | 10 | 4 | 8 | 2 | 1 | 0 | 24 | 9360 | 48360
| 1.2.7.12.5 | Readout controllers | 1 day | 2008-10-01 08:00 | 2008-10-01 17:00 | 0.26712 | 0.375 | 10000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 4600 | 14600
| 1.2.7.12.6 | Control for CPUs | 1 day | 2008-10-01 08:00 | 2008-10-01 17:00 | 0.26712 | 0.375 | 10000 |  |  | Fixed Units | 2008-10-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 0 | 2 | 1 | 0 | 5 | 500 | 10500
| 1.2.7.13 | Commissioning | 201 days | 2008-10-23 08:00 | 2009-07-30 17:00 | 199.7192 | 280.375 | 48723.2 |  | 98FS-1 day | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 22412.672 | 71135.872
| 1.2.7.13.1 | Trigger Control Program | 61 days | 2008-10-23 08:00 | 2009-01-15 17:00 | 60.1027 | 84.375 | 0 |  |  | Fixed Duration | 2008-10-23 08:00 | Start No Earlier Than | 4 | 15 | 4 | 15 | 2 | 1 | 0 | 0 | 0 | 0
| 1.2.7.13.2 | Trigger Readout Program | 61 days | 2008-10-23 08:00 | 2009-01-15 17:00 | 60.1027 | 84.375 | 0 |  |  | Fixed Duration | 2008-10-23 08:00 | Start No Earlier Than | 4 | 15 | 4 | 15 | 2 | 1 | 0 | 0 | 0 | 0
| 1.2.7.13.3 | Test Logic Chain | 41 days | 2009-01-15 08:00 | 2009-03-12 17:00 | 40.1575 | 56.375 | 12180.8 |  |  | Fixed Duration | 2009-01-15 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 5603.168 | 17783.968
| 1.2.7.13.4 | Test Logic Chain & Supervisor | 41 days | 2009-03-12 08:00 | 2009-05-07 17:00 | 40.1575 | 56.375 | 12180.8 |  |  | Fixed Duration | 2009-03-12 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 5603.168 | 17783.968
| 1.2.7.13.5 | Test Collectors with Cosmic Rays | 41 days | 2009-01-15 08:00 | 2009-03-12 17:00 | 40.1575 | 56.375 | 12180.8 |  |  | Fixed Duration | 2009-01-15 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 5603.168 | 17783.968
| 1.2.7.13.6 | Test Full Chain | 61 days | 2009-05-07 08:00 | 2009-07-30 17:00 | 60.1027 | 84.375 | 12180.8 |  |  | Fixed Duration | 2009-05-07 08:00 | Start No Earlier Than | 6 | 15 | 4 | 15 | 2 | 1 | 0 | 46 | 5603.168 | 17783.968
| 1.2.7.14 | LV3 Event Selection Software | 51 days | 2009-07-30 08:00 | 2009-10-08 17:00 | 50.1301 | 70.375 | 0 | 91FS-1 day |  | Fixed Duration | 2009-07-30 08:00 | Start No Earlier Than | 6 | 6 | 4 | 15 | 2 | 1 | 0 | 0 | 0 | 0
| Count | 98 | [5 empty] | Count | 69 | 63 |  | 62 | 62
[8 empty] | Assigned | 70.41% | 64.29% |  | 63.27%
[8 empty] | Missing | 29.59% | 35.71%

## 1.2.7 Durations & Milestone
| Excessive Durations |  |  | Sort by |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration
1.2.7.11.1 | Master Clock | 2005-10-03 08:00 | 2006-12-13 17:00 | 1.1955 |  | Trigger Design Review | 2006-02-17 17:00 | 2006-02-17 17:00 | 0 days
1.2.7.8 | Boolean Logic Card | 2006-09-04 08:00 | 2007-12-25 17:00 | 1.3079 |  | Design Review | 2006-02-17 17:00 | 2006-02-17 17:00 | 0 days
1.2.7.7 | Pattern Card | 2006-05-15 08:00 | 2007-10-02 17:00 | 1.3846 |  | Design Review | 2006-04-14 17:00 | 2006-04-14 17:00 | 0 days
1.2.7.11.3 | Clock Receivers | 2006-04-28 08:00 | 2007-11-12 17:00 | 1.5435 |  | Design Review | 2006-04-27 17:00 | 2006-04-27 17:00 | 0 days
1.2.7.10 | Supervision and Monitoring System | 2006-09-04 08:00 | 2008-08-05 17:00 | 1.9216 |  | Production Readiness Review | 2006-06-09 17:00 | 2006-06-09 17:00 | 0 days
1.2.7.11 | Clock System | 2005-10-03 08:00 | 2007-12-06 17:00 | 2.1764 |  | Design Review | 2006-06-09 17:00 | 2006-06-09 17:00 | 0 days
1.2.7.4 | Strip Routing Cards | 2006-06-12 08:00 | 2008-08-28 17:00 | 2.2147 |  | Design Review | 2006-07-20 17:00 | 2006-07-20 17:00 | 0 days
1.2.7.3 | Module collector | 2006-02-20 08:00 | 2008-10-22 17:00 | 2.6723 |  | Design Review | 2006-08-04 17:00 | 2006-08-04 17:00 | 0 days
1.2.7.5 | Strip Collector | 2006-04-17 08:00 | 2009-01-15 17:00 | 2.7517 |  | Production Readiness Review | 2006-08-31 17:00 | 2006-08-31 17:00 | 0 days
1.2.7 | Trigger | 2005-03-07 08:00 | 2009-10-08 17:00 | 4.5928 | OK | Design Review | 2006-09-01 17:00 | 2006-09-01 17:00 | 0 days
|  |  | Count Excessive | 10 |  | Production Readiness Review | 2006-10-12 17:00 | 2006-10-12 17:00 | 0 days
|  |  |  | >1 year |  | Production Readiness Review | 2006-10-30 17:00 | 2006-10-30 17:00 | 0 days
|  |  |  | 10.2% |  | Production Readiness Review | 2006-11-01 17:00 | 2006-11-01 17:00 | 0 days
[6 empty] | Design Review | 2006-11-24 17:00 | 2006-11-24 17:00 | 0 days
[6 empty] | Production Readiness Review | 2007-01-23 17:00 | 2007-01-23 17:00 | 0 days
[6 empty] | Design Review | 2007-02-16 17:00 | 2007-02-16 17:00 | 0 days
[6 empty] | Production Readiness Review | 2007-04-16 17:00 | 2007-04-16 17:00 | 0 days
[6 empty] | Production Readiness Review | 2007-06-12 17:00 | 2007-06-12 17:00 | 0 days
[6 empty] | Production Readiness Review | 2007-07-09 17:00 | 2007-07-09 17:00 | 0 days
[6 empty] | Production Readiness Review | 2008-03-17 17:00 | 2008-03-17 17:00 | 0 days
[6 empty] | Count | 20

## 1.2.8 Observations
Observations |  | WBS 1.2.8 DAQ | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type
Project Start Date | 2004-11-15
Project Finish Date | 2010-07-01
Project Calendar | Kopio Standard | 220 work days per yr. (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Count Tasks | 60
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 98.33%
Successors | Missing | 98.33%
Task Type (Units,Work,Duration) | Mostly Fixed Duration | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 47, (78%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 7.1
Hours/week | 35.5
Hours/year | 1760
Days/month | 18 | ~220 work days /12 months (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Excessive Durations | 18 Tasks | 30%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 16 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
| 1.2.8 | DAQ | 1039.25 days | 2005-10-17 08:00 | 2010-07-01 12:00 | 1035.6073 | 1718.1667 | 2595132.8 |  |  | Fixed Duration | 2005-12-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.5311 | 922078.508 | 3517211.308
| 1.2.8.1 | Event Builder | 1038.75 days | 2005-10-17 08:00 | 2010-07-01 08:00 | 1035.5068 | 1718 | 773960 |  |  | Fixed Duration | 2006-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.8399 | 246428.3 | 1020388.3
| 1.2.8.1.1 | Event Builder System Development | 337.13 days | 2005-10-17 08:00 | 2007-04-30 17:00 | 337.7603 | 560.375 | 79610 |  |  | Fixed Duration | 2007-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10349.3 | 89959.3
| 1.2.8.1.1.1 | Test Cluster Procurement | 18 days | 2005-10-17 08:00 | 2005-11-15 10:00 | 17.5297 | 29.0833 | 79610 |  |  | Fixed Duration |  |  | 1 | 4 | 8 | 0 | 1 | 1 | 1 | 13 | 10349.3 | 89959.3
| 1.2.8.1.1.2 | Installation of XDAQ tools | 18 days | 2005-11-15 08:00 | 2005-12-15 12:00 | 18.1826 | 30.1667 | 0 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.1.3 | Simple data transfer tests | 18 days | 2005-11-15 08:00 | 2005-12-15 12:00 | 18.1826 | 30.1667 | 0 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.1.4 | Tests in XDAQ framework | 81 days | 2005-12-15 08:00 | 2006-04-28 09:00 | 80.7922 | 134.0417 | 0 |  |  | Fixed Duration | 2007-11-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.1.5 | Measurement of data transfer speed | 220 days | 2006-05-01 08:00 | 2007-04-30 17:00 | 219.6233 | 364.375 | 0 |  |  | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.2 | Event builder Beam or Cosmic Test | 240 days | 2006-10-02 08:00 | 2007-11-01 11:00 | 238.1575 | 395.125 | 0 |  |  | Fixed Duration | 2008-04-30 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.2.1 | Preparation for Beam or Cosmic Test | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 219.6233 | 364.375 | 0 |  |  | Fixed Duration | 2008-10-31 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.2.2 | Beam or Cosmic Test | 21 days | 2007-10-01 08:00 | 2007-11-01 11:00 | 18.7603 | 31.125 | 0 |  |  | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.3 | Design Modification and Review | 108 days | 2007-11-01 08:00 | 2008-04-30 12:00 | 109.1963 | 181.1667 | 0 |  |  | Fixed Duration | 2009-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preliminary Design Review | 0 days | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-04-30 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.4 | EB procurement (25%) | 57 days | 2008-04-30 08:00 | 2008-07-31 09:00 | 55.4772 | 92.0417 | 218350 |  |  | Fixed Duration | 2009-11-02 08:00 | Start No Earlier Than | 1 | 10 | 8 | 15 | 1 | 1 | 1 | 34 | 74239 | 292589
|  | Procurement Complete | 0 days | 2008-08-01 08:00 | 2008-08-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.5 | Final design test | 220 days | 2008-05-01 08:00 | 2009-04-30 16:00 | 219.5982 | 364.3333 | 0 |  |  | Fixed Duration | 2010-07-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Final Design Review | 0 days | 2009-05-01 08:00 | 2009-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.6 | EB procurement (75%) | 114 days | 2009-04-30 08:00 | 2009-10-30 11:00 | 110.3767 | 183.125 | 476000 |  |  | Fixed Duration | 2005-11-15 08:00 | Start No Earlier Than | 1 | 10 | 8 | 15 | 1 | 1 | 1 | 34 | 161840 | 637840
|  | Procurement Complete | 0 days | 2009-11-02 08:00 | 2009-11-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-11-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.1.7 | Integration | 259 days | 2009-05-01 08:00 | 2010-06-30 12:00 | 256.2648 | 425.1667 | 0 |  |  | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Qualification Review | 0 days | 2010-07-01 08:00 | 2010-07-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2 | Level 3 Trigger | 1021 days | 2005-11-15 08:00 | 2010-07-01 08:00 | 1018.0274 | 1689 | 1052350 |  |  | Fixed Duration | 2009-05-04 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 410416.5 | 1462766.5
| 1.2.8.2.1 | Level 3 Trigger System Development | 320 days | 2005-11-15 08:00 | 2007-05-01 14:00 | 320.8082 | 532.25 | 0 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.1.1 | Algorithm development | 320 days | 2005-11-15 08:00 | 2007-05-01 14:00 | 320.8082 | 532.25 | 0 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.2 | Software Performance Tests | 301.88 days | 2005-12-15 08:00 | 2007-04-30 17:00 | 302.1986 | 501.375 | 0 |  |  | Fixed Duration | 2005-11-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.2.1 | Running in XDAQ | 81 days | 2005-12-15 08:00 | 2006-04-28 09:00 | 80.7922 | 134.0417 | 0 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.2.2 | Speed measurements | 220 days | 2006-05-01 08:00 | 2007-04-30 17:00 | 219.6233 | 364.375 | 0 |  |  | Fixed Duration | 2006-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Simulation Review | 0 days | 2007-05-01 08:00 | 2007-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.3 | Beam or Cosmic Test | 240 days | 2006-10-02 08:00 | 2007-11-01 11:00 | 238.1575 | 395.125 | 0 |  |  | Fixed Duration | 2007-11-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.3.1 | Preparation for Beam or Cosmic Test | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 219.6233 | 364.375 | 0 |  |  | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.3.2 | Beam or Cosmic Test | 21 days | 2007-10-01 08:00 | 2007-11-01 11:00 | 18.7603 | 31.125 | 0 |  |  | Fixed Duration | 2008-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.4 | Design Modification and Review | 108 days | 2007-11-01 08:00 | 2008-04-30 12:00 | 109.1963 | 181.1667 | 0 |  |  | Fixed Duration | 2009-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preliminary Design Review | 0 days | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-05-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.5 | Trigger procurement (25%) | 114 days | 2008-04-30 08:00 | 2008-10-30 10:00 | 110.3516 | 183.0833 | 272940 |  |  | Fixed Duration | 2010-06-30 08:00 | Start No Earlier Than | 1 | 15 | 8 | 15 | 1 | 1 | 1 | 39 | 106446.6 | 379386.6
|  | Procurement Complete | 0 days | 2008-10-31 08:00 | 2008-10-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.6 | Final design test | 220 days | 2008-05-01 08:00 | 2009-04-30 16:00 | 219.5982 | 364.3333 | 0 |  | 40 | Fixed Duration | 2007-06-12 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  | Final Design Review | 0 days | 2009-05-01 08:00 | 2009-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-08-07 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.7 | Trigger procurement (75%) | 114 days | 2009-04-30 08:00 | 2009-10-30 11:00 | 110.3767 | 183.125 | 779410 |  |  | Fixed Duration | 2007-10-30 08:00 | Start No Earlier Than | 1 | 15 | 8 | 15 | 1 | 1 | 1 | 39 | 303969.9 | 1083379.9
|  | Procurement Complete | 0 days | 2009-11-02 08:00 | 2009-11-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.2.8 | Integration | 259 days | 2009-05-01 08:00 | 2010-06-30 12:00 | 256.2648 | 425.1667 | 0 | 36 |  | Fixed Duration | 2006-05-15 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Qualification Review | 0 days | 2010-07-01 08:00 | 2010-07-01 08:00 | 0 | 0 | 0 |  |  | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.3 | Level 2 Trigger | 762.5 days | 2005-11-15 08:00 | 2009-05-04 08:00 | 763.0685 | 1266 | 726072.8 |  |  | Fixed Duration | 2006-09-04 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 261386.208 | 987459.008
| 1.2.8.3.1 | Preliminary design | 222 days | 2005-11-15 08:00 | 2006-11-16 09:00 | 220.6279 | 366.0417 | 164659.2 |  |  | Fixed Duration | 2006-11-27 08:00 | Start No Earlier Than | 8 | 1 | 4 | 15 | 2 | 1 | 1 | 36 | 59277.312 | 223936.512
| 1.2.8.3.2 | Prototype | 320 days | 2006-11-15 08:00 | 2008-04-30 11:00 | 320.7329 | 532.125 | 409754.4 |  |  | Fixed Units |  |  | 8 | 1 | 4 | 15 | 2 | 1 | 1 | 36 | 147511.584 | 557265.984
|  | Preliminary Design Review | 0 days | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-07-11 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.3.3 | Final design | 220 days | 2008-05-01 08:00 | 2009-04-30 16:00 | 219.5982 | 364.3333 | 151659.2 |  |  | Fixed Duration |  |  | 8 | 1 | 4 | 15 | 2 | 1 | 1 | 36 | 54597.312 | 206256.512
|  | Final Design Review | 0 days | 2009-05-04 08:00 | 2009-05-04 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-09-04 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4 | Online software | 1020.5 days | 2005-11-15 08:00 | 2010-06-30 12:00 | 1017.5251 | 1688.1667 | 42750 |  |  | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3847.5 | 46597.5
| 1.2.8.4.1 | Online Software System Development | 99 days | 2005-11-15 08:00 | 2006-04-28 14:00 | 99 | 164.25 | 0 |  |  | Fixed Duration | 2006-11-27 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4.1.1 | Simple Online System Running in XDAQ Framework | 99 days | 2005-11-15 08:00 | 2006-04-28 14:00 | 99 | 164.25 | 0 |  |  | Fixed Duration | 2007-04-17 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4.2 | Beam or Cosmic Test | 334.13 days | 2006-05-01 08:00 | 2007-11-01 11:00 | 330.9795 | 549.125 | 0 |  |  | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4.2.1 | Preparation for Beam or Cosmic Test | 314.13 days | 2006-05-01 08:00 | 2007-10-01 17:00 | 312.4452 | 518.375 | 0 |  |  | Fixed Duration | 2007-10-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4.2.2 | Beam or Cosmic Test | 21 days | 2007-10-01 08:00 | 2007-11-01 11:00 | 18.7603 | 31.125 | 0 |  |  | Fixed Units | 2007-12-26 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4.3 | Design Modification and Review | 108 days | 2007-11-01 08:00 | 2008-04-30 12:00 | 109.1963 | 181.1667 | 0 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preliminary Design Review | 0 days | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2006-09-04 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4.4 | Prototype and test | 220 days | 2008-05-01 08:00 | 2009-04-30 16:00 | 219.5982 | 364.3333 | 0 |  |  | Fixed Units |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Final Design Review | 0 days | 2009-05-01 08:00 | 2009-05-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-02-20 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.4.5 | Integration | 259 days | 2009-05-01 08:00 | 2010-06-30 12:00 | 256.2648 | 425.1667 | 42750 |  |  | Fixed Duration | 2007-06-12 08:00 | Start No Earlier Than | 1 | 4 | 4 | 0 | 1 | 1 | 1 | 9 | 3847.5 | 46597.5
|  | Qualification Review | 0 days | 2010-06-30 08:00 | 2010-06-30 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-10-30 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.8.5 | Administration | 828 days | 2006-10-02 08:00 | 2010-07-01 12:00 | 824.6484 | 1368.1667 | 0 |  |  | Fixed Duration | 2007-02-19 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Count | 60 | [5 empty] | Count | 1 | 1 |  | 47 | 47
[8 empty] | Assigned | 1.667% | 1.667% |  | 78.33%
[8 empty] | Missing | 98.33% | 98.33%

## 1.2.8 Durations & Milestone
| Excessive Durations |  |  | Sort by |  |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration
1.2.8.1.2 | Event builder Beam or Cosmic Test | 2006-10-02 08:00 | 2007-11-01 11:00 | 1.0825 |  | Simulation Review | 2007-05-01 08:00 | 2007-05-01 08:00 | 0 days
1.2.8.2.3 | Beam or Cosmic Test | 2006-10-02 08:00 | 2007-11-01 11:00 | 1.0825 |  | Preliminary Design Review | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 days
1.2.8.1.7 | Integration | 2009-05-01 08:00 | 2010-06-30 12:00 | 1.1648 |  | Preliminary Design Review | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 days
1.2.8.2.8 | Integration | 2009-05-01 08:00 | 2010-06-30 12:00 | 1.1648 |  | Preliminary Design Review | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 days
1.2.8.4.5 | Integration | 2009-05-01 08:00 | 2010-06-30 12:00 | 1.1648 |  | Preliminary Design Review | 2008-05-01 08:00 | 2008-05-01 08:00 | 0 days
1.2.8.2.2 | Software Performance Tests | 2005-12-15 08:00 | 2007-04-30 17:00 | 1.3736 |  | Procurement Complete | 2008-08-01 08:00 | 2008-08-01 08:00 | 0 days
1.2.8.4.2.1 | Preparation for Beam or Cosmic Test | 2006-05-01 08:00 | 2007-10-01 17:00 | 1.4202 |  | Procurement Complete | 2008-10-31 08:00 | 2008-10-31 08:00 | 0 days
1.2.8.3.2 | Prototype | 2006-11-15 08:00 | 2008-04-30 11:00 | 1.4579 |  | Final Design Review | 2009-05-01 08:00 | 2009-05-01 08:00 | 0 days
1.2.8.2.1 | Level 3 Trigger System Development | 2005-11-15 08:00 | 2007-05-01 14:00 | 1.4582 |  | Final Design Review | 2009-05-01 08:00 | 2009-05-01 08:00 | 0 days
1.2.8.2.1.1 | Algorithm development | 2005-11-15 08:00 | 2007-05-01 14:00 | 1.4582 |  | Final Design Review | 2009-05-01 08:00 | 2009-05-01 08:00 | 0 days
1.2.8.4.2 | Beam or Cosmic Test | 2006-05-01 08:00 | 2007-11-01 11:00 | 1.5045 |  | Final Design Review | 2009-05-04 08:00 | 2009-05-04 08:00 | 0 days
1.2.8.1.1 | Event Builder System Development | 2005-10-17 08:00 | 2007-04-30 17:00 | 1.5353 |  | Procurement Complete | 2009-11-02 08:00 | 2009-11-02 08:00 | 0 days
1.2.8.3 | Level 2 Trigger | 2005-11-15 08:00 | 2009-05-04 08:00 | 3.4685 |  | Procurement Complete | 2009-11-02 08:00 | 2009-11-02 08:00 | 0 days
1.2.8.5 | Administration | 2006-10-02 08:00 | 2010-07-01 12:00 | 3.7484 |  | Qualification Review | 2010-06-30 08:00 | 2010-06-30 08:00 | 0 days
1.2.8.4 | Online software | 2005-11-15 08:00 | 2010-06-30 12:00 | 4.6251 |  | Qualification Review | 2010-07-01 08:00 | 2010-07-01 08:00 | 0 days
1.2.8.2 | Level 3 Trigger | 2005-11-15 08:00 | 2010-07-01 08:00 | 4.6274 |  | Qualification Review | 2010-07-01 08:00 | 2010-07-01 08:00 | 0 days
1.2.8.1 | Event Builder | 2005-10-17 08:00 | 2010-07-01 08:00 | 4.7068 |  | Count | 16
1.2.8 | DAQ | 2005-10-17 08:00 | 2010-07-01 12:00 | 4.7073 | OK
| 18 |  | Count Excessive | 18
>1 year
30%

## 1.2.9 Observations
Observations |  | WBS 1.2.9 Off-line Computing | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type
Project Start Date | 2004-10-01
Project Finish Date | 2010-11-27
Project Calendar | MS Project Standard | 260 work days per yr. (No adj'd for Holidays, pd. abs or vacation)
Count Tasks | 32
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 100%
Successors | Missing | 100%
Task Type (Units,Work,Duration) | Mixed | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 27, (84%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 8
Hours/week | 40
Hours/year | 2080 | Equals 260 days x 8 hours.
Days/month | 21.7 | Equals 260 days / 12 months.
Excessive Durations | 23 Tasks | 72%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 7 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | [7 empty] | Contg % | Contg | Cost w/Contg | Notes
| 1.2.9 | Off-line Computing | 1606 days | 2004-10-01 08:00 | 2010-11-27 08:00 | 1607.474 | 2248 | 775730 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.4153 | 65280.1 | 841010.1
| 1.2.9.1 | Off-line Computing Hardware | 1345 days | 2005-10-03 08:00 | 2010-11-27 08:00 | 1345.0438 | 1881 | 566930 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2 | 46488.1 | 613418.1
|  | Preliminary Design Review | 0 days | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 | 0 | 0 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Final Design Review | 0 days | 2008-05-02 08:00 | 2008-05-02 08:00 | 0 | 0 | 0 |  |  | Fixed Units | 2008-05-02 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.9.1.1 | Processors | 390 days | 2008-07-01 08:00 | 2009-12-28 17:00 | 389.9805 | 545.375 | 255360 |  |  | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 8 | 20428.8 | 275788.8
| 1.2.9.1.2 | Workstations | 1301 days | 2005-10-03 08:00 | 2010-09-27 17:00 | 1301.6928 | 1820.375 | 15000 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 8 | 1200 | 16200
| 1.2.9.1.3 | Disks and Peripherals | 390 days | 2008-07-01 08:00 | 2009-12-28 17:00 | 389.9805 | 545.375 | 183200 |  |  | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 1 | 1 | 1 | 8 | 14656 | 197856
| 1.2.9.1.4 | Switches | 390 days | 2008-07-01 08:00 | 2009-12-28 17:00 | 389.9805 | 545.375 | 58320 |  |  | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 9 | 5248.8 | 63568.8
| 1.2.9.1.5 | Racks, Infrastructure | 300 days | 2008-07-01 08:00 | 2009-08-24 17:00 | 299.8818 | 419.375 | 10000 |  |  | Fixed Duration | 2008-07-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 9 | 900 | 10900
|  | Complete Procurement | 0 days | 2010-07-01 08:00 | 2010-07-01 08:00 | 0 | 0 | 0 |  |  | Fixed Units | 2010-07-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.9.1.6 | System Support | 450 days | 2008-10-01 08:00 | 2010-06-22 17:00 | 450.0462 | 629.375 | 45050 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 9 | 4054.5 | 49104.5
| 1.2.9.1.7 | Integration | 715 days | 2008-01-01 08:00 | 2010-09-27 17:00 | 715.3366 | 1000.375 | 0 |  |  | Fixed Duration | 2008-01-01 08:00 | Start No Earlier Than | 0 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0
|  | Commission Off-line Farm | 0 days | 2010-11-27 08:00 | 2010-11-27 08:00 | 0 | 0 | 0 |  |  | Fixed Units | 2010-11-27 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.9.2 | Off-line Computing Software | 1583 days | 2004-10-01 08:00 | 2010-10-27 08:00 | 1585.3068 | 2217 | 184800 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 16632 | 201432
|  | Preliminary Design Review | 0 days | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 | 0 | 0 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.9.2.1 | Simulations | 1562 days | 2004-10-01 08:00 | 2010-09-27 17:00 | 1564.1229 | 2187.375 | 0 |  |  | Fixed Duration | 2004-10-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 0 | 0 | 0
| 1.2.9.2.2 | Event Reconstruction | 1562 days | 2004-10-01 08:00 | 2010-09-27 17:00 | 1564.1229 | 2187.375 | 0 |  |  | Fixed Duration | 2004-10-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 0 | 0 | 0
|  | Off-line Software Review | 0 days | 2008-10-01 08:00 | 2008-10-01 08:00 | 0 | 0 | 0 |  |  | Fixed Units | 2008-10-01 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.9.2.3 | Analysis | 1562 days | 2004-10-01 08:00 | 2010-09-27 17:00 | 1564.1229 | 2187.375 | 0 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.9.2.3.1 | Calibrations | 715 days | 2008-01-01 08:00 | 2010-09-27 17:00 | 715.3366 | 1000.375 | 0 |  |  | Fixed Duration | 2008-01-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 0 | 0 | 0
| 1.2.9.2.3.2 | Physics | 1562 days | 2004-10-01 08:00 | 2010-09-27 17:00 | 1564.1229 | 2187.375 | 0 |  |  | Fixed Duration | 2004-10-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 0 | 0 | 0
| 1.2.9.2.3.3 | Monitoring System | 453 days | 2009-01-01 08:00 | 2010-09-27 17:00 | 453.6216 | 634.375 | 0 |  |  | Fixed Duration | 2009-01-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 0 | 0 | 0
| 1.2.9.2.4 | Tools | 1301 days | 2005-10-03 08:00 | 2010-09-27 17:00 | 1301.6928 | 1820.375 | 184800 |  |  | Fixed Duration |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 16632 | 201432
| 1.2.9.2.4.1 | Analysis Framework | 772.97 days | 2005-10-03 08:00 | 2008-09-17 16:47 | 772.5357 | 1080.366 | 80080 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 9 | 7207.2 | 87287.2
| 1.2.9.2.4.2 | Data Format | 212.9 days | 2006-05-01 08:00 | 2007-02-21 16:14 | 211.9056 | 296.3431 | 18480 |  |  | Fixed Duration | 2006-05-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 9 | 1663.2 | 20143.2
| 1.2.9.2.4.3 | Data Management System | 452 days | 2009-01-02 08:00 | 2010-09-27 17:00 | 452.9065 | 633.375 | 0 |  |  | Fixed Duration | 2009-01-02 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 0 | 0 | 0
| 1.2.9.2.4.4 | Calibration Databases | 412.5 days | 2007-03-01 08:00 | 2008-09-29 12:00 | 413.4288 | 578.1667 | 36960 |  |  | Fixed Duration | 2007-03-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 9 | 3326.4 | 40286.4
| 1.2.9.2.4.5 | Detector Description Language | 146.67 days | 2005-10-03 08:00 | 2006-04-25 14:20 | 146.0627 | 204.2639 | 12320 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 9 | 1108.8 | 13428.8
| 1.2.9.2.4.6 | Documentation | 776.47 days | 2005-10-03 08:00 | 2008-09-23 11:46 | 776.6766 | 1086.1569 | 36960 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 9 | 3326.4 | 40286.4
| 1.2.9.2.5 | Integration & Coordination | 1562 days | 2004-10-01 08:00 | 2010-09-27 17:00 | 1564.1229 | 2187.375 | 0 |  |  | Fixed Duration | 2004-10-01 08:00 | Start No Earlier Than | 2 | 1 | 2 | 4 | 1 | 1 | 1 | 0 | 0 | 0
|  | Commissioning | 0 days | 2010-10-27 08:00 | 2010-10-27 08:00 | 0 | 0 | 0 |  |  | Fixed Units | 2010-10-27 08:00 | Start No Earlier Than | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2.9.2.6 | Workshops and Education | 1301 days | 2005-10-03 08:00 | 2010-09-27 17:00 | 1301.6928 | 1820.375 | 24000 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than | 1 | 1 | 2 | 4 | 2 | 1 | 1 | 9 | 2160 | 26160
|  | 32 | [6 empty] | 0 | 0 | 32 | 27 | 27
84.38%

## 1.2.9 Durations & Milestone
| Excessive Durations |  |  | Sort by |  |  |  | Sort by
WBS | Name | Start | Finish | Duration Yrs |  | Milestone | Start | Finish | Duration
1.2.9.1.5 | Racks, Infrastructure | 2008-07-01 08:00 | 2009-08-24 17:00 | 1.149 |  | Preliminary Design Review | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 days
1.2.9.1.1 | Processors | 2008-07-01 08:00 | 2009-12-28 17:00 | 1.4942 |  | Final Design Review | 2008-05-02 08:00 | 2008-05-02 08:00 | 0 days
1.2.9.1.3 | Disks and Peripherals | 2008-07-01 08:00 | 2009-12-28 17:00 | 1.4942 |  | Complete Procurement | 2010-07-01 08:00 | 2010-07-01 08:00 | 0 days
1.2.9.1.4 | Switches | 2008-07-01 08:00 | 2009-12-28 17:00 | 1.4942 |  | Commission Off-line Farm | 2010-11-27 08:00 | 2010-11-27 08:00 | 0 days
1.2.9.2.4.4 | Calibration Databases | 2007-03-01 08:00 | 2008-09-29 12:00 | 1.584 |  | Preliminary Design Review | 2005-10-03 08:00 | 2005-10-03 08:00 | 0 days
1.2.9.1.6 | System Support | 2008-10-01 08:00 | 2010-06-22 17:00 | 1.7243 |  | Off-line Software Review | 2008-10-01 08:00 | 2008-10-01 08:00 | 0 days
1.2.9.2.4.3 | Data Management System | 2009-01-02 08:00 | 2010-09-27 17:00 | 1.7353 |  | Commissioning | 2010-10-27 08:00 | 2010-10-27 08:00 | 0 days
1.2.9.2.3.3 | Monitoring System | 2009-01-01 08:00 | 2010-09-27 17:00 | 1.738 |  | Count | 7
1.2.9.1.7 | Integration | 2008-01-01 08:00 | 2010-09-27 17:00 | 2.7408
1.2.9.2.3.1 | Calibrations | 2008-01-01 08:00 | 2010-09-27 17:00 | 2.7408
1.2.9.2.4.1 | Analysis Framework | 2005-10-03 08:00 | 2008-09-17 16:47 | 2.9599
1.2.9.2.4.6 | Documentation | 2005-10-03 08:00 | 2008-09-23 11:46 | 2.9758
1.2.9.1.2 | Workstations | 2005-10-03 08:00 | 2010-09-27 17:00 | 4.9873
1.2.9.2.4 | Tools | 2005-10-03 08:00 | 2010-09-27 17:00 | 4.9873
1.2.9.2.6 | Workshops and Education | 2005-10-03 08:00 | 2010-09-27 17:00 | 4.9873
1.2.9.1 | Off-line Computing Hardware | 2005-10-03 08:00 | 2010-11-27 08:00 | 5.1534
1.2.9.2.1 | Simulations | 2004-10-01 08:00 | 2010-09-27 17:00 | 5.9928
1.2.9.2.2 | Event Reconstruction | 2004-10-01 08:00 | 2010-09-27 17:00 | 5.9928
1.2.9.2.3 | Analysis | 2004-10-01 08:00 | 2010-09-27 17:00 | 5.9928
1.2.9.2.3.2 | Physics | 2004-10-01 08:00 | 2010-09-27 17:00 | 5.9928
1.2.9.2.5 | Integration & Coordination | 2004-10-01 08:00 | 2010-09-27 17:00 | 5.9928
1.2.9.2 | Off-line Computing Software | 2004-10-01 08:00 | 2010-10-27 08:00 | 6.074
1.2.9 | Off-line Computing | 2004-10-01 08:00 | 2010-11-27 08:00 | 6.1589 | OK
|  |  | Count Excessive | 23
>1 year
71.88%

## 1.2.10 Observations
Observations |  | WBS 1.2.10 Systems Integration | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type
Project Start Date | 2005-10-01
Project Finish Date | 2011-06-23
Project Calendar | Kopio Standard | 220 work days per yr. (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Count Tasks | 365
Estimated dates??? | None | Durations with (??) indicate estimated dates. Make dates firm - removed estimates.
Predecessors | Missing | 53.97%
Successors | Missing | 48.49%
Task Type (Units,Work,Duration) | Mixed | Eventually must be Fixed Work so duration moves with schedule
Constraints | Remove | Qty 104, (28%) Please remove. Schedule will not flow properly. Must assign predecessors & successors first.
Resource Naming Convention | Pool | OK, used conventional coding
Hours/day | 7.1
Hours/week | 35.5
Hours/year | 1760
Days/month | 18 | ~220 work days /12 months (220 adj'd for 11.5 Hol, 4.5d pd. abs & 24d Vac)
Excessive Durations | 57 Tasks | 16%, Tasks >1year (see tab). Please keep tasks at <=1 year. If you must, all 1 year tasks require quarterly tracking milestones for deliverables and other, such as progress payments.
Embeded MS Project Notes | None | Unique Labor or other contractual conventions should be explained.
Milestones | 38 | Interim goals to mark the completion of major phases.
Project costs will be reported via the Web, at level 5 (design, fabrication & installation). Schedule may have to be adjusted to meet this requirement.
Additionally, the schedule must accurately reflect your planned resources for FY06. FY06 MOUs to allocate project dollars will be predicated upon the completeness of your schedule. The schedule will define and drive the distribution of project dollars.
| WBS | Name | Duration | Start | Finish | Calculation | All Days | Cost wo/Contg. | Predecessor | Successor | Task Type | Constraint Date | Constraint Type | Contg % | Contg | Cost w/Contg | Notes
| 1.2.10 | Systems Integration | 1264.63 days | 2005-10-03 08:00 | 2011-06-23 11:00 | 1264.9223 | 2089.125 | 6058934.264 |  |  | Fixed Duration
| 1.2.10.1 | Integration | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 455286.4 |  |  | Fixed Duration
| 1.2.10.1.1 | Subsystem Dimensional Control | 880 days | 2005-10-03 08:00 | 2009-09-28 15:00 | 881.7547 | 1456.2917 | 142841.6 |  |  | Fixed Duration
| 1.2.10.1.1.1 | Design | 880 days | 2005-10-03 08:00 | 2009-09-28 15:00 | 881.7547 | 1456.2917 | 142841.6 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.1.2 | Subsystem Utilities Routing | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 218.7799 | 361.3333 | 35710.4 |  |  | Fixed Duration
| 1.2.10.1.2.1 | Design | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 218.7799 | 361.3333 | 35710.4 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.1.3 | Assembly & Services Modeling | 862.5 days | 2005-10-03 08:00 | 2009-08-31 08:00 | 864.6247 | 1428 | 35710.4 |  |  | Fixed Duration
| 1.2.10.1.3.1 | Design | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 218.7799 | 361.3333 | 35710.4 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.1.3.2 | C-A Construction Milestones | 535.25 days | 2007-04-02 08:00 | 2009-08-31 08:00 | 534.0329 | 882 | 0 |  |  | Fixed Duration
| 1.2.10.1.3.2.1 | B Primary Beam Complete | 0 days | 2007-04-02 08:00 | 2007-04-02 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2007-04-02 08:00 | Start No Earlier Than
| 1.2.10.1.3.2.2 | Experimental Pit Complete | 0 days | 2007-06-04 08:00 | 2007-06-04 08:00 | 0 | 0 | 0 |  | 202 | Fixed Duration | 2007-06-04 08:00 | Start No Earlier Than
| 1.2.10.1.3.2.3 | Neutral Beam Complete | 0 days | 2008-09-01 08:00 | 2008-09-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-09-01 08:00 | Start No Earlier Than
| 1.2.10.1.3.2.4 | 25 Mz Cavity Complete | 0 days | 2008-10-01 08:00 | 2008-10-01 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.1.3.2.5 | D-4 Magnet Complete | 0 days | 2009-08-31 08:00 | 2009-08-31 08:00 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-08-31 08:00 | Start No Earlier Than
| 1.2.10.1.4 | Management Activities | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 241024 |  |  | Fixed Duration
| 1.2.10.1.4.1 | Manager | 1100 days | 2005-10-03 08:00 | 2010-09-23 16:00 | 1099.7525 | 1816.3333 | 0 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.1.4.2 | Engineering | 880 days | 2005-10-03 08:00 | 2009-09-28 15:00 | 881.7547 | 1456.2917 | 167024 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.1.4.3 | Procurement | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 74000 |  |  | Fixed Duration
| 1.2.10.1.4.3.1 | MSTC FY06 | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 218.7799 | 361.3333 | 6000 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.2 | MSTC FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Units | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.3 | MSTC FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 6000 |  |  | Fixed Units | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.4 | MSTC FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Units | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.5 | MSTC FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Units | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.6 | Computer Hardware/Software FY06 | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 218.7799 | 361.3333 | 13000 |  |  | Fixed Units | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.7 | Computer Hardware/Software FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 13000 |  |  | Fixed Units | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.8 | Computer Hardware/Software FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 6000 |  |  | Fixed Units | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.9 | Computer Hardware/Software FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Units | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.1.4.3.10 | Computer Hardware/Software FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Units | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.2 | Detector Installation | 1112 days | 2005-10-03 08:00 | 2010-10-13 12:00 | 1111.7612 | 1836.1667 | 3327254.464 |  |  | Fixed Duration
| 1.2.10.2.1 | Subsystem Installation | 839.63 days | 2007-01-02 08:00 | 2010-10-13 12:00 | 835.6626 | 1380.1667 | 2259403.264 |  |  | Fixed Duration
| 1.2.10.2.1.1 | Vacuum | 534.88 days | 2007-10-02 08:00 | 2010-03-08 12:00 | 537.7667 | 888.1667 | 220977.44 |  |  | Fixed Duration
| 1.2.10.2.1.1.1 | Start U/S Decay Vessel Assembly | 0 days | 2008-09-11 08:00 | 2008-09-11 08:00 | 0 | 0 | 0 |  | 33 | Fixed Duration | 2008-09-11 08:00 | Start No Earlier Than
| 1.2.10.2.1.1.2 | Deliver U/S Decay Vessel | 2 days | 2008-09-11 08:00 | 2008-09-15 10:00 | 2.4724 | 4.0833 | 4472.64 | 32 | 34 | Fixed Units
| 1.2.10.2.1.1.3 | Uncrate and Stage | 3 days | 2008-09-15 10:00 | 2008-09-18 14:00 | 1.9174 | 3.1667 | 3591.84 | 33 | 35 | Fixed Units
| 1.2.10.2.1.1.4 | Install CPV & Supports | 0 days | 2008-09-18 14:00 | 2008-09-18 14:00 | 0 | 0 | 0 | 34 | 139SS-20 days,140 | Fixed Duration
| 1.2.10.2.1.1.5 | Clean and Pre-Assemble | 10 days | 2009-04-10 08:00 | 2009-04-27 11:00 | 10.3688 | 17.125 | 11972.8 | 141 | 37 | Fixed Duration
| 1.2.10.2.1.1.6 | Install Feed-throughs in Adapter Flanges | 5 days | 2009-04-27 11:00 | 2009-05-04 16:00 | 4.3645 | 7.2083 | 5986.4 | 36 | 142 | Fixed Duration
| 1.2.10.2.1.1.7 | Deliver HV Membrane | 0 days | 2007-10-02 08:00 | 2007-10-02 08:00 | 0 | 0 | 0 |  | 39 | Fixed Duration | 2007-10-02 08:00 | Start No Earlier Than
| 1.2.10.2.1.1.8 | Install HV Membrane and Window | 10 days | 2009-05-20 11:00 | 2009-06-05 15:00 | 9.7886 | 16.1667 | 11972.8 | 142,38 | 40 | Fixed Duration
| 1.2.10.2.1.1.9 | Close U/S Decay Vessel | 5 days | 2009-06-05 15:00 | 2009-06-15 12:00 | 5.9791 | 9.875 | 5986.4 | 39 | 41 | Fixed Duration
| 1.2.10.2.1.1.10 | Vessel Leak Testing | 5 days | 2009-06-15 13:00 | 2009-06-23 10:00 | 4.7682 | 7.875 | 6789.2 | 40 | 144 | Fixed Duration
| 1.2.10.2.1.1.11 | Roll Calorimeter Out of Way | 5 days | 2009-12-18 14:00 | 2009-12-29 15:00 | 6.6855 | 11.0417 | 5986.4 | 146 | 43 | Fixed Duration
| 1.2.10.2.1.1.12 | Open Preradiator Modules | 5 days | 2009-12-29 15:00 | 2010-01-07 12:00 | 5.3736 | 8.875 | 5986.4 | 42 | 44 | Fixed Duration
| 1.2.10.2.1.1.13 | Position Barrel Photon Veto | 5 days | 2010-01-07 13:00 | 2010-01-15 10:00 | 4.7682 | 7.875 | 5986.4 | 43,172 | 45 | Fixed Duration
| 1.2.10.2.1.1.14 | Install Vessel Supports in BPV | 5 days | 2010-01-15 10:00 | 2010-01-25 16:00 | 6.2062 | 10.25 | 5986.4 | 44 | 46 | Fixed Duration
| 1.2.10.2.1.1.15 | Install U/S Vacuum Decay Vessel | 5 days | 2010-01-26 08:00 | 2010-02-02 14:00 | 4.3897 | 7.25 | 5986.4 | 45 | 47 | Fixed Duration
| 1.2.10.2.1.1.16 | Rout Fiber and Cable | 5 days | 2010-02-02 14:00 | 2010-02-10 11:00 | 4.7682 | 7.875 | 5986.4 | 46 | 48 | Fixed Duration
| 1.2.10.2.1.1.17 | Close Barrel Photon Veto | 5 days | 2010-02-10 11:00 | 2010-02-18 09:00 | 4.7934 | 7.9167 | 5986.4 | 47 | 49 | Fixed Duration
| 1.2.10.2.1.1.18 | Close Preradiator Modules | 5 days | 2010-02-18 09:00 | 2010-02-26 15:00 | 4.9952 | 8.25 | 5986.4 | 48 | 50 | Fixed Duration
| 1.2.10.2.1.1.19 | Position Calorimeter | 5 days | 2010-02-26 15:00 | 2010-03-08 12:00 | 5.9791 | 9.875 | 5986.4 | 49 | 51 | Fixed Duration
| 1.2.10.2.1.1.20 | U/S Decay Vessel Assembly Complete | 0 days | 2010-03-08 12:00 | 2010-03-08 12:00 | 0 | 0 | 0 | 50 |  | Fixed Duration
| 1.2.10.2.1.1.21 | Install D-4 Magnet Vacuum Box | 0 days | 2008-04-02 08:00 | 2008-04-02 08:00 | 0 | 0 | 0 |  | 53 | Fixed Duration | 2008-04-02 08:00 | Start No Earlier Than
| 1.2.10.2.1.1.22 | Deliver Vacuum Box | 1 day | 2008-04-02 08:00 | 2008-04-02 17:00 | 0.22705 | 0.375 | 2236.32 | 52 | 54 | Fixed Duration | 2006-06-01 08:00 | Start No Earlier Than
| 1.2.10.2.1.1.23 | Uncrate & Stage | 3 days | 2008-04-03 08:00 | 2008-04-08 10:00 | 3.0779 | 5.0833 | 3591.84 | 53 | 55 | Fixed Duration
| 1.2.10.2.1.1.24 | Clean and Assemble | 5 days | 2008-04-08 10:00 | 2008-04-15 16:00 | 4.3897 | 7.25 | 5986.4 | 54 | 56 | Fixed Duration
| 1.2.10.2.1.1.25 | Install Feed-throughs and Flanges | 5 days | 2008-04-16 08:00 | 2008-04-23 14:00 | 4.3897 | 7.25 | 5986.4 | 55 | 57 | Fixed Duration
| 1.2.10.2.1.1.26 | Vessel Leak Testing | 3 days | 2008-04-23 14:00 | 2008-04-29 09:00 | 3.5067 | 5.7917 | 4073.52 | 56 | 58 | Fixed Duration
| 1.2.10.2.1.1.27 | Install Magnet Veto | 20 days | 2008-04-29 09:00 | 2008-05-30 14:00 | 18.896 | 31.2083 | 5986.4 | 57 |  | Fixed Duration
| 1.2.10.2.1.1.28 | Install Vacuum Box in Magnet | 2 days | 2009-06-08 13:00 | 2009-06-10 15:00 | 1.2614 | 2.0833 | 2394.56 | 352FS+20 days |  | Fixed Duration
| 1.2.10.2.1.1.29 | Connect to Vacuum Decay Vessels | 2 days | 2009-10-07 14:00 | 2009-10-09 16:00 | 1.2614 | 2.0833 | 2394.56 | 74 | 61 | Fixed Duration
| 1.2.10.2.1.1.30 | D-4 Vacuum Box Complete | 0 days | 2009-10-09 16:00 | 2009-10-09 16:00 | 0 | 0 | 0 | 60 |  | Fixed Duration
| 1.2.10.2.1.1.31 | Start D/S Vessel Assembly | 0 days | 2009-07-24 08:00 | 2009-07-24 08:00 | 0 | 0 | 0 |  | 63 | Fixed Duration | 2009-07-24 08:00 | Start No Earlier Than
| 1.2.10.2.1.1.32 | Deliver Support Stands | 2 days | 2009-07-24 08:00 | 2009-07-28 10:00 | 2.4724 | 4.0833 | 4472.64 | 62 | 64,67SS | Fixed Duration | 2009-05-07 14:24 | Start No Earlier Than
| 1.2.10.2.1.1.33 | Establish Reference Datums | 3 days | 2009-07-28 10:00 | 2009-07-31 14:00 | 1.9174 | 3.1667 | 5387.76 | 63 | 65 | Fixed Duration | 2009-05-12 14:24 | Start No Earlier Than
| 1.2.10.2.1.1.34 | Install Floor Anchors | 3 days | 2009-07-31 14:00 | 2009-08-05 16:00 | 3.0779 | 5.0833 | 4472.64 | 64 | 66 | Fixed Duration | 2009-05-18 11:34 | Start No Earlier Than
| 1.2.10.2.1.1.35 | Install Support Stands | 5 days | 2009-08-06 08:00 | 2009-08-13 14:00 | 4.3897 | 7.25 | 5986.4 | 65 | 73 | Fixed Duration | 2009-05-26 09:44 | Start No Earlier Than
| 1.2.10.2.1.1.36 | Deliver D/S Vessel | 2 days | 2009-07-24 08:00 | 2009-07-28 10:00 | 2.4724 | 4.0833 | 4472.64 | 63SS | 68 | Fixed Duration
| 1.2.10.2.1.1.37 | Uncrate and Stage | 5 days | 2009-07-28 10:00 | 2009-08-04 15:00 | 4.3645 | 7.2083 | 5986.4 | 67 | 69 | Fixed Duration | 2009-06-19 10:24 | Start No Earlier Than
| 1.2.10.2.1.1.38 | Install Veto Detector Supports | 5 days | 2009-08-04 15:00 | 2009-08-12 12:00 | 4.7682 | 7.875 | 5986.4 | 68 | 70 | Fixed Duration | 2009-06-29 08:34 | Start No Earlier Than
| 1.2.10.2.1.1.39 | Clean | 5 days | 2009-08-12 13:00 | 2009-08-20 10:00 | 4.7682 | 7.875 | 5986.4 | 69 | 71 | Fixed Duration | 2009-07-06 15:44 | Start No Earlier Than
| 1.2.10.2.1.1.40 | Install Feed-throughs and Flanges | 5 days | 2009-08-20 10:00 | 2009-08-27 16:00 | 4.3897 | 7.25 | 5986.4 | 70 | 72 | Fixed Duration | 2009-07-23 09:14 | Start No Earlier Than
| 1.2.10.2.1.1.41 | Vessel Leak Testing | 3 days | 2009-08-28 08:00 | 2009-09-02 09:00 | 3.0526 | 5.0417 | 4073.52 | 71 | 75,73 | Fixed Duration | 2009-08-07 14:34 | Start No Earlier Than
| 1.2.10.2.1.1.42 | Install D/S Veto | 20 days | 2009-09-02 09:00 | 2009-10-05 11:00 | 20.0313 | 33.0833 | 5986.4 | 72,66 | 74 | Fixed Duration
| 1.2.10.2.1.1.43 | Install D/S Tanks in Beam | 2 days | 2009-10-05 11:00 | 2009-10-07 14:00 | 1.2866 | 2.125 | 4472.64 | 73 | 60 | Fixed Duration
| 1.2.10.2.1.1.44 | Rout Fiber and Cable | 5 days | 2009-09-02 09:00 | 2009-09-10 15:00 | 4.9952 | 8.25 | 5986.4 | 72 |  | Fixed Duration | 2009-08-17 11:44 | Start No Earlier Than
| 1.2.10.2.1.1.45 | D/S Vessel Assembly Complete | 0 days | 2009-09-02 08:04 | 2009-09-02 08:04 | 0 | 0 | 0 |  |  | Fixed Duration | 2009-09-02 08:04 | Start No Earlier Than
| 1.2.10.2.1.1.46 | Start Vacuum Pumping Station | 0 days | 2008-06-27 08:00 | 2008-06-27 08:00 | 0 | 0 | 0 |  | 78 | Fixed Duration | 2008-06-27 08:00 | Start No Earlier Than
| 1.2.10.2.1.1.47 | Deliver Equipment | 1 day | 2008-06-27 08:00 | 2008-06-27 17:00 | 0.22705 | 0.375 | 1490.88 | 77 | 79 | Fixed Duration
| 1.2.10.2.1.1.48 | Install Floor Anchors | 1 day | 2008-06-30 08:00 | 2008-06-30 17:00 | 0.22705 | 0.375 | 1490.88 | 78 | 80 | Fixed Duration
| 1.2.10.2.1.1.49 | Install Support Stands | 2 days | 2008-07-01 08:00 | 2008-07-02 17:00 | 0.83253 | 1.375 | 2394.56 | 79 | 81 | Fixed Duration
| 1.2.10.2.1.1.50 | Hook-up AC Power | 5 days | 2008-07-03 08:00 | 2008-07-11 12:00 | 4.9447 | 8.1667 | 9044.8 | 80 | 82 | Fixed Duration
| 1.2.10.2.1.1.51 | Vacuum Pump Station Complete | 0 days | 2008-07-11 12:00 | 2008-07-11 12:00 | 0 | 0 | 0 | 81 |  | Fixed Duration
| 1.2.10.2.1.2 | Preradiator | 664 days | 2007-01-02 08:00 | 2009-12-31 12:00 | 662.4954 | 1094.1667 | 478379.84 |  |  | Fixed Duration
| 1.2.10.2.1.2.1 | Start Mechanical Assembly | 0 days | 2007-07-02 08:00 | 2007-07-02 08:00 | 0 | 0 | 0 |  | 85 | Fixed Duration | 2007-07-02 08:00 | Start No Earlier Than
| 1.2.10.2.1.2.2 | Deliver Support Structure | 3 days | 2007-07-02 08:00 | 2007-07-09 10:00 | 4.2888 | 7.0833 | 6708.96 | 84 | 86 | Fixed Duration
| 1.2.10.2.1.2.3 | Establish Reference Datums | 3 days | 2007-07-09 10:00 | 2007-07-12 14:00 | 1.9174 | 3.1667 | 5387.76 | 85 | 87 | Fixed Duration
| 1.2.10.2.1.2.4 | Install Floor Anchors | 5 days | 2007-07-12 14:00 | 2007-07-20 11:00 | 4.7682 | 7.875 | 7454.4 | 86 | 88 | Fixed Duration
| 1.2.10.2.1.2.5 | Install Floor Plates | 10 days | 2007-07-20 11:00 | 2007-08-06 11:00 | 10.2932 | 17 | 11972.8 | 87 | 89FF | Fixed Duration
| 1.2.10.2.1.2.6 | Level Floor Plates | 5 days | 2007-07-30 09:00 | 2007-08-06 11:00 | 4.2888 | 7.0833 | 8979.6 | 88FF | 90 | Fixed Duration
| 1.2.10.2.1.2.7 | Install Grout Frames | 3 days | 2007-08-06 11:00 | 2007-08-09 15:00 | 1.9174 | 3.1667 | 4472.64 | 89 | 91 | Fixed Duration
| 1.2.10.2.1.2.8 | Grout Floor Plates | 5 days | 2007-08-09 15:00 | 2007-08-17 12:00 | 4.7682 | 7.875 | 2461.6 | 90 | 92 | Fixed Duration
| 1.2.10.2.1.2.9 | Assemble Support Structure | 20 days | 2007-08-17 13:00 | 2007-09-20 10:00 | 20.5106 | 33.875 | 23945.6 | 91 | 101,107 | Fixed Duration
| 1.2.10.2.1.2.10 | Deliver Module Support Fixtures | 1 day | 2007-01-02 08:00 | 2007-01-03 09:00 | 0.63071 | 1.0417 | 2236.32 |  | 94 | Fixed Duration | 2007-01-01 08:00 | Start No Earlier Than
| 1.2.10.2.1.2.11 | Assemble Module Support Fixtures | 2 days | 2007-01-03 09:00 | 2007-01-05 11:00 | 1.2614 | 2.0833 | 2394.56 | 93 | 95,99 | Fixed Duration
| 1.2.10.2.1.2.12 | Deliver Modules | 660 days | 2007-01-05 11:00 | 2009-12-30 11:00 | 659.9726 | 1090 | 35781.12 | 94 | 96FF,104SS | Fixed Duration
| 1.2.10.2.1.2.13 | Stage Modules on Fixtures | 660 days | 2007-01-05 11:00 | 2009-12-30 11:00 | 659.9726 | 1090 | 71836.8 | 95FF | 97FF | Fixed Duration
| 1.2.10.2.1.2.14 | Pre-Testing of Modules | 660 days | 2007-01-05 11:00 | 2009-12-30 11:00 | 659.9726 | 1090 | 71836.8 | 96FF | 98FF | Fixed Duration
| 1.2.10.2.1.2.15 | Install Modules in Support Structure | 660 days | 2007-01-05 11:00 | 2009-12-30 11:00 | 659.9726 | 1090 | 57469.44 | 97FF | 110SS,102 | Fixed Duration
| 1.2.10.2.1.2.16 | Deliver Gas System | 1 day | 2007-01-05 11:00 | 2007-01-08 12:00 | 1.8417 | 3.0417 | 2236.32 | 94 | 100 | Fixed Duration
| 1.2.10.2.1.2.17 | Install Gas System | 10 days | 2007-01-08 13:00 | 2007-01-24 16:00 | 9.7634 | 16.125 | 11972.8 | 99 |  | Fixed Duration
| 1.2.10.2.1.2.18 | Install Hydraulic Drives | 5 days | 2007-09-20 10:00 | 2007-09-27 16:00 | 4.3897 | 7.25 | 5986.4 | 92 |  | Fixed Duration
| 1.2.10.2.1.2.19 | Roll Into Operating Position | 1 day | 2009-12-30 11:00 | 2009-12-31 12:00 | 0.63071 | 1.0417 | 1197.28 | 98 | 103 | Fixed Duration
| 1.2.10.2.1.2.20 | Mechanical Assembly Complete | 0 days | 2009-12-31 12:00 | 2009-12-31 12:00 | 0 | 0 | 0 | 102 |  | Fixed Duration
| 1.2.10.2.1.2.21 | Start Electrical Assembly | 0 days | 2007-01-05 11:00 | 2007-01-05 11:00 | 0 | 0 | 0 | 95SS | 105 | Fixed Duration
| 1.2.10.2.1.2.22 | Deliver Crates and Cables | 2 days | 2007-01-05 11:00 | 2007-01-09 14:00 | 2.4976 | 4.125 | 4472.64 | 104 | 106 | Fixed Duration
| 1.2.10.2.1.2.23 | Install Crates in Racks | 120 days | 2007-01-09 14:00 | 2007-07-24 16:00 | 118.7244 | 196.0833 | 35918.4 | 105 |  | Fixed Duration
| 1.2.10.2.1.2.24 | Install Subsystem Cable Tray | 5 days | 2007-09-20 10:00 | 2007-09-27 16:00 | 4.3897 | 7.25 | 9044.8 | 92 | 108 | Fixed Duration
| 1.2.10.2.1.2.25 | Install Cable Bundles | 120 days | 2007-09-28 08:00 | 2008-04-15 14:00 | 121.2473 | 200.25 | 35918.4 | 107 |  | Fixed Duration
| 1.2.10.2.1.2.28 | Subsystem Testing | 660 days | 2007-01-05 11:00 | 2009-12-30 11:00 | 659.9726 | 1090 | 58694.4 |  |  | Fixed Duration
| 1.2.10.2.1.2.28.1 | Engineering | 660 days | 2007-01-05 11:00 | 2009-12-30 11:00 | 659.9726 | 1090 | 22776 | 98SS | 111SS | Fixed Duration
| 1.2.10.2.1.2.28.2 | Technical | 660 days | 2007-01-05 11:00 | 2009-12-30 11:00 | 659.9726 | 1090 | 35918.4 | 110SS | 112 | Fixed Duration
| 1.2.10.2.1.2.29 | Electrical Assembly Complete | 0 days | 2009-12-30 11:00 | 2009-12-30 11:00 | 0 | 0 | 0 | 111 |  | Fixed Duration
| 1.2.10.2.1.3 | Calorimeter | 717.63 days | 2007-01-03 08:00 | 2010-04-01 10:00 | 716.9381 | 1184.0833 | 210089.744 |  |  | Fixed Duration
| 1.2.10.2.1.3.1 | Start Mechanical Assembly | 0 days | 2008-11-28 08:00 | 2008-11-28 08:00 | 0 | 0 | 0 |  | 115 | Fixed Duration | 2008-11-28 08:00 | Start No Earlier Than
| 1.2.10.2.1.3.2 | Deliver Support Structure | 2 days | 2008-12-01 08:00 | 2008-12-03 10:00 | 1.2614 | 2.0833 | 4472.64 | 114 | 116 | Fixed Duration
| 1.2.10.2.1.3.3 | Establish Reference Datums | 3 days | 2008-12-03 10:00 | 2008-12-08 14:00 | 3.1283 | 5.1667 | 5387.76 | 115 | 117 | Fixed Duration
| 1.2.10.2.1.3.4 | Install Floor Anchors | 5 days | 2008-12-08 14:00 | 2008-12-16 11:00 | 4.7682 | 7.875 | 7454.4 | 116 | 118 | Fixed Duration
| 1.2.10.2.1.3.5 | Install Floor Plates | 10 days | 2008-12-16 11:00 | 2009-01-07 09:00 | 13.2701 | 21.9167 | 11972.8 | 117 | 119FF | Fixed Duration
| 1.2.10.2.1.3.6 | Level Floor Plates | 5 days | 2008-12-24 09:00 | 2009-01-07 09:00 | 8.4767 | 14 | 8979.6 | 118FF | 120 | Fixed Duration
| 1.2.10.2.1.3.7 | Install Grout Frames | 3 days | 2009-01-07 09:00 | 2009-01-13 12:00 | 3.7086 | 6.125 | 4472.64 | 119 | 121 | Fixed Duration
| 1.2.10.2.1.3.8 | Grout Floor Plates | 5 days | 2009-01-13 13:00 | 2009-01-21 10:00 | 4.7682 | 7.875 | 2461.6 | 120 | 122 | Fixed Duration
| 1.2.10.2.1.3.9 | Assemble Support Structure | 20 days | 2009-01-21 10:00 | 2009-02-24 09:00 | 20.5611 | 33.9583 | 20353.76 | 121 | 129,132,135,126 | Fixed Duration
| 1.2.10.2.1.3.10 | Deliver Shashlyk Modules | 530 days | 2007-01-03 08:00 | 2009-05-27 10:00 | 529.845 | 875.0833 | 22363.2 |  |  | Fixed Duration | 2007-01-03 08:00 | Start No Earlier Than
| 1.2.10.2.1.3.11 | Install Left Half Modules | 70 days | 2009-08-03 08:00 | 2009-11-23 16:00 | 68.0155 | 112.3333 | 17959.2 |  | 125 | Fixed Duration | 2009-08-01 08:00 | Start No Earlier Than
| 1.2.10.2.1.3.12 | Install Right Half Modules | 75 days | 2009-11-24 08:00 | 2010-03-31 10:00 | 76.9463 | 127.0833 | 17959.2 | 124 | 127 | Fixed Duration
| 1.2.10.2.1.3.13 | Install Hydraulic Drives | 5 days | 2009-02-24 09:00 | 2009-03-03 15:00 | 4.3897 | 7.25 | 5986.4 | 122 |  | Fixed Duration
| 1.2.10.2.1.3.14 | Roll Into Operating Position | 1 day | 2010-03-31 10:00 | 2010-04-01 10:00 | 0.60548 | 1 | 1197.28 | 125 | 128 | Fixed Duration
| 1.2.10.2.1.3.15 | Mechanical Assembly Complete | 0 days | 2010-04-01 10:00 | 2010-04-01 10:00 | 0 | 0 | 0 | 127 |  | Fixed Duration
| 1.2.10.2.1.3.16 | Start Electrical Assembly | 0 days | 2009-02-24 09:00 | 2009-02-24 09:00 | 0 | 0 | 0 | 122 | 130 | Fixed Duration
| 1.2.10.2.1.3.17 | Deliver Crates and Cables | 120 days | 2009-02-24 09:00 | 2009-09-03 09:00 | 115.6466 | 191 | 11628.864 | 129 | 131SS | Fixed Duration
| 1.2.10.2.1.3.18 | Install Crates in Racks | 220 days | 2009-02-24 09:00 | 2010-02-18 14:00 | 217.4933 | 359.2083 | 19755.12 | 130SS |  | Fixed Duration
| 1.2.10.2.1.3.19 | Install Subsystem Cable Tray | 5 days | 2009-02-24 09:00 | 2009-03-03 15:00 | 4.3897 | 7.25 | 9044.8 | 122 | 133 | Fixed Duration
| 1.2.10.2.1.3.20 | Install Cable Bundles | 220 days | 2009-03-03 15:00 | 2010-03-01 11:00 | 219.6881 | 362.8333 | 0 | 132 |  | Fixed Duration
| 1.2.10.2.1.3.21 | Subsystem Testing | 240 days | 2009-02-24 09:00 | 2010-03-24 12:00 | 238.0291 | 393.125 | 38640.48 |  |  | Fixed Duration
| 1.2.10.2.1.3.21.1 | Engineering | 240 days | 2009-02-24 09:00 | 2010-03-24 12:00 | 238.0291 | 393.125 | 14994.2 | 122 | 136SS | Fixed Duration
| 1.2.10.2.1.3.21.2 | Technical | 240 days | 2009-02-24 09:00 | 2010-03-24 12:00 | 238.0291 | 393.125 | 23646.28 | 135SS | 137 | Fixed Duration
| 1.2.10.2.1.3.22 | Electrical Assembly Complete | 0 days | 2010-03-24 12:00 | 2010-03-24 12:00 | 0 | 0 | 0 | 136 |  | Fixed Duration
| 1.2.10.2.1.4 | Charged Particle Veto | 295 days | 2008-08-18 10:00 | 2009-12-18 14:00 | 294.9694 | 487.1667 | 43913.392 |  |  | Fixed Duration
| 1.2.10.2.1.4.1 | Deliver CPV Modules & Supports | 1 day | 2008-08-18 10:00 | 2008-08-19 11:00 | 0.63071 | 1.0417 | 598.64 | 35SS-20 days |  | Fixed Duration
| 1.2.10.2.1.4.2 | Install CPV Supports in Decay Vessel | 10 days | 2008-09-18 14:00 | 2008-10-03 15:00 | 9.1074 | 15.0417 | 11972.8 | 35 | 141 | Fixed Duration
| 1.2.10.2.1.4.3 | Install CPV Modules in Decay Vessel | 110 days | 2008-10-03 15:00 | 2009-04-09 16:00 | 113.8554 | 188.0417 | 0 | 140 | 36 | Fixed Duration
| 1.2.10.2.1.4.4 | Fiber and Cable Connections | 10 days | 2009-05-05 08:00 | 2009-05-20 11:00 | 9.1579 | 15.125 | 11972.8 | 37 | 39 | Fixed Duration
| 1.2.10.2.1.4.5 | Subsystem Testing | 110 days | 2009-06-23 10:00 | 2009-12-18 14:00 | 107.8763 | 178.1667 | 19369.152 |  |  | Fixed Duration
| 1.2.10.2.1.4.5.1 | Engineering | 110 days | 2009-06-23 10:00 | 2009-12-18 14:00 | 107.8763 | 178.1667 | 7516.08 | 41 | 145SS | Fixed Duration
| 1.2.10.2.1.4.5.2 | Technical | 110 days | 2009-06-23 10:00 | 2009-12-18 14:00 | 107.8763 | 178.1667 | 11853.072 | 144SS | 146 | Fixed Duration
| 1.2.10.2.1.4.6 | CPV Installed | 0 days | 2009-12-18 14:00 | 2009-12-18 14:00 | 0 | 0 | 0 | 145 | 42 | Fixed Duration
| 1.2.10.2.1.5 | Photon Veto | 554 days | 2007-06-15 08:00 | 2009-12-16 16:00 | 554.2155 | 915.3333 | 249404.336 |  |  | Fixed Duration
| 1.2.10.2.1.5.1 | Start Mechanical Assembly | 0 days | 2009-03-10 08:00 | 2009-03-10 08:00 | 0 | 0 | 0 |  | 149 | Fixed Duration | 2009-03-10 08:00 | Start No Earlier Than
| 1.2.10.2.1.5.2 | Deliver Support Structure | 2 days | 2009-03-10 08:00 | 2009-03-12 10:00 | 1.2614 | 2.0833 | 4472.64 | 148 | 150 | Fixed Duration
| 1.2.10.2.1.5.3 | Establish Reference Datums | 5 days | 2009-03-12 10:00 | 2009-03-19 16:00 | 4.3897 | 7.25 | 8979.6 | 149 | 151 | Fixed Duration
| 1.2.10.2.1.5.4 | Install Floor Anchors | 5 days | 2009-03-20 08:00 | 2009-03-27 14:00 | 4.3897 | 7.25 | 7454.4 | 150 | 152 | Fixed Duration
| 1.2.10.2.1.5.5 | Install Floor Plates | 10 days | 2009-03-27 14:00 | 2009-04-13 10:00 | 10.1922 | 16.8333 | 11972.8 | 151 | 153FF | Fixed Duration
| 1.2.10.2.1.5.6 | Level Floor Plates | 5 days | 2009-04-03 14:00 | 2009-04-13 10:00 | 5.9539 | 9.8333 | 8979.6 | 152FF | 154 | Fixed Duration
| 1.2.10.2.1.5.7 | Install Grout Frames | 3 days | 2009-04-13 10:00 | 2009-04-16 14:00 | 1.9174 | 3.1667 | 4472.64 | 153 | 155 | Fixed Duration
| 1.2.10.2.1.5.8 | Grout Floor Plates | 5 days | 2009-04-16 14:00 | 2009-04-24 11:00 | 4.7682 | 7.875 | 2461.6 | 154 | 156 | Fixed Duration
| 1.2.10.2.1.5.9 | Install U/S Wall Support Structure | 10 days | 2009-04-24 11:00 | 2009-05-11 14:00 | 10.3688 | 17.125 | 5986.4 | 155 | 158,167 | Fixed Duration
| 1.2.10.2.1.5.10 | Deliver U/S Wall Modules | 220 days | 2008-06-16 08:00 | 2009-06-16 09:00 | 221.0252 | 365.0417 | 22363.2 |  | 164SS | Fixed Duration | 2008-06-15 08:00 | Start No Earlier Than
| 1.2.10.2.1.5.11 | Install Lower Half U/S Wall Modules | 30 days | 2009-05-11 14:00 | 2009-06-29 15:00 | 29.6937 | 49.0417 | 17959.2 | 156 | 159 | Fixed Duration
| 1.2.10.2.1.5.12 | Install Upper Half U/S Wall Modules | 30 days | 2009-06-29 15:00 | 2009-08-17 11:00 | 29.5676 | 48.8333 | 17959.2 | 158 |  | Fixed Duration
| 1.2.10.2.1.5.13 | Install Cylindrical Support Structure | 10 days | 2009-02-16 08:00 | 2009-03-04 11:00 | 9.7634 | 16.125 | 7183.68 |  | 162 | Fixed Duration | 2009-02-15 08:00 | Start No Earlier Than
| 1.2.10.2.1.5.14 | Deliver Cylindrical Ring Modules | 440 days | 2007-06-15 08:00 | 2009-06-12 16:00 | 440.9909 | 728.3333 | 22363.2 |  |  | Fixed Duration | 2007-06-15 08:00 | Start No Earlier Than
| 1.2.10.2.1.5.15 | Install Cylindrical Ring Super Modules | 100 days | 2009-03-04 11:00 | 2009-08-11 15:00 | 96.9776 | 160.1667 | 35918.4 | 160 | 163 | Fixed Duration
| 1.2.10.2.1.5.16 | Mechanical Ass'y. Complete | 0 days | 2009-08-11 15:00 | 2009-08-11 15:00 | 0 | 0 | 0 | 162 |  | Fixed Duration
| 1.2.10.2.1.5.17 | Start Electrical Assembly | 0 days | 2008-06-16 08:00 | 2008-06-16 08:00 | 0 | 0 | 0 | 157SS | 165 | Fixed Duration
| 1.2.10.2.1.5.18 | Deliver Crates and Cables | 3 days | 2008-06-16 08:00 | 2008-06-19 11:00 | 1.8921 | 3.125 | 6708.96 | 164 | 166,170 | Fixed Duration
| 1.2.10.2.1.5.19 | Install Crates in Racks | 220 days | 2008-06-19 11:00 | 2009-06-19 12:00 | 221.0252 | 365.0417 | 23706.144 | 165 | 168SS | Fixed Duration
| 1.2.10.2.1.5.20 | Install Subsystem Cable Tray | 5 days | 2009-05-11 14:00 | 2009-05-19 11:00 | 4.7682 | 7.875 | 9044.8 | 156 |  | Fixed Duration
| 1.2.10.2.1.5.21 | Install Cable Bundles | 220 days | 2008-06-19 11:00 | 2009-06-19 12:00 | 221.0252 | 365.0417 | 11853.072 | 166SS |  | Fixed Duration
| 1.2.10.2.1.5.22 | Subsystem Testing | 330 days | 2008-06-19 11:00 | 2009-12-16 16:00 | 330.1124 | 545.2083 | 19564.8 |  |  | Fixed Duration
| 1.2.10.2.1.5.22.1 | Engineering | 330 days | 2008-06-19 11:00 | 2009-12-16 16:00 | 330.1124 | 545.2083 | 7592 | 165 | 171FF | Fixed Duration
| 1.2.10.2.1.5.22.2 | Technical | 330 days | 2008-06-19 11:00 | 2009-12-16 16:00 | 330.1124 | 545.2083 | 11972.8 | 170FF | 172 | Fixed Duration
| 1.2.10.2.1.5.23 | Electrical Assembly Complete | 0 days | 2009-12-16 16:00 | 2009-12-16 16:00 | 0 | 0 | 0 | 171 | 44 | Fixed Duration
| 1.2.10.2.1.6 | Catcher | 181 days | 2009-09-02 08:04 | 2010-06-28 16:04 | 181.2402 | 299.3333 | 132308.112 |  |  | Fixed Duration
| 1.2.10.2.1.6.1 | Start Catcher Assembly | 0 days | 2009-09-02 08:04 | 2009-09-02 08:04 | 0 | 0 | 0 |  | 175 | Fixed Duration | 2009-09-02 08:04 | Start No Earlier Than
| 1.2.10.2.1.6.2 | Deliver Support Structure | 2 days | 2009-09-02 08:04 | 2009-09-04 10:04 | 1.2614 | 2.0833 | 4472.64 | 174 | 176 | Fixed Duration
| 1.2.10.2.1.6.3 | Establish Reference Datums | 3 days | 2009-09-04 10:04 | 2009-09-10 14:04 | 3.7338 | 6.1667 | 5387.76 | 175 | 177 | Fixed Duration
| 1.2.10.2.1.6.4 | Install Floor Anchors | 5 days | 2009-09-10 14:04 | 2009-09-18 11:04 | 4.7682 | 7.875 | 7454.4 | 176 | 178 | Fixed Duration
| 1.2.10.2.1.6.5 | Install Support Structure | 60 days | 2009-09-18 11:04 | 2009-12-29 10:04 | 61.7337 | 101.9583 | 35918.4 | 177 | 179 | Fixed Duration
| 1.2.10.2.1.6.6 | Install Detector Modules | 80 days | 2009-12-29 10:04 | 2010-05-07 14:04 | 78.2078 | 129.1667 | 47891.2 | 178 | 180SS | Fixed Duration
| 1.2.10.2.1.6.7 | Deliver Crates and Cables | 1 day | 2009-12-29 10:04 | 2009-12-30 11:04 | 0.63071 | 1.0417 | 2236.32 | 179SS | 181 | Fixed Duration
| 1.2.10.2.1.6.8 | Install Crates in Racks | 80 days | 2009-12-30 11:04 | 2010-05-10 15:04 | 79.4187 | 131.1667 | 4789.12 | 180 | 182SS,184SS | Fixed Duration
| 1.2.10.2.1.6.9 | Install Cable Bundles | 80 days | 2009-12-30 11:04 | 2010-05-10 15:04 | 79.4187 | 131.1667 | 4789.12 | 181SS |  | Fixed Duration
| 1.2.10.2.1.6.10 | Subsystem Testing | 110 days | 2009-12-30 11:04 | 2010-06-28 16:04 | 109.1124 | 180.2083 | 19369.152 |  |  | Fixed Duration
| 1.2.10.2.1.6.10.1 | Engineering | 110 days | 2009-12-30 11:04 | 2010-06-28 16:04 | 109.1124 | 180.2083 | 7516.08 | 181SS | 185SS | Fixed Duration
| 1.2.10.2.1.6.10.2 | Technical | 110 days | 2009-12-30 11:04 | 2010-06-28 16:04 | 109.1124 | 180.2083 | 11853.072 | 184SS | 186 | Fixed Duration
| 1.2.10.2.1.6.11 | Catcher Assembly Complete | 0 days | 2010-06-28 16:04 | 2010-06-28 16:04 | 0 | 0 | 0 | 185 | 195 | Fixed Duration
| 1.2.10.2.1.7 | Conventional Systems | 767.13 days | 2007-04-30 08:00 | 2010-10-13 12:00 | 764.216 | 1262.1667 | 924330.4 |  |  | Fixed Duration
| 1.2.10.2.1.7.1 | Mechanical Utilities | 722.5 days | 2007-07-11 16:00 | 2010-10-13 12:00 | 720.4196 | 1189.8333 | 142015.68 |  |  | Fixed Duration
| 1.2.10.2.1.7.1.1 | Chilled Water Systems | 52 days | 2007-07-12 08:00 | 2007-10-03 12:00 | 50.3557 | 83.1667 | 68863.04 |  |  | Fixed Duration
| 1.2.10.2.1.7.1.1.1 | Staging | 2 days | 2007-07-12 08:00 | 2007-07-16 10:00 | 2.4724 | 4.0833 | 4472.64 | 203,273 | 191 | Fixed Duration
| 1.2.10.2.1.7.1.1.2 | Installation & Distribution | 40 days | 2007-07-16 10:00 | 2007-09-18 11:00 | 38.7759 | 64.0417 | 47891.2 | 190 | 192 | Fixed Duration
| 1.2.10.2.1.7.1.1.3 | Piping | 5 days | 2007-09-18 11:00 | 2007-09-26 09:00 | 4.7934 | 7.9167 | 7454.4 | 191 | 193 | Fixed Duration
| 1.2.10.2.1.7.1.1.4 | Electrical | 5 days | 2007-09-26 09:00 | 2007-10-03 12:00 | 4.314 | 7.125 | 9044.8 | 192 | 228 | Fixed Duration
| 1.2.10.2.1.7.1.2 | Conditioned Air Systems | 47 days | 2010-07-29 14:00 | 2010-10-13 12:00 | 45.966 | 75.9167 | 73152.64 |  |  | Fixed Duration
| 1.2.10.2.1.7.1.2.1 | Staging | 2 days | 2010-07-29 14:00 | 2010-08-02 16:00 | 2.4724 | 4.0833 | 4472.64 | 186,278 | 196 | Fixed Duration
| 1.2.10.2.1.7.1.2.2 | Install Enclosure | 20 days | 2010-08-03 08:00 | 2010-09-02 10:00 | 18.2148 | 30.0833 | 29817.6 | 195 | 197 | Fixed Duration
| 1.2.10.2.1.7.1.2.3 | Ducting & Piping | 20 days | 2010-09-02 10:00 | 2010-10-05 15:00 | 20.107 | 33.2083 | 29817.6 | 196 | 198 | Fixed Duration
| 1.2.10.2.1.7.1.2.4 | Electrical | 5 days | 2010-10-05 15:00 | 2010-10-13 12:00 | 4.7682 | 7.875 | 9044.8 | 197 |  | Fixed Duration
| 1.2.10.2.1.7.1.3 | Compressed Air Systems | 0 days | 2007-07-11 16:00 | 2007-07-11 16:00 | 0 | 0 | 0 | 203 |  | Fixed Duration
| 1.2.10.2.1.7.2 | Electrical Utilities | 313 days | 2007-06-04 08:00 | 2008-10-28 11:00 | 310.0812 | 512.125 | 508715.04 |  |  | Fixed Duration
| 1.2.10.2.1.7.2.1 | Commercial Power Distribution | 23 days | 2007-06-04 08:00 | 2007-07-11 16:00 | 22.6046 | 37.3333 | 42888.16 |  |  | Fixed Duration
| 1.2.10.2.1.7.2.1.1 | Staging | 3 days | 2007-06-04 08:00 | 2007-06-07 11:00 | 1.8921 | 3.125 | 6708.96 | 11 | 203 | Fixed Duration
| 1.2.10.2.1.7.2.1.2 | Installation | 20 days | 2007-06-07 11:00 | 2007-07-11 16:00 | 20.7124 | 34.2083 | 36179.2 | 202 | 190,205,210,199 | Fixed Duration
| 1.2.10.2.1.7.2.2 | Clean Power Distribution | 63 days | 2007-07-12 08:00 | 2007-10-19 15:00 | 60.1191 | 99.2917 | 115246.56 |  |  | Fixed Duration
| 1.2.10.2.1.7.2.2.1 | Staging | 3 days | 2007-07-12 08:00 | 2007-07-17 11:00 | 3.1031 | 5.125 | 6708.96 | 203 | 206 | Fixed Duration
| 1.2.10.2.1.7.2.2.2 | Installation | 60 days | 2007-07-17 11:00 | 2007-10-19 15:00 | 57.016 | 94.1667 | 108537.6 | 205 | 220 | Fixed Duration
| 1.2.10.2.1.7.2.3 | UPS Distribution | 6 days | 2008-09-26 08:00 | 2008-10-06 11:00 | 6.1305 | 10.125 | 8222.72 |  |  | Fixed Duration
| 1.2.10.2.1.7.2.3.1 | Staging | 1 day | 2008-09-26 08:00 | 2008-09-29 09:00 | 1.8417 | 3.0417 | 2236.32 | 217 | 209 | Fixed Duration
| 1.2.10.2.1.7.2.3.2 | Electrical Installation | 5 days | 2008-09-29 09:00 | 2008-10-06 11:00 | 4.2888 | 7.0833 | 5986.4 | 208 |  | Fixed Duration
| 1.2.10.2.1.7.2.4 | Emergency Power Distribution | 0 days | 2007-07-11 16:00 | 2007-07-11 16:00 | 0 | 0 | 0 | 203 |  | Fixed Duration
| 1.2.10.2.1.7.2.5 | Grounding | 12 days | 2008-05-19 15:00 | 2008-06-09 12:00 | 12.6394 | 20.875 | 14367.36 |  |  | Fixed Duration
| 1.2.10.2.1.7.2.5.1 | Mechanical Installation | 2 days | 2008-05-19 15:00 | 2008-05-22 09:00 | 1.6651 | 2.75 | 2394.56 | 216 | 213 | Fixed Duration
| 1.2.10.2.1.7.2.5.2 | Electrical Installation | 10 days | 2008-05-22 09:00 | 2008-06-09 12:00 | 10.9743 | 18.125 | 11972.8 | 212 |  | Fixed Duration
| 1.2.10.2.1.7.2.6 | Electronics Racks | 165 days | 2008-02-05 13:00 | 2008-10-28 11:00 | 161.0071 | 265.9167 | 214980 |  |  | Fixed Duration
| 1.2.10.2.1.7.2.6.1 | Staging | 5 days | 2008-02-05 13:00 | 2008-02-13 10:00 | 4.7682 | 7.875 | 11181.6 | 221 | 216 | Fixed Duration
| 1.2.10.2.1.7.2.6.2 | Mechanical Installation | 60 days | 2008-02-13 10:00 | 2008-05-19 15:00 | 58.2522 | 96.2083 | 71836.8 | 215 | 212,217 | Fixed Duration
| 1.2.10.2.1.7.2.6.3 | Electrical Installation | 80 days | 2008-05-19 15:00 | 2008-09-25 16:00 | 78.1321 | 129.0417 | 95782.4 | 216 | 208,218 | Fixed Duration
| 1.2.10.2.1.7.2.6.4 | Power Connection | 20 days | 2008-09-26 08:00 | 2008-10-28 11:00 | 19.451 | 32.125 | 36179.2 | 217 | 224,231,237,238 | Fixed Duration
| 1.2.10.2.1.7.2.7 | Cable Distribution Systems | 62 days | 2007-10-19 15:00 | 2008-02-05 12:00 | 65.9216 | 108.875 | 113010.24 |  |  | Fixed Duration
| 1.2.10.2.1.7.2.7.1 | Staging | 2 days | 2007-10-19 15:00 | 2007-10-24 09:00 | 2.876 | 4.75 | 4472.64 | 206 | 221 | Fixed Duration
| 1.2.10.2.1.7.2.7.2 | Tray Installation | 60 days | 2007-10-24 09:00 | 2008-02-05 12:00 | 63.0455 | 104.125 | 108537.6 | 220 | 215 | Fixed Duration
| 1.2.10.2.1.7.3 | Safety Systems | 332 days | 2007-10-03 13:00 | 2009-04-08 11:00 | 334.7797 | 552.9167 | 154329.28 |  |  | Fixed Duration
| 1.2.10.2.1.7.3.1 | Global Interlocks and Alarm Systems | 82 days | 2008-10-28 11:00 | 2009-03-20 12:00 | 86.6088 | 143.0417 | 65469.76 |  |  | Fixed Duration
| 1.2.10.2.1.7.3.1.1 | Mechanical Installation | 2 days | 2008-10-28 11:00 | 2008-10-30 14:00 | 1.2866 | 2.125 | 2394.56 | 218 | 225 | Fixed Duration
| 1.2.10.2.1.7.3.1.2 | Electrical Installation | 40 days | 2008-10-30 14:00 | 2009-01-14 15:00 | 46.0417 | 76.0417 | 47891.2 | 224 | 226,236 | Fixed Duration
| 1.2.10.2.1.7.3.1.3 | Programing | 40 days | 2009-01-14 15:00 | 2009-03-20 12:00 | 39.2805 | 64.875 | 15184 | 225 | 233 | Fixed Duration
| 1.2.10.2.1.7.3.2 | Water Leak Detection Systems | 22 days | 2007-10-03 13:00 | 2007-11-07 11:00 | 21.1413 | 34.9167 | 26340.16 |  |  | Fixed Duration
| 1.2.10.2.1.7.3.2.1 | Mechanical Installation | 2 days | 2007-10-03 13:00 | 2007-10-05 12:00 | 1.1857 | 1.9583 | 2394.56 | 193 | 229 | Fixed Duration
| 1.2.10.2.1.7.3.2.2 | Electrical Installation | 20 days | 2007-10-05 13:00 | 2007-11-07 11:00 | 19.9304 | 32.9167 | 23945.6 | 228 |  | Fixed Duration
| 1.2.10.2.1.7.3.3 | Smoke and Heat Detection Systems | 20 days | 2008-10-28 11:00 | 2008-12-03 11:00 | 21.7973 | 36 | 36179.2 |  |  | Fixed Duration
| 1.2.10.2.1.7.3.3.1 | Electrical Installation | 20 days | 2008-10-28 11:00 | 2008-12-03 11:00 | 21.7973 | 36 | 36179.2 | 218 |  | Fixed Duration
| 1.2.10.2.1.7.3.4 | Flamable Gas Detection Systems | 12 days | 2009-03-20 13:00 | 2009-04-08 11:00 | 11.4537 | 18.9167 | 14367.36 |  |  | Fixed Duration
| 1.2.10.2.1.7.3.4.1 | Mechanical Installation | 2 days | 2009-03-20 13:00 | 2009-03-24 15:00 | 2.4724 | 4.0833 | 2394.56 | 226 | 234 | Fixed Duration
| 1.2.10.2.1.7.3.4.2 | Electrical Installation | 10 days | 2009-03-24 15:00 | 2009-04-08 11:00 | 8.9813 | 14.8333 | 11972.8 | 233 |  | Fixed Duration
| 1.2.10.2.1.7.3.5 | Emergency Shutdown Systems | 10 days | 2009-01-14 15:00 | 2009-01-30 10:00 | 9.5615 | 15.7917 | 11972.8 |  |  | Fixed Duration
| 1.2.10.2.1.7.3.5.1 | Electrical Installation | 10 days | 2009-01-14 15:00 | 2009-01-30 10:00 | 9.5615 | 15.7917 | 11972.8 | 225 |  | Fixed Duration
| 1.2.10.2.1.7.3.6 | Fire Suppression Systems | 0 days | 2008-10-28 11:00 | 2008-10-28 11:00 | 0 | 0 | 0 | 218 |  | Fixed Duration
| 1.2.10.2.1.7.3.7 | ODH Detection Systems | 0 days | 2008-10-28 11:00 | 2008-10-28 11:00 | 0 | 0 | 0 | 218 |  | Fixed Duration
| 1.2.10.2.1.7.4 | Personnel Access Systems | 80 days | 2007-04-30 08:00 | 2007-09-06 15:00 | 78.2834 | 129.2917 | 119270.4 |  |  | Fixed Duration
| 1.2.10.2.1.7.4.1 | Scaffolding Systems | 60 days | 2007-05-31 11:00 | 2007-09-06 15:00 | 59.4379 | 98.1667 | 89452.8 |  |  | Fixed Duration
| 1.2.10.2.1.7.4.1.1 | Erect Scaffolding | 60 days | 2007-05-31 11:00 | 2007-09-06 15:00 | 59.4379 | 98.1667 | 89452.8 | 243 |  | Fixed Duration
| 1.2.10.2.1.7.4.2 | Stairs and Walkways | 20 days | 2007-04-30 08:00 | 2007-05-31 11:00 | 18.8455 | 31.125 | 29817.6 |  |  | Fixed Duration
| 1.2.10.2.1.7.4.2.1 | Mechanical Installation | 20 days | 2007-04-30 08:00 | 2007-05-31 11:00 | 18.8455 | 31.125 | 29817.6 |  | 241 | Fixed Duration | 2007-04-30 08:00 | Start No Earlier Than
| 1.2.10.2.2 | Installation Equipment | 882.13 days | 2006-10-02 08:00 | 2010-09-28 11:00 | 882.2592 | 1457.125 | 152000 |  |  | Fixed Duration
| 1.2.10.2.2.1 | Procurement | 882.13 days | 2006-10-02 08:00 | 2010-09-28 11:00 | 882.2592 | 1457.125 | 152000 |  |  | Fixed Duration
| 1.2.10.2.2.1.1 | Man-lifts | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 50000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.2 | MSTS FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 19000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.3 | MSTS FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 19000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.4 | MSTS FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.5 | MSTS FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Duration | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.6 | Misc. Fabrication FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 13000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.7 | Misc. Fabrication FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 13000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.8 | Misc. Fabrication FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 13000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.2.1.9 | Misc. Fabrication FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 13000 |  |  | Fixed Duration | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.3 | Management Activities | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 915851.2 |  |  | Fixed Duration
| 1.2.10.2.3.1 | Manager | 880 days | 2005-10-03 08:00 | 2009-09-28 15:00 | 881.7547 | 1456.2917 | 0 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.2.3.2 | Engineering | 880 days | 2005-10-03 08:00 | 2009-09-28 15:00 | 881.7547 | 1456.2917 | 334048 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.2.3.3 | Technical Supervisor | 880 days | 2005-10-03 08:00 | 2009-09-28 15:00 | 881.7547 | 1456.2917 | 526803.2 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.2.3.4 | Procurement | 882.13 days | 2006-10-02 08:00 | 2010-09-28 11:00 | 882.2592 | 1457.125 | 55000 |  |  | Fixed Duration
| 1.2.10.2.3.4.1 | MSTS FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.2.3.4.2 | MSTS FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 6000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.3.4.3 | MSTS FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.3.4.4 | MSTS FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Duration | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.3.4.5 | Computer Hardware/Software FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 13000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.2.3.4.6 | Computer Hardware/Software FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 6000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.3.4.7 | Computer Hardware/Software FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.2.3.4.8 | Computer Hardware/Software FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Duration | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.3 | Conventional Systems | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 2233393.4 |  |  | Fixed Duration
| 1.2.10.3.1 | Mechanical Utilities | 876.63 days | 2006-08-10 08:00 | 2010-07-29 14:00 | 877.4911 | 1449.25 | 451451.2 |  |  | Fixed Duration
| 1.2.10.3.1.1 | Chilled Water Systems | 200 days | 2006-08-10 08:00 | 2007-07-10 14:00 | 202.3815 | 334.25 | 263718.4 |  |  | Fixed Duration
| 1.2.10.3.1.1.1 | Engineering | 120 days | 2006-08-10 08:00 | 2007-03-01 15:00 | 123.0889 | 203.2917 | 22776 |  | 272SS | Fixed Duration | 2006-08-10 08:00 | Start No Earlier Than
| 1.2.10.3.1.1.2 | Design | 80 days | 2006-08-10 08:00 | 2006-12-20 15:00 | 80.0999 | 132.2917 | 51942.4 | 271SS | 273 | Fixed Duration
| 1.2.10.3.1.1.3 | Procurement | 120 days | 2006-12-20 15:00 | 2007-07-10 14:00 | 122.2816 | 201.9583 | 189000 | 272 | 274FF,190 | Fixed Duration
| 1.2.10.3.1.1.4 | Fabrication | 120 days | 2006-12-20 15:00 | 2007-07-10 14:00 | 122.2816 | 201.9583 | 0 | 273FF |  | Fixed Duration
| 1.2.10.3.1.2 | Conditioned Air Systems & Enclosure | 180 days | 2009-10-06 08:00 | 2010-07-29 14:00 | 179.3733 | 296.25 | 187732.8 |  |  | Fixed Duration
| 1.2.10.3.1.2.1 | Engineering | 120 days | 2009-10-06 08:00 | 2010-04-23 09:00 | 120.5156 | 199.0417 | 22776 |  | 277SS | Fixed Duration | 2009-10-06 08:00 | Start No Earlier Than
| 1.2.10.3.1.2.2 | Design | 60 days | 2009-10-06 08:00 | 2010-01-15 11:00 | 61.2291 | 101.125 | 38956.8 | 276SS | 278 | Fixed Duration
| 1.2.10.3.1.2.3 | Procurement | 120 days | 2010-01-15 11:00 | 2010-07-29 14:00 | 118.1442 | 195.125 | 126000 | 277 | 195 | Fixed Duration
| 1.2.10.3.1.3 | Compressed Air Systems | 0 days | 2007-05-02 10:00 | 2007-05-02 10:00 | 0 | 0 | 0 | 284 |  | Fixed Duration
| 1.2.10.3.2 | Electrical Utilities | 430.5 days | 2006-10-12 08:00 | 2008-09-23 14:00 | 431.2527 | 712.25 | 983025.4 |  |  | Fixed Duration
| 1.2.10.3.2.1 | Commercial Power Distribution | 120 days | 2006-10-12 08:00 | 2007-05-02 10:00 | 122.3573 | 202.0833 | 135155.2 |  |  | Fixed Duration
| 1.2.10.3.2.1.1 | Engineering | 80 days | 2006-10-12 08:00 | 2007-02-28 10:00 | 84.2121 | 139.0833 | 15184 |  | 283SS | Fixed Duration | 2006-10-12 08:00 | Start No Earlier Than
| 1.2.10.3.2.1.2 | Design | 40 days | 2006-10-12 08:00 | 2006-12-19 10:00 | 41.2231 | 68.0833 | 25971.2 | 282SS | 284 | Fixed Duration
| 1.2.10.3.2.1.3 | Procurement | 80 days | 2006-12-19 10:00 | 2007-05-02 10:00 | 81.1342 | 134 | 94000 | 283 | 279,292 | Fixed Duration
| 1.2.10.3.2.2 | Clean Power Distribution | 140 days | 2006-11-20 08:00 | 2007-07-12 14:00 | 141.8336 | 234.25 | 243140.8 |  |  | Fixed Duration
| 1.2.10.3.2.2.1 | Engineering | 80 days | 2006-11-20 08:00 | 2007-04-05 10:00 | 82.3957 | 136.0833 | 15184 |  | 287SS | Fixed Duration | 2006-11-20 08:00 | Start No Earlier Than
| 1.2.10.3.2.2.2 | Design | 60 days | 2006-11-20 08:00 | 2007-03-05 12:00 | 63.6763 | 105.1667 | 38956.8 | 286SS | 288 | Fixed Duration
| 1.2.10.3.2.2.3 | Procurement | 80 days | 2007-03-05 13:00 | 2007-07-12 14:00 | 78.1321 | 129.0417 | 189000 | 287 |  | Fixed Duration
| 1.2.10.3.2.3 | Uninterrupted Power Systems | 100 days | 2008-04-15 08:00 | 2008-09-23 14:00 | 97.6336 | 161.25 | 66796 |  |  | Fixed Duration
| 1.2.10.3.2.3.1 | Engineering | 20 days | 2008-04-15 08:00 | 2008-05-15 12:00 | 18.2653 | 30.1667 | 3796 |  | 291 | Fixed Duration | 2008-04-15 08:00 | Start No Earlier Than
| 1.2.10.3.2.3.2 | Procurement | 80 days | 2008-05-15 13:00 | 2008-09-23 14:00 | 79.343 | 131.0417 | 63000 | 290 |  | Fixed Duration
| 1.2.10.3.2.4 | Emergency Power Distribution | 0 days | 2007-05-02 10:00 | 2007-05-02 10:00 | 0 | 0 | 0 | 284 |  | Fixed Duration
| 1.2.10.3.2.5 | Detector Electrical Ground | 140 days | 2007-09-28 08:00 | 2008-05-16 10:00 | 139.9162 | 231.0833 | 84127.2 |  |  | Fixed Duration
| 1.2.10.3.2.5.1 | Engineering | 60 days | 2007-09-28 08:00 | 2008-01-08 16:00 | 61.9607 | 102.3333 | 11388 |  | 295SS | Fixed Duration | 2007-09-28 08:00 | Start No Earlier Than
| 1.2.10.3.2.5.2 | Design | 60 days | 2007-09-28 08:00 | 2008-01-08 16:00 | 61.9607 | 102.3333 | 9739.2 | 294SS | 296 | Fixed Duration
| 1.2.10.3.2.5.3 | Procurement | 80 days | 2008-01-09 08:00 | 2008-05-16 10:00 | 77.5518 | 128.0833 | 63000 | 295 |  | Fixed Duration
| 1.2.10.3.2.6 | Electronics Rack Systems | 220 days | 2007-03-05 08:00 | 2008-02-29 15:00 | 218.7547 | 361.2917 | 290447 |  |  | Fixed Duration
| 1.2.10.3.2.6.1 | Engineering | 220 days | 2007-03-05 08:00 | 2008-02-29 15:00 | 218.7547 | 361.2917 | 13475.8 |  | 299SS | Fixed Duration | 2007-03-05 08:00 | Start No Earlier Than
| 1.2.10.3.2.6.2 | Design | 80 days | 2007-03-05 08:00 | 2007-07-12 09:00 | 78.1321 | 129.0417 | 25971.2 | 298SS | 300 | Fixed Duration
| 1.2.10.3.2.6.3 | Procurement | 120 days | 2007-07-12 09:00 | 2008-01-29 09:00 | 121.7014 | 201 | 251000 | 299 | 325,326 | Fixed Duration
| 1.2.10.3.2.7 | Cable Distribution Systems | 200 days | 2006-11-27 08:00 | 2007-10-22 09:00 | 199.228 | 329.0417 | 163359.2 |  |  | Fixed Duration
| 1.2.10.3.2.7.1 | Engineering | 60 days | 2006-11-27 08:00 | 2007-03-08 12:00 | 61.2543 | 101.1667 | 11388 |  | 303SS | Fixed Duration | 2006-11-23 08:00 | Start No Earlier Than
| 1.2.10.3.2.7.2 | Design | 80 days | 2006-11-27 08:00 | 2007-04-10 10:00 | 81.1847 | 134.0833 | 25971.2 | 302SS | 304 | Fixed Duration
| 1.2.10.3.2.7.3 | Procurement | 120 days | 2007-04-10 10:00 | 2007-10-22 09:00 | 118.0433 | 194.9583 | 126000 | 303 |  | Fixed Duration
| 1.2.10.3.3 | Safety Systems | 416.25 days | 2007-05-01 08:00 | 2009-03-23 10:00 | 419.0422 | 692.0833 | 278389.6 |  |  | Fixed Duration
| 1.2.10.3.3.1 | Global Interlocks and Alarm Systems | 180 days | 2008-01-04 08:00 | 2008-10-21 15:00 | 176.3711 | 291.2917 | 112846.4 |  |  | Fixed Duration
| 1.2.10.3.3.1.1 | Engineering | 80 days | 2008-01-04 08:00 | 2008-05-13 10:00 | 78.7628 | 130.0833 | 30368 |  | 308SS | Fixed Duration | 2008-01-04 08:00 | Start No Earlier Than
| 1.2.10.3.3.1.2 | Design | 60 days | 2008-01-04 08:00 | 2008-04-10 14:00 | 58.8829 | 97.25 | 19478.4 | 307SS | 309 | Fixed Duration
| 1.2.10.3.3.1.3 | Procurement | 120 days | 2008-04-10 14:00 | 2008-10-21 15:00 | 117.4882 | 194.0417 | 63000 | 308 |  | Fixed Duration
| 1.2.10.3.3.2 | Water Leak Detection Systems | 100 days | 2007-05-01 08:00 | 2007-10-10 10:00 | 98.1381 | 162.0833 | 58577.6 |  |  | Fixed Duration
| 1.2.10.3.3.2.1 | Engineering | 40 days | 2007-05-01 08:00 | 2007-07-03 15:00 | 38.3218 | 63.2917 | 7592 |  | 312SS | Fixed Duration | 2007-05-01 08:00 | Start No Earlier Than
| 1.2.10.3.3.2.2 | Design | 40 days | 2007-05-01 08:00 | 2007-07-03 15:00 | 38.3218 | 63.2917 | 12985.6 | 311SS | 313 | Fixed Duration
| 1.2.10.3.3.2.3 | Procurement | 60 days | 2007-07-03 15:00 | 2007-10-10 10:00 | 59.8163 | 98.7917 | 38000 | 312 |  | Fixed Duration
| 1.2.10.3.3.3 | Smoke and Heat Detection Systyems | 100 days | 2008-05-16 08:00 | 2008-10-24 12:00 | 97.5831 | 161.1667 | 38592 |  |  | Fixed Duration
| 1.2.10.3.3.3.1 | Engineering | 40 days | 2008-05-16 08:00 | 2008-07-21 16:00 | 40.1635 | 66.3333 | 7592 |  | 316 | Fixed Duration | 2008-05-16 08:00 | Start No Earlier Than
| 1.2.10.3.3.3.2 | Procurement | 60 days | 2008-07-22 08:00 | 2008-10-24 12:00 | 57.016 | 94.1667 | 31000 | 315 |  | Fixed Duration
| 1.2.10.3.3.4 | Flammable Gas Detection Systems | 100 days | 2008-10-01 08:00 | 2009-03-23 10:00 | 104.7984 | 173.0833 | 52084.8 |  |  | Fixed Duration
| 1.2.10.3.3.4.1 | Engineering | 40 days | 2008-10-01 08:00 | 2008-12-08 11:00 | 41.2483 | 68.125 | 7592 |  | 319SS | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.3.3.4.2 | Design | 40 days | 2008-10-01 08:00 | 2008-12-08 11:00 | 41.2483 | 68.125 | 6492.8 | 318SS | 320 | Fixed Duration
| 1.2.10.3.3.4.3 | Procurement | 60 days | 2008-12-08 11:00 | 2009-03-23 10:00 | 63.5501 | 104.9583 | 38000 | 319 |  | Fixed Duration
| 1.2.10.3.3.5 | Emergency Shutdown Systems | 60 days | 2008-10-14 08:00 | 2009-01-28 16:00 | 64.3826 | 106.3333 | 16288.8 |  |  | Fixed Duration
| 1.2.10.3.3.5.1 | Engineering | 20 days | 2008-10-14 08:00 | 2008-11-14 14:00 | 18.9212 | 31.25 | 3796 |  | 323SS | Fixed Duration | 2008-10-14 08:00 | Start No Earlier Than
| 1.2.10.3.3.5.2 | Design | 20 days | 2008-10-14 08:00 | 2008-11-14 14:00 | 18.9212 | 31.25 | 6492.8 | 322SS | 324 | Fixed Duration
| 1.2.10.3.3.5.3 | Procurement | 40 days | 2008-11-14 14:00 | 2009-01-28 16:00 | 45.4614 | 75.0833 | 6000 | 323 |  | Fixed Duration
| 1.2.10.3.3.6 | Fire Suppression Systems | 0 days | 2008-01-29 09:00 | 2008-01-29 09:00 | 0 | 0 | 0 | 300 |  | Fixed Duration
| 1.2.10.3.3.7 | ODH Detection Systems | 0 days | 2008-01-29 09:00 | 2008-01-29 09:00 | 0 | 0 | 0 | 300 |  | Fixed Duration
| 1.2.10.3.4 | Personnel Access Systems | 236.5 days | 2006-06-01 08:00 | 2007-06-27 14:00 | 236.8938 | 391.25 | 237747.2 |  |  | Fixed Duration
| 1.2.10.3.4.1 | Scaffolding Systems | 100 days | 2007-01-18 08:00 | 2007-06-27 14:00 | 97.0281 | 160.25 | 70592 |  |  | Fixed Duration
| 1.2.10.3.4.1.1 | Engineering | 40 days | 2007-01-18 08:00 | 2007-03-23 09:00 | 38.7759 | 64.0417 | 7592 |  | 330 | Fixed Duration | 2007-01-18 08:00 | Start No Earlier Than
| 1.2.10.3.4.1.2 | Procurement | 60 days | 2007-03-23 09:00 | 2007-06-27 14:00 | 58.2522 | 96.2083 | 63000 | 329 |  | Fixed Duration
| 1.2.10.3.4.2 | Stairs and Walkways | 200 days | 2006-06-01 08:00 | 2007-04-30 14:00 | 201.776 | 333.25 | 167155.2 |  |  | Fixed Duration
| 1.2.10.3.4.2.1 | Engineering | 80 days | 2006-06-01 08:00 | 2006-10-10 10:00 | 79.3683 | 131.0833 | 15184 |  | 333SS | Fixed Duration | 2006-06-01 08:00 | Start No Earlier Than
| 1.2.10.3.4.2.2 | Design | 80 days | 2006-06-01 08:00 | 2006-10-10 10:00 | 79.3683 | 131.0833 | 25971.2 | 332SS | 334 | Fixed Duration
| 1.2.10.3.4.2.3 | Procurement | 120 days | 2006-10-10 10:00 | 2007-04-30 14:00 | 122.4078 | 202.1667 | 126000 | 333 |  | Fixed Duration
| 1.2.10.3.5 | Management Activities | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 282780 |  |  | Fixed Duration
| 1.2.10.3.5.1 | Manager | 1100 days | 2005-10-03 08:00 | 2010-09-23 16:00 | 1099.7525 | 1816.3333 | 0 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.3.5.2 | Engineering | 1100 days | 2005-10-03 08:00 | 2010-09-23 16:00 | 1099.7525 | 1816.3333 | 208780 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.3.5.5 | Procurement | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 74000 |  |  | Fixed Duration
| 1.2.10.3.5.5.1 | MSTS FY06 | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 218.7799 | 361.3333 | 6000 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.2 | MSTS FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.3 | MSTS FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 6000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.4 | MSTS FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.5 | MSTS FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Duration | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.6 | Computer Hardware/Software FY06 | 220 days | 2005-10-03 08:00 | 2006-09-29 16:00 | 218.7799 | 361.3333 | 13000 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.7 | Computer Hardware/Software FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 13000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.8 | Computer Hardware/Software FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 6000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.9 | Computer Hardware/Software FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.3.5.5.10 | Computer Hardware/Software FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Duration | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.4 | Testing & Commissioning | 1264.63 days | 2005-10-03 08:00 | 2011-06-23 11:00 | 1264.9223 | 2089.125 | 43000 |  |  | Fixed Duration
| 1.2.10.4.1 | Testing | 75 days | 2009-01-05 08:00 | 2009-05-05 14:00 | 72.8089 | 120.25 | 0 |  |  | Fixed Duration
| 1.2.10.4.1.1 | FY09 Neutral Beam Test | 75 days | 2009-01-05 08:00 | 2009-05-05 14:00 | 72.8089 | 120.25 | 0 |  |  | Fixed Duration
| 1.2.10.4.1.1.1 | Scientist Shift Coverage | 75 days | 2009-01-05 08:00 | 2009-05-05 14:00 | 72.8089 | 120.25 | 0 |  | 59FS+20 days | Fixed Duration | 2009-01-05 08:00 | Start No Earlier Than
| 1.2.10.4.2 | Commissioning | 347 days | 2009-12-01 08:00 | 2011-06-23 11:00 | 344.5935 | 569.125 | 0 |  |  | Fixed Duration
| 1.2.10.4.2.1 | FY10 Engineering Run | 125 days | 2009-12-01 08:00 | 2010-06-23 15:00 | 123.6944 | 204.2917 | 0 |  |  | Fixed Duration
| 1.2.10.4.2.1.1 | Scientist Shift Coverage | 125 days | 2009-12-01 08:00 | 2010-06-23 15:00 | 123.6944 | 204.2917 | 0 |  |  | Fixed Duration | 2009-12-01 08:00 | Start No Earlier Than
| 1.2.10.4.2.4 | FY11 Engineering Run | 125 days | 2010-12-01 08:00 | 2011-06-23 11:00 | 123.5935 | 204.125 | 0 |  |  | Fixed Duration
| 1.2.10.4.2.4.5 | Scientist Shift Coverage | 125 days | 2010-12-01 08:00 | 2011-06-23 11:00 | 123.5935 | 204.125 | 0 |  |  | Fixed Duration | 2010-12-01 08:00 | Start No Earlier Than
| 1.2.10.4.3 | Management Activities | 1102.13 days | 2005-10-03 08:00 | 2010-09-28 11:00 | 1102.6538 | 1821.125 | 43000 |  |  | Fixed Duration
| 1.2.10.4.3.1 | Manager | 1100 days | 2005-10-03 08:00 | 2010-09-23 16:00 | 1099.7525 | 1816.3333 | 0 |  |  | Fixed Duration | 2005-10-03 08:00 | Start No Earlier Than
| 1.2.10.4.3.4 | Procurement | 882.13 days | 2006-10-02 08:00 | 2010-09-28 11:00 | 882.2592 | 1457.125 | 43000 |  |  | Fixed Duration
| 1.2.10.4.3.4.1 | MSTS FY07 | 220 days | 2006-10-02 08:00 | 2007-10-01 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2006-10-02 08:00 | Start No Earlier Than
| 1.2.10.4.3.4.2 | MSTS FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 6000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
| 1.2.10.4.3.4.3 | MSTS FY09 | 220 days | 2008-10-01 08:00 | 2009-09-30 17:00 | 220.6216 | 364.375 | 6000 |  |  | Fixed Duration | 2008-10-01 08:00 | Start No Earlier Than
| 1.2.10.4.3.4.4 | MSTS FY10 | 220 days | 2009-10-01 08:00 | 2010-09-28 11:00 | 219.2592 | 362.125 | 6000 |  |  | Fixed Duration | 2009-10-01 08:00 | Start No Earlier Than
| 1.2.10.4.3.4.5 | Computer Hardware/Software FY08 | 220 days | 2007-10-01 08:00 | 2008-09-25 11:00 | 218.0483 | 360.125 | 19000 |  |  | Fixed Duration | 2007-10-01 08:00 | Start No Earlier Than
|  | 365 | [6 empty] | 197 | 177 |  | 104 | 104
[9 empty] | 53.97% | 48.49% |  | 28.49%

## 1.2.10 Durations & Milestone
| Excessive Durations |  |  | Sort by |  |  |  |  | Sort by | Sort by
WBS | Name | Start | Finish | Duration Yrs | Duration Days |  | WBS | Milestone | Start | Finish | Duration
1.2.10.3.4 | Personnel Access Systems | 2006-06-01 08:00 | 2007-06-27 14:00 | 1.0719 | 391.25 |  | 1.2.10.2.1.2.21 | Start Electrical Assembly | 2007-01-05 11:00 | 2007-01-05 11:00 | 0 days
1.2.10.2.1.3.21 | Subsystem Testing | 2009-02-24 09:00 | 2010-03-24 12:00 | 1.0771 | 393.125 |  | 1.2.10.1.3.2.1 | B Primary Beam Complete | 2007-04-02 08:00 | 2007-04-02 08:00 | 0 days
1.2.10.2.1.3.21.1 | Engineering | 2009-02-24 09:00 | 2010-03-24 12:00 | 1.0771 | 393.125 |  | 1.2.10.3.1.3 | Compressed Air Systems | 2007-05-02 10:00 | 2007-05-02 10:00 | 0 days
1.2.10.2.1.3.21.2 | Technical | 2009-02-24 09:00 | 2010-03-24 12:00 | 1.0771 | 393.125 |  | 1.2.10.3.2.4 | Emergency Power Distribution | 2007-05-02 10:00 | 2007-05-02 10:00 | 0 days
1.2.10.2.1.4 | Charged Particle Veto | 2008-08-18 10:00 | 2009-12-18 14:00 | 1.3347 | 487.1667 |  | 1.2.10.1.3.2.2 | Experimental Pit Complete | 2007-06-04 08:00 | 2007-06-04 08:00 | 0 days
1.2.10.2.1.7.2 | Electrical Utilities | 2007-06-04 08:00 | 2008-10-28 11:00 | 1.4031 | 512.125 |  | 1.2.10.2.1.2.1 | Start Mechanical Assembly | 2007-07-02 08:00 | 2007-07-02 08:00 | 0 days
1.2.10.2.1.5.22 | Subsystem Testing | 2008-06-19 11:00 | 2009-12-16 16:00 | 1.4937 | 545.2083 |  | 1.2.10.2.1.7.1.3 | Compressed Air Systems | 2007-07-11 16:00 | 2007-07-11 16:00 | 0 days
1.2.10.2.1.5.22.1 | Engineering | 2008-06-19 11:00 | 2009-12-16 16:00 | 1.4937 | 545.2083 |  | 1.2.10.2.1.7.2.4 | Emergency Power Distribution | 2007-07-11 16:00 | 2007-07-11 16:00 | 0 days
1.2.10.2.1.5.22.2 | Technical | 2008-06-19 11:00 | 2009-12-16 16:00 | 1.4937 | 545.2083 |  | 1.2.10.2.1.1.7 | Deliver HV Membrane | 2007-10-02 08:00 | 2007-10-02 08:00 | 0 days
1.2.10.2.1.7.3 | Safety Systems | 2007-10-03 13:00 | 2009-04-08 11:00 | 1.5148 | 552.9167 |  | 1.2.10.3.3.6 | Fire Suppression Systems | 2008-01-29 09:00 | 2008-01-29 09:00 | 0 days
1.2.10.4.2 | Commissioning | 2009-12-01 08:00 | 2011-06-23 11:00 | 1.5592 | 569.125 |  | 1.2.10.3.3.7 | ODH Detection Systems | 2008-01-29 09:00 | 2008-01-29 09:00 | 0 days
1.2.10.3.3 | Safety Systems | 2007-05-01 08:00 | 2009-03-23 10:00 | 1.8961 | 692.0833 |  | 1.2.10.2.1.1.21 | Install D-4 Magnet Vacuum Box | 2008-04-02 08:00 | 2008-04-02 08:00 | 0 days
1.2.10.3.2 | Electrical Utilities | 2006-10-12 08:00 | 2008-09-23 14:00 | 1.9514 | 712.25 |  | 1.2.10.2.1.5.17 | Start Electrical Assembly | 2008-06-16 08:00 | 2008-06-16 08:00 | 0 days
1.2.10.2.1.5.14 | Deliver Cylindrical Ring Modules | 2007-06-15 08:00 | 2009-06-12 16:00 | 1.9954 | 728.3333 |  | 1.2.10.2.1.1.46 | Start Vacuum Pumping Station | 2008-06-27 08:00 | 2008-06-27 08:00 | 0 days
1.2.10.2.1.3.10 | Deliver Shashlyk Modules | 2007-01-03 08:00 | 2009-05-27 10:00 | 2.3975 | 875.0833 |  | 1.2.10.2.1.1.51 | Vacuum Pump Station Complete | 2008-07-11 12:00 | 2008-07-11 12:00 | 0 days
1.2.10.1.3.2 | C-A Construction Milestones | 2007-04-02 08:00 | 2009-08-31 08:00 | 2.4164 | 882 |  | 1.2.10.1.3.2.3 | Neutral Beam Complete | 2008-09-01 08:00 | 2008-09-01 08:00 | 0 days
1.2.10.2.1.1 | Vacuum | 2007-10-02 08:00 | 2010-03-08 12:00 | 2.4333 | 888.1667 |  | 1.2.10.2.1.1.1 | Start U/S Decay Vessel Assembly | 2008-09-11 08:00 | 2008-09-11 08:00 | 0 days
1.2.10.2.1.5 | Photon Veto | 2007-06-15 08:00 | 2009-12-16 16:00 | 2.5078 | 915.3333 |  | 1.2.10.2.1.1.4 | Install CPV & Supports | 2008-09-18 14:00 | 2008-09-18 14:00 | 0 days
1.2.10.2.1.2.12 | Deliver Modules | 2007-01-05 11:00 | 2009-12-30 11:00 | 2.9863 | 1090 |  | 1.2.10.1.3.2.4 | 25 Mz Cavity Complete | 2008-10-01 08:00 | 2008-10-01 08:00 | 0 days
1.2.10.2.1.2.13 | Stage Modules on Fixtures | 2007-01-05 11:00 | 2009-12-30 11:00 | 2.9863 | 1090 |  | 1.2.10.2.1.7.3.6 | Fire Suppression Systems | 2008-10-28 11:00 | 2008-10-28 11:00 | 0 days
1.2.10.2.1.2.14 | Pre-Testing of Modules | 2007-01-05 11:00 | 2009-12-30 11:00 | 2.9863 | 1090 |  | 1.2.10.2.1.7.3.7 | ODH Detection Systems | 2008-10-28 11:00 | 2008-10-28 11:00 | 0 days
1.2.10.2.1.2.15 | Install Modules in Support Structure | 2007-01-05 11:00 | 2009-12-30 11:00 | 2.9863 | 1090 |  | 1.2.10.2.1.3.1 | Start Mechanical Assembly | 2008-11-28 08:00 | 2008-11-28 08:00 | 0 days
1.2.10.2.1.2.28 | Subsystem Testing | 2007-01-05 11:00 | 2009-12-30 11:00 | 2.9863 | 1090 |  | 1.2.10.2.1.3.16 | Start Electrical Assembly | 2009-02-24 09:00 | 2009-02-24 09:00 | 0 days
1.2.10.2.1.2.28.1 | Engineering | 2007-01-05 11:00 | 2009-12-30 11:00 | 2.9863 | 1090 |  | 1.2.10.2.1.5.1 | Start Mechanical Assembly | 2009-03-10 08:00 | 2009-03-10 08:00 | 0 days
1.2.10.2.1.2.28.2 | Technical | 2007-01-05 11:00 | 2009-12-30 11:00 | 2.9863 | 1090 |  | 1.2.10.2.1.1.31 | Start D/S Vessel Assembly | 2009-07-24 08:00 | 2009-07-24 08:00 | 0 days
1.2.10.2.1.2 | Preradiator | 2007-01-02 08:00 | 2009-12-31 12:00 | 2.9977 | 1094.1667 |  | 1.2.10.2.1.5.16 | Mechanical Ass'y. Complete | 2009-08-11 15:00 | 2009-08-11 15:00 | 0 days
1.2.10.2.1.3 | Calorimeter | 2007-01-03 08:00 | 2010-04-01 10:00 | 3.2441 | 1184.0833 |  | 1.2.10.1.3.2.5 | D-4 Magnet Complete | 2009-08-31 08:00 | 2009-08-31 08:00 | 0 days
1.2.10.2.1.7.1 | Mechanical Utilities | 2007-07-11 16:00 | 2010-10-13 12:00 | 3.2598 | 1189.8333 |  | 1.2.10.2.1.1.45 | D/S Vessel Assembly Complete | 2009-09-02 08:04 | 2009-09-02 08:04 | 0 days
1.2.10.2.1.7 | Conventional Systems | 2007-04-30 08:00 | 2010-10-13 12:00 | 3.458 | 1262.1667 |  | 1.2.10.2.1.6.1 | Start Catcher Assembly | 2009-09-02 08:04 | 2009-09-02 08:04 | 0 days
1.2.10.2.1 | Subsystem Installation | 2007-01-02 08:00 | 2010-10-13 12:00 | 3.7813 | 1380.1667 |  | 1.2.10.2.1.1.30 | D-4 Vacuum Box Complete | 2009-10-09 16:00 | 2009-10-09 16:00 | 0 days
1.2.10.1.3 | Assembly & Services Modeling | 2005-10-03 08:00 | 2009-08-31 08:00 | 3.9123 | 1428 |  | 1.2.10.2.1.5.23 | Electrical Assembly Complete | 2009-12-16 16:00 | 2009-12-16 16:00 | 0 days
1.2.10.3.1 | Mechanical Utilities | 2006-08-10 08:00 | 2010-07-29 14:00 | 3.9705 | 1449.25 |  | 1.2.10.2.1.4.6 | CPV Installed | 2009-12-18 14:00 | 2009-12-18 14:00 | 0 days
1.2.10.1.1 | Subsystem Dimensional Control | 2005-10-03 08:00 | 2009-09-28 15:00 | 3.9898 | 1456.2917 |  | 1.2.10.2.1.2.29 | Electrical Assembly Complete | 2009-12-30 11:00 | 2009-12-30 11:00 | 0 days
1.2.10.1.1.1 | Design | 2005-10-03 08:00 | 2009-09-28 15:00 | 3.9898 | 1456.2917 |  | 1.2.10.2.1.2.20 | Mechanical Assembly Complete | 2009-12-31 12:00 | 2009-12-31 12:00 | 0 days
1.2.10.1.4.2 | Engineering | 2005-10-03 08:00 | 2009-09-28 15:00 | 3.9898 | 1456.2917 |  | 1.2.10.2.1.1.20 | U/S Decay Vessel Assembly Complete | 2010-03-08 12:00 | 2010-03-08 12:00 | 0 days
1.2.10.2.3.1 | Manager | 2005-10-03 08:00 | 2009-09-28 15:00 | 3.9898 | 1456.2917 |  | 1.2.10.2.1.3.22 | Electrical Assembly Complete | 2010-03-24 12:00 | 2010-03-24 12:00 | 0 days
1.2.10.2.3.2 | Engineering | 2005-10-03 08:00 | 2009-09-28 15:00 | 3.9898 | 1456.2917 |  | 1.2.10.2.1.3.15 | Mechanical Assembly Complete | 2010-04-01 10:00 | 2010-04-01 10:00 | 0 days
1.2.10.2.3.3 | Technical Supervisor | 2005-10-03 08:00 | 2009-09-28 15:00 | 3.9898 | 1456.2917 |  | 1.2.10.2.1.6.11 | Catcher Assembly Complete | 2010-06-28 16:04 | 2010-06-28 16:04 | 0 days
1.2.10.2.2 | Installation Equipment | 2006-10-02 08:00 | 2010-09-28 11:00 | 3.9921 | 1457.125 |  |  | Count | 38
1.2.10.2.2.1 | Procurement | 2006-10-02 08:00 | 2010-09-28 11:00 | 3.9921 | 1457.125
1.2.10.2.3.4 | Procurement | 2006-10-02 08:00 | 2010-09-28 11:00 | 3.9921 | 1457.125
1.2.10.4.3.4 | Procurement | 2006-10-02 08:00 | 2010-09-28 11:00 | 3.9921 | 1457.125
1.2.10.1.4.1 | Manager | 2005-10-03 08:00 | 2010-09-23 16:00 | 4.9763 | 1816.3333
1.2.10.3.5.1 | Manager | 2005-10-03 08:00 | 2010-09-23 16:00 | 4.9763 | 1816.3333
1.2.10.3.5.2 | Engineering | 2005-10-03 08:00 | 2010-09-23 16:00 | 4.9763 | 1816.3333
1.2.10.4.3.1 | Manager | 2005-10-03 08:00 | 2010-09-23 16:00 | 4.9763 | 1816.3333
1.2.10.1 | Integration | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.1.4 | Management Activities | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.1.4.3 | Procurement | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.2.3 | Management Activities | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.3 | Conventional Systems | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.3.5 | Management Activities | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.3.5.5 | Procurement | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.4.3 | Management Activities | 2005-10-03 08:00 | 2010-09-28 11:00 | 4.9894 | 1821.125
1.2.10.2 | Detector Installation | 2005-10-03 08:00 | 2010-10-13 12:00 | 5.0306 | 1836.1667
1.2.10 | Systems Integration | 2005-10-03 08:00 | 2011-06-23 11:00 | 5.7236 | 2089.125 | OK
1.2.10.4 | Testing & Commissioning | 2005-10-03 08:00 | 2011-06-23 11:00 | 5.7236 | 2089.125
|  |  | Count Excessive | 57
>1 year
15.62%