## Current design status checklist
CMS CSC Frame status | 234/2 | 2/1 | 3/1 | 1/2 | 1/3 | 4/1 | Notes
When the whole column below (all pages) turns to only "yes" or "NA" entries, we are ready to go to full production on a given chamber frame. Ready now? | no | no | no | no | no | no | ME234/2 frames went to initial production procurement in spring 1999. Others have not yet begun.
base chamber design available from FNAL? | yes | yes | yes | yes | yes | no
basic structural frame design drafted & checked? (may be without integration or alignment or other required features) | yes | yes | yes | yes | not checked | no
basic structural frame prototyped ever? | yes | yes | yes | yes | no | no
frame feature requirements frozen | no | no | no | no | no | no | We need a feature freeze to allow orderly production and a viable project schedule
current (today's) frame design prototyped ever? | maybe | no | no | no | no | no | mostly no, as a consequence of the continuing lack of feature freeze
mounting for 96-channel anode cards removed from frame design? | yes | na | na | na | na | na
mounting for RPC's removed from frame design? | yes | yes | na | na | na | na
datum reference marks added to sheet metal part drawings as applicable (for symmetric parts) for use in QC | no | no | no | no | no | no
cathode connector rivet spotfaces added to design | yes | yes | yes | yes | no | no
existing parts retrofitted for connector rivet spotfaces | yes but uninspected | na | na | na | na | na | 4 of 25 were retrofitted & shipped; 21 were retrofitted but remain to be inspected, on B588696-155
anode card cover design exists | both box & trough | yes | yes | yes | no | partial | To use box style covers, ME1/2 would require either frame redesign, or several special box cover styles; ME2/1 3/1 & 4/1 have anode connectors too close together for box style & so have their own trough styles.
anode card cover prototyped | both box & trough | yes | yes | no | no | no
retrofit anode covers for 1/8 chmfr | na | yes | yes | na | na | na
V1 cathode cooler mounting removed from drawings | yes | no | no | na | na | na | V1 cathode cooler was prototyped in summer 1999 on an ME234/2 prototype; the mount features are present in all ME234/2, ME2/1, and ME3/1 prototypes through June 2000, and in all ME234/2 initial production (25 frames)
mounting for V2 cooling plate for cathode/alct/lvdb defined | yes | no | no | no | no | no | most are waiting for definition from integration
mounting for V2 cooling plate for cathode/alct/lvdb drafted | yes | no | no | no | no | no | most are waiting for definition from integration
mounting for V2 cooling plate for cathode/alct/lvdb prototyped | yes | no | no | no | no | no | most are waiting for definition from integration
existing parts retrofitted for V2 cooling plate mount | yes | na | na | na | na | na | 2 were done @PSL before shipment; 2@FNAL status unknown; 21 in PSL stock rack
cable exit tiedowns defined | no | no | no | no | no | no | at least HV, ALCT output, LV input, cathode output, anode output, alignment
cable exit tiedowns drafted | no | no | no | no | no | no | waiting for definition from integration
cable exit tiedowns prototyped | no | no | no | no | no | no | waiting for definition from integration
existing parts retrofitted for cable exit tiedowns | no | na | na | na | na | na | 2 ME234/2 shipped March 23 to be retrofitted by Sergei Lusin at FNAL; others waiting for definition
drawings revised for cathode/alct/lvdb cooling connection strain relief | yes | partial | partial | no | no | na | requirement added to frames May 2000
existing parts retrofitted for cathode/alct/lvdb cooling connection strain relief | yes | na | no | na | na | na | ME3/1 prototype pair is in mfg now; 2 ME234/2 were done @PSL before shipment; 2@FNAL status unknown; 21 in PSL stock rack
redesigned to accommodate 19-pin Caton HV connectors (from 13-pin & 7-pin Caton) | yes | yes | yes | yes | ? | no
existing parts retrofitted for 19-pin HV connectors | yes | na | na | na | na | na | 4 of 25 ME234/2 were retrofitted & shipped; 21 remain to be inspected
redesigned to accommodate HV grounding & interlock proposed by Florida in mid-May 2000 | no | no | no | no | no | no | requirements TBD
existing parts retrofitted for HV grounding/interlock proposed by Florida in mid-May 2000 | no | na | na | na | na | na | requirements TBD
anode side panel redesigned for ground lugs etc. | yes | yes | no | yes | na | no | Most are waiting for the ME234/2 prototypes to be tried & the base design approved; also ME4/1 waits for locations of anode protection board connectors to be specified by FNAL
anode side panel prototyped for ground lugs etc. | yes | yes | no | no | no | no | ME234/2 qty 2 shipped; 24 received but uninspected
initial prod. Qty anode side panel bid, built & inspected? | bid & built | na | na | na | na | na | bids available for ME234/2 with & without box mount holes at qty 23, 125, & 148; 23 more were ordered for which vendor shipped 24 while we are still waiting for design/functional approval from anode electronics team for full production. Parts arrived while frames project at PSL was being shut down and so inspection was not authorized & not performed
anode cable paths thru frame decided? (notches in extrusion vs. holes in side panel at each location) | yes | yes | yes | ? | yes | yes | Go with protruding-card path for July 2000 prototype of ME1/2, despite known interference with cable tray
anode cable strain relief holes on anode top extrusion drawing? | yes | yes | yes | yes | no | yes | requirements for ME1/3 differ from other chambers and are TBD
existing parts retrofitted for anode cable strain relief? | yes | na | na | na | na | na | 2 of 25 were retrofitted & shipped; 23 & 1 spare remain to be inspected
alignment features included in frame design? | yes | yes | yes | yes | yes | no
gas line integration with frame | no | no | no | no | no | no | requirements TBD. ME1/3 needs gas connector holes in wide end top also, in both PSL and FNAL drawings. (See 5520-ME-368130)
cooling line integration with frame defined? | yes | no | no | no | no | no | requirements for most TBD
drawings for cooling line integration with frame | yes | no | no | no | no | no | waiting for definition from integration
existing parts retrofitted for cooling line integration with frame | partial | no | no | na | na | na | 2 ME234/2 shipped March 23 to be retrofitted by FNAL; 2 ME234/2 shipped May 2000 retrofitted by PSL; qty 21 for ME234/2 bids back; award should be this week.
forgotten items! Add here
PSL on-chamber integration assembly drawing completed | partial | partial | no | no | no | no | waiting for definition from integration
fixed point selection and tolerance reviewed | yes | yes | yes | no | no | yes
prod. Qty/prototype qty/kitting/bulk/shipping defined & signed off | no | no | no | no | no | no
final feature definition of frame signed off | no | no | no | no | no | no | see also requirements freeze, near top of this list
FNAL drawings converged to PSL's in all respects? | no | no | no | no | no | no | PSL does not have funding for checking FNAL duplicate drawings, so detection of discrepencies is incidental to funded work only. (Since FNAL chose to duplicate drawings, it is FNAL's responsibility to assure correctness of their drawings.)
final frame and chamber design prototyped together? | no | no | no | no | no | no
final frame, chamber, electronics, & integration design prototyped together? | no | no | no | no | no | no
Note, frame procurement, integration design, and integration procurement are among the topics beyond the scope of this spreadsheet

## Current procurement status
CMS CSC Frame status |  | layers 2 & 3 only | [6 empty] | approx. % of full production ordered or built
| common parts | ME234/2 | ME2/1 | ME3/1 | ME1/2 | ME1/3 | ME4/1 | Notes
# needed for full endcaps | NA | 144 | 36 | 36 | 72 | 72 | 36 | layer 4 decision impacts most component quantities heavily
# future prototypes (after summer 2000 list of 2 ME2/1, 2 ME3/1, 1 ME1/2) | NA | 0 | 0 | 0 | 0 | 3 | 2 | quantity needs definition/signoff for bidding and ordering full production quantities
frame sets for spare complete chambers | NA | 4 | 2 | 2 | 3 | 3 | 2 | quantity needs definition/signoff for bidding and ordering full production quantities
frame set equivalents of spare parts | NA | 2 | 2 | 2 | 2 | 2 | 2 | quantity needs definition/signoff for bidding and ordering full production quantities
total frame equivalents |  | 150 | 40 | 40 | 77 | 80 | 42
less initial production |  | 25 | 0 | 0 | 0 | 0 | 0 |  | 5.828%
remaining production |  | 125 | 40 | 40 | 77 | 80 | 42
Extrusion stock
Extrusion stock 5185c100-1 (material for most of chamber frame) | full prod received 6/1/00 | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 100
Extrusion stock 5185c100-2 (material for small end of chamber frame) | full prod received 6/1/00 | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 100
Extrusion stock 5185D042 (z-bracket material) | full prod. order on hold due to production difficulties; some matl on hand for prototyping ME1/2, ME1/3 | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | Time critical item; extruders have been unable to reliably meet specifications | 7
End plates
Small end plate 5599B008 | 50 expected 6/4/00, plus 42 shipped or in stock; 2 needed per most chambers | see common parts column | see common parts column | see common parts column | NA | NA | see common parts column |  | 16.91%
End plate 5599B009 | 50 expected 6/4/00 plus 42 shipped or in stock; 2 needed per most chambers | see common parts column | see common parts column | see common parts column | 4 per chamber; 4 expected 6/4/00 | 4 per chamber; 4 expected 6/4/00 | see common parts column |  | 8.532%
Panel bolts
5599B007 (used 2 per z-bracket pair) | 200 rev b expected 5/28/00 plus 190 shipped or in stock | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | no more will be ordered at revision B, which have screwdriver slot on top; use up existing stock and switch to rev c which have slot on bottom | 14.75%
5599B006 | 206 shipped or in stock | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 14.93%
5599B005 | 989 shipped or in stock | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 12.52%
Shims
(5599B003, 5599C004, 5599A042 in 3 thicknesses each) | full prod run received 6/13/00 | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 100
Sheet metal
Stiffener plates (4 required per certain chambers) | 105 received 5/22/00; 8 are for summer 00 ME3/1 prototype pair | 100 shipped or on hand; 4 needed per chamber | see common parts | see common parts | NA | NA | see common parts |  | 19.58%
HV side panel | NA | 4 shipped; 9 in stock; 50 expected 6/12/00 of which 12 are for initial production | 2 ordered beyond prototypes | 2 ordered beyond prototypes | none ordered | none ordered | none ordered |  | 15.62%
big end panel | none ordered beyond prototypes; fit ME234/1 | 2 shipped; full prod qty 150 expected 6/6/00 (1 reqd/frame) | see common parts column | see common parts column | none ordered | none ordered | see common parts column |  | 39.18%
small end panel | NA | initial prod on hand or shipped | none ordered beyond prototypes | none ordered beyond prototypes | none ordered | none ordered | none ordered |  | 8.091%
anode side panel | NA | 2 shipped; bids back for qty 23, 125, & 148; 24 received | 2 received for summer prototypes 5/22/00 | design not completed, so even prototypes not yet in procurement | none ordered | none ordered | none ordered |  | 6.443%
Z brackets
generic (4 types for big end) | 25 ME234/2 frames worth built; 4 frames worth shipped; drawing from existing stock for 2 ME2/1 & 2 ME3/1 & 1 ME1/2 prototypes, leaving 16 ME234/2 frames worth on hand | see common parts column | see common parts column | see common parts column | see common parts column | NA | see common parts column | all z brackets are on production hold to conserve material for prototyping until the extrusion production problem is resolved | 7.163%
generic (2 types for 3-point mount at small end) | 25 ME234/2 frames worth built; 4 frames worth shipped; drawing from existing stock for 2 ME2/1 & 2 ME3/1 prototypes, leaving 17 ME234/2 frames worth on hand | see common parts column | see common parts column | see common parts column | NA | NA | see common parts column | see above | 9.191%
ME1/2 specials (4 types) | NA | NA | NA | NA | none ordered | NA | NA | see above | 0
ME1/3 specials (8 types) | NA | NA | NA | NA | NA | none ordered | NA | see above | 0
Frame extrusions
HV top | NA | 4 shipped; 21 here | none ordered beyond prototypes | none ordered beyond prototypes | none ordered | none ordered | none ordered |  | 5.828%
HV bottom | NA | 4 shipped, 21 shippable | none ordered beyond prototypes | none ordered beyond prototypes | none ordered | none ordered | none ordered |  | 5.828%
Anode top | NA | 4 shipped; 21 here | none ordered beyond prototypes | none ordered beyond prototypes | none ordered | none ordered | none ordered |  | 5.828%
Anode bottom | NA | 4 shipped, 21 shippable | none ordered beyond prototypes | none ordered beyond prototypes | none ordered | none ordered | none ordered |  | 5.828%
Big end top | none ordered beyond prototypes | 4 shipped; 21 here | see common parts column | see common parts column | none ordered | none ordered | see common parts column |  | 5.828%
Big end bottom | none ordered beyond prototypes | 25 shipped | see common parts column | see common parts column | none ordered | none ordered | see common parts column |  | 5.828%
Small end top | NA | 25 shipped | none ordered beyond prototypes | none ordered beyond prototypes | none ordered | none ordered | none ordered |  | 5.828%
Small end bottom | NA | 25 shipped | none ordered beyond prototypes | none ordered beyond prototypes | none ordered | none ordered | none ordered |  | 5.828%
Misc.
Alignment pins 5599B066A | will have 36 left after ME3/1, ME1/2 prototypes ship June & July 2000; 60 more expected 5/26/00 | 8 shipped (4 chambers worth) | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | discrepancy of +4 found in June 20 200 inventory | 12.82%
Fasteners
M10-1.5 thin nuts | 3001 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 10.2%
M10-20 od flat washer | 1076 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 13.57%
M10-30 od flat washer | 293 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 11.08%
M6-1x10 thd forming screw | 4115 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 15.64%
1/4" int-ext toothed lock washer | 3045 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 11.58%
m6-1x16 thd forming screw | 1176 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 11.32%
m6 int toothed lock washer | 1257 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 13.5%
m6-1x12 flat head hex socket screw | 294 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 11.12%
3/8-24 hex jam nut steel | 102 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 13.14%
3/8 snap ring | 189 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 24.36%
10mm snap ring | 679 shipped or on hand | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column | see common parts column |  | 25.68%
Note, no integration components are listed above; there will be of order 100,000 pieces required for on-chamber integration