## Control Panel
| Title | Sample Development
| As of Date | 2003-08-15 | Date Calculator |  | D-O-W
| Week Before | 2003-08-15 | Start | 2003-08-15 | 2003-08-15
|  |  | Workdays | 10
| Activity | Value | Complete | 2003-08-28 | 2003-08-28
Act #1 | Design | 3
Act #2 | Code | 2
Act #3 | Test | 3
| Delta Lower | 0.3
You may define up to 3 activities
Act #1 and Act #2 are optional
You must define Act #3 and place completion dates in the third activity column
Summary
| as of | 2003-08-15
To Date: | Planned Pts | 0
| Actual Pts | 0
| % Complete | 0%
| % (A-P) | 0%
Note on G4: Enter a Start date and the number of work days to complete
Note on H7: Date on whick work will complete (work day count includes start day and complete day)

## Tracking
| As of Date | 2003-08-15
| Trend start | 2003-08-15
| Period | 7 |  | Planned dates in red are not workdays | Actual dates in red are after the 'as of' date |  |  | Planned dates in red are not workdays
Activity Weight
| Total Activity Weight | 8 |  |  | 3 | 2 | 3
Index | Item | Item Weight | Assigned to | Start | Design | Code | Test | Complete | Work Days | Earned | Flag
|  |  |  | Planned | Actual | Actual | Actual | Planned |  |  |  | 2003-08-15 | 2003-08-22 | 2003-08-29 | 2003-09-05 | 2003-09-12 | 2003-09-19 | 2003-09-26 | 2003-10-03 | 2003-10-10 | 2003-10-17 | 2003-10-24 | 2003-10-31 | 2003-11-07
1 | ACInput | 10 | GH | 2003-08-18 | * | * | * | 2003-08-29 | 10 | 0 |  | 2003-08-22: actv; 2003-08-29: due
2 | ACParse | 10 | GH | 2003-09-02 | * | * | * | 2003-09-12 | 9 | 0 |  | 2003-09-05: actv; 2003-09-12: due
3 | ACFormat | 10 | GH | 2003-09-15 | * | * | * | 2003-09-26 | 10 | 0 |  | 2003-09-19: actv; 2003-09-26: due
4 | ACError | 5 | GH | 2003-09-29 | * | * | * | 2003-10-03 | 5 | 0 |  | 2003-10-03: due
5 | BTComplex | 10 | GH | 2003-10-06 | * | * | * | 2003-10-17 | 10 | 0 |  | 2003-10-10: actv; 2003-10-17: due
6 | BTHours | 10 | GH | 2003-10-20 | * | * | * | 2003-10-31 | 10 | 0 |  | 2003-10-24: actv; 2003-10-31: due
7 | BTGraph | 5 | GH | 2003-11-03 | * | * | * | 2003-11-07 | 5 | 0 |  | 2003-11-07: due
8 | BTOutput | 10 | FE | 2003-10-13 | * | * | * | 2003-10-24 | 10 | 0 |  | 2003-10-17: actv; 2003-10-24: due
9 | BTForm | 10 | FE | 2003-10-27 | * | * | * | 2003-11-07 | 10 | 0 |  | 2003-10-31: actv; 2003-11-07: due
10 | RAReadout | 5 | FE | 2003-08-18 | * | * | * | 2003-08-22 | 5 | 0 |  | 2003-08-22: due
11 | RARecall | 5 | FE | 2003-08-25 | * | * | * | 2003-08-29 | 5 | 0 |  | 2003-08-29: due
12 | RADrop | 10 | FE | 2003-09-02 | * | * | * | 2003-09-12 | 9 | 0 |  | 2003-09-05: actv; 2003-09-12: due
13 | RAMarkup | 10 | FE | 2003-09-15 | * | * | * | 2003-09-26 | 10 | 0 |  | 2003-09-19: actv; 2003-09-26: due
14 | STFile | 10 | FE | 2003-09-29 | * | * | * | 2003-10-10 | 10 | 0 |  | 2003-10-03: actv; 2003-10-10: due
15 | STYear | 10 | AV | 2003-09-02 | * | * | * | 2003-09-12 | 9 | 0 |  | 2003-09-05: actv; 2003-09-12: due
16 | STError | 10 | AV | 2003-09-15 | * | * | * | 2003-09-26 | 10 | 0 |  | 2003-09-19: actv; 2003-09-26: due
17 | STPut | 10 | AV | 2003-09-29 | * | * | * | 2003-10-10 | 10 | 0 |  | 2003-10-03: actv; 2003-10-10: due
18 | STBuffer | 10 | AV | 2003-10-13 | * | * | * | 2003-10-24 | 10 | 0 |  | 2003-10-17: actv; 2003-10-24: due
19 | STNew | 10 | JC | 2003-09-02 | * | * | * | 2003-09-12 | 9 | 0 |  | 2003-09-05: actv; 2003-09-12: due
20 | STClose | 5 | JC | 2003-09-15 | * | * | * | 2003-09-19 | 5 | 0 |  | 2003-09-19: due
21 | STNew | 10 | JC | 2003-09-22 | * | * | * | 2003-10-03 | 10 | 0 |  | 2003-09-26: actv; 2003-10-03: due
| Sum | 185 | [7 empty] | 0 | Plan |  | 40 | 160 | 160 | 480 | 520 | 760 | 880 | 1040 | 1120 | 1280 | 1360 | 1480
[10 empty] | 0 | Actual |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[10 empty] | 1480 | Baseline |  | 1192 | 1104 | 1248 | 1248 | 1388 | 1480 | 1480 | 1480 | 1480 | 1480 | 1480 | 1480
[10 empty] | 0.3 | Lower |  | 0 | 0 | 0 | 249.6 | 259.6 | 544 | 700 | 908 | 1012 | 1220 | 1324 | 1480
[10 empty] | 0% | Plan (%) |  | 3.356% | 14.49% | 12.82% | 38.46% | 37.46% | 51.35% | 59.46% | 70.27% | 75.68% | 86.49% | 91.89% | 100%
[10 empty] | 0% | Actual (%) |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[11 empty] | Lower (%) |  | 0% | 0% | 0% | 20% | 18.7% | 36.76% | 47.3% | 61.35% | 68.38% | 82.43% | 89.46% | 100%
Note on A6: Column for preserving order after sort
Note on B6: Work items to be accomplished
Note on C6: Relative size, complexity, or difficulty of an item
Note on D6: Resource assigned (usually a person or team)
Note on E6: Date on which activity will start for this work item
Note on F6: Activity 1 actual completion date (must be either an * or a valid date)
Note on G6: Activity 2 actual completion date (must be either an * or a valid date)
Note on H6: Activity 3 actual completion date (must be either an * or a valid date)
Note on I6: Date on which activity will complete for this work item
Note on J6: Number of workdays including start date and completion date
Note on K6: Number of points accumulated for this work item
Note on L6: Flag for late items (activity 3 is not complete and 'as of' date is past the planned completion date)

## Tracking Chart (Points)
As of
8/15/2003
Sample Development