## ChamberCommon Pts. (not frames)
size | Dwg # | Description | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Qty |  | Total Reqd | (Old) Est. | Jan. 18 '00 | 2000-05-17 | 2000-05-17 | Rounded |  | Order | ME234/2 |  | FNAL |  | Actual (blk)
|  | Common Parts for All Chambers (ex. Frames) | ME1/2 |  | ME1/3 |  | ME2/1 |  | ME3/1 |  | ME4/1 |  | ME234/2 |  | Qty | Buy Qty | Est. Buy | Spare | Plan | Plan |  | From | Prod.Code | Comments | Procurement | P0 # | or Est (red)
|  | Total Number of Chambers to be Produced | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | (Pcs UOS) |  | % | Qty | Qty | Extra/Short |  | G.A. 8/11/99 |  | Status (3/14/00) |  | $/piece
A | 106778 | PNPI Kapton, Adhes Back, 1.0" x .002" x 36 yd. (rolls) | 0 | 0 | 0 | 0 | 0.015432 | 0.61728 | 0.027006 | 1.0802 | 0.027006 | 1.0802 | 0 | 0 | 2.7778
A | 274450 | Kapton Non-Adhesive 4" x .002" x 100 yd (roll) |  | 1 |  | 1 |  | 0.666 |  | 0.666 |  | 0.666 |  | 0 | 3.998
A | 368005 | Stud, Center Gap Bar, 5-40 UNC x 5.93" | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 4 | 600 | 1144 | 1100 | 1100 | 5 | 1201.2 | 1200 | -100 | Industry | EPQ |  | 140 in Stock, option to PNPI for 1100 | PO 526820 | 2.26
A | 368006 | Nut, Center Gap Bar Stud, 5-40 UNC | 4 | 304 | 4 | 304 | 4 | 160 | 4 | 160 | 4 | 160 | 8 | 1200 | 2288 | 2200 | 2200 | 5 | 2402.4 | 2400 | -200 | Industry | EPQ |  | 280 in stock, option to PNPI for 2200 | PO 526820 | 2.98
A | 368012 | Mounting Plate, HV Terminal | 3 | 228 | 3 | 228 | 3 | 120 | 3 | 120 | 3 | 120 | 5 | 750 | 1566 | 1500 | 1600 | 10 | 1722.6 | 1700 | -100 | Industry | EPQ | Ordered 1500 from PNPI+175 Basic | 175 in stock, option to PNPI for 1500 | PO 526820 | 1.98
A | 368014 | Copper Foil Roll 2.75" x .002" x 235 ft. (roll) | 0.14894 | 11.3191 | 0.14894 | 11.3191 | 0.14894 | 5.9574 | 0.14894 | 5.9574 | 0.14894 | 5.9574 | 0.21277 | 31.9149 | 72.4255 | 16000 | 17000 | 10 | 0.33901 |  | 17000 | Industry | EPQ | 235 ft/roll, 6 rolls already in stock | 12 in stock, option for 58 | PO 526370 | 41.25
A | 368015 | Screw, Pan Head Phillips, Stainless 6-32UNC x 3/8" | 6 | 456 | 6 | 456 | 6 | 240 | 6 | 240 | 6 | 240 | 10 | 1500 | 3132 | 3000 | 3100 | 10 | 3445.2 | 3500 | ?? | Industry | EPQ |  | 4500 in stock | LA483 | 0.0235
A | 368019 | Wire, Gold Plated Tungsten, 50 micron dia.(.002") 2.6km | 1.5 | 114 | 1.5 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 450 | 678 | 735 | 735 | 10 | 745.8 | 750 | -15 | Industry | EPK | chd 11/15/99 | 110 in stock, option for 625 | PO 526044 | 302.9
A | 368020 | O-Ring, Fluorocarbon., 9/16"ID x 3/4" OD, #2-113 parker | 196 | 14896 | 184 | 13984 | 208 | 8320 | 196 | 7840 | 184 | 7360 | 284 | 42600 | 95000 | 85000 | 90000 | 10 | 104500 | 104500 | -14500 | Industry | EPQ |  | 10K in stock, option for 80K | PO 525248 | 0.22
A | 368022 | Bulkhead Connector, male 1/4 NPT to 1/4" tube | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 800 | 800 | 5 | 886.2 | 900 | -100 | Industry | EPQ | updated 8/30/99 was rev B | 800 in stock | LA468 | 8.6
A | 368026 | Screw, Pan Head Phillips, clear polycarb. #4-40 x 3/8 | 24 | 1824 | 24 | 1824 | 24 | 960 | 24 | 960 | 24 | 960 | 48 | 7200 | 13728 | 13000 | 14000 | 10 | 15100.8 | 15100 | -1100 | Industry | EPQ | Hold | 18K in stock | LA492 | 0.099
A | 368027 | Cable Tie, Nylon, 4" lg x .100", Mc Mast #7130K12 | 13 | 988 | 13 | 988 | 13 | 520 | 13 | 520 | 13 | 520 | 21 | 3150 | 6686 | 6300 | 6400 | 5 | 7020.3 | 7000 | -600 | Industry | EPQ |  | 7100 in stock | LA476 | 0.0147
A | 368033 | Label, Test Strip Connector | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 400 | 400 | 5 | 443.1 | 440 | -40 | R. Jensen | EPQ |  | Ordered 3K on 11/5/99 | - | 0.0157
A | 368034 | RTV 41 Rubber & Catalyst RTV 9811 (liters) | 0.2 | 15.2 | 0.2 | 15.2 | 0.2 | 8 | 0.2 | 8 | 0.2 | 8 | 0.2 | 30 | 84.4 | 0 | 84.4 | 20 | 101.28 | 101
A | 368042 | Lug, Ground, .25 push on, male | 30 | 2280 | 24 | 1824 | 30 | 1200 | 30 | 1200 | 30 | 1200 | 30 | 4500 | 12204 | 0 | 0 | 10 | 13424.4 | 13500
ES | 368047 | Wire, Gold Plated Be/Cu, 200 u, (008") dia (5k'/spool) (km) | 0.1 | 7.6 | 0.1 | 7.6 | 0.1 | 4 | 0.1 | 4 | 0.1 | 4 | 0.15 | 22.5 | 49.7 | 50 km | 50 km/ 30 spools | 10 | 54.67 | 60 | -10 | Industry | EPK | dwg released. | 30 spools in stock | PO 526703 | 475
B | 368048 | Lead Wire Assembly, High Voltage 4" long (pieces) | 18 | 1368 | 18 | 1368 | 18 | 720 | 18 | 720 | 18 | 720 | 30 | 4500 | 9396 | 8600 | 9000 | 5 | 9865.8 | 9900 | -900 | Industry | EPP | Order Assembled | 1950 in stock, option for 7050 | PO 525367 | 1.38
A | 368049 | Lead Wire, High Voltage, white (1000' spool) (ft.) | 6 | 456 | 6 | 456 | 6 | 240 | 6 | 240 | 6 | 240 | 10 | 1500 | 3132 | 3 | 3 | 5 | 3288.6 | 3300 | -3297 | Industry | EPP | Part of 368048 | Part of 368048 | -
A | 368092 | Connect. Assy, 34 Pin Cath. Strip Output w grd strip | 30 | 2280 | 24 | 1824 | 30 | 1200 | 30 | 1200 | 30 | 1200 | 30 | 4500 | 12204 | 11500 | 12000 | 10 | 13424.4 | 13400 | -1400 | Industry | EPN |  | To be assembled in MP9 | - | 0
A | 368093 | Resistor, 51 ohm, 1/2w carbon | 12 | 912 | 12 | 912 | 12 | 480 | 12 | 480 | 12 | 480 | 12 | 1800 | 5064 | 4700 | 4800 | 5 | 5317.2 | 5300 | -500 | Industry | EPN |  | 5K in stock | LA484 | 0.092
A | 368094 | Resistor 51 ohm, 1/2 watt, with bent leads | 12 | 912 | 12 | 912 | 12 | 480 | 12 | 480 | 12 | 480 | 12 | 1800 | 5064 | 4700 | 4800 | 5 | 5317.2 | 5300 | -500 | Industry | EPN | Make from 368093 | To be assembled in MP9 | TSG0622 | 0
A | 368095 | Plug, Miniature Banana, 2mm dia. Red | 18 | 1368 | 18 | 1368 | 18 | 720 | 18 | 720 | 18 | 720 | 30 | 4500 | 9396 | 8600 | 9000 | 5 | 9865.8 | 9900 | -900 | Industry | EPO | Part of 368048 | Part of 368048 | - | 0
A | 368096 | Plug, Miniature Lemo connector, Kings-Lemo # 1075-1 | 6 | 456 | 6 | 456 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 2532 | 2300 | 2400 | 5 | 2658.6 | 2700 | -300 | Industry | EPN | Part of 368099 | 2300 in stock, option for 100 | PO 526380 | 4.99
A | 368097 | Connector, Adapter, Mini Lemo Socket | 6 | 456 | 6 | 456 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 2532 | 2300 | 2400 | 5 | 2658.6 | 2700 | -300 | Industry | EPN |  | 2500 in stock | PO 526614 | 5.36
A | 368098 | Cable, Coaxial, RG174/U (1000 ft. spool) (ft.) | 8 | 608 | 8 | 608 | 8 | 320 | 8 | 320 | 8 | 320 | 8 | 1200 | 3376 | 32 | 32 | 0 | 3376 | 3400 | -3368 | Industry | EPN | Part of 368099 | 3 rolls in stock | LA500
B | 368099 | Cable Assembly, Test | 6 | 456 | 6 | 456 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 2532 | 2300 | 2400 | 5 | 2658.6 | 2700 | -300 | Industry | EPN |  | To be assembled in MP9 | TSG0620 | 0
A | 368100 | Target, Retro-Reflective | 8 | 608 | 8 | 608 | 8 | 320 | 8 | 320 | 8 | 320 | 8 | 1200 | 3376 | 3100 | 3200 | 5 | 3544.8 | 3500 | -300 | Industry | EPQ |  | 280 in stock, option for 2920 | PO 526651 | 8.25
A | 368114 | SIP 1Meg, 8 pin Resistor Network | 30 | 2280 | 24 | 1824 | 30 | 1200 | 30 | 1200 | 30 | 1200 | 30 | 4500 | 12204 | na | 6500 | 10 | 13424.4 | 13400 | -6900 | Industry | EPN |  | Order
A | 368115 | SIP 1Meg, 10 pin Resistor Network | 30 | 2280 | 24 | 1824 | 30 | 1200 | 30 | 1200 | 30 | 1200 | 30 | 4500 | 12204 | na | 6500 | 10 | 13424.4 | 13400 | -6900 | Industry | EPN |  | Order
A | 368116 | Street Elbow 1/4" male to 1/4" female NPT | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 0 | 0 | 5 | 886.2 | 900 | -900 | Industry
A | 368117 | St. Adapter, 12 mm OD tube compression to 1/4" male NPT | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 0 | 0 | 5 | 886.2 | 900 | -900 | Industry
A | 368118 | Heat Shrink Tubing, 1/8" ID, Polyolefin 500' roll (feet) | 2.25 | 171 | 2.25 | 171 | 2.25 | 90 | 2.25 | 90 | 2.25 | 90 | 3.75 | 562.5 | 1174.5 | 0 | 0 | 10 | 1291.95 | 1500 | -1500 | Industry | EPP | Rework item #18 368048 | Spoke to Linda 10/31, ECO going thru
A | 368119 | CAPLUG .75 Inside Dia.polyethylene/red | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 0 | 0 | 5 | 886.2 | 900 | -900
A | 368248 | Spacer Bar | 12 | 912 | 12 | 912 | 12 | 480 | 12 | 480 | 12 | 480 | 24 | 3600 | 6864 | 6500 | 6500 | 5 | 7207.2 | 7200 | -700 | Florida U | EPQ | Andrey Korytov @ (352)392-3482 | Ordered 875 from UF, exercise option for 5625 | PO 525253 | -
A | 368250 | Pin, Fiberglass, 1/8" dia. For Wire fixation bar location | 54 | 4104 | 54 | 4104 | 54 | 2160 | 54 | 2160 | 54 | 2160 | 90 | 13500 | 28188 | 26000 | 27300 | 5 | 29597.4 | 29600 | -2300 | Florida U. | EPL | Andrey Korytov @ (352)392-3483 | Ordered 3200 from UF, exercise option for 24100 | PO 525253 | -
A | 368252 | Pin, brass .84" lg for strip connector | 60 | 4560 | 48 | 3648 | 60 | 2400 | 60 | 2400 | 60 | 2400 | 60 | 9000 | 24408 | 22500 | 23500 | 10 | 26848.8 | 26800 | -3300 | Industry | EPN |  | 2100 in stock, option to PNPI | PO 526820 | 0.6
A | 368254 | Resistor, 4.7M ohm, 1/2w with Bent Leads | 384 | 29184 | 192 | 14592 | 672 | 26880 | 576 | 23040 | 576 | 23040 | 384 | 57600 | 174336 | 150000 | 157000 | 5 | 183052.8 | 183100 | -26100 | Industry | EPO | Make from 368255 | To be assembled in MP9 | TSG 0622 | 0
A | 368255 | Resistor, Carbon 4.7 M ohm, 1/2 W | 384 | 29184 | 192 | 14592 | 672 | 26880 | 576 | 23040 | 576 | 23040 | 384 | 57600 | 174336 | 150000 | 157000 | 5 | 183052.8 | 183100 | -26100 | Industry | EPO |  | 150000 in stock, option for 7000 | PO 525997 | 0.081
A | 368256 | Resistor, 1.0 M ohm, 1/2w with bent Leads | 36 | 2736 | 36 | 2736 | 36 | 1440 | 36 | 1440 | 36 | 1440 | 60 | 9000 | 18792 | 18000 | 18200 | 5 | 19731.6 | 19700 | -1500 | Industry | EPO | Make from 368257 | To be assembled in MP9 | TSG 0622 | 0
A | 368257 | Resistor, Carbon 1.0 Mohm, 1/2 W | 36 | 2736 | 36 | 2736 | 36 | 1440 | 36 | 1440 | 36 | 1440 | 60 | 9000 | 18792 | 18000 | 18200 | 5 | 19731.6 | 19700 | -1500 | Industry | EPO |  | 18000 in Stock | LA 482 | 0.092
A | 368258 | Capacitor with Bent Leads (Config. #1) | 384 | 29184 | 192 | 14592 | 672 | 26880 | 576 | 23040 | 576 | 23040 | 384 | 57600 | 174336 | 150000 | 158500 | 5 | 183052.8 | 183100 | -24600 | Industry | EPN | Make from 368272 | To be assembled in MP9 | TSG 0618 | -
A | 368259 | Capacitor - 1 nf Ceramic DHR15 Y5P 102M 7.5kV | 420 | 31920 | 228 | 17328 | 708 | 28320 | 612 | 24480 | 612 | 24480 | 444 | 66600 | 193128 | 175000 | 176600 | 5 | 202784.4 | 202800 | -26200 | Industry | EPN |  | Ordered 176600 on 11/10/99 (G.A.) | PO 133499 | 0.07
A | 368260 | Capacitor with Bent Leads (Config. #2) | 36 | 2736 | 36 | 2736 | 36 | 1440 | 36 | 1440 | 36 | 1440 | 60 | 9000 | 18792 | 18000 | 18100 | 5 | 19731.6 | 19700 | -1600 | Industry | EPN | Make from 368273 | To be assembled in MP9 | TSG 0618 | -
A | 368261 | Nut, Bulkhead Connector, Chamfered OBSOLETE 10/2/01 | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 800 | 800 | 5 | 886.2 | 800 | 0 | Industry | EPQ | Make from std. part | 800 in stock | PO 526046 | 0.93
C | 368262 | Board, Protection, Assembly "ME234/2 ONLY" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3600 | 3600 | 3600 | 4000 | 10 | 3960 | 4000 | 0 | Industry | EPM | Purchase Assembled, supply parts | 840 instock, option for 3160 | PO 133478 | 7
D | 368263 | Board, Protection, Finished, made from ES-368264 mat'l. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 3600 | 3600 | 9600 | 4000 | 10 | 3960 | 4000 | 0 | Industry | EPM | Purchase Assembled, supply parts | Vendor to procure | - | 0
A | 368273 | Connector, 6 Pin Strip Header | 96 | 7296 | 48 | 3648 | 168 | 6720 | 144 | 5760 | 144 | 5760 | 144 | 21600 | 50784 | 58000 | - | - | - | - | - | Industry | EPM | Make from 368274 | Vendor to procure | - | 0
A | 368274 | Connector, 36 Pin Strip, Sullins # S1012-36-ND | 24 | 1824 | 12 | 912 | 42 | 1680 | 36 | 1440 | 36 | 1440 | 24 | 3600 | 10896 | 9600 | - | - | - | - | - | Industry | EPM | Make into 368273 | Vendor to procure | - | 0
A | 368276 | Diode, Mot. # BAV99LT1, or Allied # 858-2469; Surf. Mt., case SOT-23 | 384 | 29184 | 192 | 14592 | 672 | 26880 | 576 | 23040 | 576 | 23040 | 384 | 57600 | 174336 | #REF! | - | - | - | - | - | Industry | EPM | Used on 368262 & 368307 | Vendor to procure | - | 0
A | 368278 | Resistor, 15 ohm, 1/4w, 5% carbon comp. thru hole mt.; | 384 | 29184 | 192 | 14592 | 672 | 26880 | 576 | 23040 | 576 | 23040 | 384 | 57600 | 174336 | 150000 | - | - | - | - | - | Industry | EPM | Used on 368262 & 368307 | Vendor to procure | - | 0
A | 368279 | Resistor, 10 ohm, 1/4w, 1%, surface mount, case 1206; | 384 | 29184 | 192 | 14592 | 672 | 26880 | 576 | 23040 | 576 | 23040 | 384 | 57600 | 174336 | 150000 | - | - | - | - | - | Industry | EPM | Used on 368262 & 368307 | Vendor to procure | - | 0
A | 368280 | Braid, Flat Copper, Chem Wik #10-100L (100' spool) | 0.1 | 7.6 | 0.1 | 7.6 | 0.1 | 4 | 0.1 | 4 | 0.1 | 4 | 0.1 | 15 | 42.2 | 40 | 42 | 10 | 46.42 | 0 | 42 | Industry | EPV |  | 37 rolls in stock, increase by 2 rolls | PO 368280 | 39.63
A | 368282 | Spring Pin, SS 0.1" dia x 1/2" | 60 | 4560 | 48 | 3648 | 60 | 2400 | 60 | 2400 | 60 | 2400 | 60 | 9000 | 24408 | 23500 | 25000 | 10 | 26848.8 | 26800 | -1800 | Industry | EPN | ok to buy nsc 9/7 | 23500 in stock, 1500 to be ordered | LA 499 | 0.03
A | 368283 | Connector, Latch Ejector, 34 Pin w/ long latch | 30 | 2280 | 24 | 1824 | 30 | 1200 | 30 | 1200 | 30 | 1200 | 30 | 4500 | 12204 | 11700 | 12000 | 10 | 13424.4 | 13400 | -1400 | Industry | EPN | Part of 368092 | Ordered ~11700 on 11/5/99 (G.A.) | PO 526397 | 1.02
A | 368285 | Connector, 34 St. Pin Latch Ejector .100x.100 no latch | 24 | 1824 | 12 | 912 | 42 | 1680 | 36 | 1440 | 36 | 1440 | 24 | 3600 | 10896 | 9600 | - | - | - | - | - | Industry | EPN | Part of 368263 | Vendor to procure | -
A | 368287 | Wire, Gold Plated Tungsten, 50 micron dia.(.002") 1.5 km | 0 | 0 | 0 | 0 | 3 | 120 | 3 | 120 | 3 | 120 | 0 | 0 | 360 | 250 | 265 | 10 | 396 | 400 | -135 | Industry | EPK | chd 11/15/99 | 30 in stock, option for 235 | PO 526044 | 172
A | 368288 | Epoxy, 3M-2216, Parts A and B (50/50%) (qt. cans each part) | 0.31 | 23.56 | 0.31 | 23.56 | 0.41 | 16.4 | 0.41 | 16.4 | 0.41 | 16.4 | 1 | 150 | 246.32 | 0 | 340 | 20 | 350 | 350
A | 368289 | Epoxy Resin Epolite 5313 (90%) & (resin cans 1 qt. ea.) Hard, DETA (10%) [hardener cans 2 oz. ea.] | 0.16 | 12.16 | 0.16 | 12.16 | 0.21 | 8.4 | 0.21 | 8.4 | 0.21 | 8.4 | 0.4 | 60 | 109.52 | 0 | #REF! | 20 | 131.424
A | 368291 | ALMIT Solder, w/Flux cored, KR-19 SHrma, .65mm (roll) | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 400 | 420 | 10 | 464.2 | 500 | -80 | Industry | EPV |  |  | -
A | 368300 | Tape, Dbl Sided Adhes, .002" x 1" wide 3M 966 (36yd) (rolls) | 1.1111 | 84.4444 | 1.1 | 83.6 | 1.3889 | 55.5556 | 1.3889 | 55.5556 | 1.3889 | 55.5556 | 1.8519 | 277.7778 | 612.4889 | 600 | 650 | 10 | 6.2383 | 10 | 640 | Industry | EPW | chd 12/15/99 | 216 rolls in stock, option for 434 | LA 474 | 9.65
A | 368303 | Shim, Corner Heavy | 0 | 0 | 0 | 0 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 1620 |  |  |  | 1620 | 1600 | -1600
A | 368304 | Mylar Tape, 3 mil x .375" wide no adhesive (1650 ft.) (rolls) | 0.048485 | 3.6848 | 0.048485 | 3.6848 | 0.051515 | 2.0606 | 0.048485 | 1.9394 | 0.048485 | 1.9394 | 0.090909 | 13.6364 | 26.9455 | 25 | 28 | 10 | 0.017964 | 0 | 28 | Industry | EPW |  | Ordered 41K ft on 11/10/99 (G.A.) | PO 526252 | 0.0112
A | 368305 | Sleeve, Gas (0+4+6(5)+4+6(5)+4+0) | 24 | 1824 | 22 | 1672 | 24 | 960 | 24 | 960 | 24 | 960 | 24 | 3600 | 9976 | #REF! | 9450 | 5 | 10474.8 | 10500 | -1050 | Florida U. | EPQ | Andrey Korytov @ (352)392-3482 | 900 in stock, option for 8550 | - | -
C | 368307 | Board, Protection, Assembly "All Except ME234/2" | 24 | 1824 | 12 | 912 | 42 | 1680 | 36 | 1440 | 36 | 1440 | 0 | 0 | 7296 | 5800 | 6400 | 10 | 8025.6 | 8000 | -1600 | Industry | EPM | Purchase Assembled, supply parts | 310 in stock, option for 6090 | PR 134071
D | 368308 | Board, Protection, Finished, made from ES-368264 mat'l. | 24 | 1824 | 12 | 912 | 42 | 1680 | 36 | 1440 | 36 | 1440 | 0 | 0 | 7296 | 5800 | 6400 | 10 | 8025.6 | 8000 | -1600 | Industry | EPM |  | Vendor to procure | -
A | 368328 | Screw, Pan Head Phillips, Polycarb 6-32UNC x 3/8" | 6 | 456 | 6 | 456 | 6 | 240 | 6 | 240 | 6 | 240 | 10 | 1500 | 3132 | 3000 | 3200 | 10 | 3445.2 | 3400 | -200 | Industry | EPQ |  | 6000 in stock | LA 492 | 0.157
A | 368424 | Tape, Dbl Sided Adhesive, .002" x 1/4" wide x 72 yds. (rolls) | 0.55556 | 42.2222 | 0.55556 | 42.2222 | 0.69444 | 27.7778 | 0.69444 | 27.7778 | 0.69444 | 27.7778 | 0.92593 | 138.8889 | 306.6667 | 307 | 307 | 10 | 337.3333 | 300 | 7 | Industry |  | New 3/22/00
A | 368427 | Connector, 4 Pin Strip Header | 24 | 1824 | 12 | 912 | 42 | 1680 | 36 | 1440 | 36 | 1440 | 0 | 0 | 7296 | 58000 | - | - | - | - | - | Industry | EPM | Make from 368274 | Vendor to procure | -
A | 368428 | Connector, 5 Pin Strip Header | 24 | 1824 | 12 | 912 | 42 | 1680 | 36 | 1440 | 36 | 1440 | 0 | 0 | 7296 | 58000 | - | - | - | - | - | Industry | EPM | Make from 368274 | Vendor to procure | -
A | 368461 | Tape, Teflon Sealing, 1/2" x 260" roll (rolls) | 0.061538 | 4.6769 | 0.061538 | 4.6769 | 0.061538 | 2.4615 | 0.061538 | 2.4615 | 0.061538 | 2.4615 | 0.061538 | 9.2308 | 25.9692 | 0 | 0 | 10 | 28.5662 | 30 rolls | (15 rolls) | Industry
B | 368523 | HV Cable Mounting Block | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 0 | 0 | 10 | 464.2 | 450
B | 368524 | HV Chamber Cable Connector Channel Cover | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 0 | 0 | 10 | 464.2 | 450
A | 368525 | Screw, Pan Hd Thd Form M6-40 for Cable Cover | 4 | 304 | 4 | 304 | 4 | 160 | 4 | 160 | 4 | 160 | 4 | 600 | 1688 | 0 | 0 | 10 | 1856.8 | 2000
A | 368526 | Grommet Buna-N | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 0 | 0 | 10 | 464.2 | 460
B | 368527 | HV Cable Connector Channel Cover | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 0 | 0 | 10 | 464.2 | 460
B | 368528 | Cable Holding/Interlock Block | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 0 | 0 | 10 | 464.2 | 460
B | 368529 | HV Cable Cover Assembly | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 0 | 0 | 10 | 464.2 | 460
B | 368530 | Switch, NO Momentary, | 1 | 76 | 1 | 76 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 422 | 0 | 0 | 10 | 464.2 | 460
A | 368671 | Silicone Rubber RTV 41 (2.5 gal can=12 lb. can) | 0.02 | 1.52 | 0.02 | 1.52 | 0.025 | 1 | 0.025 | 1 | 0.025 | 1 | 0.05 | 7.5 | 13.54 | 21.04 | 0 | 10 | 14.894 | 15?
A | 368673 | Ring, Connector Lifting, use with MA-368078 | 0.18 | 13.68 | 0.18 | 13.68 | 0.2 | 8 | 0.2 | 8 | 0.2 | 8 | 0.8 | 120 | 171.36 |  |  |  | 188.496
A | 368674 | Silicone Paste Catalyst RTV 9811 (2.5 gal can=12 lb. Can) | 0.0135 | 1.026 | 0.0135 | 1.026 | 0.017 | 0.68 | 0.017 | 0.68 | 0.017 | 0.68 | 0.04 | 6 | 10.092 | 0 | 0 | 10
A | 368675 | Insulator, Kapton, 4"x9.56"x.002" m/f MA-274450 100 yd (rolls) | 0.0083333 | 0.63333 | 0.017 | 1.292 | 0.0083333 | 0.33333 | 0.0083333 | 0.33333 | 0.0083333 | 0.33333 | 0.013889 | 2.0833 | 5.0087 | 0 | 0 | 10 | 5.5095
A | 368676 | Silicone Spray Lubricant (can - est one can for 40 chambers) | 0.025 | 1.9 | 0.025 | 1.9 | 0.025 | 1 | 0.025 | 1 | 0.025 | 1 | 0.025 | 3.75 | 10.55 | 0 | 0 | 10 | 11.605
A | 368677 | Primer, RTV 41, Silicone (pint container - est 1 pt.for 40 chambers) | 0.025 | 1.9 | 0.025 | 1.9 | 0.025 | 1 | 0.025 | 1 | 0.025 | 1 | 0.025 | 3.75 | 10.55 | 0 | 0 | 10 | 11.605 | 12

## Chamber Frame Pts, Common
|  | Chamber Common Frame Parts List | Wisc | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Total Qty | Spares |  | Qty | Total | Used | Net | Net | Agreed
size | Dwg. # | Description | PN | ME1/2 |  | ME1/3 |  | ME2/1 |  | ME3/1 |  | ME4/1 |  | ME234/2 |  | Req'd. | Percent |  | with | Avail. | 4 | Pc's | Need/ | To | Comments
|  | Date Parts Needed |  | 2001-01-15 |  |  |  | 2001-01-15 | [5 empty] | 2001-01-01 |  |  |  |  | Spares | Pc's | Chamb | Avail | (excess) | Order
|  | Detector Requirements |  | -1 | 72 | -1 | 72 | -1 | 36 | -1 | 36 | -1 | 36 | -1 | 144 | 324
|  | Spares Required |  |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 6 | 22
|  | Total Frame Sets Required |  |  | 76 |  | 76 |  | 40 |  | 40 |  | 40 |  | 150 | 346
A | 368010 | Washer, Flat, M10 x 30mm O.D. DIN 9021B, Z/P Stl |  | 8 | 608 | 8 | 608 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 2836 | 10 | 283.6 | 3119.6 | 275 | 24 | 251 | 2868.6 | 3000
A | 368011 | Pin, Alignment | 5599066B-a | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 5 | 42.2 | 886.2 | 118 | 8 | 110 | 776.2 | 760
A | 368018 | Ring, Retaining Ext., 3/8 Dia.Z/P Stl, McM #98410A117 |  | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 10 | 84.4 | 928.4 | 182 | 8 | 174 | 754.4 | 800
A | 368039 | Nut, Hex, DIN 439B M10-1.5, A2/18-8 SST |  | 68 | 5168 | 64 | 4864 | 72 | 2880 | 66 | 2640 | 62 | 2480 | 94 | 14100 | 32132 | 10 | 3213.2 | 35345.2 | 2872 | 376 | 2496 | 32849.2 | 34000
C | 368043 | Bracket, 'YZ' Fixed Top Mounting LLE | 5599010C-b | 1 | 76 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 346 | 2 | 6.92 | 352.92 | 25 | 4 | 21 | 331.92 | 335
C | 368044 | Bracket, 'Z' Fixed Top Mounting RLE | 5599012C-b | 1 | 76 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 346 | 2 | 6.92 | 352.92 | 25 | 4 | 21 | 331.92 | 335
C | 368045 | Bracket, 'XYZ' Fixed Top Mounting | 5599014C-a | 0 | 0 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 270 | 2 | 5.4 | 275.4 | 25 | 4 | 21 | 254.4 | 260
A | 368046 | Washer, Lock, M6 Int. Tooth, 18-8 SST |  | 24 | 1824 | 24 | 1824 | 24 | 960 | 24 | 960 | 24 | 960 | 24 | 3600 | 10128 | 10 | 1012.8 | 11140.8 | 1227 | 96 | 1131 | 10009.8 | 10200
B | 368051 | Bolt, Panel 'C', M10 x 212.7mm lg (8.38") | 5599007B-c | 8 | 608 | 8 | 608 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 2836 | 1 | 28.36 | 2864.36 | 373 | 24 | 349 | 2515.36 | 2550
B | 368052 | Bolt, Panel 'B', M10 x 201.5 mm lg (7.93") | 5599006B- | 0 | 0 | 0 | 0 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 1620 | 1.5 | 24.3 | 1644.3 | 202 | 24 | 178 | 1466.3 | 1480
B | 368053 | Bolt, Panel 'A', M 10 x 195 mm lg (7.68") | 5599005B- | 22 | 1672 | 20 | 1520 | 20 | 800 | 18 | 720 | 16 | 640 | 32 | 4800 | 10152 | 1 | 101.52 | 10253.52 | 947 | 128 | 819 | 9434.52 | 9530 | Cells this color require ordering changes
A | 368054 | Tubing, Mylar,Heat Shrink (25 x 7" pc. Pkg) (piece) |  | 30 | 2280 | 28 | 2128 | 32 | 1280 | 30 | 1200 | 28 | 1120 | 44 | 6600 | 14608 | 10 | 1460.8 | 16068.8
A | 368055 | Nut, Jam, STL 3/8-24-UNF, 18-8 SST |  | 2 | 152 | 2 | 152 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 844 | 10 | 84.4 | 928.4 | 96 | 8 | 88 | 840.4 | 900
A | 368056 | Washer, Flat M10, DIN 125, 18-8 SST |  | 24 | 1824 | 24 | 1824 | 18 | 720 | 18 | 720 | 18 | 720 | 18 | 2700 | 8508 | 10 | 850.8 | 9358.8 | 1030 | 72 | 958 | 8400.8 | 8600
C | 368058 | Bracket, 'YZ' Fixed Bot Mounting LLE | 5599011C-c | 1 | 76 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 346 | 2 | 6.92 | 352.92 | 25 | 4 | 21 | 331.92 | 335
C | 368059 | Bracket, 'Z' Fixed Bot Mounting RLE | 5599013C-b | 1 | 76 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 346 | 2 | 6.92 | 352.92 | 25 | 4 | 21 | 331.92 | 335
C | 368060 | Bracket, 'XYZ' Fixed Bottom Mounting | 5599015C-a | 0 | 0 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 270 | 2 | 5.4 | 275.4 | 25 | 4 | 21 | 254.4 | 260
A | 368069 | Screw, Hex Wash Hd Thrd Form M6-1 x 10, Z/P Steel |  | 50 | 3800 | 46 | 3496 | 56 | 2240 | 56 | 2240 | 54 | 2160 | 96 | 14400 | 28336 | 10 | 2833.6 | 31169.6 | 3985 | 384 | 3601 | 27568.6 | 28000
A | 368070 | Washer, Lock Tooth, .25 Dia., Int/Ext, Z/P Steel |  | 50 | 3800 | 46 | 3496 | 56 | 2240 | 56 | 2240 | 54 | 2160 | 96 | 14400 | 28336 | 10 | 2833.6 | 31169.6 | 3030 | 384 | 2646 | 28523.6 | 29000
B | 368074 | Plate, End, Big | 5599009B-b | 4 | 304 | 4 | 304 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 1148 | 2 | 22.96 | 1170.96 | 110 | 8 | 102 | 1068.96 | 1100
B | 368075 | Plate, End, Small | 5599008B-b | 0 | 0 | 0 | 0 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 540 | 2 | 10.8 | 550.8 | 100 | 8 | 92 | 458.8 | 470
A | 368076 | Screw, Hex Washer Hd Thd Forming M6-1 x 16, Z/P Steel |  | 26 | 1976 | 26 | 1976 | 26 | 1040 | 26 | 1040 | 26 | 1040 | 26 | 3900 | 10972 | 8 | 877.76 | 11849.76 | 1125 | 104 | 1021 | 10828.76 | 11000
A | 368077 | Screw, Soc/Hd. Flat/Hd. Cap M6-1 x 12 mm; Steel |  | 8 | 608 | 8 | 608 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 2836 | 10 | 283.6 | 3119.6 | 276 | 24 | 252 | 2867.6 | 3000
A | 368078 | Ring, Swivel McMaster Carr # 29495T42 |  | 0.33333 | 25.3333 | 0.33333 | 25.3333 | 0.33333 | 13.3333 | 0.33333 | 13.3333 | 0.33333 | 13.3333 | 0.33333 | 50 | 140.6667 | 10 | 14.0667 | 154.7333 | 0 | 1.3333 | -1.3333 | 156.0667 | 160
B | 368080 | Shim, Light, 2 Slot | 5599003B-a | 4 | 304 | 4 | 304 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 1148 | 2 | 22.96 | 1170.96 | 1202 | 8 | 1194 | -23.04 | 0 | available
B | 368081 | Shim, Medium, 2 Slot | 5599003B-a | 4 | 304 | 4 | 304 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 1148 | 2 | 22.96 | 1170.96 | 1203 | 8 | 1195 | -24.04 | 0 | available
B | 368082 | Shim, Heavy, 2 Slot | 5599003B-a | 8 | 608 | 8 | 608 | 4 | 160 | 4 | 160 | 4 | 160 | 4 | 600 | 2296 | 2 | 45.92 | 2341.92 | 2406 | 16 | 2390 | -48.08 | 0 | available
B | 368083 | Shim, Light, 3 Slot | 5599004C-a | 0 | 0 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 270 | 2 | 5.4 | 275.4 | 269 | 4 | 265 | 10.4 | 21 | available
B | 368084 | Shim, Medium, 3 Slot | 5599004C-a | 0 | 0 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 270 | 2 | 5.4 | 275.4 | 269 | 4 | 265 | 10.4 | 21 | available
B | 368085 | Shim, Heavy, 3 Slot | 5599004C-a | 0 | 0 | 0 | 0 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 540 | 2 | 10.8 | 550.8 | 536 | 8 | 528 | 22.8 | 30 | available
A | 368106 | Ring, Retng, 10mm 'E' Style SP stl, McM # 98543A117 |  | 8 | 608 | 8 | 608 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 2836 | 10 | 283.6 | 3119.6 | 864 | 24 | 840 | 2279.6 | 2400
B | 368191 | Plate, Stiffening, Frame | 5599027C-b | 0 | 0 | 0 | 0 | 4 | 160 | 4 | 160 | 4 | 160 | 0 | 0 | 480 | 2 | 9.6 | 489.6 | 114 | 0 | 114 | 375.6 | 400
C | 368271 | Extrusion, 'Z' Mounting Bracket Profile (ft.) | 5185042C-e | 4.2 | 319.2 | 4.2 | 319.2 | 4 | 160 | 4 | 160 | 4 | 160 | 4 | 500 | 1618.4 | 5 | 80.92 | 1699.32 | 0 | 0 | 0 | 1699.32 | ?
B | 368284 | Extrusion, Side Frame Profile, 130" +.125/-000 | 5185100C1-b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 500 | 500 | 2 | 10 | 510 | 508 | 0 | 508 | 2 | 0 | 30 boxes; Approx 18 pcs/box; 11.5# ea.
B | 368286 | Extrusion, NE Frame Profile, 112.5" +.125/-000 | 5185100C2-b | 0.4 | 30.4 | 0.5 | 38 | 0.66667 | 26.6666 | 0.66666 | 26.6664 | 0.66667 | 26.6667 | 0.66666 | 83.3325 | 231.7322 | 2 | 4.6346 | 236.3668 | 524 | 0 | 524 | -287.6332 | 0 | 20 boxes; Approx 28 pcs/box; 9.5# ea.
A | 368303 | Shim, Corner Light | 5599042A-a | 0 | 0 | 0 | 0 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 540 | 2 | 10.8 | 550.8 | 530 | 8 | 522 | 28.8 | 0 | Cells this color require ordering changes
A | 368306 | Shim, Corner Medium | 5599042A-a | 0 | 0 | 0 | 0 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 300 | 540 | 2 | 10.8 | 550.8 | 535 | 8 | 527 | 23.8 | 0 | Cells this color require ordering changes
A | 368309 | Shim, Corner Heavy | 5599042A-a | 0 | 0 | 0 | 0 | 6 | 240 | 6 | 240 | 6 | 240 | 6 | 900 | 1620 | 2 | 32.4 | 1652.4 | 1602 | 24 | 1578 | 74.4 | 0 | Cells this color require ordering changes
B | 368341 | Extrusion, Side/WE Frame Profile, 78" +.125/-000 | 5185100C1-b | 5 | 380 | 5 | 380 | 4 | 160 | 4 | 160 | 4 | 160 | 0 | 0 | 1240 | 2 | 24.8 | 1264.8 | 1367 | 0 | 1367 | -102.2 | 0 | 50 boxes; Approx.28 pcs/box; 6.5# ea.
B | 368423 | Extrusion, WE Frame Profile, 53" +.125/-000 | 5185100C1-b | 0 | 0 | 0 | 0 | 2 | 80 | 2 | 80 | 2 | 80 | 2 | 250 | 490 | 2 | 9.8 | 499.8 | 524 | 0 | 524 | -24.2 | 0 | 20 boxes; Approx 28 pcs/box; 4.5# ea.
A | 368673 | Ring, Lifting Connector, 3/8" use with 368078 | none | 0.8 | 60.8 | 0.8 | 60.8 | 0.8 | 32 | 0.8 | 32 | 0.8 | 32 | 0.8 | 120 | 337.6 | 15 | 50.64 | 388.24 | 0 |  | 0 |  | 400
A | 368676 | Silicone Spray Lubricant (can - est 1per 40 chambers) |  | 0.025 | 1.9 | 0.025 | 1.9 | 0.025 | 1 | 0.025 | 1 | 0.025 | 1 | 0.025 | 3.75 | 10.55 | 0 | 0 | 10.55 | 0 | 0 | 0 | 12 | ??
A | 368677 | Primer, RTV 41, Silicone (pint container - est 1 pt.for 40 chambers) | none | 0.025 | 2 | 0.025 | 2 | 0.025 | 1 | 0.025 | 1 | 0.025 | 1 | 0.05 | 6 | 11 | 10 | 1.1 | 12

## Chamber Frame Pts, Unique
|  | Foreign Site Chamber Unique Parts List | Qty/ | Total | Raw
size | Dwg. # |  | Chamber | Quantity | Mat'l
B | 368286 | Extrusion, NE Frame Profile, 112.5" +.125/-000 | x | x | by Fnal
B | 368341 | Extrusion, Side/WE Frame Profile, 78" +.125/-000 | x | x | by Fnal
B | 368423 | Extrusion, WE Frame Profile, 53" +.125/-000 | x | x | by Fnal
C | 368271 | Extrusion, 'Z' Mounting Bracket Profile (ft.) | x | x | by Fnal
ME 1/2 Parts
C | 368190 | ME1/2 Mounting Bracket, 'Z' Top Half RSE | 1 | 75 | by Fnal
C | 368332 | ME1/2 Mounting Bracket, 'XYZ' Top Half LSE | 1 | 75 | by Fnal
C | 368333 | ME1/2 Mounting Bracket, 'XYZ' Bottom Half LSE | 1 | 75 | by Fnal
B | 368358 | ME1/2 Panel, Small End | 1 | 75 | by IHEP
B | 368359 | ME1/2 Panel, HV Side | 1 | 75 | by IHEP
B | 368360 | ME1/2 Panel, Big End | 1 | 75 | by IHEP
D | 368378 | ME1/2 Extrusion, Small End Top | 1 | 75 | by Fnal
D | 368379 | ME1/2 Extrusion, Small End Bottom | 1 | 75 | by Fnal
D | 368380 | ME1/2 Extrusion, Anode Side Top | 1 | 75 | by Fnal
D | 368381 | ME1/2 Extrusion, Anode Side Bottom | 1 | 75 | by Fnal
E | 368382 | ME1/2 Extrusion, HV Side Top | 1 | 75 | by Fnal
D | 368383 | ME1/2 Extrusion, HV Side Bottom | 1 | 75 | by Fnal
E | 368384 | ME1/2 Extrusion, Big End Top | 1 | 75 | by Fnal
D | 368385 | ME1/2 Extrusion, Big End Bottom | 1 | 75 | by Fnal
C | 368467 | ME1/2 Panel, Anode Side | 1 | 75 | by IHEP
C | 368483 | ME1/2 Mounting Bracket, 'Z' Bottom Half RSE | 1 | 75 | by Fnal
ME 1/3 Parts
C | 368651 | ME1/3 Mounting Bracket, YZ Top | 1 | 75 | by Fnal
C | 368652 | ME1/3 Mounting Bracket, YZ Bottom | 1 | 75 | by Fnal
C | 368653 | ME1/3 Mounting Bracket, Z Top | 1 | 75 | by Fnal
C | 368654 | ME1/3 Mounting Bracket, Z Bottom | 1 | 75 | by Fnal
C | 368655 | ME1/3 Mounting Bracket, Z Top(sm end) | 1 | 75 | by Fnal
C | 368656 | ME1/3 Mounting Bracket, Z Bottom(sm end) | 1 | 75 | by Fnal
C | 368657 | ME1/3 Mounting Bracket, XYZ Top | 1 | 75 | by Fnal
C | 368658 | ME1/3 Mounting Bracket, XYZ Bottom | 1 | 75 | by Fnal
D | 368659 | ME1/3 Extrusion, Small End Top | 1 | 75 | by Fnal
D | 368660 | ME1/3 Extrusion, Small End Bottom | 1 | 75 | by Fnal
D | 368661 | ME1/3 Extrusion, Anode Side Top | 1 | 75 | by Fnal
D | 368662 | ME1/3 Extrusion, Anode Side Bottom | 1 | 75 | by Fnal
D | 368663 | ME1/3 Extrusion, HV Side Top | 1 | 75 | by Fnal
D | 368664 | ME1/3 Extrusion, HV Side Bottom | 1 | 75 | by Fnal
D | 368665 | ME1/3 Extrusion, Big End Top | 1 | 75 | by Fnal
D | 368666 | ME1/3 Extrusion, Big End Bottom | 1 | 75 | by Fnal
B | 368667 | ME1/3 Panel, Small End | 1 | 75 | by IHEP
B | 368668 | ME1/3 Panel, Anode Side | 1 | 75 | by IHEP
B | 368669 | ME1/3 Panel, Big End | 1 | 75 | by IHEP
B | 368669 | ME1/3 Panel, HV Side | 1 | 75 | by IHEP
ME 2/1 Parts
D | 368172 | ME2/1 Extrusion, Small End Top | 1 | 40 | avail @ FNAL
D | 368173 | ME2/1 Extrusion, Small End Bottom | 1 | 40 | avail @ FNAL
E | 368174 | ME2/1 Extrusion, Anode Side Top | 1 | 40 | avail @ FNAL
D | 368175 | ME2/1 Extrusion, Anode Side Bottom | 1 | 40 | avail @ FNAL
E | 368176 | ME2/1 Extrusion, HV Side Top | 1 | 40 | avail @ FNAL
D | 368177 | ME2/1 Extrusion, HV Side Bottom | 1 | 40 | avail @ FNAL
E | 368178 | Common ME2/1, 3/1, 4/1 Extrusion, Top Big End | 1 | 40 | avail @ FNAL
D | 368179 | Common ME2/1, 3/1, 4/1 Extrusion, Bottom Big End | 1 | 40 | avail @ FNAL
B | 368191 | Common ME2/1, 3/1, 4/1 Plate, Stiffening, Frame | 4 | 160 | avail @ FNAL
B | 368180 | ME2/1 Panel, Small End | 2 | 80 | by PNPI
C | 368181 | ME2/1 Panel, HV Side | 1 | 40 | by PNPI
C | 368182 | Common ME2/1, 3/1, 4/1 Panel, Big End | 1 | 40 | by PNPI
D | 368422 | ME2/1 Panel, Anode Side | 1 | 40 | by PNPI
E | 368638 | ME2/1 Extrusion, Anode Side Top (from 368174) | 1 | 36 | by PNPI
E | 368639 | ME2/1 Extrusion, HV Side Top (from 368176) | 1 | 36 | by PNPI
ME 3/1 Parts
E | 368178 | Common ME2/1, 3/1, 4/1 Extrusion, Top Big End | 1 | 40 | by Fnal
D | 368179 | Common ME2/1, 3/1, 4/1 Extrusion, Bottom Big End | 1 | 40 | by Fnal
C | 368182 | Common ME2/1, 3/1, 4/1 Panel, Big End | 1 | 40 | by Fnal
B | 368191 | Common ME2/1, 3/1, 4/1 Plate, Stiffening, Frame | 4 | 160 | by PNPI
D | 368513 | ME3/1 Extrusion, Small End Top | 1 | 40 | by Fnal
D | 368514 | ME3/1 Extrusion, Small End Bottom | 1 | 40 | by Fnal
D | 368515 | ME3/1 Extrusion, Anode Side Top | 1 | 40 | by Fnal
D | 368516 | ME3/1 Extrusion, Anode Side Bottom | 1 | 40 | by Fnal
D | 368517 | ME3/1 Extrusion, HV Side Top[ | 1 | 40 | by Fnal
D | 368518 | ME3/1 Extrusion, HV Side Bottom | 1 | 40 | by Fnal
B | 368519 | ME3/1 Panel, Small End | 2 | 80 | by PNPI
B | 368520 | ME3/1 Panel, Anode Side | 1 | 40 | by PNPI
B | 368521 | ME3/1 Panel, HV Side | 1 | 40 | by PNPI
ME 4/1 Parts
E | 368178 | Common ME2/1, 3/1, 4/1 Extrusion, Top Big End | 1 | 40 | by Fnal
D | 368179 | Common ME2/1, 3/1, 4/1 Extrusion, Bottom Big End | 1 | 40 | by Fnal
C | 368182 | Common ME2/1, 3/1, 4/1 Panel, Big End | 1 | 40 | by Fnal
B | 368191 | Common ME2/1, 3/1, 4/1 Plate, Stiffening, Frame | 4 | 160 | by PNPI
D | 368504 | ME4/1 Extrusion, Small End Top | 1 | 40 | by Fnal
D | 368505 | ME4/1 Extrusion, Small End Bottom | 1 | 40 | by Fnal
D | 368506 | ME4/1 Extrusion, Anode Side Top | 1 | 40 | by Fnal
D | 368507 | ME4/1 Extrusion, Anode Side Bottom | 1 | 40 | by Fnal
D | 368508 | ME4/1 Extrusion, HV Side Top | 1 | 40 | by Fnal
D | 368509 | ME4/1 Extrusion, HV Side Bottom | 1 | 40 | by Fnal
B | 368510 | ME4/1 Panel, Small End | 2 | 80 | by PNPI
B | 368511 | ME4/1 Panel, Anode Side | 1 | 40 | by PNPI
B | 368512 | ME4/1 Panel, HV Side | 1 | 40 | by PNPI

## 1.2, 2.1 Cu Pts order 7.27.00
N. Chester Printed: 7/27/00 |  |  |  | Order Parts for ME 1/2 and ME 2/1 Chambers | Qty. |  | Qty. |  | Spare | Total | Budget
size | Dwg. | Rev. |  | Description | ME1/2 |  | ME2/1 |  | Parts | Parts | Codes
|  |  |  | Date Parts Needed | 2001-01-15 |  | 2001-01-15 |  | ~5% | to
|  |  |  | Detector Requirements | -1 | 72 | -1 | 36 |  | Order
|  |  |  | Spares Required |  | 3 |  | 4
|  |  |  | Total Sets Required |  | 75 |  | 40
Reflects quantities ordered by Linda as verified 8/22/00
B | 368150 | A | Cu | ME2/1 Wire Fixation Bar LHWE L1 |  |  | 6 | 240 | 12 | 252 | EPL
D | 368151 | A | Cu | ME2/1 Wire Fixation Bar Artwork L1 |  |  | 6 | 240 | 12 | 252 | EPL
B | 368152 | A | Cu | ME2/1 Wire Fixation Bar RHWE R1 |  |  | 6 | 240 | 12 | 252 | EPL
D | 368153 | A | Cu | ME2/1 Wire Fixation Bar Artwork R1 |  |  | 6 | 240 | 12 | 252 | EPL
B | 368154 | A | Cu | ME2/1 Wire Fixation Bar LHC L2 |  |  | 6 | 240 | 12 | 252 | EPL
D | 368155 | A | Cu | ME2/1 Wire Fixation Bar Artwork L2 |  |  | 6 | 240 | 12 | 252 | EPL
B | 368156 | A | Cu | ME2/1 Wire Fixation Bar RHC R2 |  |  | 6 | 240 | 12 | 252 | EPL
D | 368157 | A | Cu | ME2/1 Wire Fixation Bar Artwork R2 |  |  | 6 | 240 | 12 | 252 | EPL
B | 368158 | A | Cu | ME2/1 Wire Fixation Bar LHNE L3 |  |  | 6 | 240 | 12 | 252 | EPL
D | 368159 | A | Cu | ME2/1 Wire Fixation Bar Artwork L3 |  |  | 6 | 240 | 12 | 252 | EPL
B | 368160 | A | Cu | ME2/1 Wire Fixation Bar RHNE R3 |  |  | 6 | 240 | 12 | 252 | EPL
D | 368161 | A | Cu | ME2/1 Wire Fixation Bar Artwork R3 |  |  | 6 | 240 | 12 | 252 | EPL
C | 368192 | B | Cu | ME2/1 Gap Bar, Narrow End (ALL) |  |  | 6 | 240 | 12 | 252 | Fla.
C | 368193 | B | Cu | ME2/1, 3/1, 4/1 Gap Bar, Wide End (OP) |  |  | 2 | 80 | 4 | 84 | Fla.
C | 368194 | B | Cu | ME2/1, 3/1, 4/1 Gap Bar, Wide End (IP) |  |  | 4 | 160 | 8 | 168 | Fla.
C | 368195 | B | Cu | ME2/1 Gap Bar, Left Hand Side (ALL) |  |  | 6 | 240 | 12 | 252 | Fla.
C | 368196 | B | Cu | ME2/1 Gap Bar, Right Hand Side (ALL) |  |  | 6 | 240 | 12 | 252 | Fla.
A | 368198 | - | Cu | ME2/1 Isolation Strip, Outer Panels |  |  | 4 | 160 | 8 | 168 | Fla.
A | 368199 | - | Cu | ME2/1 Isolation Strip, Inner Panels |  |  | 8 | 320 | 16 | 336 | Fla.
B | 368388 | A | Cu | ME1/2 Wire Fixation Bar LHWE L1 | 6 | 450 |  |  | 24 | 474 | EPL
D | 368389 | A | Cu | ME1/2 Wire Fixation Bar Artwork L1 | 6 | 450 |  |  | 24 | 474 | EPL
B | 368390 | A | Cu | ME1/2 Wire Fixation Bar RHWE R1 | 6 | 450 |  |  | 24 | 474 | EPL
D | 368391 | A | Cu | ME1/2 Wire Fixation Bar Artwork R1 | 6 | 450 |  |  | 24 | 474 | EPL
B | 368392 | A | Cu | ME1/2 Wire Fixation Bar LHC L2 | 6 | 450 |  |  | 24 | 474 | EPL
D | 368393 | A | Cu | ME1/2 Wire Fixation Bar Artwork L2 | 6 | 450 |  |  | 24 | 474 | EPL
B | 368394 | A | Cu | ME1/2 Wire Fixation Bar RHC R2 | 6 | 450 |  |  | 24 | 474 | EPL
D | 368395 | A | Cu | ME1/2 Wire Fixation Bar Artwork R2 | 6 | 450 |  |  | 24 | 474 | EPL
B | 368396 | A | Cu | ME1/2 Wire Fixation Bar LHNE L3 | 6 | 450 |  |  | 24 | 474 | EPL
D | 368397 | A | Cu | ME1/2 Wire Fixation Bar Artwork L3 | 6 | 450 |  |  | 24 | 474 | EPL
B | 368398 | A | Cu | ME1/2 Wire Fixation Bar RHNE R3 | 6 | 450 |  |  | 24 | 474 | EPL
D | 368399 | A | Cu | ME1/2 Wire Fixation Bar Artwork R3 | 6 | 450 |  |  | 24 | 474 | EPL
C | 368400 | B | Cu | ME1/2 Gap Bar, Narrow End (ALL) | 6 | 450 |  |  | 24 | 474 | Fla.
C | 368401 | #REF! | Cu | ME1/2 Gap Bar, Wide End (OP) | 2 | 150 |  |  | 8 | 158 | Fla. | updated 10/6/00
C | 368402 | B | Cu | ME1/2 Gap Bar, Left Hand Side (ALL) | 6 | 450 |  |  | 24 | 474 | Fla.
C | 368403 | B | Cu | ME1/2 Gap Bar, Right Hand Side (ALL) | 6 | 450 |  |  | 24 | 474 | Fla.
C | 368404 | C | Cu | ME1/2 Gap Bar, Wide End (IP) | 4 | 300 |  |  | 8 | 308 | Fla.
A | 368405 | A | Cu | ME1/2 Isolation Strip, Outer Panels | 4 | 300 |  |  | 8 | 308 | Fla.
A | 368406 | A | Cu | ME1/2 Isolation Strip, Inner Panels | 8 | 600 |  |  | 32 | 632 | Fla.

## 1.3, 3.1, 4.1 Cu Pts to Order
N. Chester Updated 8/7/01 |  |  |  | Unique Parts to be Ordered ME 1/3, ME 3/1, and ME4/1 Chambers | Qty. |  | Qty. |  | Qty. |  | Add'l Spare | Total Sets to | Budget
size | Dwg. | Rev. | type | Description | ME1/3 |  | ME3/1 |  | ME4/1 |  | Sets | Order | Codes
|  |  |  | Date Parts Needed | 2001-09-01 |  | 2001-09-01 |  | 2001-09-01
|  |  |  | Detector Requirements | -1 | 72 | -1 | 36 | -1 | 36 | -
|  |  |  | Spares Required |  | 2 |  | 2 |  | 2 | -
|  |  |  | Total Sets Required |  | 74 |  | 38 |  | 38 | 2
Chamber ME 1/3
A | 368112 | A | Cu | ME1/3 1/4" SS Gas Flow Tube, Upper | 1 | 74 |  |  |  |  | 2 | 76 | EPQ
B | 368113 | A | Cu | ME1/3 1/4" SS Gas Flow Tube, Lower | 1 | 74 |  |  |  |  | 2 | 76 | EPQ
A | 368429 | A | Cu | ME1/3 Chamber Nameplate Label | 1 | 74 |  |  |  |  | 2 | 76 | FNAL
C | 368440 | - | Cu | ME1/3 Gap Bar, Narrow End (ALL) | 6 | 444 |  |  |  |  | 12 | 456 | Florida
C | 368441 | - | Cu | ME1/3 Gap Bar, Wide End (OP) | 2 | 148 |  |  |  |  | 4 | 152 | Florida
C | 368442 | A | Cu | ME1/3 Gap Bar, Left Hand Side (ALL) | 6 | 444 |  |  |  |  | 12 | 456 | Florida
C | 368443 | A | Cu | ME1/3 Gap Bar, Right Hand Side (ALL) | 6 | 444 |  |  |  |  | 12 | 456 | Florida
C | 368444 | - | Cu | ME1/3 Gap Bar, Wide End (IP) | 4 | 296 |  |  |  |  | 8 | 304 | Florida
A | 368445 | - | Cu | ME1/3 Isolation Strip, Outer Panels | 4 | 296 |  |  |  |  | 8 | 304 | Florida
A | 368446 | - | Cu | ME1/3 Isolation Strip, Inner Panels | 8 | 592 |  |  |  |  | 16 | 608 | Florida
B | 368448 | A | Cu | ME1/3 Wire Fixation Bar LHWE L1 from 368449 Rev A. | 6 | 444 |  |  |  |  | 12 | 456 | EPL
B | 368450 | A | Cu | ME1/3 Wire Fixation Bar RHWE R1 from 368451 Rev A. | 6 | 444 |  |  |  |  | 12 | 456 | EPL
B | 368452 | A | Cu | ME1/3 Wire Fixation Bar LHC L2 from 368453 Rev A. | 6 | 444 |  |  |  |  | 12 | 456 | EPL
B | 368454 | A | Cu | ME1/3 Wire Fixation Bar RHC R2 from 368455 Rev A. | 6 | 444 |  |  |  |  | 12 | 456 | EPL
B | 368456 | A | Cu | ME1/3 Wire Fixation Bar LHNE L3 from 368457 Rev A. | 6 | 444 |  |  |  |  | 12 | 456 | EPL
B | 368458 | B | Cu | ME1/3 Wire Fixation Bar RHNE R3 from 368459 Rev B. | 6 | 444 |  |  |  |  | 12 | 456 | EPL
Chamber ME 3/1
A | 368008 | C | Cu | 1/4" Stainless Stl Gas Flow Tube, Upper, except IHEP |  |  | 1 | 38 |  |  | 2 | 40 | EPQ
A | 368009 | B | Cu | 1/4" Stainless Gas Flow Tube, Lower, except IHEP |  |  | 1 | 38 |  |  | 2 | 40 | EPQ
C | 368193 | B | Cu | PNPI Gap Bar, Wide End (OP) |  |  | 2 | 76 |  |  | 4 | 80 | Florida
C | 368194 | B | Cu | PNPI Gap Bar, Wide End (IP) |  |  | 4 | 152 |  |  | 8 | 160 | Florida
C | 368460 | B | Cu | ME3/1 Gap Bar, Narrow End (ALL) |  |  | 6 | 228 |  |  | 12 | 240 | Florida
C | 368463 | A | Cu | ME3/1 Gap Bar, Left Hand Side (ALL) |  |  | 6 | 228 |  |  | 12 | 240 | Florida
C | 368464 | A | Cu | ME3/1 Gap Bar, Right Hand Side (ALL) |  |  | 6 | 228 |  |  | 12 | 240 | Florida
A | 368465 | - | Cu | ME3/1 Isolation Strip, Outer Panels |  |  | 4 | 152 |  |  | 8 | 160 | Florida
A | 368466 | - | Cu | ME3/1 Isolation Strip, Inner Panels |  |  | 8 | 304 |  |  | 16 | 320 | Florida
B | 368468 | A | Cu | ME3/1 Wire Fixation Bar LHWE L1 from 368469 Rev B. |  |  | 6 | 228 |  |  | 12 | 240 | EPL
B | 368470 | A | Cu | ME3/1 Wire Fixation Bar RHWE R2 from 368471 Rev B. |  |  | 6 | 228 |  |  | 12 | 240 | EPL
B | 368472 | A | Cu | ME3/1 Wire Fixation Bar LHC L2 from 368473 Rev B. |  |  | 6 | 228 |  |  | 12 | 240 | EPL
B | 368474 | A | Cu | ME3/1 Wire Fixation Bar RHC R2 from 368475 Rev B. |  |  | 6 | 228 |  |  | 12 | 240 | EPL
B | 368476 | A | Cu | ME3/1 Wire Fixation Bar LHNE L3 from 368477 Rev B. |  |  | 6 | 228 |  |  | 12 | 240 | EPL
B | 368478 | A | Cu | ME3/1 Wire Fixation Bar RHNE R3 from 368479 Rev B. |  |  | 6 | 228 |  |  | 12 | 240 | EPL
A | 368480 | - | Cu | ME3/1 Label, Chamber Nameplate |  |  | 1 | 38 |  |  | 2 | 40 | -
Chamber ME 4/1
A | 368008 | C | Cu | 1/4" Stainless Stl Gas Flow Tube, Upper, except IHEP |  |  |  |  | 1 | 38 | 2 | 40 | EPQ
A | 368009 | B | Cu | 1/4" Stainless Gas Flow Tube, Lower, except IHEP |  |  |  |  | 1 | 38 | 2 | 40 | EPQ
B | 368486 | A | Cu | ME4/1 Wire Fixation Bar LHWE L1 from 368487 Rev A. |  |  |  |  | 6 | 228 | 12 | 240 | Florida
B | 368488 | A | Cu | ME4/1 Wire Fixation Bar RHWE R1 from 368489 Rev A. |  |  |  |  | 6 | 228 | 12 | 240 | Florida
B | 368490 | A | Cu | ME4/1 Wire Fixation Bar LHC L2 from 368491 Rev A. |  |  |  |  | 6 | 228 | 12 | 240 | Florida
B | 368492 | A | Cu | ME4/1 Wire Fixation Bar RHC R2 from 368493 Rev A. |  |  |  |  | 6 | 228 | 12 | 240 | Florida
B | 368494 | A | Cu | ME4/1 Wire Fixation Bar LHNE L3 from 368495 Rev A. |  |  |  |  | 6 | 228 | 12 | 240 | Florida
B | 368496 | A | Cu | ME4/1 Wire Fixation Bar RHNE R3 from 368497 Rev A. |  |  |  |  | 6 | 228 | 12 | 240 | Florida
C | 368193 | B | Cu | PNPI Gap Bar, Wide End (OP) |  |  |  |  | 2 | 76 | 4 | 80 | Florida
C | 368194 | B | Cu | PNPI Gap Bar, Wide End (IP) |  |  |  |  | 4 | 152 | 8 | 160 | EPL
C | 368498 | - | Cu | ME4/1 Gap Bar, Narrow End (ALL) |  |  |  |  | 6 | 228 | 12 | 240 | EPL
C | 368499 | - | Cu | ME4/1 Gap Bar, Left Hand Side (ALL) |  |  |  |  | 6 | 228 | 12 | 240 | EPL
C | 368500 | - | Cu | ME4/1 Gap Bar, Right Hand Side (ALL) |  |  |  |  | 6 | 228 | 12 | 240 | EPL
A | 368501 | - | Cu | ME4/1 Isolation Strip, Outer Panels |  |  |  |  | 4 | 152 | 8 | 160 | EPL
A | 368502 | - | Cu | ME4/1 Isolation Strip, Inner Panels |  |  |  |  | 8 | 304 | 16 | 320 | EPL
A | 368503 | - | Cu | ME4/1 Label Nameplate |  |  |  |  | 1 | 38 | 2 | 40 | -

## z bracket lengths
|  |  | Z Bracket List for All Chambers | Wisc | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Qty. |  | Total Qty | Spares |  | Qty
size | Dwg. |  | Description | PN | ME1/2 |  | ME1/3 |  | ME2/1 |  | ME3/1 |  | ME4/1 |  | ME234/2 |  | Req'd. | Percent |  | with
[18 empty] | (%) | (Qty.) | Spares
|  |  | Detector Requirements |  | -1 | 72 | -1 | 72 | -1 | 36 | -1 | 36 | -1 | 36 | -1 | 144 | 324
|  |  | Spares Required |  |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  | 6 | 22
|  |  | Total Unique Part Sets Required |  |  | 76 |  | 76 |  | 40 |  | 40 |  | 40 |  | 150 | 346
C | 368043 | cF | Bracket, 'YZ' Fixed Top Mounting 5.80" | 5599010C-b | 0.5 | 38 | 0 | 0 | 0.5 | 20 | 0.5 | 20 | 0.5 | 20 | 0.5 | 75 | 173 | 10 | 17.3 | 190.3
C | 368044 | cF | Bracket, 'Z' Fixed Top Mounting 5.80" | 5599012C-b | 0.5 | 38 | 0 | 0 | 0.5 | 20 | 0.5 | 20 | 0.5 | 20 | 0.5 | 75 | 173 | 10 | 17.3 | 190.3
C | 368045 | cF | Bracket, 'XYZ' Fixed Top Mounting 10.00" | 5599014C-a | 0 | 0 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 270 | 10 | 27 | 297
C | 368058 | cF | Bracket, 'YZ' Fixed Bot Mounting 5.80" | 5599011C-c | 0.5 | 38 | 0 | 0 | 0.5 | 20 | 0.5 | 20 | 0.5 | 20 | 0.5 | 75 | 173 | 10 | 17.3 | 190.3
C | 368059 | cF | Bracket, 'Z' Fixed Bot Mounting 5.80" | 5599013C-b | 0.5 | 38 | 0 | 0 | 0.5 | 20 | 0.5 | 20 | 0.5 | 20 | 0.5 | 75 | 173 | 10 | 17.3 | 190.3
C | 368060 | cF | Bracket, 'XYZ' Fixed Bottom Mounting 10.00" | 5599015C-a | 0 | 0 | 0 | 0 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 150 | 270 | 10 | 27 | 297
C | 368190 |  | ME1/2 Bracket, 'Z' Top Half Small End Mounting 6.10" | 5599069C-e | 0.55 | 41.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.8 | 10 | 4.18 | 45.98
C | 368332 |  | ME1/2 Bracket, 'XYZ' Top Half Sm End Mtg 6.10" | 5599071C- | 0.55 | 41.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.8 | 10 | 4.18 | 45.98
C | 368333 | uF | ME1/2 Bracket, 'XYZ' Bottom Half Sm End Mtg 6.10" | 5599072C- | 0.55 | 41.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.8 | 10 | 4.18 | 45.98
C | 368483 | uF | ME1/2 Bracket, 'Z' Bottom Half Sm End Mtg 6.10" | 5599070C- | 0.55 | 41.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.8 | 10 | 4.18 | 45.98
| 368651 | uF | ME1/3 Mounting Bracket, Top YZ 5.80" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368652 | uF | ME1/3 Mounting Bracket, Bottom YZ 5.80" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368653 | uF | ME1/3Mounting Bracket, Top Z 5.80" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368654 | uF | ME1/3 Mounting Bracket, Bottom Z 5.80" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368655 | uF | ME1/3 Mounting Bracket, Top Z (sm end) 5.78" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368656 | uF | ME1/3 Mounting Bracket, Bottom Z (sm end) 5.78" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368657 | uF | ME1/3 Mounting Bracket, Top XYZ 5.78" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368658 | uF | ME1/3 Mounting Bracket, Bottom XYZ 5.78" |  | 0 | 0 | 0.5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 10 | 3.8 | 41.8
| 368271 | cF | Extrusion, 'Z' Mounting Bracket Profile (ft.) | 5185042C-e | 4.2 | 319.2 | 4 | 304 | 4 | 160 | 4 | 160 | 4 | 160 | 4 | 600 | 1703.2 | 10 | 170.32 | 1873.52
[19 empty] | ORDER | 2000 FEET