## engr
FME - ENGINEERING JOBHOURS ESTIMATE
TITLE |  | W.O.#
BLDG |  | PROGRAM
ENGINEERING DESIGN PHASE
GROUP | ACTIVITY | QTY | HOURS | TOTAL | ACTIVITY CODE
PM | LEVEL OF EFFORT |  |  |  | DPM
MECHANICAL | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
| 15% PRELIMINARY ENGINEERING |  |  |  | DPE
Sub Total
| CALCULATIONS |  |  |  | DCA
| DEVELOP SPECIFICATIONS/PR |  |  |  | DSP
| DRAWINGS |  |  |  | DDD
| CHECKING |  | 0 |  | DCK
Sub Total
Mech. Total
ELECTRICAL/I&C | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
| 15% PRELIMINARY ENGINEERING |  |  |  | DPE
Sub Total
| CALCULATIONS |  |  |  | DCA
| DEVELOP SPECIFICATIONS/PR |  |  |  | DSP
| DRAWINGS |  |  |  | DDD
| CHECKING |  | 0 |  | DCK
Sub Total
Elec. Total
ARCHITECTURAL | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
| 15% PRELIMINARY ENGINEERING |  |  |  | DPE
Sub Total
| CALCULATIONS |  |  |  | DCA
| DEVELOP SPECIFICATIONS/PR |  |  |  | DSP
| DRAWINGS |  |  |  | DDD
| CHECKING |  | 0 |  | DCK
Sub Total
Arch. Total
CONSTRUCTION ADMINISTRATION | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
| 15% PRELIMINARY ENGINEERING |  |  |  | DPE
Sub Total
| CALCULATIONS |  |  |  | DCA
| DEVELOP SPECIFICATIONS/PR |  |  |  | DSP
| DRAWINGS |  |  |  | DDD
| CHECKING |  | 0 |  | DCK
Sub Total
Const. Adm. Total
CAD | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
| 15% PRELIMINARY ENGINEERING |  |  |  | DPE
Sub Total
| CALCULATIONS |  |  |  | DCA
| DEVELOP SPECIFICATIONS/PR |  |  |  | DSP
FMEP-P-0350 | DRAWINGS |  |  |  | DDD
Revision 2 | CHECKING |  | 0 |  | DCK
Exhibit I(A) | Sub Total
Page 1 of 4 | Cad Total
SHEET TOTAL

## engr_ae
FME - ENGINEERING JOBHOURS ESTIMATE
TITLE |  | W.O.#
BLDG |  | PROGRAM
A&E DESIGN PHASE
GROUP | ACTIVITY | QTY | HOURS | TOTAL | ACTIVITY CODE
PM | LEVEL OF EFFORT |  |  |  | DPM
MECHANICAL | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
Sub Total
| 15% PRELIMINARY ENGINEERING |  |  |  | DAE
| 35% PRELIMINARY ENGINEERING |  |  |  | DAE
| 65% PRELIMINARY ENGINEERING |  |  |  | DAE
| BID/CONSTRUCTION DRAWINGS |  |  |  | DAE
Sub Total
Mech. Total
ELECTRICAL/I&C | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
Sub Total
| 15% PRELIMINARY ENGINEERING |  |  |  | DAE
| 35% PRELIMINARY ENGINEERING |  |  |  | DAE
| 65% PRELIMINARY ENGINEERING |  |  |  | DAE
| BID/CONSTRUCTION DRAWINGS |  |  |  | DAE
Sub Total
Elec. Total
ARCHITECTURAL | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
Sub Total
| 15% PRELIMINARY ENGINEERING |  |  |  | DAE
| 35% PRELIMINARY ENGINEERING |  |  |  | DAE
| 65% PRELIMINARY ENGINEERING |  |  |  | DAE
| BID/CONSTRUCTION DRAWINGS |  |  |  | DAE
Sub Total
Arch. Total
CONSTRUCTION ADMINISTRATION | CONCEPTUAL SCOPE ESTIMATE |  |  |  | DPE
| PREPARE SOW |  |  |  | DPE
Sub Total
| 15% PRELIMINARY ENGINEERING |  |  |  | DAE
| 35% PRELIMINARY ENGINEERING |  |  |  | DAE
FMEP-P-0350 | 65% PRELIMINARY ENGINEERING |  |  |  | DAE
Revision 2 |  |  |  |  | DAE
Exhibit I(A) | Sub Total
Page 2 of 4 | Const. Adm. Total
CAD | PRELIMINARY ENGINEERING |  |  |  | DPE
| AE REVIEW |  |  |  | DAE
| FINAL |  |  |  | DAE
Cad Total
SHEET TOTAL

## shop_const
FME - ENGINEERING JOBHOURS ESTIMATE
TITLE |  | W.O.#
BLDG |  | PROGRAM
SHOP CONSTRUCTION PHASE
GROUP | ACTIVITY | QTY | HOURS | TOTAL | ACTIVITY CODE
PM | LEVEL OF EFFORT |  |  |  | DPM
MECHANICAL | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Mech. Total
ELECTRICAL/I&C | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Elec. Total
ARCHITECTURAL | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Arch. Total
CONSTRUCTION ADMINISTRATION | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Const. Adm. Total
CAD | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Cad Total
SHOP
See Detailed Shop Estimate
SHEET TOTAL
FMEP-P-0350
Revision 2
Exhibit I(A)
Page 3 of 4

## sc_const
FME - ENGINEERING JOBHOURS ESTIMATE
TITLE |  | W.O.#
BLDG |  | PROGRAM
SC CONSTRUCTION PHASE
GROUP | ACTIVITY | QTY | HOURS | TOTAL | ACTIVITY CODE
PM | LEVEL OF EFFORT |  |  |  | DPM
MECHANICAL | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Mech. Total
ELECTRICAL/I&C | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Elec. Total
ARCHITECTURAL | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Arch. Total
CONSTRUCTION ADMINISTRATION | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Const. Adm. Total
CAD | CONSTRUCTION SUPPORT |  |  |  | DCS
| REVIEW SUBMITTALS |  |  |  | DSR
| STARTUP and ACCEPTANCE |  |  |  | DCO
| AS BUILTS |  |  |  | DCO
Cad Total
FMEP-P-0350
Revision 2 | SHEET TOTAL
Exhibit I(A)
Page 4 of 4