## Attachment A
| Fair Act Information | [6 empty] | FTE Information |  |  | Planned Date |  | Actual Date |  |  | Post Competition Accountability
OPDIV/FY | FY 06 Seq # | Function Code | Reason Code | Description | City/State | Type Study | Status | Filled | Vacant | Total | Start | Comp | Start | Comp | Total Days to Complete | Annual Savings | Productivity | Disposition as of June 15, 2006 (including disposition of FTE's reassigned, retired, etc.)
AHRQ/07 | 0 |  |  | None | [13 empty] | In FY 2006, AHRQ is studying 33 FTE's in its Office of Communications and Knowledge Transfer (OCKT). This is the first study the Agency has undertaken utilizing the standard competition method and anticipates a radical change in the way business is done within the public affairs, publishing, web management and knowledge transfer areas. The Agency will use FY07 to implement the new organization and transition functions to the new organization.
AHRQ/08 | 41 | L000 | B | Grants Management Specialists | Rockville, MD | STR | Planned | 7 | 0 | 7 | 2007-09-07 | 2008-03-15 | [5 empty] | Will begin pre-planning summer 07
| 54 | R140 | A | Health Scientist Administrators | Rockville, MD | STR | Planned | 3 | 0 | 3 | 2007-09-15 | 2008-03-15 | [5 empty] | Will begin pre-planning summer 07
| 72 | U800 | B | Extramural Trng Prog Spec | Rockville, MD | STR | Planned | 1 | 0 | 1 | 2007-09-15 | 2008-03-15 | [5 empty] | Will begin pre-planning summer 07

## Attachment B
OPDIV | Year | # of competitions likely to be announced | # of FTE to be studied | Rationale for Competition
AHRQ | 2007 | 0 | 0 | In FY 2006, AHRQ is studying 33 FTE's in its Office of Communications and Knowledge Transfer (OCKT). This is the first study the Agency has undertaken utilizing the standard competition method and anticipates a radical change in the way business is done within the public affairs, publishing, web management and knowledge transfer areas. The Agency will use FY07 to implement the new organization and transition functions to the new organization. In FY 2007, the Agency plans to study the grant receipt and review function. With the advent of the e-grants initiative, the manner in which the Agency receives and reviews grants has already begun to change dramatically. The Agency sees an opportunity to reshape and restructure the grants process to achieve efficiencies and redeploy staff to other more mission-critical areas within the Agency.
AHRQ | 2008 | 1 to 2 | 11

## Attachment C
In addition to the evaluation factors noted in Section II.c and constraints in Section V of the GCP, the following
rationale defines the basis for determination of Activities that will not be publicly announced for competition
by the end of FY 2008.
| Activity |  |  |  | Total
OPDIV | Fct Code | Description | Status | Reason | FTEs | Rationale
AHRQ | None | None to date

## Attachment D
| Activity |  |  |  | Total | Time Period
OPDIV | Fct Code | Description | Status | Reason | FTEs | for Analysis | Rationale
AHRQ | F000 | Accountant | C | D | 1 | FY 2007 | These functions were competed in FY 2003 and will be reviewed in FY 2007 to determine when the function will be recompeted.
AHRQ | Y000 | Program Assistant (OA) | C | D | 1
AHRQ | W310 | Information Technology Specialist | C | D | 1
AHRQ | T807 | Visual Information Specialist | C | D | 2
AHRQ | L000 | Grants Mgmt Spec | C | B |  | FY 2008 | The Agency's grants review and management function will be studied in order to ascertain any opportunities for efficiences. The plan is to study the the receipt and review function in order to identify any potential delayering and reorganization opportunities, assess the administrative personnel to professional ratio, analyze the number and complexity of current contracts and strive for more business process improvements.
AHRQ | L000 | Committee Mgmt Asst | C | B
AHRQ | L000 | Grants Mgmt Spec | C | B
AHRQ | L000 | Grants Mgmt Spec | C | B
AHRQ | L000 | Public Hlth Analyst | C | B
AHRQ | L000 | Grants Mgmt Spec | C | B
AHRQ | L000 | Grants Tech Asst | C | B
AHRQ | R140 | Hlth Scientist Admin | C | A
AHRQ | R140 | Hlth Scientist Admin | C | A
AHRQ | R140 | Hlth Scientist Admin | C | A
AHRQ | U800 | Extramural Trng Prog Spec | C | B