## reviews sheet
Time Key: |  |  |  | Status Key:
red WBS/device is needed for summer 2003 shutdown |  |  |  | fuscia (dated expected) | Review & Documentation needed
green WBS/device is needed for US BO |  |  |  | underline (date to reviewer) | Engineering note in review process
blue WBS/Device needed for DS BO |  |  |  | bold - ready for Schuh Committee | Engineering Note Complete & Reviewed
purple WBS/Device needed for summer 2004 shutdown |  |  |  | italics (date to committee) | Engineering note to Schuh Committee
|  |  |  | pink, not sure of data | qeustions
1.1.1 Updated 7/22/03 byJGM, 1.1.2 updated 8/27/03 by DAH |  |  | Dates Listed are from "Early Start" Date in April 03 Schedule
WBS | Device/Procedures | Hazards | Location | Design Review Date/Link | Safety Reviews: M, S, E, F, O, R, T | Projected Installation Date | Review Status
1.1 | NuMI Installation |  |  | 2002 dec_04.html |  | 2004-12-08 17:00 | on going
1.1 | NuMI Radiation Safety |  |  | 2002 july_17.html |  |  | covered in Shielding Assessment
1.1 | NuMI Commissioning |  |  | 2003 march.html |  |  | complete
1.1 | NuMI Accident Conditions |  |  | 2003 march.html |  |  | complete
1.1.1 | Specs and Design for Primary Beamline |  |  | 2002 nov_01.html |  |  | complete
1.1.1 | Beam Optics Design |  |  | 2002 apr_02.html |  |  | complete
1.1.1 | Beam Extraction Permit System |  |  | Aesook Review | D&P post-shutdown |  | NuMI review fall 2003
1.1.1 | Primary Beamline Instrumentations |  |  | 2002 jun_25.html 2002 nov_01.html | n/a | 2004-02-18 17:00 | complete
1.1.1.a | BPM |  |  | specs reviewed 3/03 (NG) | n/a |  | complete
1.1.1.b | Multiwire |  |  | Tech Review of specs 10/02 | n/a |  | complete
1.1.1, 1.1.3 ** | Kicker Magnet & PS & Cooling Sys (F17 test setup) |  | Testing in service building. Using fence & procedures ala MI8 | 2002 july_01.html | n/a - in existing test facility with previous reviews |  | complete
1.1.1, 1.1.3 | Kicker Magnet & PS & Cooling Sys (Kicker-load cooling with active system and circulating coolant) | M | Installation in MI tunnel uses standard tunnel access procedures | 2002 jun_14.html | Installation review (internal) required MSD/BD | 2004-07-06 | date?
1.1.1, 1.1.3 | Kicker Magnet & PS & Cooling Sys | T | After significant beam losses on kicker. Maintenance procedures needed? | Design 6/14/02 | Toxic material hazard after radiation exposure - Operational review needed in '04 |  | date?
1.1.1 | Kicker magnet |  | EE | 2002 feb_01.html | n/a |  | complete
**** | Kicker magnet- stands |  | EE | generic magnet stand EN | EN 1321-ES-296397 | 2003-12-09 17:00 | 1 complete Schuh iteration, waiting final word from Schuh
*** | Kicker magnet-installation |  | EE | R.Reily wrote Installation Procedure | HA needed | 2004-07-06 08:00 | n/a
1.1.1 | Lambertsons (3) |  | EE | generic (MI spares) | n/a |  | complete
**** | Lambertsons (3) - stands |  | EE | generic magnet stand EN | EN 1321-ES-296397 | 2003-12-09 17:00 | 1 complete Schuh iteration, waiting final word from Schuh
*** | Lambertsons (3) - installation |  | EE | L.Sauer wrote Installation Procedure | HA needed | 2004-07-12 17:00 | n/a
1.1.1 | HV101 EPB (5) |  | EE |  | n/a |  | n/a
**** | EPB (5) Stands | M | EE |  | EN 1321-ES-296390 | 2003-07-30 | returned from Schuh, comments on Hilti anchor tests from D.Pushka, awaiting approval
*** | EPB Installation |  | EE | standard magnet mover installation | n/a | 2003-08-26 08:00 | n/a
1.1.1 | Q101-Q106 3Q120 (5) |  | EE |  | n/a | 2003-08-26 08:00 | n/a
1.1.1 | Q104 3Q60 |  | EE |  | n/a | 2003-08-26 08:00 | n/a
| Q101 Stand | M | EE |  | n/a |  | n/a
| Q102-Q104 Stands | M | EE |  | EN 1321-ES-296390,96,97 |  | Need FESS review for 90,96, and 97 awaits final word from Schuh
| Q105 - Q106 Stands |  | NS |  | EN 1321-ES-296399/400 |  | Need FESS review for 90, 96
| HQ107 stands | M | NS |  | EN still to finish 1321-ES-296401 |  | EN still to finish 1321-ES-296401
| Q107 Installation |  | NS | L.Sauer to write Installation Procedure | HA needed |  | n/a
| Quad Installation |  | NS | standard magnet mover installation | n/a |  | n/a
1.1.1 | V108 B2 (5) |  | NS |  | n/a | 2003-09-23 08:00 | n/a
**** | B2 Stands | M | NS | new design to be certified | MD-ENG-03-001 | 2003-08-26 | returned from Schuh, response provided by engineer, awaiting approval
*** | B2 Installation |  | NS |  | MSDN-ME-000036+ HA needed | 2003-08-26 | n/a
| HQ108-112 Stands |  |  | generic
| HQ108-112 Installation |  |  |  | MSDN-ME-000036+ HA needed |  | n/a
1.1.1 | HQ113-HQ116 3Q120 (4) |  | CR |  | n/a | 2003-11-13 08:00 | n/a
| Transport/Installation Carts |  |  | MD-ENG-03-002 6 March 2003 | MD-ENG-03-002 | 2003-08-26 | ok'd by Schuh
| Magnet Installation Lifting Fixtures |  |  | MD-ENG-03-004 6 March 2003 | MD-ENG-03-004 | 2003-08-26 | ok'd by Schuh
1.1.1 | HQ117-HQ121 3Q120 (5) |  | Pre-TGT |  | N/A | 2003-12-08 08:00 | n/a
| HQ113-HQ121 Stands |  | CR/Pre-TGT | MayLing Wong EN written | NEED EN NUMBER! |  | ok'd by Schuh
| HQ113 - 121 Installation |  | CR/Pre-TGT |  | MSDN-ME-000036+ HA needed |  | n/a
1.1.1 | V118 B2 (4) |  | Pre-TGT |  | N/A | 2003-12-08 08:00 | n/a
* | B2 Stands | M | Pre-TGT | mid-July design note | EN to come |  | status, date?
* | B2 Installation |  | Pre-TGT | need separate installation review | HA needed | 2003-12-08 08:00 | n/a
1.1.1 **** | Magnet Installation Lifting Fixtures |  |  | MD-ENG-03-005 6 March 2003 | MD-ENG-03-005, FESHM 5022 | 2003-08-26 | ok'd by Schuh
1.1.1 **** | Magnet Installation Transport/Installation Carts |  |  | MD-ENG-03-003 6 March 2003 | MD-ENG-03-003 | 2003-08-26 | ok'd by Schuh
1.1.1 | Beam vacuum pipe |  | CR,Pre-TGT | Already installed in CR, Pre-TGT next | n/a by FESHM, since OD under or at 12" | 2004-07-16 08:00 | n/a
1.1.1 | Be Window before target | T | TH |  | Tied to TGT Review | 2003-12-01 | Tied to TGT Review
1.1.2 | do we need to do prev completed, such as horn test stand? |  | look through the book inherited from Dave Boehlien
1.1.2 | Target and Horns
1.1.2 | Chase cooling system | R | TH | http://www-numi.fnal.gov/numwork/reviews/july_30.html | final review on 7/30/03, EN by A.Stefanik , to be reviewed | 2004-05-27 08:00 | final review on 7/30/03
1.1.2 | Radioactive component handling & work cell | R | TH | 2002 feb_27.html |  | 2004-04-19 08:00 | covered in Shielding Assessment
1.1.2 | Target hall radiation shielding | R | TH | Rad Safety review 7/17/02, 2002 july_17.html | Shielding Assessment on Safetydocs web page | 2004-03-23 | covered in Shielding Assessment
1.1.2 | Neoprene Air Seal | F | TH |  | Approved by J.Priest |  | ?? Need email confirmation
1.1.2 | Tgt module | M | THC | 2002 aug_01.html | EN not yet complete E.Villegas | 2004-05-20 08:00 | EN not yet complete E.Villegas
1.1.2 | Target (inc. Be windows) | R,T | THC | 2002 aug_01.html | documentation complete & reviewed | 2004-08-02 08:00 | ready for Schuh committee
1.1.2 | Baffle | R,T | THC | 2002 aug_01.html | documentation complete & reviewed | 2004-08-02 08:00 | ready for Schuh committee
1.1.2 | Horn 1 module | M | THC | 2001 aug_10.html | MD-ENG-012, R.Silva | 2004-05-25 08:00 | ok'd by Schuh
1.1.2 | Horn 1 | M,E | THC | 2001 aug_10.html | K.Anderson'sTalk | 2004-06-17 08:00 | ready for Schuh committee
1.1.2 | Horn 2 module | M | THC | 2001 aug_10.html | MD-ENG-013,R.Silva | 2004-05-28 08:00 | comments received-need independent review
1.1.2 | Module plus components stand | M | MI8 | EN: J.Misek (in progress) | EN Reviewed? |  | status?
1.1.2 | Module assembly stand | M | MI8 | EN: V.Sidorov, reviewed by J.Sims | July 9 2003 note |  | ready for Schuh committee
1.1.2 | Module transportation stand | M | TH |  | n/a |  | n/a
1.1.2 | Horn lifting fixture (horn 1 & 2) | M | MI8, TH |  | MSG-EAR-03-322, B.Wands (LD#138) |  | ready for Schuh committee
1.1.2 | Work Cell | M,T | TH | EN: A. Szymulanski | EN Reviewed? | 2004-04-19 08:00 | EN Reviewed?
1.1.2 | Chase Duratek shielding | M | 10% prototype in Meson Detector Bldg | A.Stefanik has HA |  |  | complete
1.1.2 | Chase Duratek shielding | M | THC | A.Stefanik has HA |  |  | complete
1.1.2 | T Block Steel Cutting Procedure | M |  |  | MD-ENG-03-008, A. Stefanik |  | n/a
1.1.2 | Target Pile: Zero Layer Grout |  | THC | EN Complete | MD-ENG-03-015, A. Stefanik |  | n/a
1.1.2 | T-Blocks | M | Prototype in MAB | EN Complete | MSG-EAR-01-294, A. Stefanik, B.Wands | 2004-08-23 08:00 | ready for Schuh committee
1.1.2 | T-Blocks | M | THC | Tested as fabricated |  | 2004-08-23 08:00 | n/a
1.1.2 | Green Duratek block lifting fixture (Tongs) | M | THC | Complete | LD#142, J.Kilmer, B.Wands |  | ready for Schuh committee
1.1.2 | Blue Duratek block lifting fixture | M | THC |  | MD-ENG/03-0014, I. Fang | 2004-01-12 08:00 | ready for Schuh committee
1.1.2 | T-Block lifting fixture | M | THC | Complete | MSG-EAR-01-293, B.Wands, LD#130 | 2004-05-04 08:00 | ready for Schuh committee
1.1.2 | Module lifting fixture | M | MI8,TH | Complete | LD#132, B.Wands |  | ready for Schuh committee
1.1.2 | Stripline block assembly fixture |  | TH | EN: B. Boettinger | EN Reviewed? | 2004-04-27 08:00 | Status?
1.1.2 | Duratek shaft basket | M | TH | Being written by I.Fang | Being written by I.Fang |  | EN + review to come
1.1.2 | TSB transporter cart | M | TH | n/a (standard) |  |  | n/a
1.1.2 | R Block | M | TH | Complete |  |  | n/a
1.1.2 | monitor readout module (Budal, Bdot) | E | TSR |  | EN + review to come |  | EN + review to come
1.1.2 | Neutrino Device Instruments |  | TSR | n/a | n/a |  | n/a
1.1.2 | Hot Cell Door Transportation Stand | M | TH | EN to come, not designed yet | EN to come, not designed yet |  | EN + review to come
1.1.3 | Conventional magnet power supplies | E | MI60, MI65 | 2003 mar_PS.html |  | 2004-02-05 08:00 | n/a
1.1.3 | Kicker magnet PS (included in 111) | E | NA |  | SAR & LOTO to come | 2003-08-27 08:00 | SAR & LOTO to come
1.1.3 | Kicker PS installation |  | TSR |  | n/a |  | n/a
1.1.3 | Horn power supply | E | MI8 test stand |  | NuMI safety comm, complete |  | complete
1.1.3 | Horn power supply | E | TSR | complete | SAR & LOTO for PS Room | 2003-10-28 08:00 | update SAR & LOTO for PS Room
1.1.3 | Install Horn Power supplies | M | TSR |  | EN + review to come (includes TL) |  | EN + review to come
1.1.3 | Flexjoint |  |  |  | 1 EN for TL joints, TL & stands |  | 1 EN for TL joints, TL & stands
1.1.3 | Horn transmission line | E | TH,TSR | 2003 apr_23.html | 1 EN for TL joints, TL & stands | 2004-04-19 08:00 | 1 EN for TL joints, TL & stands
1.1.3 | transmission line Stands | M,E | TH,TSR |  | 1 EN for TL joints, TL & stands | 2004-04-19 08:00 | 1 EN for TL joints, TL & stands
1.1.3 | transmission line installation | M | TH,TSR |  | Horn PS & TL installation EN together | 2004-04-19 08:00 | Horn PS & TL installation EN together
1.1.4 | Decay pipe (note 1) | R | DR
1.1.4 | Decay Pipe Upstream end lifting fixture | M | THC | LD#143, D.Pushka | LD#143, D.Pushka |  | Reviewed and Ready for Schuh
1.1.4 | Decay pipe vacuum vessel | M | DR | MD-Eng/01-004-A, Chicago Bridge and Iron, ed by E.Chi | All but vacuum test(as per FESHM 5033) | Done during civil constr/ | Reviewed and Ready for Schuh
1.1.4 | Upstream decay pipe end cap | M | Test at MAB | contains MSG-EAR-02317 | All but vacuum test(as per FESHM 5033) |  | Reviewed and Ready for Schuh
1.1.4 | Upstream decay pipe end cap | M | THC | contains MSG-EAR-02317 | All but vacuum test(as per FESHM 5033) | 2003-11-24 | Reviewed and Ready for Schuh
1.1.4 | Downstream decay pipe end cap | M | Test at MAB | MD-Eng/01-004-B, E.Chi | All but vacuum test(as per FESHM 5033) |  | Reviewed and Ready for Schuh
1.1.4 | Downstream decay pipe end cap | M | THC | MD-Eng/01-004-B, E.Chi | All but vacuum test(as per FESHM 5033) | 2004-09-27 08:00 | Reviewed and Ready for Schuh
1.1.4 | Absorber | R,M |  |  | EN written, include core, shielding? | 2004-09-27 08:00 | EN written, include core, shielding?
1.1.4 | Absorber aluminum cores (8) | R | AH |  | EN written, include core, shielding? | 2004-09-30 13:00 | EN written, include core, shielding?
| Absorber stacking procedure |  |  |  | HA needed |  | n/a
| Base of Shaft Materials Handling |  |  |  | HA needed |  | n/a
1.1.4 | Absorber shielding | M | AH |  | EN written, include core, shielding? |  | EN written, include core, shielding?
1.1.4 | Installation crane headframe (note 2) | M | AH |  | need? |  | need?
1.1.4 | Fork truck lifting fixture (note 3) | M | AH,AP |  | need? |  | need?
1.1.5 | Muon monitors | O,E | MA1,MA2,MA3 | 2002 july_24.html | EN + review to come? | 2004-03-29 08:00 | EN + review to come?
1.1.5 | Hadron monitors | O,E | AH | 2002 july_24.html | EN + review to come? | 2004-10-14 08:00 | EN + review to come?
1.1.6 | Alignment | none | n/a | n/a |  |  | n/a
1.1.7 | Infrastructure: Water, Gas and Vacuum |  |  | 2002 mar_06.html |  |  | complete
1.1.7 | MI-62 (upstream) LCW |  | in MI-62 and MI | 2002 oct.html complete | 2002 oct.html complete | 2004-01-29 08:00 | complete
1.1.7 | MI-62 (upstream) Heat Exchanger | M | in MI-62? | Peer review submitted to reviewers (Fritz) 12 mos. Ago, no response yet | reviewed info? |  | comments received-need engineer response
1.1.7 | Beamline Vacuum pipe | M | MI to TH | n/a because pipes all under 12"OD (FESHM5033) | n/a | n/a | n/a
1.1.7 | Beamline Vacuum pipe Vacuum System | M | MI to TH | EN by Jim Klen, being reviewed by D.Pushka | EN in review process | 2004-07-16 08:00 | EN in review process
1.1.7 | Absorber RAW system | R | in Absorber access tunnel | awaits SB&O revisions before starting updates & review | EN note nearly ready for review | 2004-02-02 | EN note nearly ready for review
1.1.7 | Target RAW system | R | in Absorber access tunnel | Validation Comp | review complete? Need to go to Schuh? | 2004-04-05 | review complete? Need to go to Schuh?
1.1.7 | Horn 1 and 2 RAW system | R | in Absorber access tunnel | User, peer & Rad. Safety Reviews 2002 nov.html Complete | User, peer & Rad. Safety Reviews 2002 nov.html Complete | 2003-10-30 | Comments received,review on 9/05/03, request additional review
1.1.8 | Cables | F | All areas |  | status & what does Bob think is needed? |  | n/a?
| Cable installation |  |  |  | n/a | 2004-03-08 | n/a?
1.1.8 | NuMI stub monorail | M | in NuMI stub |  | n/a? |  | n/a?
| NuMI stub monorail - install |  |  |  | n/a? | 2003-08-08 | n/a?
1.1.8 | Beam transport |  | Primary beam transport |  | what is this? |  | n/a?
1.1.8 | Radiation safety interlock system | E,R | Main Injector to Absorber Hall access tunnel |  | will be reviewed according to FESHM |  | n/a?
1.1.8 | Controls |  |  | 2003 mar_L3.html | n/a? | 2004-04-27 | n/a?
all | All | see below (1) | Main Injector to MINOS Hall | Internal 7/17/03 |  | Final review / Shielding Assessment, 1/04 | Final review / Shielding Assessment, 1/04
all | All | all | Main Injector to MINOS Hall | SAD |  | start through BD by 6/04 | start through BD by 6/04
all | access procedures |  |  |  | draft complete & reviewed internally |  | OK'd by Schuh
all | training req. |  |  |  | draft in progress |  | n/a
1.1.2 + 1.1.3 + 1.1.7 | Horn power supply, Horn to raw, target, module, etc | see below (2) | Target hall |  |  |  | n/a?
1.2 | Infrastructure | see below (3) | All new underground areas |  |  |  | I think this is covered in other reviews, access procedures, etc. You can ask Ducar.
2.1 | Magnets: Steel and Coil
2.1.1 | Steel Plane Fabrication | M,S | S,NM,MH |  | M: S:
2.1.2 | Steel Handling Fixtures | M | S,NM,MH |  | M: |  | JK 11/22/99
2.1.3 | Near Detector Support Structure | M,S | NM,MH | NI: 8/24/2000 | M: S: |  | IF 1/31/00
2.5.1 | ND Support Structure installation(SB&O ) | M | MH |  |  | 2004-01-08 17:00
2.5.3 | Detector Installation | M | MH |  |  | 2004-02-24 08:00
2.5.3 | Remove Planes from Detector | M | NM | n/a |  | 2004-02-24 08:00 | IF 2/23/00
2.5.3 | Load truck at New Muon Lab | M | NM | n/a |  | 2004-02-24 08:00 | IF 2/23/00
2.5.3 | Move planes down shaft | M | MSA | n/a |  | 2004-02-24 08:00
2.5.3 | Base of Shaft Materials Handling | M | MSA | n/a |  | 2004-02-24 08:00
2.5.3 | Mounting Planes on Detector | M,S | MH | n/a |  | 2004-02-24 08:00 | IF 1/31/00
2.1.4 | Magnet Coil | E | S,NM,MH | NI: 4/13/2000 | E: | 2004-08-24 08:00 | JK 10/26/01, JK 8/17/01
2.5.3 | Coil Transport down Shaft | M | MSA,MH |  | M: | 2004-08-24 08:00
2.5.3 | Magnet Coil Installation | M | S,NM,MH | n/a | M: | 2004-08-24 08:00 | 2002-02-07
| Magnet Coil Welding Procedure | F | MH |  | F:
2.1.4 | low current coil tests | E | MH |  | E:
2.1.4 | high current coil tests | E | MH |  | E:
2.1.4 | remote operations of coil | E | MH |  | E:
1.1.8 | LCW System | M | MH
2.1.5 | Detector Plane Prototypes | M,S,E | NM |  | M: S: E: |  | IF 2/23/00
2.2 | Scintillator Detector Fabrication
2.2.1 | Scintillator Strips | n/a | ANL | n/a | n/a |  | n/a
2.2.2 | Fiber | n/a | ANL | n/a | n/a |  | n/a
2.2.3 | Scintillator Modules | M | ANL,MH | n/a | n/a |  | n/a
2.2.3/2.5.2 | Scintillator Module Installation | M | NM |  |  | 2002-02-18 08:00
2.5.2 | Plane Assembly | M | NM |  |  | 2002-02-18 08:00
2.5.2 | Unload truck at New Muon Lab | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
2.5.2 | NM materials handling (Ingrid's cart) | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
2.5.2 | Mounting planes on Detector | M | NM | n/a |  | 2002-02-18 08:00 | IF 1/31/00
2.5.2 | Unload ND Steel Planes | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
2.5.2 | materials handling (Ingrid's cart) | M | NM | n/a |  | 2002-02-18 08:00 | IF 2/23/00
| Attach Modules to Steel | M | NM | n/a |  | 2002-02-18 08:00
2.5.2 | Mounting Planes on Bookend | M | NM | n/a |  | 2002-02-18 08:00 | IF 1/31/00
2.2.4 | PMT's | n/a | MH
| PMT Installation into Alner Boxes | n/a | MH
2.2.5 | Spectrometer Mux Boxes | n/a | ANL,NM
| Mux Box Installation | n/a | MH
2.2.6 | Light Injection System | E | ANL | NI: 9/22/2000 | E:
2.2.7 | Assembly and Test Equipment | n/a | ANL | n/a | n/a |  | n/a
2.2.8 | Factories | n/a | ANL | n/a | n/a |  | n/a
2.3 | Electronics DAQ, and Database
2.3.1 | Near Detector Front End | E | MH | NI: 4/17/2002
2.3.1 | Fiber Cables |  |  | NI: 4/17/2002
2.3.1 | All Other Cables |  |  | NI: 4/17/2002
2.3.1 | PMT (Alner) Boxes |  |  | NI: 4/17/2002
2.3.1 | Printed Circuit Boards (Master, Minder) |  |  | NI: 4/17/2002
2.3.2 | Far Detector Front End | n/a | S | NI: 10/24/2000 | n/a | done | n/a
2.3.3 | Data Routing and Trigger Farm | n/a | NM,S |  | n/a |  | n/a
2.3.4 | DAQ and Triggering | n/a | NM,S | NI: 2/20/2001 | n/a |  | n/a
2.3.5 | Database--UMN | n/a | NM,S | NI: 2/13/2001 | n/a |  | n/a
2.3.6 | Auxiliary systems (clock, gps) | n/a | NM,S | NI: 2/20/2001 | n/a |  | n/a
2.3.7 | Electronics Management | n/a | n/a | n/a | n/a |  | n/a
2.3.8 | Slow Control and Monitoring | n/a | NM,S | NI: 1/9/2001
2.5.3 | Electronics Installation | E | MH |  |  | 2004-04-20 08:00
2.5.1 | Rack Installation | E | MH |  |  | 2003-09-23 08:00
2.3.9 | HV System | E | NM,S
2.5.3 | HV system Installation | E | MH |  |  | ???
2.4 | Far Detector Installation
2.4.1 | Completed Design Tasks | n/a | n/a | n/a |  | done
2.4.2 | Management | n/a | S | n/a |  | done
2.4.3 | MINOS Construction Oversight | n/a | S | n/a |  | done
2.4.4 | Soudan Lab Infrastructure | n/a | S | NI: 3/24/2000 |  | done
2.4.5 | Detector Installation | M,E | S |  |  | 6/3/2003
2.5 | Near Detector Installation--for most, see under other WBS elements
2.5.1 | Infrastructure | M,E | MH |  |  | 2004-01-08 17:00
2.5.3 | Power Distribution System | E | MH |  |  | 2004-08-27 08:00
2.5.4 | FNAL Outfitting Systems-LCW?
2.5.5 | SB&O Experimental | n/a | n/a | n/a |  |  | n/a
| Locations: |  | Review Types: | Operational Reviews may include:
| NS=NuMI Stub |  | M=Mechanical | ORC's (Detector)
| EE=Extraction Enclosure |  | S=Structural | NuMI Internal Reviews
| CR=Carrier Region |  | E=Electrical | FESHM's
| Pre-TGT=Pre-target |  | R=Radiation
| TSA=Target Shaft area |  | T=Toxic Materials
| TSR=Target Support Rooms |  | O=Oxygen Displacing Gasses
| HP=Horn Pit |  | F=Fire
TH=Target Hall
| THC=Target Hall Chase |  | Key, notes:
| DR=Decay Region |  | Review & Documentation needed | fuscia (dated expected)
| AH=Absorber Hall (but not MA1) |  | Engineering note in review process | underline (date to reviewer)
| AP=Absorber Passageway |  | Engineering Note Complete & Reviewed | bold - ready for Schuh Committee
| MA# = Muon Alcove 1,2,3,4 |  | Engineering note to Schuh Committee | italics (date to committee)
| MSA=MINOS Shaft Area |  | qeustions | pink, not sure of data
| MHP = MINOS Hall Passageway |  | LD#: lifting device number, original is in WH11X Binder, includes load test and review of calcs
| MH=MINOS Hall |  | NI: NuMI Internal (Review)
| NM=New Muon Lab |  | Means the date is wrong--now included in SB&O contract, and is done |  | orange
| S= Soudan |  | (note 1) Rad: ground water activation, prompt and residual radiation, air activation |  |  | blue
| ANL=Argonne Nat'l Lab |  | (note 2) Elect: good ground for water skid? Module? Target? |  | green
| MI65= itself |  | (note 3) Fire protection, FIRUS, access limits |  | yellow
complete as of 7/03 means reviews completed, comments from reviews being addressed, elements not thought to need Schuh
review.
Note on E9: HTML Source: http://www-numi.fnal.gov/numwork/reviews/
Note on F9: M = Mechanical G = Flammable Gas E = Electrical F = Fire ) = ODH R = Radiation T = Toxic Material

## Status Sheet
Status 9/04/03, DAH
| Total # EN, Doc needed* | ENs, Docs to be written* | % To be Written | # in Presently in or ready for NuMI review process | # ready for Schuh | # given to Schuh | # Returned from Schuh | % to Schuh | % Returned from Schuh | # read by Schuh, iterating | # Completed and OK'd by Schuh
NuMI EN or other documentation | 63 | 36 | 57.14% | 2 | 15 | 16 | 16 | 25.4% | 25.4% | 9 | 7
MINOS EN or other documentation |  |  | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
*best guess, numbers good to +/- 2 for total & needed
Still need for summer shutdown: | Status:
EPB (5) Stands | returned from Schuh, comments on Hilti anchor tests from D.Pushka, awaiting approval
Q102-Q104 Stands | Need FESS review for 90,96, and 97 awaits final word from Schuh
HQ107 stands | EN still to finish 1321-ES-296401
B2 Stands | returned from Schuh, response provided by engineer, awaiting approval