T. Dombeck

9/11/02

FERMILAB ACCELRATOR CHAIN VULNERABILITIES

Summary

A study was undertaken to answer questions raised by Fermilab management about the vulnerability of the accelerator chain to the failure of one or more critical elements that might put the physics program out of commission for a long period of time.  In this report we limit the study to those components that would jeopardize Collider operations for a period of three or more months.  This question was posed to those responsible for the development, operation, and maintenance of the facility.  There were tens of critical components identified whose failure might pose such a threat to operations.  These items are summarized in this report, along with recommendations that might mitigate the possibility of a failure.

Historically, the Fermilab accelerator chain has had a few such catastrophic failures that occurred during the early decades of operation.  A substation power transformer was lost in 1985 at which time Fermilab was running only external beams [1].  Though the repair required about eight months, the physics program at that time was able to limp along, but with much reduced capability.  Another catastrophic failure during the first decade of Tevatron running resulted in the loss of thirty-three superconducting dipole magnets in the single year of 1989 [2, 3].  Such a loss occurring at this time would virtually exhaust the pool of spare magnets jeopardizing future running.  The cause of these particular catastrophic failures was investigated and their sources have been addressed to ensure they do not recur.

The current study has uncovered an additional set of components that might cause catastrophic downtimes due to failure.  A number of these critical elements lay in the oldest parts of the accelerator chain, namely the Linac, the 8-GeV Booster, and their associated transfer lines.  These Proton Source systems have performed remarkably well over their thirty years of operations.  In the case of the Booster, there is no reason to doubt it will continue to perform at its current repetition rate of about 2 Hz.  However, the proposed increase in pulse rate from 2 to 12 Hz to meet the demands of the Mini-Boone and NUMI experiments, will place a strain on the aging equipment.

Furthermore, there are some components that were not designed for the increased Booster repetition rates, for instance, the four orbit bump magnets.  There have not been any failures in these magnets over the ten years of their operation, and there are two spares, however there are concerns of heating problems at the highest repetition rates.  Tests indicate that the magnets may perform appropriately up to 7.5 Hz and this would meet the requirements for the Tevatron and Mini-Boone.  Higher repetition rates (~12 Hz) needed to include NUMI, may require a modification of the Booster injection system [4].

In this report, vulnerabilities due to one-of-a-kind components are also discussed.  Such items appear throughout the accelerator complex.  Though reliability has been good, some of these items do not have spares, such as the 400-MeV chopper at the end of the Linac.  Other specialty items, such as kicker magnets, have single spares, but the lack of availability of replacement parts could pose a problem.  To limit the scope of the present study, some one-of-a-kind components were not considered, for example a failure in the focusing horns in the NUMI or Mini-Boone beamlines, or failures in the experimental detectors.  The repair of such devices might require much time to implement and put those experiments out of commission.  However, such components were not considered because the Collider accelerator complex would not necessarily be affected by their failure.

In some cases, having spares would be prohibitively expensive, such as the Linac accelerating cavities.  Creating spares would require much resource due to the number of unique structures down the length of the machine.  Furthermore, experience at other laboratories, ANL [5] and LAMPF [6], have shown that accelerating cavities rarely experience catastrophic damage even after many decades of operation.  Even though replacing a damaged structure would require many months of downtime, building an inventory of replacement parts would seem unwarranted.

There are other one-of-a-kind electrical devices that could stop operations where it would be less expensive to provide a spare.  Some of these components are thirty years old, such as the 345-KV MSS switchgear, and are beyond the Laboratory's capability to repair in-house.  In other cases, the expertise to fix the item has dissipated, such as the low-level rf for the 8-GeV Booster.  Presently, estimates to repair or replace these items cover a range of potential downtimes and may constitute a risk to operations.  Other one-of-a-kind devices, such as pickups in the Accumulator stochastic cooling system, are not as much of a risk.  In a crisis where one of these units is lost, it is believed that a work-around or a replacement could be devised within a few weeks.

There are a few specialty components where multiple failures might jeopardize operations because only one spare exists.  In this category are the low-beta magnets, the low-beta power supplies, and the Main Injector power supply transformers.  In each case, replacements require a special order with a long-lead time.  Procuring additional spares would be advisable.  However, as they are moderately expensive, a staged approach might be possible.  For instance, the greatest risk for the Main Injector supplies occurs when the NUMI experiment is operational, so for the immediate future the emphasis could be to provide an additional spare for the Tevatron low-beta supplies.

Another example of high-risk specialty items, are the kicker magnets in the Main Injector and in the Tevatron.  In general, a failed kicker magnet could be quickly repaired except for one critical component, the long ceramic insert.  Except for the single spares on hand, there is currently no source available to fabricate ceramic replacements.  In view of this problem, the handling of the spare kickers should be placed under particular scrutiny to prevent inadvertent breakage of these key components.  A long-term solution to obtain ceramic inserts should also be considered.

There are a number of infrastructure items that might produce long down periods if allowed to progress to the point of failure.  Among these are the silting of the cooling ponds around the Tevatron and the degeneration of the wooden power poles.  These items are inspected on a regular basis, and there is a progressive remedial plan worked out, though sufficient funding has not been identified as yet to complete the work.

Finally, there are staffing concerns at all levels throughout the Beams Division accelerator groups.  The general feeling is that the complexity of the system has grown in the last decade with the addition of the Main Injector, the Recycler and various external beam experiments.  The plans are to expand the program further with B-TeV and a 120-GeV beamline.  There has not been a corresponding increase in personnel and has resulted in more reliance on contract labor.  In some cases there has been a loss of particular expertise due to attrition.  This could result in accidents due to "human error."  Such was the case last year when a technician unfamiliar with the Tevatron components inadvertently connected a water cooling line to a He feed line resulting in the contamination of ten superconducting components.  The results were not disastrous in this case, however, lack of proper personnel could make it difficult to recover from a large-scale failure in a timely fashion, thus jeopardizing the core physics research program of the Collider.

Introduction and Methodology

The definition of what constitutes a critical component whose failure could shut down Fermilab operations is intimately connected to the resulting downtime that can be tolerated.  The number of such components increases dramatically, probably exponentially, with the inverse of the tolerated downtime.  For instance, there are probably thousands of such items that might cause a one-week downtime.  Fortunately, each such failure has a small probability of occurring and this situation is best analyzed from a machine reliability standpoint [8].

On the other hand, there are perhaps one hundred such critical components that might cause a one-month downtime, tens of items causing a three-month downtime, and only a few items that might cause a six-month downtime.  As one month is on the order of the usual downtime for routine maintenance, a failure of this magnitude would probably result in the next scheduled maintenance period being advanced.  Therefore, in this study we limited consideration to those items that might cause extended downtimes of three months or longer.

That said, it is difficult to assess if a certain component failure would indeed result in a downtime of three or more months.  Facing such a disaster, the Laboratory would muster its forces to provide workarounds to bring operations back on line as soon as possible.  On the other hand, it is equally difficult to analyze how a particular failure might cascade and generate related failures that spread throughout the complex, e. g., a power failure that ruins electronic circuits or computing files in other systems resulting in months of trouble shooting.  Therefore, the philosophy in this report is to err on the conservative side, if a three-month downtime were believed to be possible for any particular component, it was put on the list.

This report contains a set of tables presented by accelerator type and/or subsystem with items identified by accelerator personnel that were deemed to pose a risk to operations.  Comments are given on the current status of the identified components.  A risk factor (high, medium or low) is assigned based on the perceived probability for a failure, though no attempt has been made to quantitatively analyze the probability of a failure occurring.  Only in a few cases, such as superconducting dipoles, has there been a sufficient sample to arrive at meaningful conclusions.  Finally, a discussion follows with recommendations to mitigate the effect of a potential failure for the highest risk items.

A summary is presented at the end of the report of a mutual study performed between Beams and Technical Division personnel.  This study addressed the status of spares and the general question of performing repairs on large components such as conventional and superconducting magnets, as well as Tevatron spool pieces.  These components require large-scale in-house maintenance facilities.  In essence it was felt that there were sufficient spares on hand for most of the accelerator chain.  There were exceptions.  For instance, there are sufficient spares for the gradient magnets in the Booster, however the operational status of these spares is not confirmed.  There are also a few specialty magnets, such as the kickers in the Main Injector and Tevatron, that have a spare, but fixing a broken device might not be possible.  For other one-of-a-kind magnets, it was felt that even with a need to bring old tooling out of "moth balls," repairs could be achieved in the allotted time with the initiation of a crash program at the time of the failure.

Finally, there could be catastrophic losses due to fires or floods that might affect large parts of the accelerator complex.  Disasters of this sort are better studied from an historical perspective along with the standard equipment installed to mitigate losses.  Therefore, these are not discussed in this report.  On the other hand, there are a number of potential risks for "human error" accidents, some of which are discussed in this report.  For example, there are cases where both the piece of equipment and its spare are stored in the same location.  This practice might jeopardize the recovery of operations after a fire.  The vulnerability due to such procedural concerns are not discussed in any detail in this report, however, it might warrant a future investigation to determine what mitigating actions might be undertaken.

Front End Source, Linac, and Associated Beamlines

| Component | No. | Spares | Risk* | Vulnerability Comments |
| --- | --- | --- | --- | --- |
| Cockroft-Walton | 2 |  | L | Aging equipment, but two sources in operation, thus providing a spare (See discussion below.). |
| 750-kV, 200-MHz Buncher Cavity | 1 | 0 | L | One of the oldest pieces of equipment in the accelerator chain (See discussion below.). |
| 200-MHZ Structures and In-Tank Quads | 5 | 0 | L | Some of the oldest pieces of equipment in the accelerator chain (See discussion below.). |
| #7835 Amplifier Tubes (200 MHz) | 5 | 1 | H | Failure rate is about 3.5/yr., 7 in rebuild, single vendor (See discussion below.) |
| Modulator Switching Tubes (200 MHz) | 15 | 40 | M | Failure rate is about 7/yr., single vendor (See discussion below.) |
| 805-MHz Structures and In-Tank Quads | 28 | 0 | L | 10 yrs. old (See discussion below.). |
| 400-MeV Chopper | 1 | 0 | L | Required to run booster, no backup, but reliability high so not deemed risk at this time (See discussion below.) |
| 400-MeV Spectrometer Magnet | 1 | 0 | L | No backup, but magnet has spare coil capacity and so not deemed risk at this time |

*Risk of failure deemed H=high, M=medium, and L=low.

The Front End Source and the 200-MHz Components are some of the oldest pieces of equipment in the accelerator chain.  They must be operational in order to have any protons available for the physics program.  They are expected to operate with high availability, >97%, and have done so for many years.  However, signs of aging are appearing, such as the modulators and the Amplifier Tubes, and the lack of vendors to make replacement parts.

The Front End Source situation was recently summarized in a talk presented by Bob Webber to the Laboratory Directorate [9] along with a proposal to replace the oldest items with more up-to-date components, such as an rfQ and 402-MHz accelerating cavities.  The cost of such an upgrade is estimated to be about $27.5M, however, there are a number of reasons to consider such an upgrade, including a promise of a five times brighter proton beam.  Even with the most optimistic timetable for the upgrade to take place, there would be a fairly long period of at least 6 years using the present equipment, in which backup 200-MHz parts must be maintained.

The Linac already runs continuously at 15 Hz, so the additional strain on operations imposed by the MiniBoone and NUMI experiments, will not affect the Linac requirements.  Therefore, the average failure rates observed for Linac components are not anticipated to change in the near term and the required number of spare parts can be determined with a reasonable accuracy.  For instance, the accelerating cavities and the quadrupoles that reside in the tanks can be expected to operate with little risk of failure as experience at other longer-running Linacs has shown [5-6].  However, the external rf power generation system requires an adequate flow of replacement parts.  Maintaining this flow probably poses the greatest risk to continued Linac operations at this time (see below).

Amplifier Tubes (#7835, 200 MHz) are required for generation of rf power for the first section of Linac cavities, with five in operation at any given time.  Experience with these tubes [10] indicates that the failure rate is about 3.5 tubes per year.  Currently, there is one "good" spare and one "bad" spare in the inventory.  However, there is one vendor, Burle Industries [11], that builds new amplifier tubes and rebuilds failed ones.  It requires about nine months to complete one tube.  In recent times there have also been concerns that the life expectancy of the rebuilt tubes may be less than hoped [10].

The ideal situation would be to have eight spares on hand [9].  This would allow some recovery time in case of the possible loss of the sole vendor, or a rash of replacement tubes that do not meet specifications.

Recommendation:  There is excess capacity at Burle Industries at this time to double the rate of delivered Amplifier Tubes [11].  Though the additional rate would be expensive, it would permit the inventory of spares to rise to a sufficient level to avert long downtimes due to tube rebuilds.

Modulator Switching Tubes (200-MHz) fail at the rate of about seven per year, out of the fifteen in operation at any given time.  There was an order of fifty tubes from the single vendor, out of which there are now about forty tubes in the spares inventory.  There has been a successful rebuild of a failed tube.

Recommendation:  The capability to rebuild failed Modulator Switching Tubes should be encouraged.

400-MeV Chopper is required for the operation of the Booster.  There is no spare chopper or backup to its driving electronics, though spare cards exist.  Furthermore, there has been the loss of expertise recently.  The effect of the loss of the chopper has not been ascertained, though it does clean up the Linac pulses to reduce beam losses in the Booster.

The chopper is an electrostatic device that requires fine alignment of the plates.  There are few elements that can break if left as is, however, there would be a risk of upsetting the device if it were moved.

8-GeV Booster and MI-8 Beamline

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| Gradient Magnets | 98 | 8 | L | Operational status of the spares is not known (See discussion below.) |
| Orbit Bump Magnets | 4 | 2 | H | High rep rate will cause thermal problems (See discussion below.) |
| Kicker Magnet | 9 | 1 | L | Replacement ceramic inserts under fabrication (See discussion below.) |
| Low-Level rf System | 1 | 0 | H | Outdated electronics (See discussion below.) |

Ring Gradient Magnets cycle at 15 Hz so the increased repetition rate of the Booster for the neutrino experiments should not stress these components more than under present operations.  Furthermore, there have not been any failures in these magnets over many decades.  There are spares, but they have not been checked for many years, so their operational readiness is not guaranteed.

Recommendation:  Identify where all spare gradient magnets for the Booster ring are stored and power test a few of them to ensure their viability.

The Orbit Bump Magnets were installed ten years ago when the injection energy was increased to 400 MeV.  They were originally designed for low repetition rates appropriate for Tevatron operations (~2 Hz) and have poor heat transfer making cooling difficult.  Mini-Boone requirements will increase the repetition rate to 6.5 Hz and the heat generation will increase accordingly.  A spare orbit bump magnet was tested at 7.5 Hz operation for 36 hours and though the temperature rose significantly, there was no failure.  This might allow operations for the Mini-Boone experiment with the currently installed magnets.

The addition of NUMI operations will increase the repetition rate further to about 12.5 Hz with a corresponding increase in temperature.  There is a risk is these magnets will fail at the higher repetition rates.  There are two spares, but they will not suffice in the case of the added requirements.

As part of the Proton Driver study, there were suggestions presented for improved injection lines that would operate at 15 Hz thus alleviating the orbit bump problem [4].  These upgrades might be expensive and require downtime to install.

Recommendation:  Studies should continue on ways to improve cooling of the present orbit bump magnets.  However, a parallel study should be initiated on improving the Booster injection line to accommodate 15 Hz operations.

Kicker Magnets in the Booster system are smaller than those in the Main Injector or Tevatron.  They do not suffer the same problems of replacement parts, such as the ceramic inserts.  (See general discussion on Kickers in the Main Injector section.)  Those needed for Booster operations can be fabricated on the Laboratory site.

The Low-Level rf System is old and was created from diverse modules.  The expertise to maintain it has dissipated.  There are replacement electronics cards.

Recommendation:  The backup modules should be checked to ensure their operational readiness in case of a failure.  The long-term solution would be to replace the system with more up-to-date electronics that matches other systems throughout the accelerator complex.

Main Injector and Associated Beamlines

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| Harmonic Filter Damping Resistors | 2 | 1 | H | Requires a double failure, but could occur in either Main Injector or Tevatron (See discussion of Power Grid in Site Infrastructure section.) |
| Dipole PS Transformers | 12 | 1 | H | These are long-lead time items that could reduce the physics program for up to 6 months (See discussion below.) |
| Quad PS Transformers | 6 | 1 | H | These are long-lead time items that could reduce the physics program for up to 6 months (See discussion below.) |
| Main Injector Quadrupoles | 269 | 26 | M | Had a number of failures, but able to keep up with replacement rate so far (See the section on the TD/BD Study on Magnet Spares.) |
| Kicker Magnets | 6 | 1 | L | One spare for each type (See the general discussion below.) |

Dipole and Quadrupole Power Supply Transformers have not suffered any failures to date, however, special fabrication would require about six months to replace these components.  At present there is one spare supply each for the dipole and for the quadrupole magnets.  They cost about $150k and $80k respectively to replace.  The primary risk would involve a double failure that would reduce operations, but not necessarily shutdown the Collider program, as the Main Injector could be run at a reduced repetition rate to compensate.  However, following a double failure, it might not be possible to run the NUMI experiment.

Recommendation:  Given the long-lead time, begin the procurement of two additional spare power supply transformers, one for the Main Injector dipole magnets ($150k) and one for the quadrupole magnets ($80k), to have spares arrive when NUMI becomes operational.

Kicker Magnets occur in various parts of the accelerator complex: Booster, Main Injector, Accumulator, Recycler, and the Tevatron.  There is one spare for each type.  Though the magnets suffered some "infant mortality," but in recent years there have been no failures.

Responsibility for the kicker magnets is currently under discussion to be transferred from Beams Division to Technical Division.  Repairing a damaged kicker magnet is generally not considered to be difficult, but there is one critical component, the long ceramic inserts for the Main Injector and Tevatron magnets.  The sole vendor has stopped making ceramics.  In case of failures in these components, it is not clear at this time how replacement inserts can be manufactured, though some thought has been given to alternative materials.  It should be pointed out that the Booster kickers do not suffer from this problem because the ceramic inserts are smaller and more readily available.

The difficulty in replacing the inserts places a special onus on the handling of the spare magnets to ensure the ceramics are not damaged inadvertently.  Most of the kicker spares are stored in the F0 area, but others are stored in areas around the Laboratory site.

Recommendations:  The responsibility for the kicker magnets should be resolved.  The spares should be collected together in a secure location to ensure proper handling.  Work should continue to find a replacement material for the long ceramic inserts, or a new vendor found.  Laboratories around the world should be poled to see if they have developed sources for these critical components.

P-Bar Source, Accumulator and Associated Beamlines

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| Core Stochastic Cooling System | 1 | 0 | L | Pickups and kickers have no spares (See discussion below.). |
| Kicker Magnets | 4 | 1 | H | Spare for each type (See general discussion for Kickers in the Main Injector section.) |

Core Stochastic Cooling System components have been very reliable since the early days of operations.  There were a few failures at the beginning, but these were easily repaired.  Over many years of operations, there have been no known failures inside the rf tanks, similar to the experience with the Linac cavities.  If there were a failure of the pickups or kickers, it is anticipated these could be repaired or replaced in less than three months.  Therefore, maintaining a pool of expensive spares is not deemed necessary.

Other rf elements in the p-bar cooling system have multiple tanks.  If a failure occurred in one of these, it is believed that the source could be made to work utilizing only the working modules.

Recycler

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| Gradient Magnets | 324 | 8 | L | Concerns about long-term depolarization of permanent magnets (See discussion below.) |
| Specialty Magnets | 8 | 3 | L | Concerns about long-term depolarization of permanent magnets (See discussion below.) |
| Quadrupole Magnets | 92 | 0 | M | All spares were used to modify ring lattice (See discussion below.) |
| Kicker Magnets | 2 | 1 | H | Spare for each type (See general discussion for Kickers in the Main Injector section.) |

Gradient, Quadrupole, and Specialty Permanent Magnets in the Recycler ring and beam lines might lose magnetization due to long term radiation and temperature effects.  The magnets are compensated for short-term temperature variations, and the ferrite material is also known to have excellent radiation resistance.  The long-term field variations have been measured [12], and continue to be monitored in a few magnets over long time periods.  The results have indicated a 0.35% loss in magnetization is expected over an estimated twenty-year operating period.  Therefore, the long-term loss in magnetization is not considered to be a risk.

If there were a noticeable depolarization in a set of Recycler magnets, they would have to be taken apart, the bricks remagnetized, and the magnets reassembled.  This could be accomplished at the rate of three magnets per day given the availability of equipment and trained personnel.  Currently, the magnetizer is installed in IB2 and it is estimated that reconstituting the permanent magnet factory could be accomplished in a short time with a concerted effort.

Quadrupole Magnet Spares have been used to modify the ring lattice exhausting the pool.  However, this is not considered to be a major threat to Collider operations unless an accident occurred, i. e., a forklift damaged a large section of the ring.  The Mini-Boone beamline uses quadrupoles of the same basic design as the Recycler.  There are two spare magnets for this beamline that could be retrimmed within a few weeks for use in the Recycler.

Tevatron Ring Components

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| Harmonic Filter Damping Resistors | 2 | 1 | H | (See discussion on Power Grid in Site Infrastructure section.) |
| Kicker Magnets | 4 | 1 | H | Spare for each type (See general discussion on Kickers in the Main Injector section.) |
| Superconducting Dipoles | 827 | 35 | L | Two different types (See below and the section on the TD/BD Study on Magnet Spares.) |
| Superconducting Quads | 212 | 31 | L | Eight different types. (See below and the section on the TD/BD Study on Magnet Spares.) |
| Spool Pieces | 186 | 38 | L | Fifteen different types. (See the section on the TD/BD Study on Magnet Spares.) |

Superconducting Dipole and Quadrupole Magnets had original design criteria for a twenty-year life expectancy.  The Tevatron is pushing this limit, however, the original criteria were based on the more stringent requirements of the machine ramping at higher repetition to service the fixed target program.  Collider requirements are relaxed in this regard, and it is doubtful that a fixed target Tevatron program would be re-instituted.  Furthermore, if life expectancy problems start to arise, they would most likely manifest themselves through a continual series of incidents whose frequency began to increase.

Recommendation:  Assign responsibility to track and assess the frequency of Tevatron component failures to note trends.

Tevatron Low-Beta Intersection Regions

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| PS (Magnetics) | 10 | 1 | H | Had one failure. Long-lead time to replace. (See discussion below.) |
| Q2 with 6-Lead Box | 4 | 1 | M | Shielding makes it difficult to reach (See discussion below.) |
| Low-Beta Quads | 22 | 8 | L | Six different types. A single complete spare plus one spare cold mass exists for each type. (See the section on the TD/BD Study on Magnet Spares.) |

Low-Beta Power Supplies (Magnetics) have suffered one failure in recent years.  The component is a transformer that is a special fabrication requiring about two months to replace.  At present there is a spare supply, but there is a risk of a double failure that would shutdown operations.

Recommendation:  Given the long-lead time, begin the procurement of an additional low-beta power supply (~$30k) to be used as a spare.

Q2 with 6-Lead Box replacement is made difficult due to the concrete shielding that must be removed to gain access.  Previous estimates were that two months of rigging might be needed to free a box, make the necessary change out, and restack the concrete.  The situation has since been exacerbated by the addition of more iron shielding.  However, it is felt that with a concerted effort the replacement might be accomplished in much less time.  Therefore, at this time it is not known if a Q2 failure would cause a three-month downtime.

Recommendation:  An attempt should be made to understand the time needed to accomplish a low-beta Q2 and associated 6-lead box replacement.  If there is a potential for a long downtime, means to reduce this time should be investigated.

Tevatron Cryogenics

| Component |  | No. |  | Spares |  | Risk |  | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Centrifugal Cold Compressors | 24 |  | 3 |  | H |  | Not sufficient spare parts on hand to ensure continued operations through the entire Run II program (See discussion below.). |  |
| Reciprocating Cold Compressors |  |  | 4 |  | L |  | These constitute additional spares to the Centrifugal Cold Compressors |  |
| Transfer Lines From CHL |  |  |  |  | H |  | Exposed piping under busiest roadway on Laboratory site (See discussion below.) |  |
| Controls System |  |  |  |  | L |  | Aging, but being addressed |  |
| Water Contamination in the Helium System |  |  |  |  | H |  | Cause could be human error or accident that opens system to damp air (See discussion below.). |  |

Cold Compressors are custom-made devices with long-lead times for replacement.  The philosophy has been to keep on hand sufficient replacement parts for those components most likely to fail, such as bearings, rotors and impellers.  The estimated life expectancy of the installed components, and including the replacement components on hand, still does not cover the anticipated duration of Run II.  Therefore, it will be necessary to augment the spare parts, the most expensive and longest lead-time of which are the rotors.

Recommendation:  Funding resources of about $100k should be made available to buy the needed spare cryogenic refrigerator components to ensure the successful completion of Run II.

Transfer Lines From CHL to the Tevatron are exposed as they cross under the busiest roadway on the Laboratory site.  Though protected by guard rails and other barriers from a direct vehicular accident, the piping could be damaged by falling debris, such as a gas bottle, etc.  The major concern is severing the liquid nitrogen lines that might send the Tevatron through a thermal cycle.  In that case, recovery could require up to six months.  In such circumstances, the machine might be kept cold by trucking in liquid nitrogen and pumping it in through one of the satellite areas.  All of this would incur large expenditures during the time of repairs, and of course, the Tevatron could not operate until the transfer lines were repaired.

Recommendation:  Install a culvert or some other cover that would protect the exposed CHL piping to the Tevatron from a potential damage from an accident.

Water Contamination in Helium System and subsequent clogging of the refrigerators could result from "human error."  In this case the system would have to be warmed and the contamination eliminated by purifying and conditioning with warm nitrogen and helium.  The length of time for recovery would depend on the extent of the contamination, but it might amount to many months.  Furthermore, prematurely starting operations without adequate conditioning would just result in a continual series of clogged filters.

A near miss occurred about one year ago when a spool piece was replaced and a water cooling line was interchanged with a helium gas line.  This dumped water into the crygenic system requiring the removal and replacement of ten Tevatron components.  Operations were recovered within a week, however a more serious disaster was avoided only because the error was identified quickly enough such that only a few elements were contaminated.  The erroneous hookup involved a long-time employee of the Laboratory, however, he was working in an unfamiliar environment.  To alleviate such problems in the future, the fittings on the pipe ends will no longer be the same for the Helium and for the water pipes making such an interchange impossible, however, this change out has just begun and probably will continue for some time.

Recommendation:  In the case of the change out of the Tevatron spool piece water pipe fittings, the work should proceed as planned.  However, it would be advisable to keep a record of the devices where the change has yet to be completed to be sure the change out occurs in a timely manner.

Global Systems

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| Controls System Computers | 30 | 35 | L | Uses out-dated VAX computers (See discussion below.) |
| Electronic Modules and Their Spares Stored in Same Location |  |  | M | In the case of a fire or other mishap the backup device might be lost (See discussion below) |

Controls System Computers are currently VAXes that are no longer manufactured or supported commercially.  At present, it is still possible to obtain tens of VAX computers on the used market in a short time, however, this situation might change in the future.  The controls system is being migrated to other machines, but the completed change over will require two or more years.

The risk of a long downtime would be due to fire, lightning, or some other mishap affecting the Beams Division computer room in such a way that over half of the VAX inventory were damaged.  Even then, with the current market in used VAX computers, and with a concerted effort, it is believed that the Controls System could be made operational in less than three months.

Electronic Modules and Their Spares Stored in Same Location could pose a risk in case of an accident or a fire in which everything was destroyed.  This is a question of procedure and the extent of the practice is not known.  Therefore, assessing the amount of risk is not easy.

Recommendation:  Procedural questions were not considered to be part of this study, however, the practice of storing spares with the original equipment might be widespread.  Even though there are no instances in which a disaster resulted from this practice, the situation warrants more investigated to determine the amount of risk involved.

Site Infrastructure

| Component | No. | Spares | Risk | Comment |
| --- | --- | --- | --- | --- |
| 345-KV Switchgear KRS | 1 | 0 | H | (See discussion below on the Power Grid.) |
| 345-KV Switchgear MSS | 1 | 0 | H | 30 yrs. old (See discussion below on the Power Grid.) |
| 345-KV Transformers | 2 | 0 | M | With present grid configuration if one transformer were lost the physics program could continue at a reduced level (See discussion below on the Power Grid.) |
| Central Utility Building Chillers |  |  | L | Not considered to be a risk at this time (See below.) |
| Cooling Ponds |  |  | L | Silting has occurred in Tevatron ponds around the ring, but not considered to be a risk at this time (See below.) |
| 345-KV Power Poles |  |  | L | Wooden poles are attacked by birds, etc, but not considered to be a risk at this time (See below.) |

Power Grid critical components include the 345-KV power transformers and related hardware at the Kautz Road Substation (KRS) and the Master Substation (MSS).  There was a failure of the transformer at the MSS in 1985 that caused a great upheaval in the physics program for the better part of one year.  The failure was investigated [1] and various modifications were identified to make the site less vulnerable.  These included a more robust design for the transformer and the addition of the KRS to provide a level of redundancy.  This also allowed the load to be divided between the two substations thus prolonging the life of the individual components.  If Fermilab were to suffer a similar loss of a transformer as it did in 1985, it is believed that the power grid could be reconfigured to retain operation, but at a reduced level, e. g., the Main Injector repetition rate would have to be reduced.  A replacement transformer would cost in the $1.2M range.

The review of the MSS transformer failure identified a number of potential sources, though the most probable source was later identified to be harmonic oscillations on the Fermilab side of the power grid.  During the investigation of related accelerator power supply failures, oscillations as large as 30% were observed on the grid.  It is believed these caused premature aging of the power transformer insulation.  Subsequently, harmonic filters were added to reduce the harmonics to the industrially accepted standard of less than 5% [13].  These filters are now critical elements in maintaining the integrity of the power grid.  There are four resistors costing about $10k each, two are used in the Main Injector and two in the Tevatron.  There is currently one spare for each machine.

Recommendation:  An additional spare resistor (~$10k) should be purchased for each of the harmonic filters for the Main Injector and Tevatron.

Finally, there are two sets of 345-KV switchgear, one each on KRS and MSS.  The one on MSS is thirty years old, and uses an outdated oil-based design.  If there were a failure of one of these components it would be as catastrophic as losing a 345-KV power transformer.  The responsibility for the switchgear rests with Fermilab, and there is no spare for either.  The estimated replacement cost is $200k.

Recommendation:  The best situation would be to purchase one spare 345-KV switchgear (~$200k).  The Laboratory should at least investigate the availability and time to obtain a replacement device from Com Ed, or elsewhere, in case a failure occurs.

The remaining three items in the infrastructure: chillers, cooling ponds, and power poles; are under constant review and the belief is that none poses a three-month downtime threat to operations [14].  The backup plans for each of these items are discussed below.

CUB Chillers have been upgraded with five new chillers and three new heat exchangers (plate and frame) using Utilities Investment Program (UIP) funds.  The new system allows isolation of comfort-chilled water from the process-chilled water system greatly reducing failure rates.  As a backup, there is a cross connection option that permits connecting one comfort chiller to the process-chilled water system if needed. Along with this, there are outside quick connects that permit connection to a rental chiller unit to either chilled water system in an emergency.  With all of this in place, it is believed there is sufficient capacity to supply the chilled water needs of the Collider program.

Cooling Ponds have long been allowed to deteriorate.  For instance, the Tevatron ring cooling ponds are about one-third of their designed effectiveness.  Dredging is considered to be expensive  (~$1-2M).  However, the degeneration of the Tevatron ponds is not a concern at this time because the cooling load has been reduced by 50% or more with the removal of the Main Ring and its replacement by the Main Injector.  The residual cooling loads are the Mycom compressors for the Tevatron, electronics, and a few standard magnets that were not moved to the Main Injector.  Each year a diver checks the intakes for the pumps, and generally reports increased silting around the intakes.  However, the opinion continues to be that the pumps will continue to pump water.  This spring, FESS plans to implement a complete clean-out of one pond on the site and from that experience better understand how much effort is needed to increase the reliability of the pond cooling system.  In the meantime, if a failure should occur, it is believed that a pump replacement, or the effort to un-silt an intake could be accomplished in a short time.  There is also the fallback position of installing a temporary pump and generator in place of a failed unit.

345-KV Power Poles are inspected every 5 years, with the next inspection to be conducted next spring.  In addition, each year woodpecker holes are patched with epoxy.  Currently, there are three spare poles in outside storage, any of which can be installed in a short time to replace a fallen pole.

Replacement of all of the 345-KV power poles has been included on the list of General Plant Projects (GPP).  The project has been identified as a need, but no year has been set for the replacement.  A better understanding of the requirement date will be known after the report on the condition of the poles is received this spring.

Technical and Beams Division Study on Magnet Spares and Other Issues

Technical Division (TD) is responsible for all superconducting magnets and spools, as well as all conventional magnets, except for kicker magnets and a few spares in the proton source.  The industrial facilities to fabricate, repair and store these large devices also exist in the Technical Division.  The question of a potential three-month downtime due to the lack of spares or tooling was posed to Technical Division personnel.  A summary of the current status appears in various review presentations [15].  In summary, the Collider physics program is not in immediate jeopardy of long downtimes given the number of spares on hand and the magnet failure rates observed in recent years.

A spate of simultaneous losses, or the loss of an entire string of magnets, can tax the capability of the TD facilities.  An example of this occurred for the "infant mortality" in the Main Injector quadrupole magnets.  Since 1998, six out of the 130 installed IQB magnets have failed, leaving twelve spares of varying quality.  Two out of 32 installed IQC magnets and three out of the 48 IQD magnets have failed or been damaged beyond easy repair.  Design faults in the original potting of the magnet insulation have been identified and are being corrected as magnets are repaired.  At this time, the pipeline of spares undergoing remedial action has been able to keep up with demand.  For instance, all IQC spares have been rebuilt, and one new IQC and a IQD have been fabricated.  However, the pipeline must continue in operation for the foreseeable future.  It is planned to fabricate four additional each of the IQC and IQD magnets [16].

It should be mentioned that there are two quadrupole magnets in the Main Injector for which there are no spares, the IQHs.  However, in the case of a failure an IQE can be modified into an IQH in a few hours, so there are no magnets in the Main Injector system that do not have a spare.

In the Tevatron, the "infant mortality" occurred during the first decade of operations.  It has subsided over the last decade as design faults were corrected, the last of these being the breaking of nylon ties allowing the current buses to rub together and short.  This has reduced the number of dipoles removed from the Tevatron per year to about three, out of which only about one dipole per year is lost permanently.  Therefore, it is believed there are adequate spares (~17 dipole spares of each type) in the superconducting magnet inventory to keep the machine operational for many years.

Losses of large numbers of superconducting magnets have traditionally occurred during machine warm ups and cool downs, for instance in 1989 there was a loss of 33 magnets.  Such a large loss did not occur in the latest warm up in 1997, or the subsequent cool down for Run II.  Nevertheless, maintaining a program to resurrect additional spare magnets from those that have previously been removed from the machine would be wise.  The fabrication of new magnets of the Tevatron design would be very difficult, if not impossible, due to the lack of cable and the long-lead time needed to commission the "moth balled" tooling.

The handling and specification of spare magnets has been somewhat problematic, though any components can probably be located after a few days' concerted effort.  Use of "bar code"or "rf" identification, coupled with GPS location finding, could improve the data base integrity.

Tevatron specialty magnets, such as the low-beta quads, and their associated spool pieces might present a degree of vulnerability.  There is at least one spare magnet for each type of low beta quadrupole, plus an additional cold mass.  In an "human error" incident a few years ago the CDF detector was opened and compressed a set of low-beta quads.  Ultimately, none of the magnets were lost, however, the accident resulted in each low-beta quadrupole on one side of the interaction region requiring a cold test at the Magnet Test Facility to confirm its performance.  To free the components, large amounts of concrete shielding had to be removed from the tunnel.  Though this required many months of effort, it did not delay the Collider physics program as the Tevatron was not yet ready for operations at that time.  A similar event now might result in a shut down of operations beyond the three-month downtime limit as well as leave the system vulnerable to a single element failure after the single spares were installed.

With the recent addition of rebuilt B and D spools, there is an adequate number of Tevatron spare spool pieces on hand to ensure many years of operations.  Furthermore, the usual failure mode is the loss of the corrector elements within the spool.  For this type of failure, even in a situation when all of the spares were exhausted, it is believed that the Tevatron could remain operational.  With the exception of the trim dipoles that steer the beam locally, the higher-order corrector magnets affect the beam in a combined sense.  The loss of one set of these correctors can be compensated by increasing the strengths of the remaining correctors.  It might also require the interchange the spools in regions where the Tevatron is more sensitive.

Other problems have taken spool pieces out of service; for instance a magnet was dropped on a D-spool in the tunnel, a set of safety leads were burned up, and various vacuum leaks have occurred.  In general, there are spools in storage that are deemed repairable and could augment the spares inventory if the number drops below a safe level.  However, this can only be done over a long period of time and requires an on-going remedial program.

One additional spool piece concern is the seven installed H-spools that carry the magnet power leads.  Reliability of these elements has been good over the years, though the recent introduction of one spool with a set of high-temperature superconducting power leads has yet to demonstrate its long-term integrity.  If it fails there is a spare spool piece that has the standard power leads.  However, when other H-spools with the new power leads are introduced into the machine, they might present an overall vulnerability if additional failures were encountered.

Recommendations:

- The program to recover superconducting dipoles and spool pieces from those needing repair should be continued.  The level of effort should be reviewed to see that it satisfies the future needs of the Collider program.

- The use of "bar code"or "rf" identification, coupled with GPS location finding, should be implemented throughout the accelerator complex to improve the data base integrity for installed and stored devices.

Related References, Reports and Memos

- "Report on Investigation of the Transformer," Larry Coulson, Chairman, FNAL Preliminary Report Issued March 8, 1985.

- "Tevatron Magnet Spares Requirements," John Marriner, Internal FNAL Memo, July 26, 1995.

- Memo from Ray Hanft, June 28, 2002

- "The proton Driver Design Study," Fermilab-TM-2136 (December, 2000).

- Private communication from Frank Brumwell, IPNS, Argonne National Laboratory, 2002.

- Private communication from Dick Werbeck, LANSCE, Los Alamos National Laboratory, 2002.

- Memo from Bob Webber, August 14, 2002.

- "Introduction to Reliability Theory," B. Schorr, CERN Report 74-16.

- "Fermilab Linac Status and Outlook," Talk presented by Bob Webber to the Laboratory Directorate, August 9, 2002.

- "Analysis of the Lifetime Data for the Linac 201-MHz Power Amplifiers," E. McCrory and R. Webber, Fermilab-TM-2178 (July, 2002).

- "Trip Report to Burle Industries," E. McCrory (June 24, 2002).

- B. Brown et al., "Time Dependence and Temperature Stability of the Permanent Magnets for the Fermilab Antiproton Recycler Ring," IEEE Trans. On Appl. Superconductivity, 10 (March, 2000) 879.

- Private communication from Dan Wolfe, Fermilab, 2002.

- Private communication from David Nevin, Fermilab, 2002.

- "Superconducting Magnet Support for the Tevatron in Run II," Talk presented by David Harding at the Fermilab SC Magnet Internal Review, April 25, 2002.

- Private communication from David Harding, Fermilab, 2002.