## Sheet1
APPENDIX II
SLAC Strategic Site Plan for 21st Century | [5 empty] | October, 2000
REV. 13
$ in thousands.
All estimates are in FY2002 dollars. | [7 empty] | Funding per Fiscal Year
| Type | TEC | Funding | FY02 | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | FY10 | FY11
Type
NEW BUILDINGS & BUILDING ADDITIONS
Research Yard Building - 7,000 SqFt | ADD | 1400 | HEP | FY05: 700; Funding per Fiscal Year FY06: 700
SUBTOTAL HEP |  | 1400 |  | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0 | 0
SUBTOTAL BES |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL NEW BUILDINGS & BUILDING ADDITIONS |  | 1400 |  | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0 | 0
NEW INFRASTRUCTURE
Bldg 050 Cooling/Backup Generator System | ADD | 1400 | HEP | FY02: 700; FY03: 700
Research Area Cooling Tower | ADD | 600 | HEP | FY04: 600
ESA Dump | ADD | 1000 | HEP | Funding per Fiscal Year FY06: 1000
SUBTOTAL HEP |  | 3000 |  | 700 | 700 | 600 | 0 | 1000 | 0 | 0 | 0 | 0 | 0
SUBTOTAL BES |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL NEW INFRASTRUCTURE |  | 3000 |  | 700 | 700 | 600 | 0 | 1000 | 0 | 0 | 0 | 0 | 0
BUILDING UPGRADES
Building Seismic Upgrades | Seismic | 12500 | HEP | FY02: 2500; FY03: 2500; FY04: 2500; FY05: 2500; Funding per Fiscal Year FY06: 2500
SUBTOTAL HEP |  | 12500 |  | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0
Building Seismic Upgrades | Seismic | 475 | BES | FY04: 125; FY05: 350
SUBTOTAL BES |  | 475 |  | 0 | 0 | 125 | 350 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL BUILDING UPGRADES |  | 12975 |  | 2500 | 2500 | 2625 | 2850 | 2500 | 0 | 0 | 0 | 0 | 0
INFRASTRUCTURE UPGRADES
Sanitary Sewer | UTIL | 750 | HEP | FY02: 150; FY03: 150; FY04: 300; FY05: 150
Utility DCS System Completion | UTIL | 650 | HEP | FY02: 125; FY03: 125; FY04: 225; FY05: 175
Replace LINAC VVS Subs 15ea/Thyratron Protection | ELECT | 8720 | HEP | FY02: 1800; FY03: 1800; FY04: 1800; FY05: 1800; Funding per Fiscal Year FY06: 1520
Storm Drain Upgrade | ES&H | 625 | HEP | FY02: 250; FY03: 375
HVAC DDC Upgrade | HVAC | 120 | HEP | FY04: 120
SUBTOTAL HEP |  | 10865 |  | 2325 | 2450 | 2445 | 2125 | 1520 | 0 | 0 | 0 | 0 | 0
SUBTOTAL BES |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL INFRASTRUCTURE UPGRADES |  | 10865 |  | 2325 | 2450 | 2445 | 2125 | 1520 | 0 | 0 | 0 | 0 | 0
TOTAL GPP & INFRASTRUCTURE |  | 28240 |  | 5525 | 5650 | 5670 | 5675 | 5720 | 0 | 0 | 0 | 0 | 0
CAPITAL EQUIPMENT
SUBTOTAL HEP |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUBTOTAL BES |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CAPITAL EQUIPMENT |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL HEP |  | 27765 |  | 5525 | 5650 | 5545 | 5325 | 5720 | 0 | 0 | 0 | 0 | 0
TOTAL BES |  | 475 |  | 0 | 0 | 125 | 350 | 0 | 0 | 0 | 0 | 0 | 0
GRAND TOTAL (Vertical) |  | 28240 |  | 5525 | 5650 | 5670 | 5675 | 5720 | 0 | 0 | 0 | 0 | 0
Totals (Horizontal) |  | 28240 |  | 5525 | 5650 | 5670 | 5675 | 5720 | 0 | 0 | 0 | 0 | 0

## Sheet2
Central Office Bldg
Replaces 205, 206, 206A, 207, 210, 208, 212, 213, 229, 228, 259, 283, 234, 275, 214, 239, 202, 279, 295, 296, 297
SSRL Bldg
Replaces | 451, 452, 271, 270, 294, 288, 289, 290, 453, 293
005 Addition
Replaces 5A, 5B, 5C, 5D
024 Modification internal
Replaces 299, moves ES&H out of 003, 034
Research Yard Bldg
Replaces 687, 110, 111, 113, 125, 133, 215, 224, 265, 232, 233, 209, 109, (DSL category from SUP Plan)
Buildings that include $75k for an elevator in their upgrade estimates
015, 024, 034, 041, 044, 084, 121, 131, 685