## Sheet1
Calorimeter (WBS 1.2.3)
Cost Estimate/Funding Profile
FY 05$ in thousands
|  |  | Base |  | Contingency | Total | EDIA | Mfg. | EDIA | Mfg. | Total | Physicist |  | Eng |  | Admin. |  | Designer |  | Tech |  | Total | [6 empty] | Physicist | Rate
WBS |  |  | Cost | Contingency | % | Cost | Labor | Labor | Matls | Matls | FTE's | FTE's | Hrs | FTE's | Hrs | FTE's | Hrs | FTE's | Hrs | FTE's | Hrs | Base Cost | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | Cost | Per Hour
1.2.3 | Calorimeter System |  | 7867.5922 | 0 | 0% | 7867.5922 | 1151.4764 | 2241.952 | 0 | 4475.1638 | 108.623 | 30.25 | 52360 | 5.647 | 9935.6 | 0 | 0 | 3.6645 | 6432 | 69.0614 | 121565.6722 | 7868.382 | 441.2303 | 2343.2303 | 3085.2303 | 1680.2303 | 176.2303 | 142.2303 | 1409.9184 |  | Yale | 1034.4048
[31 empty] | IHEP | 375.5136
1.2.3.1 | System Prototype |  | 359.68 | 0 | 0% | 359.68 | 41.68 | 92 | 0 | 226 | 5.4392 | 2.5 | 4400 | 0.12 | 211.2 | 0 | 0 | 0.15205 | 250 | 2.6772 | 4711.8056 | 360 | 257 | 103 | 0 | 0 | 0 | 0 | 145.2
1.2.3.1.1 | Modules |  | 75 | 0 |  | 75 |  | 41 |  | 34 | 1.2942 | [8 empty] | 1.2942 | 2277.7778 | 75 | FY 2005: 75
1.2.3.1.2 | APD Instrumentation |  | 123 | 0 |  | 123 |  | 11 |  | 112 | 0.34722 | [8 empty] | 0.34722 | 611.1111 | 123 | FY 2005: 123
1.2.3.1.3 | Mechanics |  | 29 | 0 |  | 29 | 3 | 13 | 0 | 13 | 0.49558 | [6 empty] | 0.085227 | 150 | 0.41035 | 722.2222 | 29 | FY 2005: 0; FY 2006: 29
1.2.3.1.4 | Cooling System |  | 14 | 0 |  | 14 | 2 | 5 |  | 7 | 0.21465 | [6 empty] | 0.056818 | 100 | 0.15783 | 277.7778 | 14 | FY 2005: 0; FY 2006: 14
1.2.3.1.5 | HV Control System |  | 16 | 0 |  | 16 |  |  |  | 16 | 0 | [8 empty] | 0 | 0 | 16 | FY 2005: 16
1.2.3.1.6 | Cosmic Ray Pre-Callib System |  | 10 | 0 |  | 10 | 5 | 5 |  | 0 | 0.27783 |  |  | 0.12 | 211.2 |  |  | 0 | 0 | 0.15783 | 277.7778 | 10 | FY 2005: 10
1.2.3.1.7 | Monitoring & Calibration |  | 13 | 0 |  | 13 |  | 7 |  | 6 | 0.22096 | [8 empty] | 0.22096 | 388.8889 | 13 | FY 2005: 13
1.2.3.1.8 | Readout |  | 23 | 0 |  | 23 |  |  |  | 23 | 0 | [8 empty] | 0 | 0 | 23 | FY 2005: 15; FY 2006: 8 |  |  | IHEP | Yale Univ |  | BNL
1.2.3.1.9 | Shipping |  | 10 | 0 |  | 10 |  |  |  | 10 | 0 | [8 empty] | 0 | 0 | 10 | FY 2005: 5; FY 2006: 5 |  |  | Rate per
1.2.3.1.10 | Test |  | 46.68 | 0 |  | 46.68 | 31.68 | 10 |  | 5 | 2.5888 | 2.5 | 4400 |  | 0 | 0 | 0 |  | 0 | 0.088778 | 156.25 | 47 | FY 2005: 0; FY 2006: 47 | 145.2 | Y | Hr. | 55 | Reseach Sci
[30 empty] | Post Doc | 18 | 50 | Scientist | 91
1.2.3.2 | Photon Calorimeter Production |  | 4414.8646 | 0 | 0% | 4414.8646 | 113.08 | 1760.6208 | 0 | 2539.1638 | 68.3716 | 6.26 | 10137.6 | 3.0239 | 5322.1333 | 0 | 0 | 3.5125 | 6182 | 55.5752 | 97812.2667 | 4414 | 42 | 1637 | 1936 | 799 | 0 | 0 | 330.528 | Engineer | 24 | 66 | Engineer | 80
[30 empty] | Designer | 20
1.2.3.2.1 | Design |  | 42 | 0 | 0% | 42 | 42 | 0 | 0 | 0 | 1.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1932 | 2100 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | Tech | 18 | 46 | Tech | 64
1.2.3.2.1.1 | Conceptual Design |  | 12 | 0 |  | 12 | 12 |  |  |  | 0.34091 |  | 0 | 0 | 0 | 0 | 0 | 0.34091 | 600 |  | 0 | 12 | FY 2005: 12 |  | hrs. per FTE | 1760
1.2.3.2.1.2 | Technical Design |  | 30 | 0 |  | 30 | 30 |  |  |  | 0.85227 |  | 0 | 0 | 0 | 0 | 0 | 0.85227 | 1500 |  | 0 | 30 | FY 2005: 30
1.2.3.2.2 | Tools & Test Equipment Modification |  | 102 | 0 | 0% | 102 | 0 | 17 | 0 | 85 | 0.53662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53662 | 944.4444 | 102 |  | 50 | 26 | 26 | 0 | 0 | 0
1.2.3.2.2.1 | Cosmic Ray Setup |  | 30 | 0 |  | 30 |  | 5 |  | 25 | 0.15783 | [8 empty] | 0.15783 | 277.7778 | 30 | FY 2006: 30
1.2.3.2.2.2 | Molding Forms and Stamps |  | 72 | 0 |  | 72 |  | 12 |  | 60 | 0.37879 | [8 empty] | 0.37879 | 666.6667 | 72 | FY 2006: 20; FY 2007: 26; FY 2008: 26
1.2.3.2.3 | Module -Regular |  | 1808.2186 | 0 | 0% | 1808.2186 | 0 | 1112.6208 | 0 | 694.5978 | 37.0406 | 1.92 | 3379.2 | 0 | 0 | 0 | 0 | 0 | 0 | 35.1206 | 61812.2667 | 1808 | 0 | 720 | 720 | 368 | 0 | 0 | 60.8256
1.2.3.2.3.1 | Scintillator Tiles |  | 387.1842 | 0 |  | 387.1842 |  | 288.576 |  | 97.6082 | 9.1091 | [8 empty] | 9.1091 | 16032 | 387 | 0 | 150 | 150 | 87
1.2.3.2.3.2 | Lead Tiles |  | 502.2024 | 0 |  | 502.2024 |  | 327.0528 |  | 175.1496 | 10.3236 | [8 empty] | 10.3236 | 18169.6 | 502 | 0 | 200 | 200 | 102
1.2.3.2.3.3 | WLS Fiber |  | 328.656 | 0 |  | 328.656 |  | 40.08 |  | 288.576 | 1.2652 | [8 empty] | 1.2652 | 2226.6667 | 329 | 0 | 130 | 130 | 69 |  |  |  | Mod. Units | 2672
1.2.3.2.3.4 | Assembly |  | 435.536 | 0 |  | 435.536 |  | 336.672 |  | 98.864 | 10.6273 | [8 empty] | 10.6273 | 18704 | 436 | 0 | 180 | 180 | 76
1.2.3.2.3.5 | Test |  | 96.192 | 0 |  | 96.192 |  | 96.192 |  |  | 4.9564 | 1.92 | 3379.2 | [6 empty] | 3.0364 | 5344 | 96 | FY 2006: 40; FY 2007: 40; FY 2008: 16 | 60.8256 | IHEP
1.2.3.2.3.6 | Packing |  | 58.448 | 0 |  | 58.448 |  | 24.048 |  | 34.4 | 0.75909 | [8 empty] | 0.75909 | 1336 | 58 | FY 2006: 20; FY 2007: 20; FY 2008: 18
1.2.3.2.4 | Module Instrumentation |  | 1867.526 | 0 | 0% | 1867.526 | 0 | 290 | 0 | 1576.526 | 11.074 | 1.92 | 3379.2 | 0 | 0 | 0 | 0 | 0 | 0 | 9.154 | 16111.1111 | 1867 | 0 | 757 | 757 | 353 | 0 | 0 | 60.8256
1.2.3.2.4.1 | APD |  | 1204.85 | 0 |  | 1204.85 |  | 14 |  | 1190.85 | 0.44192 | [8 empty] | 0.44192 | 777.7778 | 1205 | 0 | 500 | 500 | 205 |  |  |  | Mod. Units | 2802
1.2.3.2.4.2 | Preamplifier |  | 84.05 | 0 |  | 84.05 |  | 14 |  | 70.05 | 0.44192 | [8 empty] | 0.44192 | 777.7778 | 84 | FY 2005: 0; FY 2006: 42; FY 2007: 42
1.2.3.2.4.3 | LV-HV Converter |  | 277.388 | 0 |  | 277.388 |  | 14 |  | 263.388 | 0.44192 | [8 empty] | 0.44192 | 777.7778 | 277 | 0 | 100 | 100 | 77
1.2.3.2.4.4 | Mechanics |  | 133.238 | 0 |  | 133.238 |  | 80 |  | 53.238 | 2.5253 | [8 empty] | 2.5253 | 4444.4444 | 133 | 0 | 50 | 50 | 33
1.2.3.2.4.5 | Assembly |  | 144 | 0 |  | 144 |  | 144 |  |  | 4.5455 | [8 empty] | 4.5455 | 8000 | 144 | 0 | 55 | 55 | 34 |  |  |  | Mod. Units | 2881
1.2.3.2.4.6 | Test APD |  | 12 | 0 |  | 12 |  | 12 |  |  | 2.2988 | 1.92 | 3379.2 | [6 empty] | 0.37879 | 666.6667 | 12 | FY 2006: 5; FY 2007: 5; FY 2008: 2 | 60.8256 | IHEP
1.2.3.2.4.7 | Packing APD |  | 12 | 0 |  | 12 |  | 12 |  |  | 0.37879 | [8 empty] | 0.37879 | 666.6667 | 12 | FY 2006: 5; FY 2007: 5; FY 2008: 2
1.2.3.2.5 | Cosmic Ray Test of Module/APD |  | 24 | 0 |  | 24 |  | 24 |  |  | 4.5976 | 1.92 | 3379.2 | 1.92 | 3379.2 |  |  |  |  | 0.75758 | 1333.3333 | 24 | FY 2006: 10; FY 2007: 10; FY 2008: 4 | 141.9264 | IHEP
1.2.3.2.6 | Beam Line Modules |  | 96.12 | 0 |  | 96.12 | 6.08 | 27 |  | 63.04 | 1.6689 | 0.5 | 0 | 0.14394 | 253.3333 | 0 | 0 | 0.17273 | 304 | 0.85227 | 1500 | 96 | 0 | 0 | 48 | 48 |  |  | 15.84 | IHEP
1.2.3.2.7 | Photon Calorimeter Mechanics |  | 475 | 0 | 0% | 475 | 65 | 290 | 0 | 120 | 12.2606 | 0 | 0 | 0.96 | 1689.6 | 0 | 0 | 2.1466 | 3778 | 9.154 | 16111.1111 | 475 | 0 | 100 | 375 | 0 | 0 | 0 | 51.1104
1.2.3.2.7.1 | Support Frame |  | 230 | 0 | 0% | 230 | 20 | 180 | 0 | 30 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56818 | 1000 | 5.6818 | 10000 | 230 | 0 | 75 | 155 | 0 | 0 | 0 | 0
1.2.3.2.7.1.1 | Design |  | 20 | 0 |  | 20 | 20 |  |  |  | 0.56818 |  | 0 |  |  | 0 | 0 | 0.56818 | 1000 |  | 0 | 20 | FY 2006: 20
1.2.3.2.7.1.2 | Fabrication/Procurement |  | 210 | 0 |  | 210 |  | 180 |  | 30 | 5.6818 | [8 empty] | 5.6818 | 10000 | 210 | FY 2006: 55; FY 2007: 155
1.2.3.2.7.2 | Cooling System |  | 140 | 0 | 0% | 140 | 20 | 60 | 0 | 60 | 2.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56818 | 1000 | 1.8939 | 3333.3333 | 140 | 0 | 20 | 120 | 0 | 0 | 0 | 0
1.2.3.2.7.2.1 | Design |  | 20 | 0 |  | 20 | 20 |  |  |  | 0.56818 |  | 0 | 0 | 0 | 0 | 0 | 0.56818 | 1000 |  | 0 | 20 | FY 2006: 20
1.2.3.2.7.2.2 | Fabrication/Procurement |  | 120 | 0 |  | 120 |  | 60 |  | 60 | 1.8939 | [8 empty] | 1.8939 | 3333.3333 | 120 | FY 2007: 120
1.2.3.2.7.3 | Railway System |  | 40 | 0 | 0% | 40 | 10 | 20 | 0 | 10 | 0.9154 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28409 | 500 | 0.63131 | 1111.1111 | 40 | 0 | 5 | 35 | 0 | 0 | 0 | 0
1.2.3.2.7.3.1 | Design |  | 10 | 0 |  | 10 | 10 |  |  |  | 0.28409 |  | 0 | 0 | 0 | 0 | 0 | 0.28409 | 500 |  | 0 | 10 | FY 2006: 5; FY 2007: 5
1.2.3.2.7.3.2 | Fabrication/Procurement |  | 30 | 0 |  | 30 |  | 20 |  | 10 | 0.63131 | [8 empty] | 0.63131 | 1111.1111 | 30 | FY 2007: 30
1.2.3.2.7.4 | Assby. & Service Tools |  | 65 | 0 | 0% | 65 | 15 | 30 | 0 | 20 | 1.3731 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42614 | 750 | 0.94697 | 1666.6667 | 65 | 0 | 0 | 65 | 0 | 0 | 0 | 0
1.2.3.2.7.4.1 | Design |  | 15 | 0 |  | 15 | 15 |  |  |  | 0.42614 |  | 0 | 0 | 0 | 0 | 0 | 0.42614 | 750 |  | 0 | 15 | FY 2007: 15
1.2.3.2.7.4.2 | Fabrication/Procurement |  | 50 | 0 |  | 50 |  | 30 |  | 20 | 0.94697 | [8 empty] | 0.94697 | 1666.6667 | 50 | FY 2007: 50
1.2.3.2.7.5 | Supervision & Technical Control |  | 0 | 0 |  | 0 | 0 |  |  |  | 1.26 | 0 | 0 | 0.96 | 1689.6 | 0 | 0 | 0.3 | 528 |  | 0 | 0 | FY 2007: 0 | 51.1104 | IHEP
1.2.3.3 | Instrumentation |  | 1425 | 0 | 0% | 1425 | 10 | 145 | 0 | 1270 | 9.5338 | 4.41 | 7761.6 | 0.54674 | 962.2667 | 0 | 0 | 0 | 0 | 4.567 | 8055.5556 | 1425 | 0 | 372 | 777 | 276 | 0 | 0 | 334.4176 | 0
1.2.3.3.1 | HV Control System |  | 196 | 0 |  | 196 | 0 | 0 | 0 | 196 | 0.58 | 0.58 | 1020.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 0 | 24 | 100 | 72 | 0 | 0 | 56.144
1.2.3.3.1.1 | 44 VME Carriers |  | 24 | 0 |  | 24 |  |  |  | 24 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 24 | FY 2006: 24
1.2.3.3.1.2 | 176 IP - DA Converters |  | 132 | 0 |  | 132 |  |  |  | 132 | 0 | [8 empty] | 0 | 0 | 132 | FY 2007: 60; FY 2008: 72
1.2.3.3.1.3 | 4VME/VXI Mainframe |  | 40 | 0 |  | 40 |  |  |  | 40 | 0 | [8 empty] | 0 | 0 | 40 | FY 2007: 40 | 0
1.2.3.3.1.4 | Test |  | 0 | 0 |  | 0 |  |  |  | 0 | 0.58 | 0.58 | 1020.8 | [6 empty] | 0 | 0 | 0 | FY 2007: 0; FY 2008: 0 | 56.144 | Y
1.2.3.3.2 | Self-triggering Pre-calibration |  | 187 | 0 |  | 187 | 0 | 0 | 0 | 187 | 0.75 | 0.75 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 0 | 107 | 80 | 0 | 0 | 72.6
1.2.3.3.2.1 | 30 VME - LTD |  | 140 | 0 |  | 140 |  |  |  | 140 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 140 | FY 2007: 60; FY 2008: 80
1.2.3.3.2.2 | 6 VME - Trigger Logic |  | 27 | 0 |  | 27 |  |  |  | 27 | 0 | [9 empty] | 0 | 27 | FY 2007: 27
1.2.3.3.2.3 | 2 VME - Mainframe |  | 20 | 0 |  | 20 |  |  |  | 20 | 0 | [9 empty] | 0 | 20 | FY 2007: 20 | 0
1.2.3.3.2.4 | Test |  | 0 | 0 |  | 0 |  |  |  | 0 | 0.75 | 0.75 | 1320 | [7 empty] | 0 | 0 | [6 empty] | 72.6 | Y
1.2.3.3.3 | Monitoring & Calibration System |  | 170 | 0 | 0% | 170 | 10 | 109 | 0 | 51 | 5.0974 | 1.42 | 2499.2 | 0.23674 | 416.6667 | 0 | 0 | 0 | 0 | 3.4307 | 6055.5556 | 170 | 0 | 20 | 115 | 35 | 0 | 0 | 44.9856
1.2.3.3.3.1 | Design |  | 10 | 0 |  | 10 | 10 |  |  |  | 0.23674 |  | 0 | 0.23674 | 416.6667 | 0 | 0 |  | 0 |  | 0 | 10 | FY 2006: 10
1.2.3.3.3.2 | Prototype |  | 25 | 0 |  | 25 |  | 15 |  | 10 | 0.47348 | [8 empty] | 0.47348 | 833.3333 | 25 | FY 2006: 10; FY 2007: 15
1.2.3.3.3.3 | Fabrication/Procurement |  | 135 | 0 |  | 135 |  | 94 |  | 41 | 4.3872 | 1.42 | 2499.2 | [6 empty] | 2.9672 | 5222.2222 | 135 | FY 2007: 100; FY 2008: 35 | 44.9856 | IHEP
1.2.3.3.4 | Readout Electronics |  | 815 | 0 | 0% | 815 | 0 | 36 | 0 | 779 | 3.1064 | 1.66 | 2921.6 | 0.31 | 545.6 | 0 | 0 | 0 | 0 | 1.1364 | 2000 | 815 | 0 | 298 | 428 | 89 | 0 | 0 | 160.688
1.2.3.3.4.1 | WFD Boards |  | 511 | 0 | 0% | 511 | 0 | 32 | 0 | 479 | 1.2901 | 0 | 0 | 0.28 | 492.8 | 0 | 0 | 0 | 0 | 1.0101 | 1777.7778 | 511 | 0 | 188 | 256 | 67 | 0 | 0 | 0
1.2.3.3.4.1.3 | Fabrication/Procurement |  | 479 | 0 |  | 479 |  |  |  | 479 | 0 | [10 empty] | 479 | FY 2006: 180; FY 2007: 240; FY 2008: 59
1.2.3.3.4.1.5 | Test |  | 32 | 0 |  | 32 |  | 32 |  | 0 | 1.2901 |  |  | 0.28 | 492.8 |  |  |  |  | 1.0101 | 1777.7778 | 32 | FY 2006: 8; FY 2007: 16; FY 2008: 8 | 0
1.2.3.3.4.2 | Crate Data-Collection Boards |  | 124 | 0 | 0% | 124 | 0 | 4 | 0 | 120 | 0.15626 | 0 | 0 | 0.03 | 52.8 | 0 | 0 | 0 | 0 | 0.12626 | 222.2222 | 124 | 0 | 20 | 82 | 22 | 0 | 0 | 0
1.2.3.3.4.2.3 | Fabrication/Procurement |  | 120 | 0 |  | 120 |  |  |  | 120 | 0 | [10 empty] | 120 | FY 2006: 20; FY 2007: 80; FY 2008: 20
1.2.3.3.4.2.5 | Test |  | 4 | 0 |  | 4 |  | 4 |  | 0 | 0.15626 |  |  | 0.03 | 52.8 |  |  |  |  | 0.12626 | 222.2222 | 4 | FY 2007: 2; FY 2008: 2 | 0
1.2.3.3.4.3 | VXI Mainframes & Controller |  | 180 | 0 |  | 180 |  |  |  | 180 | 0 | [10 empty] | 180 | FY 2006: 90; FY 2007: 90
1.2.3.3.4.4 | System Test |  | 0 | 0 |  | 0 |  |  |  | 0 | 1.66 | 1.66 | 2921.6 | [8 empty] | 0 | FY 2006: 0; FY 2007: 0 | 160.688 | Y
1.2.3.3.5 | LV Power Supplies & Electronic Racks |  | 57 | 0 |  | 57 |  |  |  | 57 | 0 | [10 empty] | 57 | FY 2006: 30; FY 2007: 27
1.2.3.4 | Shipping |  | 100 | 0 |  | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 20 | 40 | 40 | 0 | 0 | 0
1.2.3.5 | Assembly & Test |  | 291.64 | 0 | 0% | 291.64 | 134.64 | 67 | 0 | 90 | 10.2049 | 8.09 | 14238.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1149 | 3722.2222 | 292 | 0 | 69 | 115 | 108 | 0 | 0 | 371.712
1.2.3.5.1 | Delivered Modules |  | 178.8944 | 0 |  | 178.8944 | 65.8944 | 33 |  | 80 | 5.0417 | 4 | 7040 | [6 empty] | 1.0417 | 1833.3333 | 179 | FY 2006: 29; FY 2007: 75; FY 2008: 75 | 185.856 | Y
1.2.3.5.2 | Cosmic Ray Test |  | 112.7456 | 0 |  | 112.7456 | 68.7456 | 34 |  | 10 | 5.1632 | 4.09 | 7198.4 | [6 empty] | 1.0732 | 1888.8889 | 113 | FY 2006: 40; FY 2007: 40; FY 2008: 33 | 185.856 | Y | Annual |  | Phy.
[31 empty] | Rate | Fringe | Org. Burden | G&A | Composite
1.2.3.6 | Installation |  | 185.3312 | 0 | 0% | 185.3312 | 66 | 120.3312 | 0 | 0 | 5.1943 | 1.16 | 2041.6 | 1.7064 | 3000 | 0 | 0 | 0 | 0 | 2.3279 | 4097.1556 | 185 | 0 | 0 | 75 | 76 | 34 | 0 | 179.6608
1.2.3.6.1 | Modules into Frame |  | 61 | 0 |  | 61 | 24 | 37 |  |  | 2.3161 | 0.58 | 1020.8 | 0.56818 | 1000 |  |  |  |  | 1.1679 | 2055.5556 | 61 | FY 2007: 30; FY 2008: 31 | 56.144 | Y
1.2.3.6.2 | Monitoring & Calibration System |  | 42 | 0 |  | 42 | 24 | 18 |  |  | 1.7282 | 0.58 | 1020.8 | 0.56818 | 1000 |  |  |  |  | 0.58 | 1020.8 | 42 | FY 2007: 15; FY 2008: 15; FY 2009: 12 | 56.144 | Y | Annual |  | Phy.
1.2.3.6.3 | Read-out Electronics |  | 82.3312 | 0 |  | 82.3312 | 18 | 65.3312 |  |  | 1.15 |  |  | 0.57 | 1000 |  |  |  |  | 0.58 | 1020.8 | 82 | FY 2007: 30; FY 2008: 30; FY 2009: 22 | 67.3728 | Y | Annual |  | Phy.
1.2.3.7 | Cabling |  | 205.3744 | 0 | 0% | 205.3744 | 18.3744 | 57 | 0 | 130 | 2.3792 | 0.58 | 1020.8 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7992 | 3166.6667 | 205 | 0 | 0 | 0 | 205 | 0 | 0 | 0
1.2.3.7.1 | LV-PS |  | 56 | 0 |  | 56 |  | 13 |  | 43 | 0.41035 |  |  | 0 | 0 |  |  |  |  | 0.41035 | 722.2222 | 56 | FY 2008: 56 | 0
1.2.3.7.2 | HV-Control |  | 14 | 0 |  | 14 |  | 7 |  | 7 | 0.22096 |  |  | 0 | 0 |  |  |  |  | 0.22096 | 388.8889 | 14 | FY 2008: 14 | 0 |  | Annual |  | Phy.
1.2.3.7.3 | Signal |  | 70 | 0 |  | 70 |  | 0 |  | 70 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 70 | FY 2008: 70 | 0 |  | Annual |  | Phy.
1.2.3.7.4 | Assembly & Installation |  | 65.3744 | 0 |  | 65.3744 | 18.3744 | 37 |  | 10 | 1.7479 | 0.58 | 1020.8 | 0 | 0 |  |  |  |  | 1.1679 | 2055.5556 | 65 | FY 2008: 65 | 0 |  | Annual |  | Phy.
1.2.3.8 | Commissioning |  | 34.32 | 0 | 0% | 34.32 | 34.32 |  |  |  | 1.5 | 1.25 | 2200 | 0.25 | 440 |  |  |  |  | 0 | 0 | 34 | FY 2008: 34 | 48.4 | Y | Annual |  | Phy.
1.2.3.9 | Scientific & Technical Support |  | 853.382 | 0 | 0% | 853.382 | 733.382 | 0 | 0 | 120 | 6 | 6 | 10560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 853.382 | 142.2303 | 142.2303 | 142.2303 | 142.2303 | 142.2303 | 142.2303 | 0
| Physicist |  | 733.382 | 0 |  | 733.382 | 733.382 |  |  |  | 6 | 6 | 10560 | [8 empty] | 733.382 | 122.2303 | 122.2303 | 122.2303 | 122.2303 | 122.2303 | 122.2303 |  | Physicist | 65 | 1.397 | 1.15 | 1.1705 | 122.2303
| Travel |  | 120 | 0 |  | 120 |  |  |  | 120 | 0 | [10 empty] | 120 | 20 | 20 | 20 | 20 | 20 | 20