## Master Schedule
LINE SEQUENCE | Raytheon System # | DELIVERY SEQUENCE | MBTS | Required # of Systems | SITE | ST | REGION | LID | PROJECT CONTROL NUMBER | CURRENT BEACON | PRIMARY RADAR | PRIMARY SAIL TYPE | ROTARY JOINT TYPE | ANTENNA NEW/FAA | MOUNTING KIT TYPE | MAIN ARTCC FEED | ALTERNATE ARTCC FEED | SITE SURVEY START DATE | CSER (PRELIM) DELIVERY DATE | CSER (FINAL) DUE DATE | RJ/ANTENNA INSTALLATION START DATE | RJ/ANTENNA INSTALLATION COMPLETION DATE | ANTENNA INSTALLED | NEW SHELTER INSTALLED | PRE-INSTALLATION TELCON DATE | PLANNED SYSTEM DELIVERY SCHEDULE | SAT COMPLETION DATE | FORM 256 SIGNED | RMC/SAT COMPLETION DATE | FAA OPTIMIZATION START DATE | FAA OPTIMIZATION COMPLETE | FLIGHT CHECK COMPLETE | IOC/OSD START DATE | ORD/OSD FINISH DATE | JAI DATE | EST. COMMISSIONING DATE | ACTUAL SITE COMMISSIONING DATE | LEGACY SYSTEM REMOVAL START DATE | LEGACY SYSTEM REMOVAL COMPLETION DATE | FAA or RAYTHEON DEINSTALLATION | Mode 4/COMSEC Interface Present | JOINT FACILITY | REGION POC | REGION POC TELEPHONE NUMBER | COMMENTS
1 | 6 | 1 | 1 | 1 | TINKER AFB (Key Site) | OK | ASW | OKC | LUYC | BI-4 | FPS-67B | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZNY | ZDC, ZBW | 1999-01-18 | X | X | 1999-02-27 | 1999-03-01 | X | NA | 2001-09-24 | 2001-11-08 | 2002-01-29 |  |  |  |  | X | 2002-07-18 | 2002-07-18 | 2002-07-18 | 2002-08-05 | 2002-07-18 |  | 2002-12-03 |  |  | YES | J. Navarro | 817-222-4655 | Commissioned 7/18/02
2 | 5 | 2 | 1 | 1 | TECH CENTER (OT&E) | NJ | N/A | ACYT | DP1U | BI-5 | SUPPORT | ARSR-2 | NA | NA | NA | N/A | N/A | 1999-01-11 | X | X | NA | NA | NA | NA | 2001-12-08 | 2002-01-22 | [5 empty] | X | NA | NA | NA | NA | NA |  | NA |  |  | YES | A. Leone | 609-485-5578
3 | 8 | 3 | 1 | 1 | PUTNAM | OK | ASW | QOT | PP1U | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZFW | ZKC | 2000-07-12 | 2000-11-01 | 2001-09-05 | 2000-08-02 | 2000-08-03 | NA | NA | 2002-03-15 | 2002-04-29 | 2002-07-21 |  |  |  | 2002-08-01 | X | 2003-12-30 | 2004-03-31 | 2003-12-30 | 2003-01-24 | 2004-03-31 |  | 2005-01-20 |  |  | YES | J. Navarro | 817-222-4655 | Commissioned 3/31/04
4 | 9 | 4 | 1 | 1 | MONROE | OR | ANM | QMO | SKJ6 | BI-4 | BOS | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZSE | N/A | 2000-07-12 | 2000-12-22 | 2001-10-02 | 2001-08-06 | 2001-08-10 | NA | NA | 2002-03-22 | 2002-05-06 | 2002-07-18 |  |  |  | 2002-07-24 | X | 2003-12-30 | 2003-11-10 | 2003-12-30 | 2003-01-31 | 2003-11-10 |  | 2004-02-09 |  |  | YES |  | 425-227-2434 | Commissioned 11/10/03
5 | 13 | 5 | 1 | 1 | PUU NIAUNIAU (MAUI) (EARTS VALIDATION) | HI | AWP | QPN | P7EO | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZHN | N/A | 2000-07-03 | 2000-12-19 | 2001-10-17 | 2001-02-12 | 2001-02-14 | NA | NA | 2002-04-29 | 2002-06-13 | 2003-02-15 |  |  |  |  | X | 2003-10-15 | 2003-11-17 | 2003-10-15 | 2003-03-10 | 2003-11-17 |  | 2004-10-28 |  |  | YES | J. Duhonich | 310-725-7770 | Commissioned 11/17/03
6 | 10 | 6 | 1 | 1 | CHELSEA | OK | ASW | QAF | 13SF | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZKC | ZME, ZFW | 2000-11-01 | 2001-03-12 | 2001-07-17 | 2001-04-14 | 2001-04-14 | NA | NA | 2002-05-05 | 2002-06-19 | 2002-08-16 |  | 2003-12-12 |  | 2002-08-28 | X | 2004-03-10 | 2004-08-10 | 2004-03-10 | 2003-03-16 | 2004-08-10 |  | 2005-02-03 |  |  | YES | J. Navarro | 817-222-4655 | Commissioned 8/10/04
7 | 11 | 7 | 1 | 1 | HALEYVILLE | AL | ASO | QPC-E | F1N7 | BI-5 | FPS-67B | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZME | ZTL | 2000-08-22 | 2001-05-30 | 2001-10-17 | 2001-02-19 | 2001-02-26 | X | NA | 2002-05-14 | 2002-06-28 | 2003-09-21 |  | 2004-04-08 |  | 2002-10-18 | X | 2004-10-21 | 2005-02-23 | 2004-10-21 | 2003-03-25 | 2005-02-23 |  | 2005-06-06 |  |  | YES | W. Carter | 404-305-6299 | Commissioned 2/23/05
8 | 12 | 8 | 1 | 1 | ANSON | TX | ASW | QOO | M6MA | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZFW | N/A | 2000-11-15 | 2001-03-12 | 2001-10-08 | 2000-10-28 | 2000-10-29 | NA | NA | 2002-06-10 | 2002-07-25 | 2002-09-27 |  | 2004-09-20 |  | 2003-05-09 | X | 2004-10-01 | 2004-10-28 | 2004-10-01 | 2003-04-21 | 2004-10-28 |  | 2005-09-30 |  |  | NO | J. Navarro | 817-222-4655 | Commissioned 10/28/04
9 | 4 | 9 | 1 | 1 | CROSSVILLE | TN | ASO | QRV | 171U | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZTL | ZID, ZME | 2000-08-14 | 2001-03-06 | 2001-10-17 | 2000-11-15 | 2000-11-16 | NA | NA | 2002-06-21 | 2002-08-05 | 2003-01-17 |  | 2004-05-06 |  | 2004-05-06 | X | 2004-07-20 | 2004-08-27 | 2004-07-20 | 2003-05-02 | 2004-08-27 |  | 2005-04-05 |  |  | YES | W. Carter | 404-305-6299 | Commissioned 8/27/04
10 | 14 | 10 | 1 | 1 | RED TABLE MOUNTAIN | CO | ANM | DBL | S0DG | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZDV | N/A | 2000-07-12 | 2001-01-23 | 2001-10-02 | 2001-07-10 | 2001-07-11 | NA | NA | 2001-10-29 | 2002-08-07 | 2002-10-15 | X |  |  |  | X | 2003-11-15 | 2004-02-23 | 2003-11-15 | 2002-07-18 | 2004-02-23 |  | 2004-08-06 |  |  | NO | D. Curran/S. Menezes | 425-227-2434 | Commissioned 2/23/04
11 | 15 | 11 | 1 | 1 | SEATTLE (FORT LAWTON) | WA | ANM | SEA-E | 09VU | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZSE | N/A | 2001-04-12 | 2002-02-02 | 2002-10-17 | 2001-05-07 | 2001-05-14 | X | NA | 2001-11-05 | 2002-09-13 | 2002-12-18 | X |  |  | 2003-03-04 | X | 2004-01-16 | NA | 2004-01-16 | NA | 2004-06-10 |  | 2004-07-23 |  |  | YES | D. Curran/S. Menezes | 425-227-2434 | Commissioned 6/10/04
12 | 16 | 12 | 1 | 1 | OAKDALE (PITTSBURGH) | PA | AEA | PIT-E | BPL9 | BI-5 | FPS-67B | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZOB | ZDC | 2000-09-13 | 2001-05-21 | 2001-10-17 | 2001-06-14 | 2001-06-18 | X | NA | 2002-08-26 | 2002-10-10 | 2002-12-17 |  | 2004-02-10 |  | 2003-02-01 | X | 2004-06-30 | 2004-11-17 | 2004-06-30 | 2003-07-07 | 2004-11-17 |  | 2006-06-30 | Raytheon |  | YES | A. Arbeiter | 718-553-4836 | Commissioned 11/17/04.
13 | 17 | 13 | 1 | 1 | BORON | CA | AWP | QSR | DD1H | BI-5 | FPS-67B | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZLA | N/A | 2001-04-03 | 2001-09-13 | 2001-10-17 | 2002-03-21 | 2002-03-25 | X | NA | 2002-03-23 | 2002-10-15 | 2003-03-04 | X | 2004-01-16 |  | 2003-03-29 | X | 2004-07-24 | 2004-08-26 | 2004-07-24 | 2004-03-31 | 2004-08-26 |  | 2004-12-14 |  |  | NO | J. Duhonich | 310-725-7770 | Commissioned 8/26/04
14 | 19 | 14 | 1 | 1 | BRECKSVILLE (CLEVELAND) | OH | AGL | QDB | 070H | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZOB | ZID | 2000-09-13 | 2001-07-24 | 2001-10-17 | 2001-04-23 | 2001-04-27 | X | NA | 2002-04-16 | 2002-11-08 | 2003-02-18 | X | 2004-04-23 |  | 2003-03-08 | X | 2004-10-15 | 2004-10-14 | 2004-10-15 | 2003-11-10 | 2004-10-14 |  | 2006-03-14 | Raytheon |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 10/14/04
15 | 18 | 15 | 1 | 1 | ACADEMY SBR-2 | OK | N/A | FAAAC | PMWA | BI-5 | SUPPORT | NA | NA | NA | NA | N/A | N/A | 2000-07-03 | 2000-11-27 | 2001-10-02 | NA | NA | NA | NA | 2002-10-19 | 2002-12-03 | 2003-05-05 |  |  |  | NA | X | NA | NA | NA | NA | NA |  | NA |  |  | YES | J. Vasquez | 405-954-3129 | (Planned SAT 12/31/05)
17 | 20 | 16 | 1 | 1 | ASHBURN | GA | ASO | QHN-E | HA56 | BI-5 | ARSR-1E | ARSR-2 | FA-10253 | FA-10250 | FA-10250/7 | ZJX | ZTL | 2000-09-25 | 2001-10-01 | 2001-10-17 | 2001-07-12 | 2001-07-16 | X | NA | 2002-12-03 | 2003-01-17 | 2003-03-20 |  | 2004-01-29 |  | 2004-01-28 | X | 2004-01-29 | 2004-10-13 | 2004-01-29 | 2003-10-14 | 2004-10-13 |  | 2006-05-30 |  |  | YES | W. Carter | 404-305-6299 | Commissioned 10/13/04
16 | 21 | 17 | 1 | 1 | ALEXANDRIA (ENGLAND) | LA | ASW | AEX-E | D9S4 | BI-5 | FPS | ARSR-2 | FA-10253 | FA-10250 | FA-10250/5 | ZHU | ZFW | 2000-11-28 | 2001-08-27 | 2001-12-05 | 2001-01-20 | 2001-01-27 | X | NA | 2002-04-29 | 2003-01-17 | 2003-04-03 | X | 2004-06-08 |  | X | X | 2005-10-05 | 2005-11-11 |  | 2005-11-30 | 2005-11-11 |  | 2006-08-10 | Raytheon |  | NO | J. Navarro | 817-222-4655 | Commissioned 11/11/05
18 | 22 | 18 | 1 | 1 | MARIETTA | GA | ASO | ATL-E | 1NX4 | BI-4 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZTL | N/A | 2001-01-09 | 2002-05-21 | 2002-10-17 | 2001-07-26 | 2001-07-30 | X | NA | 2002-05-13 | 2003-01-28 | 2003-12-15 | X | 2004-04-14 |  | 2004-03-11 | X | 2004-06-30 | 2004-06-30 | 2004-06-30 | 2004-02-11 | 2004-06-30 |  | 2005-03-22 |  |  | NO | W. Carter | 404-305-6299 | Commissioned 6/30/04
19 | 23 | 19 | 1 | 1 | HIGBY | WV | AEA | QHY | 4JOR | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZID | N/A | 2000-08-02 | 2001-01-25 | 2003-02-06 | 2001-03-27 | 2001-03-29 | NA | X | 2002-06-05 | 2003-02-24 | 2003-06-03 | X | 2004-03-26 |  | 2003-07-18 | X | 2004-06-28 | 2004-06-28 | 2004-06-28 | 2004-08-10 | 2004-06-28 |  | 2004-11-12 |  |  | NO | A. Arbeiter | 718-553-4836 | Commissioned 6/28/04
20 | 25 | 20 | 1 | 1 | TEXARKANA | AR | ASW | TXK-E | 1CA7 | BI-5 | FPS-67 | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZFW | ZME | 2000-12-07 | 2001-08-27 | 2001-11-01 | 2001-04-02 | 2001-04-07 | X | NA | 2003-01-10 | 2003-02-24 | 2003-04-30 |  | 2004-01-30 |  |  | X | 2004-08-30 | 2004-12-01 | 2004-08-30 | 2003-11-21 | 2004-12-01 |  | 2006-01-20 | Raytheon |  | YES | J. Navarro | 817-222-4655 | Commissioned 12/1/04
21 | 24 | 21 | 1 | 1 | BIORKA ISLAND | AK | AAL | BKA | 0U0J | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZAN | N/A | 1999-08-16 | 2000-04-27 | 2001-10-02 | 2000-09-06 | 2000-09-06 | NA | X | 2002-07-15 | 2003-03-08 | 2003-05-07 | X |  |  | 2003-05-30 | X | 2003-11-10 | 2003-11-12 | 2003-11-10 | 2004-10-28 | 2003-11-12 |  | 2003-12-09 |  |  | NO | G. Johanson/S. Houser | 907-271-2892 | Commissioned 11/12/03
22 | 26 | 23 | 1 | 1 | HUNTINGBURG | IN | AGL | HNB | 69M8 | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZID | ZKC | 2001-04-02 | 2002-01-24 | 2001-07-11 | 2000-10-07 | 2000-10-08 | NA | NA | 2002-07-15 | 2003-04-16 | 2003-06-18 | X | 2004-01-16 |  | 2003-08-15 | X | 2004-09-03 | 2004-09-02 | X | 2004-08-27 | 2004-09-02 |  | 2005-03-04 |  |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 9/2/04
23 | 27 | 74 | 1 | 1 | KLAMATH FALLS (MIG) | OR | ANM | LMT | KDCU | Mode S | FPS | FPS | FA-10254 | FA-10250/7 | FA-10250/7 | ZDV | N/A | 2001-05-15 | 2001-09-17 | 2001-10-17 | 2001-07-12 | 2001-07-13 | X | NA | 2002-07-29 | 2003-04-21 | 2003-06-16 | X |  |  | 2003-07-25 | X | 2003-12-30 | 2003-10-20 | 2003-12-30 | 2004-02-23 | 2003-11-06 |  | 2003-11-14 |  |  | NO | D. Curran/S. Menezes | 425-227-2434 | Commissioned 11/6/03
24 | 28 | 24 | 1 | 1 | SACRAMENTO | CA | AWP | SAC | HDYR | BI-4 | BOS | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZOA | N/A | 2001-05-24 | 2002-08-13 | 2002-12-18 | 2002-03-08 | 2002-03-12 | X | NA | 2003-03-15 | 2003-04-29 | 2003-07-03 |  | 2004-03-09 |  | 2003-12-18 | X | 2004-03-16 | 2004-07-19 | 2004-03-16 | 2004-01-24 | 2004-07-19 |  | 2004-09-17 |  |  | YES | J. Duhonich | 310-725-7770 | Commissioned 7/14/04
25 | 30 | 49 | 1 | 1 | MONTGOMERY | AL | ASO | MGM-E | NPCU | BI-4 | ARSR-1D | ARSR-1 | FA-10251 | FA-10250 | FA-10250/5 | ZTL | ZJX | 2000-11-28 | 2003-02-26 | 2003-04-09 | 2001-11-28 | 2001-12-03 | X | NA | 2002-08-05 | 2003-05-21 | 2003-09-11 | X | 2004-05-28 |  | 2004-05-28 | X | 2004-09-08 | 2004-12-21 | 2004-09-08 | 2004-11-17 | 2004-12-21 |  | 2005-07-01 |  |  | NO | W. Carter | 404-305-6299 | Commissioned 12/21/04
26 | 31 | 26 | 1 | 1 | PAHOA | HI | AWP | POA | P277 | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZHN | N/A | 2001-07-11 | 2002-04-10 | 2001-12-25 | 2001-02-07 | 2001-02-09 | NA | NA | 2002-08-05 | 2003-06-04 | 2003-08-25 | X | 2003-12-19 |  | 2004-01-15 | X | 2004-04-27 | 2004-05-10 | 2004-04-27 | 2004-08-26 | 2004-05-10 |  | 2004-07-09 |  |  | NO | J. Duhonich | 310-725-7770 | Commissioned 5/10/04
27 | 32 | 25 | 1 | 1 | BYHALIA (MEMPHIS) | MS | ASO | QYB-E | H2LA | BI-5 | ARSR-1 | ARSR-1 | FA-10251 | FA-10250 | FA-10250/5 | ZME | N/A | 2001-06-14 | 2002-04-10 | 2002-11-01 | 2001-03-05 | 2001-03-12 | X | NA | 2002-08-12 | 2003-06-10 | 2003-08-14 | X |  |  | 2004-02-20 | X | 2004-03-03 | 2004-04-06 | 2004-02-17 | 2004-06-10 | 2004-04-06 |  | 2005-01-24 |  |  | NO | W. Carter | 404-305-6299 | Commissioned 4/6/04
28 | 29 | 45 | 1 | 1 | DEAD HORSE | AK | AAL | SCC | C8TG | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZAN | N/A | 1999-07-26 | 2000-03-09 | 2001-10-02 | 2000-08-17 | 2000-08-18 | NA | NA | 2003-04-30 | 2003-06-14 | 2003-08-08 |  |  |  | 2003-08-22 | X | 2003-11-10 | 2003-11-20 | 2003-11-10 | 2004-03-10 | 2003-11-20 |  | 2003-12-11 |  |  | YES | G. Johanson/S. Houser | 907-271-2892 | Commissioned 11/20/03
29 | 33 | 29 | 1 | 1 | APPLE VALLEY | MN | AGL | QJE-E | UY9F | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZMP | N/A | 2000-07-24 | 2001-01-23 | 2001-12-05 | 2001-04-11 | 2001-04-16 | X | NA | 2002-10-10 | 2003-06-30 | 2003-09-30 | X | 2004-05-20 |  | 2003-10-24 | X | 2005-03-29 | 2005-03-31 | 2005-03-29 | 2004-10-14 | 2005-03-31 |  | 2005-09-07 |  |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 3/31/05
30 | 34 | 31 | 1 | 1 | SKOWHEGAN | ME | ANE | QYC | SQQQ | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZBW | N/A | 2002-11-19 | 2003-04-04 | 2003-05-13 | 2001-07-31 | 2001-07-31 | X | NA | 2003-06-14 | 2003-07-29 | 2003-10-10 |  | 2004-05-14 |  | 2004-08-19 | X | 2004-09-21 | 2005-03-28 | 2004-09-21 | 2004-04-24 | 2005-03-28 |  | 2006-03-17 | Raytheon |  | YES | J. Hadley | 781-238-7852 | Commissioned 3/28/05
31 | 36 | 15 | 1 | 1 | EAGLE RIVER | WI | AGL | EGV | 647V | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZMP | N/A | 2000-08-02 | 2001-03-19 | 2002-01-24 | 2001-08-27 | 2001-08-29 | NA | X | 2002-10-22 | 2003-08-12 | 2004-01-09 | X | 2004-03-04 |  | 2004-03-04 | X | 2004-08-30 | NA | 2004-08-30 | 2004-08-12 | 2004-08-12 |  | 2005-09-21 |  |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 8/12/04
32 | 35 | 37 | 1 | 1 | MAIDEN | NC | ASO | QRM-E | C2LA | BI-5 | ARSR-1 | ARSR-1 | FA-10251 | FA-10250 | FA-10250/5 | ZTL | ZJX | 2001-07-19 | 2002-05-08 | 2002-09-11 | 2001-12-07 | 2001-12-11 | X | NA | 2002-12-02 | 2003-08-14 | 2003-11-13 | X | 2004-06-21 |  | 2004-04-24 | X | 2004-10-08 | 2005-06-23 | 2004-10-08 | 2004-10-13 | 2005-06-23 |  | 2005-12-21 |  |  | NO | W. Carter | 404-305-6299 | Commissioned 6/23/05
33 | 38 | 32 | 1 | 1 | ROGERS | TX | ASW | QYS-E | HY6R | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZHU | ZFW | 2001-02-08 | 2002-06-11 | 2002-10-17 | 2002-01-10 | 2002-01-13 | X | NA | 2003-07-12 | 2003-08-26 | 2003-10-25 |  | 2004-09-24 |  |  | X | 2004-10-22 | 2005-05-24 | 2004-10-22 | 2004-05-22 | 2005-05-24 |  | 2005-07-21 |  |  | YES | J. Navarro | 817-222-4655 | Commissioned 5/24/05
34 | 39 | 33 | 1 | 1 | CUMMINGTON | MA | ANE | QHA | SYV4 | BI-5 | FPS-67B | FPS | FA-10253 | FA-10250 | FA-10250/5 | ZBW | ZNY | 2000-08-23 | 2002-05-14 | 2002-09-11 | 2002-05-29 | 2002-05-30 | X | NA | 2003-01-08 | 2003-09-10 | 2003-11-04 | X | 2004-03-19 |  | 2004-03-19 | X | 2004-06-30 | 2004-06-28 | 2004-06-30 | 2004-06-30 | 2004-06-28 |  | 2004-10-28 |  |  | NO | J. Hadley | 781-238-7852 | Commissioned 6/28/04
35 | 40 | 34 | 1 | 1 | LAGRANGE | IN | AGL | QTZ-E | N3HA | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZAU | ZOB | 2001-05-15 | 2003-01-29 | 2003-07-10 | 2002-07-15 | 2002-07-18 | X | NA | 2003-01-16 | 2003-09-25 | 2004-01-13 | X | 2004-07-22 |  | 2004-02-11 | X | 2005-03-24 | 2005-05-12 | 2005-03-24 | 2004-07-30 | 2005-05-12 |  | 2006-04-30 |  |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 5/12/05
36 | 41 | 22 | 1 | 1 | RUSSELLVILLE | AR | ASW | QXR-E | 4UHH | BI-4 | FPS-64A | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZME | ZKC | 2001-01-09 | 2001-10-01 | 2001-10-17 | 2001-03-19 | 2001-03-26 | X | NA | 2003-01-19 | 2003-10-06 | 2003-12-17 | X | 2004-02-05 |  | 2005-01-14 | X | 2005-02-01 | 2005-09-07 | 2005-09-07 | 2005-09-07 | 2005-09-07 |  | 2006-04-11 | Raytheon |  | NO | J. Navarro | 817-222-4655 | Commissioned 9/7/05
37 | 43 | 36 | 1 | 1 | SAN PEDRO | CA | AWP | QLA-E | 0YBS | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZLA | N/A | 2001-03-22 | 2003-03-18 | 2003-06-02 | 2002-03-14 | 2002-03-18 | X | NA | 2003-01-30 | 2003-10-20 | 2004-02-19 | X |  |  | 2004-04-16 | X | 2004-10-04 | 2005-06-17 | 2004-10-04 | 2004-12-01 | 2005-06-17 |  | 2005-10-31 |  |  | NO | J. Duhonich | 310-725-7770 | Commissioned 6/17/05
38 | 44 | 52 | 1 | 1 | CROCKER | MO | ACE | QJN | SE9T | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZKC | ZME | 2001-06-11 | 2001-09-18 | 2001-12-14 | 2001-05-05 | 2001-05-05 | NA | NA | 2003-02-04 | 2003-11-03 | 2004-02-23 | X | 2004-08-05 |  | 2004-08-06 | X | 2004-09-14 | 2003-11-10 | 2003-10-10 | 2003-11-12 | 2005-03-18 |  | 2005-08-04 |  |  | NO | C. Wilburn | 816-329-3609 | Commissioned 3/18/05
39 | 45 | 42 | 1 | 1 | JOELTON (NASHVILLE) | TN | ASO | QOJ-E | EHE4 | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZME | ZID, ZTL | 2001-07-10 | 2003-06-25 | 2003-08-01 | 2002-02-08 | 2002-02-12 | X | NA | 2003-10-19 | 2003-12-03 | 2004-02-25 |  | 2004-02-19 |  | 2004-07-01 | X | 2004-07-30 | 2005-04-20 | 2004-07-30 | 2004-08-29 | 2005-04-20 |  | 2006-03-15 |  |  | YES | W. Carter | 404-305-6299 | Commissioned 4/20/05
40 | 46 | 38 | 1 | 1 | WEST MESA | NM | ASW | QSA | K71U | BI-5 | FPS-66A | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZDV | ZAB | 2001-02-20 | 2002-07-11 | 2003-07-08 | 2001-10-18 | 2001-10-21 | X | X | 2003-03-12 | 2004-01-06 | 2004-02-25 | X | 2004-04-08 |  |  | X | 2004-06-23 | 2004-09-01 | 2004-09-02 | 2004-09-03 | 2004-09-01 |  | 2005-02-17 |  |  | NO | J. Navarro | 817-222-4655 | Commissioned 9/1/04
| 1001 |  | 1 | 1 | Vandenberg AFB | CA | DOD | VBG |  | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZLA |  |  |  |  | NA | NA | NA | NA | 37951 | 2004-01-10 | 2004-03-09 | 4650-12 | NA |  | 2004-11-02 | X | DOD Operatioanal | DOD Operatioanal | DOD Operatioanal | DOD Operatioanal | 2004-11-05 |  | NA |  | ** | YES | W.Schobel (USAF) | 310-725-7770 | DOD Facility, FAA Test Site, FAA receives feeds
41 | 47 | 67 | 1 | 1 | LINCOLNTON | GA | ASO | QNK-E | 7N6Q | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZTL | ZJX | 2001-01-18 | 2003-11-04 | 2003-12-05 | TBD | 2003-09-12 | 2003-12-22 | NA | 2003-03-18 | 2004-01-20 | 2004-03-18 | X | 2004-12-03 |  | 2005-02-23 | X | 2005-02-28 | 2003-11-06 | 2003-09-29 | 2003-11-06 | 2005-03-29 |  | 2006-02-15 |  |  | YES | W. Carter | 404-305-6299 | Commissioned 3/29/05
42 | 49 | 43 | 1 | 1 | LONDON | OH | AGL | QWO-E | 0JCG | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZID | ZOB | 2001-04-24 | 2002-11-27 | 2003-02-21 | 2001-02-03 | 2001-02-10 | X | NA | 2003-04-03 | 2004-01-27 | 2004-03-22 | X | 2004-09-17 |  | 2004-06-17 | X | 2005-03-30 | 2005-06-17 | 2004-07-19 | 2004-07-14 | 2005-06-17 |  | 2006-02-28 | Raytheon |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 6/17/05
43 | 51 | 44 | 1 | 1 | HOUSTON (ELLINGTON) | TX | ASW | HOU-E | 0NWU | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZHU | N/A | 2001-06-14 | 2002-11-01 | 2003-01-30 | 2002-06-15 | 2002-06-20 | X |  | 2003-12-22 | 2004-02-05 | 2004-04-27 |  | 2004-09-28 |  |  | X | 2004-10-27 | 2005-02-23 | 2004-10-27 | 2004-11-01 | 2005-02-23 |  | 2005-05-23 |  |  | NO | J. Navarro | 817-222-4655 | Commissioned 2/23/05
44 | 50 | 40 | 1 | 1 | MIDDLETON ISLAND | AK | AAL | MDO | 6URY | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZAN | N/A | 1999-08-09 | 2000-04-19 | 2001-10-02 | 2000-09-13 | 2000-09-14 | NA | NA | 2003-04-09 | 2004-03-02 | 2004-04-10 | X | 2004-05-11 |  | 2004-05-11 | X | 2004-05-21 | 2004-06-21 | 2004-05-21 | 2004-12-31 | 2004-06-21 |  | 2004-10-01 |  |  | NO | G. Johanson/S. Houser | 907-271-2892 | Commissioned 6/21/04
45 | 52 | 46 | 1 | 1 | HANNA CITY | IL | AGL | QUZ-E | DPL9 | BI-5 | FPS-67B | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZAU | ZKC | 2001-05-24 | 2003-06-16 | 2003-07-17 | 2002-02-11 | 2002-02-18 | X | NA | 2003-04-24 | 2004-03-18 | 2004-04-24 | X | 2004-08-25 |  | 2004-08-12 | X | 2004-10-15 | 2005-08-10 | 2004-10-15 | 2005-06-11 | 2005-08-10 |  | 2006-07-10 | Raytheon |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 8/10/05
46 | 53 | 47 | 1 | 1 | ODESSA | TX | ASW | QXS-E | MU1F | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZFW | ZAB | 2001-01-18 | 2003-01-29 | 2003-03-04 | 2002-01-24 | 2002-01-28 | X |  | 2004-02-09 | 2004-03-25 | 2004-05-26 |  | 2004-03-30 |  |  | X | 2004-10-28 | 2005-04-04 | 2004-10-28 | 2004-12-20 | 2005-04-04 |  | 2006-02-10 | Raytheon |  | NO | J. Navarro | 817-222-4655 | Commissioned 4/4/05
47 | 54 | 27 | 1 | 1 | BENTON | PA | AEA | QRC-E | G8QZ | BI-5 | FPS-67B | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZNY | ZDC, ZBW | 2001-04-12 | 2002-05-02 | 2002-08-13 | 2001-08-16 | 2001-08-23 | X | X | 2003-04-30 | 2004-04-14 | 2004-06-02 | X | 2004-07-22 |  | 2004-07-22 | X | 2004-10-05 | 2005-02-10 | 2004-10-05 | 2004-05-10 | 2005-02-10 |  | 2006-11-08 |  |  | NO | A. Arbeiter | 718-553-4836 | Commissioned 2/10/05 ANI will perform removal and relocation to Atlantic City, NJ. Check status of cutover.
48 | 55 | 50 | 1 | 1 | SILVER CITY | NM | ASW | SVC-E | 0BK0 | BI-5 | ARSR-2 | ARSR-2 | FA-10252 | FA-10250 | FA-10250/5 | ZAB | N/A | 2001-06-05 | 2003-01-29 | 2003-03-13 | 2002-01-17 | 2002-01-21 | X | NA | 2003-05-06 | 2004-04-15 | 2004-06-16 | X | 2004-09-29 |  |  | X | 2004-10-04 | 2003-11-10 | 2004-10-04 | 2003-11-20 | 2005-01-14 |  | 2005-02-15 |  |  | NO | J. Navarro | 817-222-4655 | Commissioned 1/14/05
49 | 56 | 124 | 1 | 1 | BATTLE MOUNTAIN | NV | AWP | BAM |  | BI-4 | ARSR-2 | ARSR-2 |  |  |  | ZLC | ZOA | 2003-05-28 | 2003-10-30 | 2004-03-01 | NA | NA |  | NA | 2003-05-13 | 2004-05-08 | 2004-08-02 | X | 2004-11-09 |  | 2004-09-08 | X | 2005-06-15 | 2005-08-02 | 2005-06-15 | 2005-02-15 | 2005-08-02 |  | 2006-06-05 | Raytheon |  | NO | J. Duhonich | 310-725-7770 | Commissioned 8/2/05
50 | 57 | 30 | 1 | 1 | SAMBURG | TN | ASO | QPB | M3HE | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZME | ZKC | 2003-08-24 | 2003-09-30 | 2004-03-01 | 2000-11-20 | 2000-11-21 | NA |  | 2004-03-29 | 2004-05-13 | 2004-07-27 | X | 2004-11-02 |  | 2004-11-05 | X | 2005-06-24 | 2006-02-13 | 2006-02-13 | 2006-04-06 | 2006-02-13 |  | 2006-09-14 |  |  | NO | W. Carter/J. Taylor | 404-305-6299 | Commissioned 2/13/06
51 | 58 | 56 | 1 | 1 | COOPERSVILLE | MI | AGL | CPV-E | D8QZ | BI-5 | FPS-66A | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZAU | ZMP, ZOB | 2002-05-20 | 2003-06-19 | 2004-04-30 | 2002-05-06 | 2002-05-10 | X | X | 2003-06-19 | 2004-05-27 | 2004-07-26 | 2004-07-26 | 2004-07-26 |  | 2005-04-06 | X | 2006-04-14 | 2006-04-14 | 2006-04-14 | 2006-03-20 | 2006-04-14 |  | 2006-09-28 |  |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 4/14/06
52 | 59 | 60 | 1 | 1 | BINNS HALL | VA | AEA | QBN-E | PVK1 | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZDC | N/A | 2001-03-13 | 2003-02-03 | 2002-12-03 | TBD | TBD | 2004-06-28 | NA | 2003-06-30 | 2004-06-17 | 2004-10-25 | 2004-10-25 | 2006-02-10 |  | 2006-02-17 | X | 2005-10-26 | 2006-02-27 | 2006-02-27 | 2006-04-17 | 2006-02-27 |  | 2006-08-03 | Raytheon |  | NO | A. Arbeiter | 718-553-4836 | Commissioned 2/27/06
53 | 60 | 48 | 1 | 1 | ST. PAUL ISLAND | AK | AAL | SNP | V7UB | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZAN | N/A | 2001-05-05 | 2002-05-23 | 2003-07-22 | 2002-05-02 | 2002-05-05 | NA | NA | 2003-07-08 | 2004-06-29 | 2004-08-19 | 2004-08-19 | 2004-09-17 |  | 2004-09-15 | X | 2004-09-23 | 2004-11-01 | 2004-10-23 | 2005-09-22 | 2004-11-01 |  | 2005-05-09 |  |  | NO | G. Johanson/S. Houser | 907-271-2892 | Commissioned 11/1/04
54 | 61 | 62 | 1 | 1 | INDIANAPOLIS | IN | AGL | IND | N9EQ | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZID | ZAU | 2002-05-09 | 2003-07-08 | 2003-10-27 | 2002-06-24 | 2002-06-28 | X | NA | 2003-07-17 | 2004-07-15 | 2004-10-06 | 2004-10-06 | 2004-09-30 |  | 2004-12-09 | X | 2006-06-29 | 2006-06-29 | 2006-06-29 | 2006-07-02 | 2006-06-29 | 2007-02-13 | 2007-02-22 | Raytheon |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 6/29/06
55 | 62 | 75 | 1 | 1 | FOSSIL | OR | ANM | QVN-E | FK3E | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZSE | ZLC | 2001-10-24 | 2002-10-01 | 2003-01-30 | TBD | TBD | 2004-08-07 | NA | 2003-08-04 | 2004-08-05 | 2005-04-08 | 2004-10-13 | 2005-05-26 |  | 2005-04-12 | X | 2005-06-30 | 2005-07-07 | 2005-07-30 | 2005-08-02 | 2005-07-07 |  | 2005-11-15 |  |  | NO | D. Curran/S. Menezes | 425-227-2434 | Commissioned 7/7/05
56 | 63 | 73 | 1 | 1 | DANSVILLE (MIG) | NY | AEA | DSV-E | U486 | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZOB | ZBW, ZNY | 2000-09-05 | 2002-11-13 | 2003-04-09 | 2001-08-24 | 2001-08-28 | X | NA | 2003-08-14 | 2004-08-05 | 2004-09-29 | 2004-09-29 | 2005-07-14 |  | 2005-07-14 | X | 2005-09-11 | 2005-11-30 | 2005-11-30 | 2005-11-12 | 2005-11-30 |  | 2006-04-10 | Raytheon |  | NO | A. Arbeiter | 718-553-4836 | Commissioned 11/30/05
57 | 64 | 55 | 1 | 1 | HUTCHINSON | KS | ACE | HTI-E | 2JAW | BI-4 | FPS-66A | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZKC | N/A | 2001-06-26 | 2001-11-01 | 2002-01-30 | 2001-10-20 | 2001-10-24 | X | NA | 2004-06-26 | 2004-08-10 | 2004-10-25 | 2004-10-25 | 2004-11-07 |  | 2004-11-18 | X | 2005-01-25 | 2005-07-14 | 2005-02-24 | 2005-02-27 | 2005-07-14 |  | 2005-10-27 |  |  | NO | C. Wilburn | 816-329-3609 | Commissioned 7/14/05.
58 | 65 | 64 | 1 | 1 | HORICON | WI | AGL | QHZ-E | S1B2 | BI-5 | ARSR-2 | ARSR-2 | FA-10252 | FA-10250 | FA-10250/5 | ZAU | ZMP | 2002-04-18 | 2003-02-28 | 2004-04-30 | 2002-05-18 | 2002-05-22 | X | NA | 2003-09-10 | 2004-08-17 | 2004-11-01 | 2004-11-01 | 2005-01-14 |  | 2005-11-04 |  | 2006-04-27 | 2006-04-27 | 2006-04-27 | 2006-04-30 | 2006-04-27 | 2007-01-01 | 2007-01-11 | Raytheon |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 4/27/06. 1/11/07: Legacy system removed.
59 | 66 | 66 | 1 | 1 | SELIGMAN | AZ | AWP | QXP-E | PL9E | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZLA | ZAB | 2001-03-01 | 2002-08-19 | 2003-01-21 | TBD | TBD | 2004-09-02 | NA | 2003-09-11 | 2004-09-23 | 2003-12-17 | 2005-01-25 | 2006-02-25 |  | 2006-03-02 | X | 2006-06-21 | 2006-07-21 | 2006-07-21 | 2006-08-18 | 2006-07-25 |  | 2007-02-24 | FAA |  | NO | J. Duhonich | 310-725-7770 | Commissioned 7/25/06
60 | Mode 4 1002 | 114 | 1 | 1 | TYNDALL AFB | FL | ASO | PAM-E | V04X | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZJX |  | 2003-11-03 | 2003-12-18 | 2004-05-05 | NA | NA | NA | X | 2003-10-03 | 2004-09-29 | 2004-02-23 | 2005-01-20 |  |  | 2005-03-18 | X | 2005-11-04 | 2006-06-05 | 2006-06-05 | 2006-06-08 | 2006-06-06 |  | 2006-10-18 |  | X | YES | W. Carter | 404-305-6299 | Commissioned 6/6/06
61 | 48 | 70 | 1 | 1 | CLEARFIELD | PA | AEA | QCF-E | PDM4 | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZOB | ZNY | 2002-06-10 | 2003-04-07 | 2004-04-30 | TBD | TBD | 2004-09-27 | NA | 2003-10-28 | 2004-10-08 | 2004-12-14 | 2004-12-14 | 2006-01-07 |  | 2006-02-16 | X | 2006-06-15 | 2006-07-17 | 2006-07-17 | 2006-07-20 | 2006-07-17 | 2007-01-15 | 2007-01-25 | Raytheon |  | NO | A. Arbeiter | 718-553-4836 | Commissioned 7/17/06
62 | 67 | 72 | 1 | 1 | PHOENIX (HUMBOLT) (MIG) | AZ | AWP | PHX-E | HMHL | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZAB | ZLA | 2001-03-13 | 2002-04-22 | 2002-07-11 | 2001-06-22 | 2001-06-26 | X | NA | 2003-12-02 | 2004-10-21 | 2004-03-18 | 2005-02-07 | 2004-04-15 |  | 2005-02-17 | X | 2005-04-08 | 2005-08-17 | 2005-08-17 | 2005-08-20 | 2005-08-17 |  | 2006-03-20 | Raytheon |  | NO | J. Duhonich | 310-725-7770 | Commissioned 8/17/05
63 | 68 | 59 | 1 | 1 | ST. LOUIS | MO | ACE | STL-E | B8QZ | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZKC | N/A | 2001-07-19 | 2002-05-02 | 2002-10-17 | TBD | 2003-07-20 | 2004-11-18 | NA | 2003-12-03 | 2004-10-28 | 2005-04-08 | 2005-02-22 | 2005-03-31 |  | 2005-03-31 | X | 2005-07-06 | 2005-10-12 | 2005-10-12 | 2005-10-07 | 2005-10-12 |  | 2006-08-17 | Raytheon |  | NO | C. Wilburn | 816-329-3609 | Commissioned 10/12/05
65 | 70 | 71 | 1 | 1 | DETROIT (MIG) | MI | AGL | QDT | OD97 | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZOB | N/A | 2000-09-25 | 2002-03-11 | 2000-07-11 | 2001-05-14 | 2001-05-17 | X | NA | 2004-09-27 | 2004-11-11 | 2005-05-06 | 2005-03-11 | 2005-05-06 |  | 2005-09-02 | X | 2006-05-25 | 2006-05-25 | 2006-05-25 | 2006-07-03 | 2006-05-25 |  | 2006-07-20 | Raytheon |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 5/25/06.
66 | 71 | 76 | 1 | 1 | THE PLAINS | VA | AEA | QPL-E | SK3E | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZDC | ZOB, ZNY | 2001-04-03 | 2003-01-31 | 2003-03-18 | TBD | TBD | 10/28/2004 12/14/2004 | NA | 2003-12-09 | 2004-12-02 | 2005-03-15 | 2005-03-15 | 2005-09-16 |  | 2005-09-23 | X | 2005-10-08 | 2005-10-26 | 2005-11-07 | 2005-11-10 | 2005-10-26 | 2007-01-27 | 2007-02-08 | Raytheon |  | NO | A. Arbeiter | 718-553-4836 | Commissioned 10/26/05 (FY-07 Goal: Planned System Removal 3/31/07)
81 | 72 | 51 | 1 | 1 | SHEMYA | AK | AAL | SYA | CP1U | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZAN | N/A | 1999-08-02 | 2000-01-10 | 2000-09-18 | 2001-10-03 | 2001-10-04 | NA | NA | 2004-01-20 | 2005-03-01 | 2005-05-25 | 2005-04-20 | 2005-05-23 |  | 2005-05-23 | X | 2005-05-27 | 2005-06-17 | 2005-06-17 | 2006-05-25 | 2005-06-17 |  | 2005-07-18 |  |  | NO | G. Johanson/S. Houser | 907-271-2892 | Commissioned 6/17/05
68 | 42R | 57 | 1 | 1 | OMAHA | NE | ACE | QHO-E | DJAW | BI-4 | FPS-66A | FPS | FA-10253 | FA-10250 | FA-10250/7 | ZMP | N/A | 2001-06-05 | 2002-09-19 | 2003-10-14 | TBD | TBD | 2005-04-22 | NA | 2004-01-21 | 2005-04-08 | 2005-06-01 | 2005-06-01 | 2005-08-05 |  | 2005-08-11 | X | 2006-01-26 | 2006-04-06 | 2006-04-06 | 2006-05-31 | 2006-07-12 | 2007-01-15 | 2007-01-25 | Raytheon |  | NO | C. Wilburn | 816-329-3609 | Commissioned 7/12/06
74 | 37 | 53 | 1 | 1 | KELLER (FT. WORTH) | TX | ASW | FTW-E | HU1F | BI-4 | ARSR-1D | ARSR-1 | FA-10251 | FA-10250 | FA-10250/5 | ZFW | N/A | 2001-04-02 | 2001-06-25 | 2002-09-10 | 2001-11-05 | 2001-11-11 | X | NA | 2005-03-07 | 2005-04-21 | 2005-07-01 | 2005-07-01 | 2006-02-07 |  | 2005-09-27 | X | 2006-04-15 | 2006-05-16 | 2006-05-16 | 2006-05-19 | 2006-05-16 | 2007-02-13 | 2007-02-22 | Raytheon |  | NO | J. Navarro | 817-222-4655 | Commissioned 5/16/06
64 | 75 | 58 | 1 | 1 | BENSON | NC | ASO | QRL-E | JFOD | BI-5 | ARSR-1E | ARSR-2 | FA-10251 | FA-10250 | FA-10250/5 | ZDC | ZTL, ZJX | 2001-03-01 | 2002-08-13 | 2002-11-27 | 2002-01-31 | 2002-02-04 | X | NA | 2004-02-03 | 2005-05-05 | 2005-08-16 | X | 2004-07-09 |  | 2005-09-02 | X | 2005-10-04 | 2006-07-13 | 2006-07-13 | 2006-07-16 | 2006-07-13 | 2006-11-15 | 2006-11-27 | FAA |  | NO | W. Carter | 404-305-6299 | Commissioned 7/13/06. (FY07 Goal: System Removal 3/31/07; Completed 11/27/06)
75 | 73 | 68 | 1 | 1 | BEDFORD | VA | AEA | QBE-E | PYAE | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZID | ZDC, ZTL | 2002-07-11 | 2003-05-28 | 2003-03-03 | TBD | TBD |  | NA | 2004-03-02 | 2005-05-20 | 2005-11-09 | 2005-11-09 |  |  | 2006-01-26 | X | 2006-03-10 | 2006-03-28 | 2006-03-28 | 2006-03-31 | 2006-03-28 |  | 2006-08-31 | FAA |  | NO | A. Arbeiter | 718-553-4836 | Commissioned 3/28/06 ANI performed removal and relocation to Lynchburg, VA, system cutover on 9/14/06.
72 | 76 | 61 | 1 | 1 | OSKALOOSA | KS | ACE | QBZ-E | 3A56 | BI-4 | ARSR-2 | ARSR-2 | FA-10252 | FA-10250 | FA-10250/5 | ZKC | N/A | 2001-07-10 | 2002-07-16 | 2002-10-29 | TBD | TBD | 2005-07-01 | NA | 2004-03-11 | 2005-06-15 | 2005-09-07 | X | 2005-03-14 |  | 2005-10-07 | X | 2005-12-08 | 2006-02-10 | 2006-02-10 | 2006-02-13 | 2006-02-13 |  | 2006-08-31 | Raytheon |  | NO | C. Wilburn | 816-329-3609 | Commissioned 2/13/06
71 | 74 | 63 | 1 | 1 | LYNCH | KY | ASO | QRI-E | BX93 | BI-5 | ARSR-2 | ARSR-2 | FA-10252 | FA-10250 | FA-10250/5 | ZTL | ZID | 2001-02-20 | 2002-10-11 | 2002-12-17 | 2002-06-14 | 2002-06-17 | X | NA | 2004-03-23 | 2005-06-28 | 2005-07-11 | 2005-07-11 | 2005-03-04 |  | 2005-08-11 | X | 2006-03-28 | 2006-04-20 | 2006-04-20 | 2006-04-30 | 2006-04-20 |  | 2007-02-26 | FAA |  |  | W. Carter | 404-305-6299 | Commissioned 4/20/06
| Mode 4 1004 |  | 1 | 1 | ACADEMY Mode 4 Trainer | OK | AMA |  | AB87 | NA | SUPPORT | ARSR-4 |  |  |  | N/A | N/A | [8 empty] | 2005-07-28 | 2005-10-12 | 2005-11-12 | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  | J. Vasquez |  | System has been accepted: ATCBI-6 Mode-4 training in process.
70 | 77 | 85 | 1 | 1 | KENAI | AK | AAL | ENA | S3FM | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZAN | N/A | 2001-04-24 | 2003-04-30 | 2003-02-11 | TBD | TBD | 2005-05-20 | NA | 2004-03-24 | 2005-08-18 | 2005-10-20 | 2005-10-20 | 2006-09-15 |  | 2006-09-22 | X | 2006-09-29 | 2006-10-29 | 2006-10-29 | 2006-11-16 | 2006-10-31 | 2007-02-26 | 2007-03-09 | Raytheon |  | NO | G. Johanson/S. Houser | 907-271-2892 | Commissioned 10/31/06. FY07 Goal: IOC 3/31/07; Completed 10/1/06
69 | 79 | 54 | 1 | 1 | CITRONELLE | AL | ASO | QRB-E | SX93 | BI-5 | ARSR-2 | ARSR-2 | FA-10252 | FA-10250 | FA-10250/5 | ZHU | ZJX, ZTL, ZME | 2003-02-06 | 2003-08-15 | 2004-01-07 | 2002-05-13 | 2002-05-16 | X | NA | 2004-07-15 | 2005-09-01 | 2005-11-03 | 2005-11-03 | 2005-02-10 |  | 2006-02-28 | X | 2006-02-16 |  | 2006-03-18 | 2006-03-21 | 2006-03-27 |  | 2006-08-01 | FAA |  | NO | W. Carter | 404-305-6299 | Commissioned 3/27/06
82 | 80 | 69 | 1 | 1 | ARLINGTON | IA | ACE | QJO-E | 73YF | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZAU | ZMP | 2002-06-10 | 2003-05-15 | 2004-04-30 | TBD | TBD |  | NA | 2005-07-30 | 2005-09-13 | 2006-02-27 | 2006-02-27 |  |  | 2006-04-14 | X | 2006-04-26 | 2006-06-07 | 2006-06-07 | 2006-06-10 | 2006-06-07 | 2007-02-13 | 2007-02-22 | Raytheon |  | NO | C. Wilburn | 816-329-3609 | Commissioned 6/7/06
78 | 1005 | 93 | 1 | 1 | MAKAH | WA | ANM | QKW-E | VG38 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZSE | N/A |  |  | 2003-09-01 | NA | NA | NA | NA |  | 2005-09-29 | 2005-12-14 | X |  |  | 2006-01-12 | X | 2006-08-23 | 2006-09-22 | 2006-09-22 | 2006-09-25 | 2006-09-29 | 2007-06-18 | 2007-06-30 | FAA | X | YES | D. Curran/S. Menezes | 425-227-2434 | Commissioned 9/29/06
98 | 1006 | 98 | 1 | 1 | OCEANA | VA | AEA | QVR-E | 23F1 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZDC | ZNY | 2001-03-22 | 2002-12-09 | 2003-08-12 | NA | NA | NA | NA | 2005-08-20 | 2005-10-04 | 2006-01-13 | 2006-01-13 |  |  | 2006-05-12 | X | 2006-05-23 | 2006-08-22 | 2006-08-22 | 2006-09-08 | 2006-08-22 | 2007-01-15 | 2007-01-25 | Raytheon | X | YES | A. Arbeiter | 718-553-4836 | Commissioned 8/22/06
76 | 81 | 77 | 1 | 1 | ELWOOD (JOLIET) | IL | AGL | JOL | VG0P | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZAU | N/A | 2002-04-29 | 2003-09-10 | 2003-12-02 | TBD | TBD |  | NA | 2005-09-12 | 2005-10-27 | 2006-01-31 | X |  |  | 2006-05-19 | X | 2006-08-16 | 2006-09-15 | 2006-09-15 | 2006-09-18 | 2006-09-16 | 2007-02-26 | 2007-03-09 | Raytheon |  | NO | J. Page/D. Sargent | 847-294-7343 | Commissioned 9/16/06. 3-9-07: Installation of the new Parrot antennas (BI-5 directional antennas will be used vs BI-6) was completed 3/6/07.(FY07 Goal BI-5 Removal 5/31/07)
79 | 1007 | 83 | 1 | 1 | OILTON | TX | ASW | QZA-E | C6GE | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZHU | N/A | 2003-02-17 | 2002-11-26 | 2005-04-01 | NA | NA | NA | NA | 2005-09-19 | 2005-11-03 | 2006-02-07 | 2006-02-07 |  | 2006-11-03 | 2007-01-10 | X | 2007-01-10 | 2007-03-06 | 2007-03-06 | 2007-02-12 | 2007-03-06 | 2007-03-12 | 2007-03-24 | Raytheon | X | YES | J. Navarro | 817-222-4655 | Commissioned 3/6/07.(FY07 Goal: IOC 2/28/07)
80 | 1008 | 91 | 1 | 1 | CROSS CITY | FL | ASO | CTY-E | VKUN | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZJX | ZMA | 2002-09-03 | 2004-02-27 | 2003-07-30 | NA | NA | NA | NA | 2005-09-24 | 2005-11-08 | 2006-02-13 | 2006-02-13 |  | 2007-07-10 | 2007-07-24 |  | 2007-09-02 | 2007-10-02 | 2007-10-02 | 2007-10-05 |  | 2008-04-03 | 2008-04-15 | Raytheon | X | YES | W. Carter | 404-305-6299 | 3/9/07: ESA continues to coordinate Parrot location, leasing agreement, and plan for parrot installation.
126 | 82 | 123 | 0 | 1 | FAALC DEPOT (TSF) | OK | N/A | FAALC | SXXR | NA | SUPPORT | NA | NA | NA | NA | NA | NA | 2005-10-12 |  |  | NA | NA | NA | NA | 2005-10-16 | 2005-11-30 | 2005-12-16 | X | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA |  |  | NO | J. VASQUEZ | 405-954-3129
| 69 |  | 1 | 1 | PSF SBR-2 | OK | N/A |  | BRB5 | NA | SUPPORT | NA |  |  |  | N/A | N/A | [7 empty] | 2005-11-26 | 2006-01-10 | 2006-03-15 | X |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 405-954-5700
| 1003 |  | 0 | 0.5 | PSF Mode 4 (Single Channel) | OK | ASW |  |  | NA | SUPPORT | NA |  |  |  | N/A | N/A | [7 empty] | 2006-11-26 | 2006-01-12 | 2006-03-15 | X |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | 817-222-4655
92 | 1009 | 92 | 1 | 1 | GIBBSBORO | NJ | AEA | QIE-E | 73K3 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZNY | ZDC, ZBW | 2002-07-01 | 2004-07-16 | 2003-09-01 | NA | NA | NA | NA | 2005-12-04 | 2006-01-18 | 2006-03-22 | 2006-03-22 |  |  | 2006-08-25 | X | 2006-08-28 | 2006-10-20 | 2006-10-20 | 2006-10-23 | 2006-11-27 | 2007-02-25 | 2007-03-09 | Raytheon | X | YES | A. Arbeiter | 718-553-4836 | Commissioned 11/27/06.
95 | 1010 | 82 | 1 | 1 | MILL VALLEY | CA | AWP | QMV-E | 5L14 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZOA | ZAB | 2002-11-04 | 2004-06-25 | 2003-05-28 | NA | NA | NA | NA | 2006-01-12 | 2006-02-08 | 2006-04-17 | 2006-04-17 |  |  | 2006-09-29 | X | 2006-10-05 | 2006-11-04 | 2006-11-04 | 2006-11-07 | 2006-11-07 | 2007-01-27 | 2007-02-08 | Raytheon | X | YES | J. Duhonich | 310-725-7770 | Commissioned 11/7/06. (FY07 Goal: IOC 11/30/06; Completed 10/5/06)
93 | 1012 | 78 | 1 | 1 | ROCKSPRINGS | TX | ASW | RSG-E | B2FF | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZHU | ZFW | 2003-02-27 | 2003-05-12 | 2005-01-10 | NA | NA | NA | NA | 2006-01-29 | 2006-03-15 | 2006-05-23 | 2006-05-23 |  |  | 2006-06-24 | X | 2006-06-27 | 2006-08-22 | 2006-07-27 | 2006-07-30 | 2006-08-22 | 2007-02-13 | 2007-02-22 | Raytheon | X | YES | J. Navarro | 405-954-5700 | Commissioned 8/22/06
67 | 83 | 39 | 1 | 1 | NEWPORT | MS | ASO | QNM-E | S0SR | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZME | N/A | 2001-06-26 | 2004-03-17 | 2002-06-25 | TBD | TBD |  | X | 2006-02-18 | 2006-04-04 | 2006-06-08 | 2006-06-08 |  |  | 2006-06-23 | X | 2006-06-22 | 2006-07-22 | 2006-07-22 | 2006-07-25 | 2006-09-25 | 2007-02-24 | 2007-03-08 | Raytheon |  | NO | W. Carter | 404-305-6299 | Commissioned 9/25/06
84 | 1013 | 80 | 1 | 1 | FINLEY | ND | AGL | QFI-E | 4YSV | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMP | N/A | 2002-12-09 | 2003-10-10 | 2003-05-01 | NA | NA | NA | NA | 2006-03-06 | 2006-04-20 | 2006-06-27 | 2006-06-27 |  | 2007-04-10 | 2007-04-24 |  | 2007-06-03 | 2007-07-03 | 2007-07-03 | 2007-07-06 |  | 2008-01-03 | 2008-01-15 |  |  | YES | J. Page/D. Sargent | 847-294-7343 | (FY 07 Goal: IOC 6/30/07)
85 | 1014 | 84 | 1 | 1 | FT. GREEN | FL | ASO | FN7 | Q0F3 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMA | ZJX | 2002-08-22 | 2004-01-21 | 2003-07-01 | NA | NA | NA | NA | 2006-03-20 | 2006-05-04 | 2006-07-11 | 2006-07-11 |  | 2007-05-22 | 2007-06-05 |  | 2007-07-15 | 2007-08-14 | 2007-08-14 | 2007-08-17 |  | 2008-01-06 | 2008-01-18 | Raytheon | X | YES | W. Carter | 404-305-6299 | 3/9/07: Parrot antennas installation on the WSUF television transmission tower completed by Raytheon. (FY07 Goal: IOC 7/31/07)
77 | 84 | 65 | 1 | 1 | KIRKSVILLE | MO | ACE | IRK-E | SDM4 | BI-5 | ARSR-3 | ARSR-3 | FA-10255 | FA-10250 | FA-10250/6 | ZKC | ZMP, ZAU | 2002-09-23 | 2003-07-17 | 2004-01-30 | TBD | TBD |  | NA | 2006-03-20 | 2006-05-04 | 2006-07-20 | X |  |  | 2006-08-03 | X | 2006-09-14 | 2006-10-14 | 2007-01-11 | 2006-10-17 | 2007-01-11 | 2007-03-12 | 2007-03-24 | Raytheon |  | YES | C. Wilburn | 816-329-3609 | Commissioned 1/11/07. (FY07 Goal: Planned system Removal 8/30/07)
87 | 1011 | 87 | 1 | 1 | MT. SANTA ROSA | GU | AWP | QLR-E | N06C | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA |  |  | 2002-11-14 | 2004-05-07 | 2003-07-01 | NA | NA | NA | NA | 2006-04-01 | 2006-05-16 | 2006-07-24 | 2006-07-24 |  | 2007-01-23 | 2007-02-09 | X | 2007-02-14 | 2007-03-16 | 2007-03-16 | 2007-03-19 |  | 2007-07-19 | 2007-07-31 | Raytheon |  | YES | J. Duhonich | 310-725-7770 | FY07 Goal: IOC 7/31/07
100 | 1015 | 99 | 1 | 1 | LAKE CHARLES | LA | ASW | LCH-E | MAHD | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZHU | N/A |  |  |  | NA | NA | NA | NA | 2006-04-23 | 2006-06-07 | 2006-08-10 | 2006-08-10 |  | 2007-01-30 | 2007-02-22 | X | 2007-02-22 | 2007-03-24 | 2007-03-24 | 2007-03-27 |  | 2007-06-18 | 2007-06-30 | Raytheon | X | YES | J. Navarro | 817-222-4655 | FY07 Goal: IOC 8/31/07
118 | 1016 | 120 | 1 | 1 | LAKESIDE | MT | ANM | QLS | N7CX | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZLC | ZSE |  |  |  | NA | NA | NA | NA | 2006-05-23 | 2006-07-07 | 2006-09-27 | 2006-09-27 |  | 2007-06-05 | 2007-06-19 |  | 2007-07-29 | 2007-08-28 | 2007-08-28 | 2007-08-31 |  | 2008-04-18 | 2008-04-30 | Raytheon |  | YES | D. Curran/S. Menezes | 425-227-2434 | FY07 Goals: SAT 11/30/06; Completed 10/1/06, IOC 9/30/07
86 | 1017 | 86 | 1 | 1 | CARIBOU | ME | ANE | QYD | BPM7 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZBW | N/A | 2002-06-20 | 2004-04-16 | 2003-07-01 | NA | NA | NA |  | 2006-06-11 | 2006-07-26 | 2006-10-02 | 2006-10-02 |  | 2007-05-01 | 2007-05-15 |  | 2007-06-24 | 2007-07-24 | 2007-07-24 | 2007-07-27 |  | 2008-05-18 | 2008-05-30 | Raytheon |  | YES | J. Hadley | 781-238-7852 | FY07 Goal: SAT 11/30/06; Completed 10/2/06
88 | 1019 | 88 | 1 | 1 | JEDBURG | SC | ASO | QRJ-E | B3EY | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZJX | N/A | 2002-08-01 | 2004-02-24 | 2003-07-30 | NA | NA | NA | NA | 2006-07-27 | 2006-08-15 | 2006-12-05 | 2006-12-05 |  | 2007-08-14 | 2007-08-28 |  | 2007-10-07 | 2007-11-06 | 2007-11-06 | 2007-11-09 |  | 2007-09-18 | 2007-09-30 |  | X | YES | W. Carter | 404-305-6299 | FY07 Goals: SAT 2/28/07, IOC 7/31/07
73 | 1018 | 94 | 1 | 1 | EMPIRE | MI | AGL | QJA-E | 06GE | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMP | ZAU | 2001-05-03 | 2002-11-26 | 2003-07-22 | NA | NA | NA | NA | 2006-07-10 | 2006-08-24 | 2006-10-24 | 2006-10-24 |  | 2007-08-07 | 2007-08-21 |  | 2007-09-30 | 2007-10-30 | 2007-10-30 | 2007-11-02 |  | 2008-05-19 | 2008-05-31 |  |  | YES | J. Page/D. Sargent | 847-294-7343 | FY07 Goal: SAT 2/28/07; Completed 10/24/06
89 | 1020 | 89 | 1 | 1 | DEMING (MAGDALEN) | NM | ASW | DMN-E | KLGP | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZAB | N/A | 2002-08-24 | 2004-05-28 | 2003-07-30 | NA | NA | NA | NA | 2006-07-17 | 2006-08-31 | 2006-10-26 | 2006-10-26 |  | 2007-07-10 | 2007-07-24 |  | 2007-09-02 | 2007-10-02 | 2007-10-02 | 2007-10-05 |  | 2008-02-16 | 2008-02-28 |  | X | YES | J. Navarro | 817-222-4655 | FY07 Goal: SAT 2/28/07; Completed 10/26/06
106 | 1021 | 107 | 1 | 1 | PASO ROBLES | CA | AWP | PRB-E | VNL1 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZLA | ZOA |  |  | 2003-10-01 | NA | NA | NA | NA | 2006-07-25 | 2006-09-08 | 2006-11-07 | 2006-11-07 |  | 2007-09-11 | 2007-09-25 |  | 2007-11-04 | 2007-12-04 | 2007-12-04 | 2007-12-07 |  | 2008-05-19 | 2008-05-31 |  | X | YES | J. Duhonich | 310-725-7770 | FY07 Goal: SAT 3/31/07; Completed 11/7/06
129 | 42 |  | 1 | 1 | BOZEMAN | MT | ANM | BZN |  | NA | NE BOS | BOS |  |  |  | ZOB | N/A | [6 empty] | NA | 2006-08-30 | 2006-09-28 | 2007-01-09 | 2007-01-09 |  | 2007-01-17 | 2007-03-01 | X | 2007-04-10 | 2007-05-10 | 2007-05-10 | 2007-05-13 |  | NA | NA |  |  | YES | D. Curran/S. Menezes | 425-227-2434 | FY07 Goals: SAT 3/31/07, IOC 5/31/07
91 | 1022 | 81 | 1 | 1 | FT. FISHER | NC | ASO | QGV-E | 07J1 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZJX | ZDC, ZNY | 2002-07-22 | 2003-07-31 | 2003-05-28 | NA | NA | NA | NA | 2006-09-12 | 2006-09-28 | 2007-01-29 | 2007-01-29 |  | 2007-10-23 | 2007-11-06 |  | 2007-12-16 | 2008-01-15 | 2008-01-15 | 2008-01-18 |  | 2008-06-18 | 2008-06-30 |  | X | YES | W. Carter | 404-305-6299 | 3/9/07: Continuing efforts to coordinate Parrot installation at US Coast Guard LORAN tower. FY07 Goal: SAT 8/30/07
101 | 1023 | 101 | 1 | 1 | RIVERHEAD (SUFFOLK) | NY | AEA | QVH-E | VYQ1 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZNY | ZDC, ZBW |  |  |  | NA | NA | NA | NA | 2006-09-19 | 2006-10-12 | 2007-01-09 | 2007-01-09 |  | 2007-10-02 | 2007-10-16 |  | 2007-11-25 | 2007-12-25 | 2007-12-25 | 2007-12-28 |  | 2008-06-18 | 2008-06-30 |  | X | YES | A. Arbeiter | 718-553-4836 | FY07Goal: SAT 3/31/07
96 | 1024 | 96 | 1 | 1 | NORTH TRURO | MA | ANE | QEA-E | SQ92 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZBW | ZNY |  |  |  | NA | NA | NA | NA | 2006-09-04 | 2006-10-19 | 2007-01-24 | 2007-01-24 |  | 2008-03-25 | 2008-04-08 |  | 2008-05-18 | 2008-06-17 | 2008-06-17 | 2008-06-20 |  | 2008-07-19 | 2008-07-31 |  | X | YES | J. Hadley | 781-238-7852 | FY07 Goal: SAT 4/30/07
130 | 85 |  | 1 | 1 | EAGLE COUNTY | CO | ANM | EGE |  | NA | NE BOS | BOS |  |  |  | ZMA | ZJX | [6 empty] | NA | 2006-09-18 | 2006-11-02 | 2007-02-08 | 2007-02-08 |  | 2007-03-06 | 2007-03-15 |  | 2007-04-24 | 2007-05-24 | 2007-05-24 | 2007-05-27 |  | NA | NA |  |  | YES | D. Curran/S. Menezes | 425-227-2434 | 3/9/07: FAA optimization in progress. Problems with Rotary Joint being coordinated with AML. (FY07 Goals: SAT 4/30/07, IOC 6/30/07)
104 | 1025 | 108 | 1 | 1 | EAGLE PEAK | TX | ASW | QNW-E | Q3G2 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZAB | ZFW | 2006-03-27 |  |  | NA | NA | NA | NA | 2006-09-18 | 2006-11-02 | 2007-02-21 | 2007-02-21 |  | 2008-02-26 | 2008-03-11 |  | 2008-04-20 | 2008-05-20 | 2008-05-20 | 2008-05-23 |  | 2008-07-19 | 2008-07-31 |  | X | YES | J. Navarro | 817-222-4655 | FY07 Goal: System Delivery 11/30/06; SAT 5/31/07
112 | 1026 | 109 | 1 | 1 | AJO | AZ | AWP | QQO | CW1V | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZAB | N/A | 2006-01-30 |  |  | NA | NA | NA |  | 2006-10-16 | 2006-11-30 | 2007-02-15 | 2007-02-15 |  | 2008-04-22 | 2008-05-06 |  | 2008-06-15 | 2008-07-15 | 2008-07-15 | 2008-07-18 |  | 2008-08-19 | 2008-08-31 |  | X | YES | J. Duhonich | 310-725-7770 | FY07 Goal: SAT 5/31/07
105 | 1027 | 115 | 1 | 1 | SLIDELL | LA | ASW | NEW-E | K5D0 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZHU | N/A |  |  |  | NA | NA | NA | NA | 2006-11-21 | 2007-01-05 | 2007-04-05 |  |  | 2008-04-29 | 2008-05-13 |  | 2008-06-22 | 2008-07-22 | 2008-07-22 | 2008-07-25 |  | 2008-09-02 | 2008-09-14 |  | X | YES | J. Navarro | 817-222-4655 | FY07 Goal: SAT 6/30/07
94 |  | 79 | 1 | 1 | TAMIAMI | FL | ASO | QM8 | V37U | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMA | N/A | 2002-08-22 | 2003-08-22 | 2003-05-01 | NA | NA | NA | NA | 2007-01-11 | 2007-02-08 | 2007-05-09 |  |  | 2008-06-03 | 2008-06-17 |  | 2008-07-27 | 2008-08-26 | 2008-08-26 | 2008-08-29 |  | 2008-10-04 | 2008-10-16 |  | X | YES | W. Carter | 404-305-6299 | FY07 Goal: SAT 7/31/07
116 |  | 105 | 1 | 1 | KING MOUNTAIN | TX | ASW | QOM | CBW6 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZAB | ZHU, ZFW | 2006-02-20 |  |  | NA | NA | NA | NA | 2007-01-26 | 2007-03-12 | 2007-06-10 |  |  | 2007-08-14 | 2007-08-28 |  | 2007-10-07 | 2007-11-06 | 2007-11-06 | 2007-11-09 |  | 2008-10-13 | 2008-10-25 |  | X | YES | J. Navarro | 817-222-4655 | FY07 Goal: SAT 7/31/07
117 |  | 118 | 1 | 1 | UTICA (REMSEN) | NY | AEA | QXU-E | V1GF | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZBW | ZOB | 2006-04-18 |  |  | NA | NA | NA | NA | 2007-03-08 | 2007-04-09 | 2007-07-08 |  |  | 2008-07-08 | 2008-07-22 |  | 2008-08-31 | 2008-09-30 | 2008-09-30 | 2008-10-03 |  | 2008-11-04 | 2008-11-16 |  |  | YES | A. Arbeiter | 718-553-4836 | FY07 Goal: SAT 8/31/07
107 |  | 113 | 1 | 1 | MT. KAALA | HI | AWP | QKA-E | A3G2 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZHN | N/A | 2006-04-24 |  |  | NA | NA | NA | NA | 2007-03-09 | 2007-04-23 | 2007-07-22 |  |  | 2008-07-29 | 2008-08-12 |  | 2008-09-21 | 2008-10-21 | 2008-10-21 | 2008-10-24 |  | 2008-11-11 | 2008-11-23 |  | X | YES | J. Duhonich | 310-725-7770 | FY07 Goal: SAT 8/31/07
97 |  | 97 | 1 | 1 | KEY WEST | FL | ASO | NQX-E | ACJE | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMA | N/A | 2006-10-23 |  |  | NA | NA | NA | NA | 2007-03-23 | 2007-05-07 | 2007-08-05 |  |  | 2008-08-05 | 2008-08-19 |  | 2008-09-28 | 2008-10-28 | 2008-10-28 | 2008-10-31 |  | 2008-11-18 | 2008-11-30 |  | X | YES | W. Carter | 404-305-6299 | FY07 Goal: SAT 9/30/07
123 |  | 126 | 1 | 1 | *GEORGETOWN | BH | ASO | FK7 | 30LA | NA | NE BOS | BOS | FA-10254 | NA | NA | [5 empty] | TBD | TBD | NA | NA | 2007-03-31 | 2007-05-15 | 2007-08-13 |  |  | 2007-08-15 | 2007-08-29 |  | 2007-10-08 | 2007-11-07 | 2007-11-07 | 2007-11-10 |  | NA | NA |  |  | YES | W. Carter | 404-305-6299 | FY07 Goal: SAT 9/30/07
109 |  | 102 | 1 | 1 | BUCKS HARBOR | ME | ANE | QYA-E | J2ME | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZBW | N/A | 2006-04-11 |  |  | NA | NA | NA | NA | 2007-04-07 | 2007-05-22 | 2007-08-20 |  |  | 2008-09-09 | 2008-09-23 |  | 2008-11-02 | 2008-12-02 | 2008-12-02 | 2008-12-05 |  | 2009-05-18 | 2009-05-30 |  | X | YES | J. Hadley | 781-238-7852 | FY07 Goal: SAT 9/30/07
99 |  | 112 | 1 | 1 | WATFORD CITY | ND | AGL | QWA-E | F2ME | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMP | ZLC | 2006-03-13 |  |  | NA | NA | NA | NA | 2007-04-27 | 2007-06-11 | 2007-09-09 |  |  | 2008-09-16 | 2008-09-30 |  | 2008-11-09 | 2008-12-09 | 2008-12-09 | 2008-12-12 |  | 2009-04-18 | 2009-04-30 |  |  | YES | J. Page/D. Sargent | 847-294-7343
|  |  | 1 | 1 | LUFKIN | TX | ASW | LFK |  | NA | NE BOS | BOS |  |  |  | N/A | N/A | [7 empty] | 2007-05-04 | 2007-06-18 | 2007-09-16 |  |  | 2007-10-10 | 2007-10-18 |  | 2007-11-27 | 2007-12-27 | 2007-12-27 | 2007-12-30 |  | NA | NA |  |  |  | J. Navarro | 817-222-4655 | FY07 Goal:SAT 9/30/07
103 |  | 103 | 1 | 1 | MELBOURNE | FL | ASO | MLB | C2FF | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMA | ZJX | 2006-08-14 |  |  | NA | NA | NA | NA | 2007-05-11 | 2007-06-25 | 2007-09-23 |  |  | 2008-10-21 | 2008-11-04 |  | 2008-12-14 | 2009-01-13 | 2009-01-13 | 2009-01-16 |  | 2009-02-03 | 2009-02-15 |  | X | YES | W. Carter | 404-305-6299
|  |  | 1 | 1 | REDMOND | OR | ANM | RDM |  | NA | NE BOS | BOS | [12 empty] | 2007-05-25 | 2007-07-09 | 2007-10-07 |  |  | 2008-01-08 | 2008-01-17 |  | 2008-02-26 | 2008-03-27 | 2008-03-27 | 2008-03-30 |  | NA | NA |  |  |  | D. Curran/S. Menezes | 425-227-2434 | FY07 Goals: Award Construction Contract 11/30/06; Completed 10/31/06, SAT 8/31/07
108 |  | 106 | 1 | 1 | NASHWAUK | MN | AGL | QJD-E | FMS3 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMP | N/A | 2002-05-30 | 2004-08-13 | 2003-09-30 | NA | NA | NA | NA | 2007-06-08 | 2007-07-23 | 2007-10-21 |  |  | 2009-01-27 | 2009-02-10 |  | 2009-03-22 | 2009-04-21 | 2009-04-21 | 2009-04-24 |  | 2009-06-18 | 2009-06-30 |  |  | YES | J. Page/D. Sargent | 847-294-7343
119 |  | 122 | 1 | 1 | MICA PEAK | WA | ANM | QMI-E | MYQ1 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZSE | ZLC | 2006-07-24 |  |  | NA | NA | NA | NA | 2007-06-22 | 2007-08-06 | 2007-11-04 |  |  | 2009-02-24 | 2009-03-10 |  | 2009-04-19 | 2009-05-19 | 2009-05-19 | 2009-05-22 |  | 2009-07-10 | 2009-07-22 |  |  | YES | D. Curran/S. Menezes | 425-227-2434
90 |  | 90 | 1 | 1 | RAINBOW RIDGE | CA | AWP | QZZ | N5XH | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZOA | ZSE | 2006-06-05 |  |  | NA | NA | NA | NA | 2007-07-07 | 2007-08-21 | 2007-11-19 |  |  | 2009-03-03 | 2009-03-17 |  | 2009-04-26 | 2009-05-26 | 2009-05-26 | 2009-05-29 |  | 2009-07-19 | 2009-07-31 |  | X | YES | J. Duhonich | 310-725-7770
111 |  | 111 | 1 | 1 | WHITEHOUSE (JACKSONVILLE) | FL | ASO | NEN-E | SUPX | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZJX | ZMA | 2006-10-02 |  |  | NA | NA | NA | NA | 2007-07-27 | 2007-09-10 | 2007-12-09 |  |  | 2009-03-31 | 2009-04-14 |  | 2009-05-24 | 2009-06-23 | 2009-06-23 | 2009-06-26 |  | 2009-09-03 | 2009-09-15 |  | X | YES | W. Carter | 404-305-6299
83 |  | 95 | 1 | 1 | MALMSTROM AFB (BOOTLEGGER RIDGE/GREAT FALLS) | MT | ANM | GFA-E | V2VB | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA |  | N/A | 2006-09-11 |  |  | NA | NA | NA | NA | 2007-08-10 | 2007-09-24 | 2007-12-23 |  |  | 2009-04-28 | 2009-05-12 |  | 2009-06-21 | 2009-07-21 | 2009-07-21 | 2009-07-24 |  | 2009-09-18 | 2009-09-30 |  |  | YES | D. Curran/S. Menezes | 425-227-2434
113 |  | 110 | 1 | 1 | MORALES | TX | ASW | QNA-E | CF5K | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZHU | N/A | 2006-03-13 |  |  | NA | NA | NA |  | 2007-08-24 | 2007-10-08 | 2008-01-06 |  |  | 2009-06-02 | 2009-06-16 |  | 2009-07-26 | 2009-08-25 | 2009-08-25 | 2009-08-28 |  | 2009-10-22 | 2009-11-03 |  | X | YES | J. Navarro | 817-222-4655
102 |  | 104 | 1 | 1 | MT. LAGUNA | CA | AWP | QRW-E | 2BHE | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZLA | N/A | 2006-02-13 |  |  | NA | NA | NA | NA | 2007-09-07 | 2007-10-22 | 2008-01-20 |  |  | 2009-06-09 | 2009-06-23 |  | 2009-08-02 | 2009-09-01 | 2009-09-01 | 2009-09-04 |  | 2009-11-03 | 2009-11-15 |  | X | YES | J. Duhonich | 310-725-7770
110 |  | 117 | 1 | 1 | SALEM | OR | ANM | SLE-E | LG38 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZSE | N/A | 2006-06-19 |  |  | NA | NA | NA | NA | 2007-09-21 | 2007-11-05 | 2008-02-03 |  |  | 2008-10-21 | 2008-11-04 |  | 2008-12-14 | 2009-01-13 | 2009-01-13 | 2009-01-16 |  | 2009-02-16 | 2009-02-28 |  | X | YES | D. Curran/S. Menezes | 425-227-2434
114 |  | 100 | 1 | 1 | GUANTANAMO BAY | CU | ASO | NAW | B97B | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | ZMA | N/A | 2006-11-27 |  |  | NA | NA | NA | NA | 2007-09-28 | 2007-11-12 | 2008-02-10 |  |  | 2009-07-07 | 2009-07-21 |  | 2009-08-30 | 2009-09-29 | 2009-09-29 | 2009-10-02 |  | 2009-08-19 | 2009-08-31 |  |  | YES | W. Carter | 404-305-6299
|  |  | 1 | 1 | JACKSON HOLE | WY | ANM | JAC |  | NA | NE BOS | BOS | [12 empty] | 2007-10-06 | 2007-11-20 | 2008-02-18 |  |  | 2008-03-17 | 2008-03-27 |  | 2008-05-06 | 2008-06-05 | 2008-06-05 | 2008-06-08 |  | NA | NA |  |  |  |  | 425-227-2434 | FY07 Goal: Award Construction Contract 4/30/07
115 |  | 116 | 1 | 1 | SAN CLEMENTE ISLAND | CA | AWP | NSD | PDY7 | BI-5 | ARSR-4 | ARSR-4 | NA | NA | NA | [5 empty] | NA | NA | NA | NA | 2007-11-26 | 2008-01-10 | 2008-04-09 |  |  | 2009-08-04 | 2009-08-18 |  | 2009-09-27 | 2009-10-27 | 2009-10-27 | 2009-10-30 |  | 2009-09-18 | 2009-09-30 |  | X | YES | J. Duhonich | 310-725-7770
125 |  | 41 | 1 | 1 | EDWARDS AFB/SALINE VALLEY (DoD) | CA | AWP | EDW |  | NA | NE BOS | BOS | NA | NA | NA | [5 empty] | TBD | TBD | NA | NA | 2008-01-01 | 2008-02-15 | 2008-05-15 |  |  | 2009-01-06 | 2009-01-15 |  | 2009-02-24 | 2009-03-26 | 2009-03-26 | 2009-03-29 |  | NA | NA |  |  | NO | J. Duhonich | 310-725-7770
128 |  | 127 | 1 | 1 | SAN ANTONIO | TX | ASW | SAT-E | SFDJ | BI-5 | BOS | BOS | FA-10253 | FA-10250 | FA-10250/7 | ZHU | N/A |  |  |  | TBD | TBD |  |  | 2008-01-16 | 2008-03-01 | 2008-05-30 |  |  | 2009-02-03 | 2009-02-12 |  | 2009-03-24 | 2009-04-23 | 2009-04-23 | 2009-04-26 |  | 2009-09-18 | 2009-09-30 |  |  |  | J. Navarro | 817-222-4655
121 |  | 28 | 1 | 1 | GRAND TURK | TC | ASO | GDT | FS3F | BI-5 | BOS | BOS | FA-10254 | NA | NA | ZMA | N/A | 2001-02-05 |  | 2002-02-05 | 2002-06-18 | 2002-06-20 | NA | NA | 2008-02-16 | 2008-04-01 | 2008-06-30 |  |  | 2008-08-05 | 2008-08-14 |  | 2008-09-23 | 2008-10-23 | 2008-10-23 | 2008-10-26 |  | 2009-03-19 | 2009-03-31 |  |  | NO | W. Carter | 404-305-6299 | FY07 Goal: Complete Site Design 4/30/07
122 |  | 125 | 1 | 1 | *FREEPORT (GRAND BAHAMA) | BH | ASO | BHF | 63JV | NA | NE BOS | BOS | FA-10254 | NA | NA | [5 empty] | TBD | TBD | NA | NA | 2008-06-17 | 2008-08-01 | 2008-10-30 |  |  | 2009-05-19 | 2009-05-28 |  | 2009-07-07 | 2009-08-06 | 2009-08-06 | 2009-08-09 |  | NA | NA |  |  | NO | W. Carter | 404-305-6299 | FY07 Goal: Complete Site Design 8/31/07
120 |  | 119 | 1 | 1 | PICO DEL ESTE (Norfolk) | PR | ASO | QJQ-E | DO66 | BI-5 | FPS-67 | FPS-67 | FA-10253 | FA-10250 | FA-10250/5 | ZSU | N/A |  |  |  | TBD | TBD |  | NA | 2008-07-18 | 2008-09-01 | 2008-11-30 |  |  | 2009-07-07 | 2009-07-16 |  | 2009-08-25 | 2009-09-24 | 2009-09-24 | 2009-09-27 |  | 2009-10-19 | 2009-10-31 |  |  | YES | W. Carter | 404-305-6299 | FY07 Goal: Award Radome Contract 9/30/07
124 |  | 128 | 1 | 1 | *YAKUTAT (Harlow) | AK | AAL | YAK | 00DG | NA | NE BOS | BOS | FA-10254 | NA | NA | [5 empty] | TBD | TBD | NA | NA | 2009-03-01 | 2009-04-15 | 2009-07-14 |  |  | 2009-08-04 | 2009-08-13 |  | 2009-09-22 | 2009-10-22 | 2009-10-22 | 2009-10-25 |  | NA | NA |  |  | YES | G. Johanson/S. Houser | 907-271-2892 | FY07 Goal: Complete Site Selection 9/30/07
| 1003 |  | 0 | 0.5 | FAALC DEPOT Mode 4 (Single Channel) | OK | ASW |  |  | NA | SUPPORT | NA |  |  |  | N/A | N/A | [7 empty] | FY08 | FY08 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| 2 |  |  | 1 | SBR I (TRR2A) | OK | NA |  |  | NA | PROTOTYPE | ARSR-3 | [17 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1
1
Formulas:
PRE-INSTALLATION TELCON DATE = [PLANNED SYSTEM DELIVERY SCHEDULE]-45
PRE-INSTALLATION TELCON DATE = +[PLANNED SYSTEM DELIVERY SCHEDULE]-45
ORD/OSD FINISH DATE = [ACTUAL SITE COMMISSIONING DATE]
ORD/OSD FINISH DATE = ([IOC/OSD START DATE]+30)
JAI DATE = [IOC/OSD START DATE]
JAI DATE = [IOC/OSD START DATE]+30
EST. COMMISSIONING DATE = [PLANNED SYSTEM DELIVERY SCHEDULE]+270
EST. COMMISSIONING DATE = [JAI DATE]+3
LEGACY SYSTEM REMOVAL COMPLETION DATE = [EST. COMMISSIONING DATE]+120
RJ/ANTENNA INSTALLATION COMPLETION DATE = [RJ/ANTENNA INSTALLATION START DATE]+4
RJ/ANTENNA INSTALLATION COMPLETION DATE = [RJ/ANTENNA INSTALLATION START DATE]
LEGACY SYSTEM REMOVAL START DATE = [LEGACY SYSTEM REMOVAL COMPLETION DATE]-12
IOC/OSD START DATE = [FAA OPTIMIZATION COMPLETE]+40
SAT COMPLETION DATE = [PLANNED SYSTEM DELIVERY SCHEDULE]+90
Note on AB72: ATO USER: A. Coggins SAT was delayed due to unanailability of ATCBI-6 antenna
Note on AJ52: acoggins: JAI=ICO+30 DAYS
Note on AJ53: acoggins: JAI=ICO+30 DAYS
Note on AJ54: acoggins: JAI=ICO+30 DAYS
Note on AJ55: acoggins: JAI=ICO+30 DAYS
Note on AJ56: acoggins: JAI=ICO+30 DAYS
Note on AJ57: acoggins: JAI=ICO+30 DAYS
Note on AJ58: acoggins: JAI=ICO+30 DAYS
Note on AJ59: acoggins: JAI=ICO+30 DAYS
Note on AJ60: acoggins: JAI=ICO+30 DAYS
Note on AJ61: acoggins: JAI=ICO+30 DAYS
Note on AJ62: acoggins: JAI=ICO+30 DAYS
Note on AJ63: acoggins: JAI=ICO+30 DAYS
Note on AJ64: acoggins: JAI=ICO+30 DAYS
Note on AJ65: acoggins: JAI=ICO+30 DAYS
Note on AJ66: acoggins: JAI=ICO+30 DAYS
Note on AJ67: acoggins: JAI=ICO+30 DAYS
Note on AJ90: acoggins: JAI=ICO+30 DAYS
Note on AJ69: acoggins: JAI=ICO+30 DAYS
Note on AJ77: acoggins: JAI=ICO+30 DAYS
Note on AJ76: acoggins: JAI=ICO+30 DAYS
Note on AJ74: acoggins: JAI=ICO+30 DAYS
Note on AJ73: acoggins: JAI=ICO+30 DAYS
Note on AJ99: acoggins: JAI=ICO+30 DAYS
Note on AJ70: acoggins: JAI=ICO+30 DAYS
Note on AJ72: acoggins: JAI=ICO+30 DAYS
Note on AJ81: acoggins: JAI=ICO+30 DAYS
Note on AJ93: acoggins: JAI=ICO+30 DAYS
Note on AJ79: acoggins: JAI=ICO+30 DAYS
Note on AJ82: acoggins: JAI=ICO+30 DAYS
Note on AJ83: acoggins: JAI=ICO+30 DAYS
Note on AJ68: acoggins: JAI=ICO+30 DAYS
Note on AJ125: acoggins: JAI=ICO+30 DAYS
Note on AJ91: acoggins: JAI=ICO+30 DAYS
Note on AJ92: acoggins: JAI=ICO+30 DAYS
Note on AJ97: acoggins: JAI=ICO+30 DAYS
Note on AJ94: acoggins: JAI=ICO+30 DAYS
Note on AJ98: acoggins: JAI=ICO+30 DAYS
Note on AJ100: acoggins: JAI=ICO+30 DAYS
Note on AJ123: acoggins: JAI=ICO+30 DAYS
Note on AJ103: acoggins: JAI=ICO+30 DAYS
Note on AJ87: acoggins: JAI=ICO+30 DAYS
Note on AJ89: acoggins: JAI=ICO+30 DAYS
Note on AJ110: acoggins: JAI=ICO+30 DAYS
Note on AJ88: acoggins: JAI=ICO+30 DAYS
Note on AJ105: acoggins: JAI=ICO+30 DAYS
Note on AJ114: acoggins: JAI=ICO+30 DAYS
Note on AJ80: acoggins: JAI=ICO+30 DAYS
Note on AJ117: acoggins: JAI=ICO+30 DAYS
Note on AJ95: acoggins: JAI=ICO+30 DAYS
Note on AJ104: acoggins: JAI=ICO+30 DAYS
Note on AJ127: acoggins: JAI=ICO+30 DAYS
Note on AJ119: acoggins: JAI=ICO+30 DAYS
Note on AJ107: acoggins: JAI=ICO+30 DAYS
Note on AJ109: acoggins: JAI=ICO+30 DAYS
Note on AJ101: acoggins: JAI=ICO+30 DAYS
Note on AJ113: acoggins: JAI=ICO+30 DAYS
Note on AJ121: acoggins: JAI=ICO+30 DAYS
Note on AJ116: acoggins: JAI=ICO+30 DAYS
Note on AJ128: acoggins: JAI=ICO+30 DAYS
Note on AJ124: acoggins: JAI=ICO+30 DAYS
Note on AJ108: acoggins: JAI=ICO+30 DAYS
Note on AJ126: acoggins: JAI=ICO+30 DAYS
Note on AJ129: acoggins: JAI=ICO+30 DAYS
Note on AJ131: acoggins: JAI=ICO+30 DAYS
Note on AJ111: acoggins: JAI=ICO+30 DAYS
Note on AJ112: acoggins: JAI=ICO+30 DAYS
Note on AJ96: acoggins: JAI=ICO+30 DAYS
Note on AJ122: acoggins: JAI=ICO+30 DAYS
Note on AJ134: acoggins: JAI=ICO+30 DAYS
Note on AJ135: acoggins: JAI=ICO+30 DAYS
Note on AJ115: acoggins: JAI=ICO+30 DAYS
Note on AJ132: acoggins: JAI=ICO+30 DAYS
Note on AJ84: acoggins: JAI=ICO+30 DAYS
Note on AJ133: acoggins: JAI=ICO+30 DAYS
Note on AJ102: acoggins: JAI=ICO+30 DAYS
Note on AJ106: acoggins: JAI=ICO+30 DAYS
Note on AJ75: acoggins: JAI=ICO+30 DAYS
Note on AJ118: acoggins: JAI=ICO+30 DAYS
Note on AJ1: Has Tech Training been completed.
Note on AA102: ATO USER: Raytheon would like to move the install up 1 week
Note on AH79: ATO USER: This date is based on a scheduled 2/22/06 Flight Check date.
Note on F69: ATO USER: New FLK CHK date established for 1-23-06; variance required to move IOC date.
Note on AI66: acoggins: JAI=ICO+30 DAYS
Note on AI70: acoggins: JAI=ICO+30 DAYS
Note on AJ130: acoggins: JAI=ICO+30 DAYS
Note on AJ120: acoggins: JAI=ICO+30 DAYS
Note on AJ136: acoggins: JAI=ICO+30 DAYS
Note on AJ137: acoggins: JAI=ICO+30 DAYS