U.S. Customs and Border Protection Modernization

Report to Congress: The Automated Commercial Environment (ACE) CBPMO-RPRT-009

December 31, 2003

U.S. Customs and Border Protection Modernization Office

# Automated Commercial Environment (ACE) Report to Congress

December 31, 2003

# Table of Contents

Executive Summary ...………………….……………..……………….……….….1

1.	Performance	2

1.1		Compliance with NAFTA Title VI Requirements	2

1.2		ACE Development Accomplishments	2

1.3		Open General Accounting Office Recommendations	6

1.3.1	Cost-Estimating Program	6

1.3.2	Human Capital Management (HCM)	7

1.3.3	Software Acquisition Capability Maturity Model (SA-CMM)	8

1.3.4	Independent Verification and Validation (IV&V)	8

1.3.5	Enterprise Architecture (EA) Certification	9

1.3.6	Use of ACE Infrastructure for DHS	9

2.	Schedule	9

3.	Cost	11

3.1		Fiscal Status:  Funding and Expenditures	11

3.2		Fiscal Year 2004 ACE Expenditure Plan	11

3.3		Cost Containment	12

4.	Near-Term Milestones	13

5.	Outlook	14

Appendix A.  NAFTA Title VI Requirements for ACE and Description of ACE Functionality………….…………………………………………………………………...17

Appendix B.  Acronyms and Selected Definitions………….………………………….27

Figure 1.  ACE Releases 3 and 4 Schedule…………….………………………………..10

Figure 2.  ACE Funding Status…...……….……………….………………………………11

Executive Summary

The Report to Congress: The Automated Commercial Environment, consolidates U.S. Customs and Border Protection (CBP) Congressional reporting requirements, which include the Homeland Security Appropriations Bill, 2004; Trade Act of 2002; and the February 2003 General Accounting Office (GAO) Report, Customs Service Modernization: Automated Commercial Environment Progressing, But Further Acquisition Management Improvements Needed.  Collectively, these reports require quarterly updates on: how ACE development and establishment is being implemented cost-effectively; how ACE meets the modernization requirements of the North American Free Trade Agreement (NAFTA) Implementation Act of 1993; and on Customs and Border Protection Modernization Office (CBPMO) progress on Human Capital Management and implementation of software acquisition practices under Carnegie Mellon University’s Software Acquisition Capability Maturity Model (SA-CMM).  The GAO has requested that the ACE quarterly report also provide a status on efforts to resolve open audit recommendations.

The reporting period for this update is October 1 - December 31, 2003.  The report is intended to provide a “snapshot” of current program status, highlighting recent accomplishments, challenges, and near-term milestones through April 30, 2004.  A review of previous reports may be helpful in understanding the full context of the information provided in this edition of the report.

This report is provided to the Senate Finance Committee, House Ways and Means Committee, and Appropriations Committees.  The report has been reformatted to enhance readability as much as possible.

- The performance section highlights key ACE program accomplishments, actions to satisfy the GAO’s audit recommendations, and a brief overview of how ACE capabilities will help satisfy the requirements of the 1993 NAFTA Implementation Act and Customs Modernization Act.  This section is supplemented by Appendix A, which contains a table that depicts the alignment between ACE capabilities, the specific electronic processing functions required under the Act, and the high-level program schedule for fielding ACE capabilities.  A description of ACE capabilities by release is also included in this appendix.

- The schedule section includes contract baseline dates, updated ACE development dates based on the October 2003 revision of the ACE Program Plan, and current milestone projections.

- The cost section updates ACE funding and expenditures; cost challenges; and describes program cost containment efforts.

- By its nature, the environment in which ACE is being developed is characterized by technical terms and acronyms.  An attempt has been made to minimize jargon as much as possible.  To assist in understanding, Appendix B provides a glossary of commonly used acronyms in the report and selected definitions.

# Performance

This section highlights how ACE will help satisfy the requirements of the 1993 NAFTA Implementation Act and Customs Modernization Act; selected program accomplish-ments, and actions related to the open GAO recommendations.

## Compliance with NAFTA Title VI Requirements

The NAFTA Implementation Act is the primary business driver and the legal foundation for the CBP Modernization effort.  The Act emphasizes electronic processing and self-compliance as the preferred method for handling commercial importations.  The Act also directs CBP to pursue automation programs.  The Act provides the foundation for the redesign of the trade compliance process and the strengthening of selectivity and targeting systems.  These are key requirements for enhancing border security and expediting legitimate trade.

Title VI of the NAFTA (Mod Act) outlines requirements for automation and provides for the electronic processing of imports.  The CBP is developing ACE to deliver these capabilities in a secure, paper-free, web-enabled environment.  The ACE is being built using an incremental approach that features a series of releases.  Each release will leverage the foundation components and functionality present in the previous releases and bring new capabilities to the trade community and government users.  The planned delivery of functionality within and across ACE releases serves to fulfill specific Subtitle requirements.  Appendix A identifies Modernization Act Subtitle requirements with the ACE Release(s) in which associated functionality will be delivered.  The table in Appendix A illustrates that particular Modernization Act Subtitle requirements may be supported across multiple ACE releases.  The table depicts the alignment between ACE capabilities, the specific electronic processing functions required under the Act, and the high-level program schedule for fielding ACE capabilities.

## ACE Development Accomplishments

Following are key program accomplishments between October 1, 2003, (closing date of previous report) and December 31, 2003.

- Achieved Level Two Rating on the Software Acquisition Capability Maturity Model® (SA-CMM).  The CBPMO system acquisition efforts were rated as a SA-CMM® Level 2, in November 2003, culminating two years of process improvement efforts.  The SA-CMM is a management tool designed to make software acquisition and management easier and more accountable by creating a sound organizational structure and institutionalizing processes for managing system acquisition projects.

- Initial On-line Account Capabilities Fully Operational.  The Operational Readiness Review (ORR) for ACE Release 2 was held in October 2003, enabling ACE capabilities, including the single screen Secure Data Portal, to be fielded and transitioned to an Operations & Maintenance (O&M) environment.  Passing this milestone also set the stage to begin expanding ACE capabilities to more end users in government and the trade community.

- Increased Trade Account Expansion Efforts.  Additional trade accounts are currently being brought on-line through the ACE Secure Data Portal.  Pre-deployment packages have been distributed to assist the CBP Account Managers and the companies that they represent in the expansion process.  More than 200 accounts are targeted for the expansion by May 2004.  Similar to the initial 41 trade accounts, these next accounts are high volume users of ACE and represent a large percentage of trade activity.

- Developed Plan to Prepare ACE End-Users.  Through the Workforce Transformation sessions with Business Process Owners (BPOs), employee-specific Workforce Transformation Outreach Plans were developed to prepare impacted end users for changes brought by ACE Release 3.  The plans provide analysis of the information and transition needs of impacted stakeholders, including risks and contingencies associated with preparing and executing outreach activities for the particular group.  Further, the plans present a schedule of events, a roles and responsibilities matrix, and resource lists designed to help BPOs execute on planned events.

- Initiated Software Integration Testing (SWIT) Testing for ACE Release 3 (Expanded Accounts Management).  ACE Release 3 entered SWIT in October 2003.  During SWIT testing, ACE Release 3 was put into an environment that closely simulates the intended technical architecture of the release under development.

- Submitted Selectivity and Targeting (S&T) Concept of Operations. Following collaboration sessions between CBPMO, the Office of Field Operations (OFO), and the Office of Information Technology (OIT), the eCP submitted a S&T concept of operations as the proposed framework for S&T activities.

- Conducted ACE Release (S&T) Workshops.  In coordination with International Trade Data System (ITDS) Board of Directors and CBPMO, the eCP held two workshops for Participating Government Agencies (PGAs) that focused on S&T requirements and capabilities to support ACE Release 5 planning.

- Initiated Technology Prototypes.  Based on direction from CBP officials to better align the ACE program to CBP mission priorities, the eCP developed a “Selectivity NOW” proposal in September 2003.  The CBP directed that the eCP initiate prototypes and develop “proof of concept” capabilities for S&T, and related enforcement tools.  The projects approved for prototyping include a Knowledge-Based Risk Management (KBRM) system, and Intelligent Information Factory (IIF) prototype.  In November 2003 the technology prototype, IIF, was initiated.  In December 2003, the CBPMO hosted a Technology Demonstration Day, an event that showcased various S&T technologies.  Also in the planning phase is TRAP-EZE, an enforcement tool to enhance vehicle inspections.

- Revised the ACE Program Plan.  Given the expanded mission priorities under the Department of Homeland Security (DHS) and the approach CBP is taking with ACE development, the ACE Program Plan was revised to reflect the realities of the operational environment.  The rebaselining of the Program recognizes the decision to incorporate SAP even more fully (ACE Release 2 already has some SAP functionality) as a commercial-off-the-shelf solution for ACE, and the lessons learned to date in ACE development.

- Delivered the Engineering Environment Upgrade Plan.  The eCP, with the support of the CBP Technology and Architecture Group, delivered the Enterprise Architecture Automated Environment Development Plan.  This plan will guide performance improvements through September 2004.

- Updated the Enterprise Concept of Operations.  The Enterprise Concept of Operations describes how CBP employees and managers will have access to broader and immediate information in every mission area.  Specifically, the document introduces the conceptual framework under which the integration of CBP, law enforcement, intelligence, and trade databases will provide employees immediate access to information relevant to their business roles and security authorizations.  It further details the new systems solutions that will enable individuals to interpret, update, and manage data.

- Updated the Enterprise Mission and Vision.  The update to the Modernization Mission and Vision was a result of CBP leadership’s evolving view of the agency since the last version of the document.  This revision was based on the results of a six-month collaboration among CBP Subject Matter Experts (SMEs), and e-Customs Partnership (eCP) staff.  Representation was provided from across CBP, including the newly incorporated functions from U.S. Citizenship and Immigration Services, Animal and Plant Health Inspection Service inspections, and Border Patrol activities.

- Completed the Organizational Vision for the Modernized CBP Document.  This document further delineates the ideas presented in the Modernization Mission and Vision document and Enterprise Concepts of Operations (CONOPS).  The document provides a model and planning considerations for how CBP will integrate processes and share information across and beyond the organizational boundaries.  It highlights the need for functional areas to work together to provide intelligence needed for decision-making in support of common goals.

- Conducted Government Support Network (GSN) Meeting.  A GSN meeting with representatives from more than 40 agencies was held in November 2003.  The GSN agenda included the following:

- Updates on ACE Releases 2, 3, and 4

- Presentation by the Food Safety Inspection Service regarding its role at the border

- Presentations by trade representatives regarding the trade community perspective on ITDS

- Updates on Data Harmonization and other ITDS initiatives.

- Established Cross-Agency Working Group on Data Access.  A cross-agency working group has been established to address principles on data access.  The working group is founded on the premise that agencies and offices with legislative mandates have a right to access data needed to execute their missions, but proper security procedures for granting access is essential.  This working group will conduct a thorough analysis of current procedures and present a recommendation regarding future procedures once ACE/ITDS becomes operational.

- Prototyped Key CBP Functionality in SAP.  The eCP prototyped and demonstrated key CBP functionality in SAP to subject matter experts and executives in early December 2003.  SAP will enable critical business processes.  The prototyping will serve as a jumpstart to the Global Business Blueprinting (GBB) activities.

- Held 4th Annual Trade Symposium.  In November 2003, The Trade Symposium focused on three topics: the role of CBP in the new DHS; top priorities and initiatives in defending our Nation against terrorism while facilitating the flow of legitimate trade and traffic; and the functionality unification at the border.  The CBPMO provided a live ACE Secure Data Portal demonstration and video outlining benefits of the Modernization and ACE.  Various informational documents were distributed to trade representatives to further educate the business community on ACE capabilities and recent program developments.

## Open General Accounting Office Recommendations

In coordination with the GAO, the CBPMO has closed three recommendations from previous GAO reports on the following topics:

- Incremental Investment Decisions.  The CBPMO has demonstrated its commitment to manage the Modernization effort in conformance with the recommendation to justify investment decisions incrementally based on ACE releases.

- Management Reserve (MR).  The CBPMO has taken the actions necessary to limit future expenditure plan requests for MR to 10 percent of total funds, or to justify MR requests in excess of 10 percent.

- Accelerated ACE Acquisition Strategy.  The ACE program has transitioned away from the accelerated schedule that was contemplated in early 2002.  Based on program rebaselining and funding profiles, ACE development is expected to be a 6-year program.

The status of the following GAO recommendations will be assessed as part of the FY04 ACE Expenditure Plan review.  A determination will be made by the GAO as to whether the actions taken by CBP dictate that the remaining recommendations can be closed.

### Cost-Estimating Program

GAO Recommendation: Develop and implement a rigorous and analytically verifiable cost-estimating program

The CBPMO has an established independent cost-estimating capability using a Life-Cycle Cost Model (LCCM).  The LCCM enables the analysis and validation of contractor cost and schedule estimates, and helps determine whether the proposed costs and schedule for specific pieces of work are realistic and reliable.  To date, the CBPMO has successfully used the LCCM to provide Independent Government Cost Estimates (IGCEs) for 11 procurement efforts.  The LCCM is independent of all cost and schedule estimates from eCP, and relies on information that is published in the ACE Program Plan.  The LCCM will produce a full Life-Cycle Cost Estimate (LCCE) subsequent to the final approval of the revised ACE Program Plan.

As part of its review of the fourth ACE Expenditure Plan, the GAO indicated that CBP actions are fully consistent with GAO’s recommendations, and that CBP is making progress regarding the GAO’s cost-estimating recommendation.

### Human Capital Management (HCM)

GAO Recommendation: Immediately develop and implement a CBPMO HCM plan and missing HCM practices, and report quarterly on progress

Ongoing HCM initiatives and activities include:

- Human Capital Capability Scorecard.  An Office of Information and Technology (OIT)-wide assessment gathered data from OIT employees and contractors, and reviewed documents that provided information on Human Capital (HC) investments and policies.  The OIT is currently analyzing the report’s recommendations.  These address, among other topics, leadership effectiveness, the creation of a more effective learning environment, and information access and sharing in the workforce.  The CBPMO will revise its Strategic Human Capital Management Plan to address the recommendations and drive improvements in the areas of greatest need.

- Jump Start Program.  Provides sponsors to new employees and contractors to assist them in navigating within the organization.  A pilot phase was completed in October 2003, and Jump Start is now an ongoing element of the CBPMO orientation program.

- Recruiting.  The CBPMO is actively working to fill nine vacancies.  A task force has been established by the Acting Assistant Commissioner, OIT, to address the CBPMO resource issues and examine future human resource needs.  At the request of DHS, the CBPMO is developing a staffing plan that will: describe the types of resources required and in what quantities; describe any new positions proposed for the organization and how those positions will be staffed; and include a responsibility assignment matrix that defines high-level roles and responsibilities for the program team.

- Training Needs Assessment.  The FY 04 Modernization Training Plan was developed based on a recently completed training needs assessment.  A new focus for 2004 is on assisting CBPMO employees with further developing their acquisition and project management skills.

- Tip of the Month.  A Human Capital Tip of the Month is published regularly and provides government supervisors and managers with information on how to leverage their human capital and improve their supervisory skills.

- Tool Kits for Managers.  As part of an Effective Manager’s Handbook, orientation and retention tool kits have been developed to facilitate educating new employees, and to help supervisors and managers in their leadership.  Tool kit topics include setting challenges, coaching for higher performance, rewarding achievement, and encouraging teamwork.

### Software Acquisition Capability Maturity Model (SA-CMM)

GAO Recommendation: Develop and implement process controls for SA-CMM Level 2 Key Process Areas (KPAs) and Level 3 Acquisition Risk Management KPA; and develop and implement missing SA-CMM practices and report quarterly on progress

Carnegie Mellon University’s Software Engineering Institute (SEI) led a rated assessment of the CBPMO using the SA-CMM framework from October 27 to November 5, 2003.  This assessment resulted in the CBPMO achieving a maturity Level 2 – the maturity level at which a software acquisition organization’s processes are institutionalized and consistently implemented.  The CBPMO was the first government modernization office to achieve this rating.  A Process Improvement Action Report is being developed to address the recommendations and process improvement opportunities reported by the CBPMO/SEI assessment team.

The Level 3 Acquisition Risk Management KPA was not included in the formal assessment.  However, input was received prior to the formal assessment, from the lead assessor, who indicated that the CBPMO was accomplishing the action and activities to satisfy the intent of the GAO recommendation.  To satisfy two related SEI concerns in this area, the CBPMO is documenting and managing sensitive risks in compliance with the approved Sensitive Risk and Issue Management Process, and has expanded risk data analysis to include forecasting capability, and reporting and reviewing additional analyses of program data.

### Independent Verification and Validation (IV&V)

GAO Recommendation: Establish an IV&V function to assist in overseeing systems integration contractor efforts.

To complement the previously implemented IV&V actions that have provided value in reducing risks, the CBPMO developed and implemented the IV&V processes to describe the independent assessment approach, organizational roles, and IV&V reporting relationships and methodologies.  Additionally, the Strategic Implementation Plan for Integrated IV&V was approved by the Acting Assistant Commissioner, Office of Information and Technology, on December 12, 2003.  The next steps are to meet with the GAO to identify any remaining concerns and to collect artifacts from existing processes to demonstrate the effectiveness of IV&V activities.

### Enterprise Architecture (EA) Certification

GAO Recommendation: Certify that the EA has been extended before building each ACE release

To support EA certification activities, a diversified architecture team is coordinating and conducting the EA Certification in concurrence with a defined plan.  The plan incorporates criteria that will verify sufficient EA breadth and depth are present to guide the Release as stated by GAO.  Currently, a joint effort is underway to mitigate any current issues prior to EA Certification.  In the future, the EA Certification work will be monitored throughout the development life cycle with use of EA evaluations.  The next expected certification will occur in spring 2004 for ACE Release 5 and Selectivity 1.

### Use of ACE Infrastructure for DHS

GAO Recommendation: Take appropriate steps to have future ACE expenditure plans specifically address proposals or plans to extend or use ACE infrastructure to support other homeland security applications

In a December 8, 2003, memorandum, CBP recommended to DHS that an advisory committee, comprised of appropriate DHS directorate and agency representatives as well as selected private industry experts, be established to support the CBPMO.  The council’s mission would be to provide recommendations – from a broad departmental and external stakeholder perspective – on CBPMO initiatives, particularly ACE.  Potential benefits include insight and recommendations on DHS-wide business process integration that could influence ACE development; input on infrastructure and cyber security for consideration in ACE development; and shared best practices and innovative technology being applied in council members’ respective organizations.  In the same memorandum, CBP invited the Transportation Security Administration and the Information Analysis and Infrastructure Protection Directorate to assign one member each to the Executive Steering Committee.  These organizations’ national perspectives on myriad security matters would add great value to CBP as it works to enhance business processes in the context of its dual mission of border security and trade facilitation.

# Schedule

With the successful ORR for ACE Release 2 accomplished, ACE Releases 3 (Expanded Accounts Management) and 4 (Cargo Release and Tracer) are the current focus in the program.  As briefed to Appropriations Committees staff members in October 2003 and reported in the October 1, 2003, ACE Report to Congress, eCP replanned the ACE project in coordination with CBPMO.  This included revising the ACE development schedule.  The CBPMO was informed by eCP that ACE Releases 3 and 4 would experience delays from the dates indicated in the revised ACE Program Plan.  There are three primary factors currently affecting ACE Release 3 and 4 schedules:    (1) design and implementation challenges with security architecture, the ACE Portal, and Alternative User Interface; (2) longer than expected lead times to procure and establish test environments (hardware and software platforms to run the applications); and (3) space requirements that exceeded the available computing space at the National Data Center (NDC) (eCP is moving some environments from NDC to their Tysons Corner, VA facility).

For context, the table below reflects original contract baselines, and subsequent performance baseline changes to dates for the ACE Release 3 and ACE Release 4 Production Readiness Reviews (PRRs) and ORRs.  The CBPMO is currently assessing the impact on the overall ACE program schedule.

| Milestone | Contract Baseline | Revised Program Plan | Current Projection |
| --- | --- | --- | --- |
| ACE Release 3 PRR | 12/15/03 | 4/30/04 | 5/30/04 |
| ACE Release 3 ORR | 3/15/04 | 7/30/04 | 8/26/04 |
| ACE Release 4 PRR | 4/14/04 | 10/29/04 | 11/26/04 |
| ACE Release 4 ORR | 7/15/04 | 1/31/05 | 2/23/05 |

Figure 1:  ACE Releases 3 and 4 Schedules

The CBPMO continues to monitor and address other requirements that could impact on  ACE Releases 3 and 4 and future release schedules.  For example, the CBPMO understands the requirement to make ACE Section 508 compliant (a 1998 amendment to Section 508 of the Rehabilitation Act of 1973 requires that Federal agencies' electronic and information technology be accessible to people with disabilities).  The eCP is building the required capabilities over the remaining release deployment schedule to ensure Section 508 obligations are satisfied as ACE becomes fully operational.  The CBPMO will continually assess this and other requirements to determine schedule and cost impacts.

The CBPMO is aggressively overseeing these schedule issues and has taken the following actions:

- Directed eCP to identify all outstanding requirements (Section 508, training, environments, other) and provide accurate cost and schedule impacts for each.

- Implemented a rigorous scope management process to minimize any non-essential work and associated cost (implemented as action from cost containment Integrated Project Team (IPT)).

- Directed eCP to conduct analysis and make recommendations regarding specific functionality that could be deferred to follow-on releases without significantly impacting the functionality delivered in ACE Releases 3 and 4.

- Continued to monitor project status closely to identify any cost containment opportunities and risk/issues that require government action.

# Cost

## Fiscal Status:  Funding and Expenditures

To date, Congress has appropriated $1.07 billion for ACE/ITDS.  Congress has released $751 million, and $584 million has been obligated (of which $457 million has been obligated specifically to ACE development task orders).  Figure 2 provides a summary of ACE funding, obligations, and expenditures through December 31, 2003.

Figure 2: ACE Funding Status (includes ITDS)

## Fiscal Year 2004 ACE Expenditure Plan

The FY04 ACE Expenditure Plan was the first submitted by CBP under DHS.  This plan requested $318.7 million for ACE development and program management.  To help ensure effective management and program integration, appropriate time had to be taken to provide comprehensive background briefings to DHS officials; to ensure CBP met DHS detailed information requirements; and to ensure proper integration investment management review and approval processes.  The coordination and lessons learned will improve the future expenditure plan cycle.

However, the result for the FY04 Expenditure Plan was a delay to the review schedule while the CBPMO worked to provide the additional information, and to update the FY 04 Expenditure Plan to align with the elements of the revised ACE Program Plan.  As a result, there is a significant funding gap between the end of FY03 and the expected release of FY04 funds in the March 2004 timeframe.  The CBP has a risk mitigation plan in effect to address this funding gap.  The strategy calls for the use of previously released funding to maintain program continuity through February 29, 2004.  Management reserve funds used for continuity of previously approved work during this period will be replenished upon approval of the FY04 Expenditure Plan.  Additionally, near-term program requirements not addressed via management reserve will be funded via internal reallocations to avoid impacting the ACE program schedule.

## Cost Containment

The CBPMO currently assesses that the delays described in Section 2 have resulted in a $34 million cost increase for the ACE Release 3 and 4 task order.  To contain and reduce cost, schedule, and performance variance in this and other program areas, the CBPMO is closely monitoring eCP performance and progress on ACE.  The CBPMO is also aggressively addressing program risks and issues so that effective corrective actions can be taken to minimize impacts to the program.  For context, the current overall program cost variance is currently an estimated 9 percent.  The CBPMO has also established a Cost Containment IPT to achieve the following objectives:

- Contain cost, schedule, and performance variance within 10 percent of program baseline

- Deliver ACE Releases 3 and 4 to satisfy all user requirements as defined in the baselined Requirements Specification Set, and within approved cost parameters

- Increase CBPMO understanding of the cost components of all eCP deliverables

- Understand scope, risk, and dependency cost drivers

- Identify, analyze, and communicate upon discovery all project-related unplanned costs

- Improve program implementation strategies to bring about cost savings

- Reduce and/or eliminate requirements creep

- Early notification and vetting of new cost requirements

- Reduce government cost risk over contract period of performance

- Develop and execute approved cost containment strategies

- Improve accuracy and quality of cost impact analyses

- Improve awareness of cost drivers and risks

- Provide greater insight into the cost management process through the Cost Performance Review.

# Near-Term Milestones

The following are key near-term milestones scheduled between January 1 and April 30, 2004.

- January 2004: Continued Global Business Blueprinting (GBB) Activities.  The GBB project will run through May 2004, with the objective of establishing the business processes and enabling technology framework for ACE Releases 6 and 7.  Activities will include joint eCP/CBP workshops, port visits, and additional SAP prototyping to support this objective.  At the conclusion of GBB, CBP and eCP will have a clear path forward, in addition to insight regarding how best to leverage SAP and build upon the work done to date in ACE Releases 2 through 5.

- January 2004: Trade Support Network (TSN).  A TSN meeting with representatives from the trade community is scheduled in January 2004.  Projected agenda topics include: review of Global Business Blueprinting Approach; Status Report on ACE Release 3 Periodic Payment and Enhanced Account Management Functionality; Periodic Payment Business Process Flow; Status Report of ACE Release 4; Results of September usability session with truck carriers; ACE Release 5: Manifest for All Modes; Global Business Blueprinting, ACE Releases 6 and 7.  Regular committee meetings to discuss ACE requirements will also be held.

- January 2004: Federal Register Notice (FRN) to Recruit Broker Accounts.  The FRN will be issued to establish designated broker accounts for participation in the periodic payment features of ACE.   This FRN will ask for confirmation from the initial 41 ACE importers who wish to participate in the test, and will permit brokers designated by the participating importers to establish ACE portal accounts so that they may make payments on the importer's behalf.

- January 2004: FRN Notice to Recruit Truck Carriers.  The FRN will be issued to establish ACE portal accounts for truck carriers.  This FRN will also provide all modes of transportation with the opportunity to submit applications to become ACE portal accounts for future releases.  Only truck carriers will be able to participate in the electronic truck manifest test that will be addressed by a subsequent FRN notice.

- January 2004: ITDS Workshops.  Preliminary planning has begun on new workshops for targeted agencies.  These workshops will include an overview of planned ACE processes and functionality, and support for the participating agencies in developing their concepts of operations documents outlining their needs with respect to ACE/ITDS.

- February 2004: Systems Integration Testing (SIT) for ACE Release 3.  Upon concluding SWIT testing, ACE Release 3 will enter SIT in January 2004 followed by System Acceptance Testing (SAT) testing March 2004.  During SIT testing, individual components will be tested to ensure their integration in the production environment.

- February 2004: ITDS Program Plan.  The ITDS Program Plan is a general description of the ITDS program, vision, goals, and objectives.  It describes how the program will be managed, and outlines what actions a government agency must take to participate in the program.  The Program Plan contains an appendix highlighting priorities for the next two fiscal years and a schedule for participating agency integration.

# Outlook

As ACE capabilities are expanded to additional users during the coming months, the CBPMO will maintain high program standards to ensure ACE capabilities continue to hit the mark once deployed.  As ACE development moves forward, the CBPMO is also actively engaged with leaders of other important DHS programs, most notably           US-VISIT.  Significant coordination and communication has and will continue to take place between the US-VISIT program office and the CBPMO.  The goal of this interface is to leverage the capabilities and infrastructure of the two programs where possible.  In earlier collaboration efforts, the US-VISIT program office and CBPMO sponsored an independent assessment of the legacy CBP and legacy Immigration and Naturalization Service networks to identify the appropriate technical approach to satisfy US-VISIT’s requirements.  Program lessons learned and best practices have been shared, and future off-sites will focus on opportunities for collaboration, including:

- Sharing program office governance, organization, and processes

- Sharing lessons on acquiring and working with prime contractors

- Synchronizing end-to-end program life cycles, from business architecture through workforce transformation

- Coordinating enterprise architecture activities

- Establishing a single security assessment office

- Consolidating targeting tools

- Coordinating creation of a core case record with the Consolidated Enforcement Environment program

- Determining approaches to leverage the Border and Transportation Security (BTS) Integration study

- Aligning future expenditure plans

- Collaborating with the Customs Automated Port Profile System II Program

ACE continues to be a complex and challenging endeavor.  Aggressive actions are being taken to address schedule delays, contain costs, and hold the systems integration contractor to high performance standards.  The program management staff knows where the ACE program stands, and what the risks are.  Program leadership is making deliberate decisions that will continue to advance the program while ensuring a high quality final outcome.  As evidenced by the recent Software Capability Maturity Model (reported in October 1, 2003 report) and SA-CMM assessments by the SEI, the CBPMO and systems integration contractor have achieved a significant process maturity rating.  These processes will be a continuing focus as the program implements  process improvement activities.

The program team will continue to build on its capabilities and improve its ability to provide effective direction and program monitoring.  A briefing on program monitoring was provided to the GAO representatives in mid-November 2003.  At this meeting, the specific program management controls that have been incorporated into the program were highlighted.  From the project level to the highest levels of CBP leadership, the focus is on continuous improvement as we move toward the final objective of putting the full complement of ACE capabilities on America’s borders to increase security and facilitate commerce.

For More Information:

Additional information on ACE may be found on the CBP website (www.cbp.gov) under the Modernization and ACE link.

The first five reports to Congress on ACE may be found on the CBP website at

http://www.cbp.gov/xp/cgov/toolbox/about/modernization/quarterly_reports/

Questions may be directed to:

L. Seth Statler

Deputy Assistant Commissioner 
Office of Congressional Affairs
(202) 927-1760

Sharon Mazur

Acting Executive Director
U.S. Customs and Border Protection Modernization Office
(703) 440-3000

NAFTA Requirements for ACE and Description of ACE Functionality

| Modernization Act Requirements for Electronic Processing | Release 1 Release 2 | Release 3 | Release 4 | Release 5 | S1 | S2 | S3 | Release 6 | Release 7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Subtitle A – Improvements in Customs Enforcement |
| Penalties for violations of arrival, reporting, entry, and clearance requirements |  |  |  |  |  |  |  |  | ( |
| CBP Testing Laboratories; Detention of Merchandise |  |  | ( | ( |  |  |  | ( | ( |
| Review of Protests |  |  |  |  |  |  |  |  | ( |
| Penalties Relating to Manifests |  |  |  |  |  |  |  |  | ( |
| Penalties for False Drawback Claims |  |  |  |  |  |  |  |  | ( |
| Interpretative Rulings and Decisions; Public Information | ( |  |  |  |  |  |  | ( | ( |
| Subtitle B – National Customs Automation Program |
| Electronic Entry of Merchandise |  |  |  |  |  |  |  | ( | ( |
| Electronic Entry Summary |  |  |  |  |  |  |  | ( | ( |
| Electronic Invoice |  |  |  |  |  |  |  | ( | ( |
| Electronic Manifest |  |  | ( | ( |  |  |  |  | ( |
| Electronic Payments of Duties and Fees |  | ( |  |  |  |  |  | ( | ( |
| Electronic Liquidation |  |  |  |  |  |  |  | ( | ( |
| Electronic Cargo and Entry Summary Selectivity |  |  | ( | ( | ( | ( | ( | ( | ( |
| Electronic Protests |  |  |  |  |  |  |  |  | ( |
| Customhouse Brokers |  | ( |  |  |  |  |  | ( | ( |
| Electronic Remote Entry Filing |  |  |  |  |  |  |  | ( | ( |
| Import Activity Summary Statements and Reconciliation |  |  |  |  |  |  |  | ( | ( |
| Electronic Bonds |  |  |  |  |  |  |  | ( | ( |
| Electronic Penalties |  |  |  |  |  |  |  |  | ( |
| Electronic Drawback Claims, Records, and Entries |  |  |  |  |  |  |  |  | ( |
| Electronic Refunds |  |  |  |  |  |  |  | ( | ( |
| Subtitle C – Miscellaneous Amendments to the Tariff Act of 1930 |
| Report of Arrival |  |  | ( | ( |  |  |  | ( |  |
| Entry of Vessels |  |  |  | ( |  |  |  |  |  |
| Unlading |  |  |  | ( |  |  |  |  |  |
| General Order |  |  |  |  |  |  |  |  | ( |
| Entry Under Regulations/ Informal Entries |  |  | ( | ( |  |  |  | ( | ( |
| Simplified Recordkeeping for Merchandise Transported by Pipeline |  |  |  |  |  |  |  |  | ( |
| Entry for Warehouse |  |  |  |  |  |  |  | ( |  |
| Collection of Fees on Behalf of Other Agencies |  |  |  |  |  |  |  | ( |  |
| Subtitle D – Miscellaneous Provisions and Consequential and Conforming Amendments to Other Laws |
| Vessel Clearance |  |  |  |  |  |  |  |  | ( |

ACE Implementation

The functional capabilities of ACE are expected to deliver increased border security and improved compliance.  The ACE will also increase efficiency and improve customer service for key stakeholders that include importers, brokers, carriers, and other government agencies.  The ACE capabilities will be delivered approximately every six months during the 6-year schedule.

The ACE Release 2 provides initial on-line account capabilities to CBP and the trade community.  Initial account revenue capabilities will be enabled in ACE Release 3, allowing accounts to centralize payment processing and to utilize monthly periodic statement and payment capabilities, as well as Automated Clearinghouse (ACH) Credit and Debit.  Cargo Processing in ACE will begin in ACE Release 4 with the implementation of Automated Truck Manifest and Preferred and Standard e-Releases for trucks at eight land border ports.  This will allow for quicker entry for pre-filed and pre-approved cargo.  Delivery of electronic release capability in ACE Release 4 will proceed in phases; phase one includes eight land border ports, and phase two will include the remaining 80-plus land ports.  These deliveries will be followed by deployment to 250 ports, including sea, air, and rail.  The ACE will ultimately be delivered to all ports, transportation modes, and locations.

The following paragraphs summarize ACE implementation activities for ACE Releases 2-4.

ACE Release 2: Spring 2003 (completed production readiness)

Features:

- Trade Account Profile – Aggregation of data pertaining to an account’s performance in all phases of its activities with CBP.  Examples include compliance issues relating to import transactions, compliance with rules and regulations, payment history, etc.  This information is used to evaluate the account’s risk of potential non-compliance.

- Action Plan – A course of action, created jointly by a trade account and CBP, which is intended to increase the level of compliance of that trade account.

- Significant Activity Log (SAL) – An auditable record of the significant activities that occur between CBP and a trade account.

- Quick View Reports – Summary reports available through the Harmonized Tariff Schedule (HTS) about CBP-related activities (i.e., Aggregated Entry Summary Compliance reports).

ACE Release 2 brought ACE to the public for the first time.  Currently, 50 importer accounts and related CBP personnel have access to the ACE Secure Data Portal to conduct their CBP business transactions on-line.

ACE Release 3: Summer 2004 (scheduled production readiness)

Features:

- Monthly Periodic Statement – A monthly summary of the receivables and disbursements relating to a particular trade account and covering a specified period.

- Monthly Periodic Payment – A financial transaction in which a trade account pays the obligations, such as duties, fees, taxes, fines, or penalties it owes to CBP.

- ACH Credit Payment – Payment method where the payer initiates payment through its financial institution.  The financial institution electronically transmits the payment through the ACH/Federal Reserve network to the CBP account maintained by the Department of the Treasury.

- ACH Debit Payment – Payment method where the payer transmits payment authorization to CBP, and CBP sends the payment information through the network to the payer's financial institution.

ACE Release 3 will expand the account management framework to a larger trade audience, including brokers, carriers, and CBP officers overseeing those areas.  The Account Profiles for importers, brokers, and carriers will support some information relevant to the Customs-Trade Partnership Against Terrorism.  It will provide a record of communications between the account and CBP (and ultimately with PGAs) via the SAL.

This release will provide a new CBP revenue capability that allows importers and their designated brokers to make periodic monthly payments for monthly statements of duties and fees.  In addition, this release will establish the first CBP customer- based subsidiary ledger for financial transaction processing, and will provide an expanded account view into account activity logs and exam findings.

ACE Release 4: Winter 2005 (scheduled production readiness)

Features:

- Automated Truck Manifest – Truck drivers submit a list of the separate items of freight being transported by a conveyance, together with their distinguishing marks, numbers, or characteristics.

- e-Release – The electronic process by which CBP authorizes the transfer (i.e., release) of goods from the carrier or warehouse to an importer, thereby allowing goods to be entered into the United States.

The ACE Release 4 will provide an electronic truck manifest, a primary inspector interface, and expedited importation processing.  The inspector interface will consolidate more than seven separate cargo release systems to provide CBP officers with a comprehensive view of enforcement and transaction history data to enhance enforcement capabilities and simultaneously expedite the movement of trade.  The electronic manifest will fulfill the mandate from the Trade Act of 2002 to provide an electronic manifest for trucks.  The automated manifest release processes will determine the admissibility of cargo, conveyances, and equipment arriving in the United States.  The Release will interface with Automated Targeting System to provide selectivity data to CBP primary officers to target high-risk transactions, and Tracer to record and track information associated with potential or actual non-compliance.  Preferred e-Release functionality will subsume the Free and Secure Trade (FAST) Declaration (manifest filing) and FAST Release (Release truck and cargo and creation of entries) functionality.

This release includes the first PGA, the Federal Motor Carrier Safety Administration, to manage truck safety issues at U.S. land borders.  The ACE Release 4 processing will be initially deployed in up to eight truck ports and then expanded to all U.S. land border crossings.  Once ACE Release 4 is deployed in all FAST ports, ACE will process all of the FAST transactions (Declaration and Release).

ACE Releases 3 and 4 passed the formal review and approval during the Critical Design Review with CBP officials in early fall 2003 and are now in the construction phase.  Following the construction phase, the test phase will begin.

While under development, communication events and activities are being scheduled to acquaint CBP personnel and trade representatives with details of ACE Releases 3 and 4.  The CBP BPOs are working closely with CBPMO and eCP to prepare Workforce Transformation Outreach plans to acquaint stakeholders with of ACE Release 3.

Training will be instructor-led for up to 3,000 CBP end-users for ACE Release 3, and up to 2,000 CBP end-users for ACE Release 4.  Computer-Based Training (CBT) will be developed to train trade participants and end-users working for PGAs for both Releases.  The UAT will follow the training for both ACE Releases 3 and 4 and will consist of reviewing tasks that are relevant to the end-users’ usual duties.

ACE Releases 3 and 4 aim to expand access to approximately 1,100 importers and their associated carriers and brokers.  A total of three FRNs will be issued for ACE Releases 3 and 4 to recruit accounts for the pilot test.

The first FRN will be issued in January 2004 to establish designated broker accounts for participation in Periodic Payment.

The second FRN notice will also be issued in January 2004 and will establish ACE portal accounts for truck carriers.

The third FRN will be issued in July 2004 to announce the pilot test for Automated Truck Manifest.

Issue dates for the FRNs are subject to change based on further development of the account expansion strategy.

ACE Release 5: Spring 2005 (scheduled production readiness)

Features:

- Security and Commercial Accounts:

- Freight Forwarders Accounts

- Cargo and Enforcement Processing:

- Air, Rail, and Sea automated manifest interface

- Air, Rail, and Sea e-Release

- Enforcement and Tracer for Air, Rail, and Sea Manifest and Release

- Reference Data:

- Tracking of Informed Compliance Pubs, Policy Changes, and Handbooks

- On-line reference library

- Manifest Reference Data

- Electronic field directives

ACE Release Selectivity 1:  Summer 2005 (scheduled production readiness)

Features:

- Initial Criteria Management

- Initial Release Selectivity functionality using Manifest and Entry for Air, Rail, Sea, and Truck

ACE Release Selectivity 2:  Winter 2006 (scheduled production readiness)

Features:

- Consolidated Release Selectivity functionality using Manifest and Entry for Air, Rail, Sea, and Truck

- Post Release Selectivity

- Enhanced Criteria Management

- System generated analysis

ACE Release Selectivity 3:  Summer 2006 (scheduled production readiness)

Features:

- Selectivity functionality for export, mail, courier, pipeline, hand carry, and multi-modal manifest

- Enhanced Risk Management Activities

ACE Release 6:  Fall 2006 (scheduled production readiness)

Features:

- Security and Commercial Accounts:

- Remaining import account types

- Bond data and bond sufficiency

- Maintain CBP licenses, permits, and certificates

- Account view of export data

- Administrative messaging

- Periodic statements

- Accept payments (including Electronic Funds Transfer and lockbox)

- Enhanced General Ledger Integration with Subsidiary Ledgers

- Refunds for liquidation

- Chief Financial Officer reports

- Violation Billing

- Cargo and Enforcement Processing:

- Accept all major entry types

- Initial Cargo, Conveyance, Individual, and Equipment (CCIE) tracking

- Enforcement and Tracer for entry summary and all entry types (except mail, courier, hand carry, and pipeline)

- Tracer for initial cargo tracking, Quote/Visa, Anti-dumping/Countervailing duty

- Port Release Processing:

- Entry summary, Temporary Importation Bond, Vessel repair

- Reconciliation

- Liquidation/Close out

- Quota, Visa, Anti-Dumping/Countervailing Duty

- Reference Data:

- Receive electronic ruling request

- Tracking of Legal Notices, Congressional Responses, and Agreements

- Quota/Visa

- Import Reference Data

- Statistical analysis and reports

- Non-CBP Licenses, Permits, and Certificate

ACE Release 7:  Winter 2007 (scheduled production readiness)

Features:

- Security and Commercial Accounts:

- Exporter Accounts

- Regulatory audit

- Full compliance analysis

- Accept cash payments

- Import Activity Summary Statement (IASS) Statements

- Miscellaneous refunds

- Full revenue processing

- Drawback and protest refunds

- Full General Ledger Integration with Subsidiary Ledgers

- Cargo and Enforcement Processing

- Mail, Courier, Hand Carry, Pipeline manifest, e-Release, and Tracking

- Multi-modal manifest

- Full CCIE tracking

- Full export processing

- Enforcement and Tracer for Mail, Courier, Hand Carry, and Pipeline

- Enforcement and Tracer for exports, drawback, IASS, Cargo and conveyance tracking, and account compliance

- Port Release Processing:

- IASS

- Protest, drawback

- Reference Data:

- Full electronic ruling processing

- e-Training

- Full Freedom of Information Act (FOIA) processing

- Export reference data

- Watch lists

Acronyms and Selected Definitions

| ACE | Automated Commercial Environment. The first project of U.S. Customs and Border Protection Modernization. Through enhanced business processes and the new technology in ACE that will support them, border security and trade facilitation will be greatly enhanced. |
| --- | --- |
| ACH | Automated Clearinghouse |
| BPO | Business Process Owners |
| CBP | U.S. Customs and Border Protection |
| CBT | Computer-Based Training |
| CBPMO | U.S. Customs and Border Protection Modernization Office. The program office for the Automated Commercial Environment. |
| DHS | Department of Homeland Security |
| EA | Enterprise Architecture |
| eCP | e-Customs Partnership |
| ESC | Executive Steering Committee |
| FAST | Free and Secure Trade |
| FRN | Federal Register Notice |
| FY | Fiscal Year |
| GAO | General Accounting Office |
| GATT | Global Agreement on Tariffs and Trade |
| GBB | Global Business Blueprinting |
| GSN | Government Support Network |
| HC | Human Capital |
| HCC | Human Capital Capability |
| HCM | Human Capital Management |
| HCMP | Human Capital Management Plan. The human capital plan that provides near and long-term HCM solutions to support recruiting, retention, training, and tying performance and reward programs to modernization goals. |

| HTS | Harmonized Tariff Schedule. A comprehensive list (i.e., schedule) of duties to be charged for each listed article, together with the governing rules and regulations. The HTS is the U.S. expression of the Harmonized Commodity Description and Coding System, an international system for categorizing commodities negotiated under the GATT, and maintained by the International Trade Commission. |
| --- | --- |
| IASS | Import Activity Summary Statement |
| I2V2 | Integrated Independent Verification and Validation |
| IIF | Intelligent Information Factory |
| IGCE | Independent Government Cost Estimate |
| IPT | Integrated Project Team |
| IT | Information Technology |
| ITDS | International Trade Data System |
| IV&V | Independent Verification and Validation |
| KBRM | Knowledge-Based Risk Management |
| KPA | Key Process Area |
| LCCE | Life-Cycle Cost Estimate |
| LCCM | Life-Cycle Cost Model |
| MR | Management Reserve |
| NAFTA | North American Free Trade Agreement |
| NDC | National Data Center |
| O&M | Operations and Maintenance |
| OIT | Office of Information and Technology |
| OMB | Office of Management and Budget |
| ORR | Operational Readiness Review |
| PGA | Participating Government Agency |
| PRR | Production Readiness Review |
| SA-CMM® | Software Acquisition-Capability Maturity Model®. The SA-CMM was developed by Carnegie Mellon University’s Software Engineering Institute as a model for acquiring or procuring software-intensive systems. It is used to assess the maturity of an organization’s systems acquisition process to ensure that cost, schedule, and performance goals are met. The CBPMO has achieved SA-CMM Level 2 maturity. At Level 2, personnel in the organization have “process discipline.” They are knowledgeable of promulgated policies, processes, and procedures that relate to the project, and have institutionalized them into their daily activities. |
| SAL | Significant Activity Log |
| SAP | Systems, Applications, and Products in Data Processing |
| SAPG | Systems Acquisition Planning Group |
| SAT | Systems Acceptance Testing |
| SDLC | Software Development Lifecycle |
| SEI® | Software Engineering Institute. See SA-CMM. |
| SIT | Systems Integration Testing |
| SME | Subject Matter Expert |
| SW-CMM | Software Capability Maturity Model |
| SWIT | Software Integration Testing |
| TSN | Trade Support Network |
| UAT | User Acceptance Testing |

# Comments

192

192

191.