U.S. ATLAS M&O Estimate

Cost Book

Funding 	All	Funding Type:	All

Institutions:	All

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:12 PM

WBS 	3	Description:	U.S. ATLAS M&O Estimate

Institution :	Contact

U.S. ATLAS Maintenance and Operations (M&O) includes detector specific costs allocated to subsystems and Common

Fund cost  related to overall experimental operations.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

8704	0	0	8704	0	6479	0	2225	96.2	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Computer Professional  B/I	0	0	0	888	888	0	0	0	0	0	1776

0	0	0	50.35	50.35	0	0	0	0	0	100.700

Faculty  B/I	0	0	7967	6159	888	888	888	888	888	888	19454

0	0	552.497	438.007	72.727	72.727	72.727	72.727	72.727	72.727	1426.866

Grad Student  B/I	0	0	2646	10113	7921	5271	5271	5271	5271	5271	47035

0	0	43.341	165.652	129.746	86.34	86.34	86.34	86.34	86.34	770.439

Post Doc  B/I	0	0	3546	9257	8840	4402	4402	4402	4402	4402	43653

0	0	111.698	291.595	278.46	138.663	138.663	138.663	138.663	138.663	1375.068

Sr Research Scientist  B/I	0	0	3546	6621	6196	1758	1767	1767	1767	1767	25189

0	0	223.398	383.909	368.172	110.754	111.321	111.321	111.321	111.321	1531.517

B/I Total	0	0	17705	33038	24733	12319	12328	12328	12328	12328	137107

0	0	930.934	1329.513	899.455	408.484	409.051	409.051	409.051	409.051	5204.590

Technician  MR	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

MR Total	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

Computer Professional  R	0	0	0	880	556	200	200	200	200	200	2436

0	0	0	49.896	31.525	11.34	11.34	11.34	11.34	11.34	138.121

Electrical Engineer  R	0	0	880	880	0	0	0	0	0	0	1760

0	0	60.984	60.984	0	0	0	0	0	0	121.968

Mechanical Engineer  R	0	0	884	0	0	0	0	0	0	0	884

0	0	61.261	0	0	0	0	0	0	0	61.261

Technician  R	0	0	4848	2666	2860	2640	2640	2640	2640	2640	23574

0	0	166.602	91.839	98.127	90.92	90.92	90.92	90.92	90.92	811.168

Page 1 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:12 PM

R Total	0	0	6612	4426	3416	2840	2840	2840	2840	2840	28654

0	0	288.847	202.719	129.652	102.26	102.26	102.26	102.26	102.26	1132.518

Total	0	0	26953	38344	28149	15159	15168	15168	15168	15168	169277

0	0	1324.95	1568.822	1029.107	510.744	511.311	511.311	511.311	511.311	6478.867

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

MR Total	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

Other  R	0.0	0.0	104.9	154.6	147.4	248.8	229.7	260.9	197.3	130.5	1528.650

Travel  R	0.0	0.0	103.0	54.0	46.2	37.0	37.0	37.0	37.0	37.0	612.238

R Total	0.0	0.0	207.9	208.6	193.6	285.8	266.7	297.9	234.3	167.5	2140.888

Total	0.0	0.0	255.4	215.6	193.6	285.8	266.7	297.9	234.3	167.5	2225.240

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	1680	1848	1259	818	800	831	767	701	8704

Page 2 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:12 PM

WBS 	3.2	Description:	TRT

Institution :	Contact

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

8704	0	0	8704	0	6479	0	2225	96.2	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Computer Professional  B/I	0	0	0	888	888	0	0	0	0	0	1776

0	0	0	50.35	50.35	0	0	0	0	0	100.700

Faculty  B/I	0	0	7967	6159	888	888	888	888	888	888	19454

0	0	552.497	438.007	72.727	72.727	72.727	72.727	72.727	72.727	1426.866

Grad Student  B/I	0	0	2646	10113	7921	5271	5271	5271	5271	5271	47035

0	0	43.341	165.652	129.746	86.34	86.34	86.34	86.34	86.34	770.439

Post Doc  B/I	0	0	3546	9257	8840	4402	4402	4402	4402	4402	43653

0	0	111.698	291.595	278.46	138.663	138.663	138.663	138.663	138.663	1375.068

Sr Research Scientist  B/I	0	0	3546	6621	6196	1758	1767	1767	1767	1767	25189

0	0	223.398	383.909	368.172	110.754	111.321	111.321	111.321	111.321	1531.517

B/I Total	0	0	17705	33038	24733	12319	12328	12328	12328	12328	137107

0	0	930.934	1329.513	899.455	408.484	409.051	409.051	409.051	409.051	5204.590

Technician  MR	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

MR Total	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

Computer Professional  R	0	0	0	880	556	200	200	200	200	200	2436

0	0	0	49.896	31.525	11.34	11.34	11.34	11.34	11.34	138.121

Electrical Engineer  R	0	0	880	880	0	0	0	0	0	0	1760

0	0	60.984	60.984	0	0	0	0	0	0	121.968

Mechanical Engineer  R	0	0	884	0	0	0	0	0	0	0	884

0	0	61.261	0	0	0	0	0	0	0	61.261

Technician  R	0	0	4848	2666	2860	2640	2640	2640	2640	2640	23574

0	0	166.602	91.839	98.127	90.92	90.92	90.92	90.92	90.92	811.168

R Total	0	0	6612	4426	3416	2840	2840	2840	2840	2840	28654

0	0	288.847	202.719	129.652	102.26	102.26	102.26	102.26	102.26	1132.518

Total	0	0	26953	38344	28149	15159	15168	15168	15168	15168	169277

0	0	1324.95	1568.822	1029.107	510.744	511.311	511.311	511.311	511.311	6478.867

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

Page 3 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:13 PM

MR Total	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

Other  R	0.0	0.0	104.9	154.6	147.4	248.8	229.7	260.9	197.3	130.5	1528.650

Travel  R	0.0	0.0	103.0	54.0	46.2	37.0	37.0	37.0	37.0	37.0	612.238

R Total	0.0	0.0	207.9	208.6	193.6	285.8	266.7	297.9	234.3	167.5	2140.888

Total	0.0	0.0	255.4	215.6	193.6	285.8	266.7	297.9	234.3	167.5	2225.240

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	1680	1848	1259	818	800	831	767	701	8704

Page 4 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:13 PM

WBS 	3.2.1	Description:	TRT-Subsystem

Institution :	Contact

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

7375	0	0	7375	0	6479	0	896	96.2	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Computer Professional  B/I	0	0	0	888	888	0	0	0	0	0	1776

0	0	0	50.35	50.35	0	0	0	0	0	100.700

Faculty  B/I	0	0	7967	6159	888	888	888	888	888	888	19454

0	0	552.497	438.007	72.727	72.727	72.727	72.727	72.727	72.727	1426.866

Grad Student  B/I	0	0	2646	10113	7921	5271	5271	5271	5271	5271	47035

0	0	43.341	165.652	129.746	86.34	86.34	86.34	86.34	86.34	770.439

Post Doc  B/I	0	0	3546	9257	8840	4402	4402	4402	4402	4402	43653

0	0	111.698	291.595	278.46	138.663	138.663	138.663	138.663	138.663	1375.068

Sr Research Scientist  B/I	0	0	3546	6621	6196	1758	1767	1767	1767	1767	25189

0	0	223.398	383.909	368.172	110.754	111.321	111.321	111.321	111.321	1531.517

B/I Total	0	0	17705	33038	24733	12319	12328	12328	12328	12328	137107

0	0	930.934	1329.513	899.455	408.484	409.051	409.051	409.051	409.051	5204.590

Technician  MR	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

MR Total	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

Computer Professional  R	0	0	0	880	556	200	200	200	200	200	2436

0	0	0	49.896	31.525	11.34	11.34	11.34	11.34	11.34	138.121

Electrical Engineer  R	0	0	880	880	0	0	0	0	0	0	1760

0	0	60.984	60.984	0	0	0	0	0	0	121.968

Mechanical Engineer  R	0	0	884	0	0	0	0	0	0	0	884

0	0	61.261	0	0	0	0	0	0	0	61.261

Technician  R	0	0	4848	2666	2860	2640	2640	2640	2640	2640	23574

0	0	166.602	91.839	98.127	90.92	90.92	90.92	90.92	90.92	811.168

R Total	0	0	6612	4426	3416	2840	2840	2840	2840	2840	28654

0	0	288.847	202.719	129.652	102.26	102.26	102.26	102.26	102.26	1132.518

Total	0	0	26953	38344	28149	15159	15168	15168	15168	15168	169277

0	0	1324.95	1568.822	1029.107	510.744	511.311	511.311	511.311	511.311	6478.867

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

Page 5 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:14 PM

MR Total	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

Other  R	0.0	0.0	60.0	70.0	15.0	0.0	0.0	0.0	0.0	0.0	199.550

Travel  R	0.0	0.0	103.0	54.0	46.2	37.0	37.0	37.0	37.0	37.0	612.238

R Total	0.0	0.0	163.0	124.0	61.2	37.0	37.0	37.0	37.0	37.0	811.788

Total	0.0	0.0	210.5	131.0	61.2	37.0	37.0	37.0	37.0	37.0	896.140

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	1635	1764	1126	570	570	570	570	570	7375

Page 6 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:14 PM

WBS 	3.2.1.1	Description:	TRT Pre-operations

Institution :	Contact	Not available

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

3692	0	0	3692	0	3247	0	445	40.0	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Computer Professional  B/I	0	0	0	888	888	0	0	0	0	0	1776

0	0	0	50.35	50.35	0	0	0	0	0	100.700

Faculty  B/I	0	0	7967	6159	888	0	0	0	0	0	15014

0	0	552.497	438.007	72.727	0	0	0	0	0	1063.231

Grad Student  B/I	0	0	2646	5711	2650	0	0	0	0	0	11007

0	0	43.341	93.547	43.406	0	0	0	0	0	180.294

Post Doc  B/I	0	0	3546	5742	4438	0	0	0	0	0	13726

0	0	111.698	180.873	139.797	0	0	0	0	0	432.368

Sr Research Scientist  B/I	0	0	3546	5742	4438	0	0	0	0	0	13726

0	0	223.398	328.532	257.418	0	0	0	0	0	809.348

B/I Total	0	0	17705	24242	13302	0	0	0	0	0	55249

0	0	930.934	1091.309	563.698	0	0	0	0	0	2585.941

Technician  MR	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

MR Total	0	0	2636	880	0	0	0	0	0	0	3516

0	0	105.169	36.59	0	0	0	0	0	0	141.759

Computer Professional  R	0	0	0	880	356	0	0	0	0	0	1236

0	0	0	49.896	20.185	0	0	0	0	0	70.081

Electrical Engineer  R	0	0	880	880	0	0	0	0	0	0	1760

0	0	60.984	60.984	0	0	0	0	0	0	121.968

Mechanical Engineer  R	0	0	884	0	0	0	0	0	0	0	884

0	0	61.261	0	0	0	0	0	0	0	61.261

Technician  R	0	0	4848	2666	220	0	0	0	0	0	7734

0	0	166.602	91.839	7.207	0	0	0	0	0	265.648

R Total	0	0	6612	4426	576	0	0	0	0	0	11614

0	0	288.847	202.719	27.392	0	0	0	0	0	518.958

Total	0	0	26953	29548	13878	0	0	0	0	0	70379

0	0	1324.95	1330.618	591.09	0	0	0	0	0	3246.658

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

Page 7 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:15 PM

MR Total	0.0	0.0	47.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	84.352

Other  R	0.0	0.0	30.0	25.0	0.0	0.0	0.0	0.0	0.0	0.0	85.950

Travel  R	0.0	0.0	103.0	54.0	19.2	0.0	0.0	0.0	0.0	0.0	275.158

R Total	0.0	0.0	133.0	79.0	19.2	0.0	0.0	0.0	0.0	0.0	361.108

Total	0.0	0.0	180.5	86.0	19.2	0.0	0.0	0.0	0.0	0.0	445.460

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	1605	1466	622	0	0	0	0	0	3692

Page 8 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:15 PM

WBS 	3.2.1.1.1	Description:	Module Check( 7/02-12/04

Institution :	Contact	Not available

Check out of modules arriving at CERN

Work done in Bldg 154 CERN.

This work will span the period Oct 02 to December 04

There are a total of 102 modules that must be tested

and cerified as the 96 modules and 6 spares.

The modules arrive at the rate of about 6 modules/month

from Hampton gain testing. The testing must keep up

with this arrival plan. The operations on each module include:

Module checkin and passport update.

Verify wire tensions.

Verfity leak tightness,

verify mechanical dimensions:

wire gain survey.

Begin of long term HV conditioning.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Page 9 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:15 PM

WBS 	3.2.1.1.1.1	Description:	Technical support (Duke)

Institution :	Duke University	Contact	Not available

Special Technical tech helping with module checkout

0.25 tech in FY03 (ebenstein)

MC 0.75  tech in FY04 (ebenstein)

0.25 tech in FY05(ebenstein)

This Duke person will be spending half of his time

in Bldg 154 doing the module checkout,( ( ~one module/week) and the other

half assisting with the installation of the modules in the spaceframe.

During the  checkout operation in Bldg 154 this specialized

technician will be responsible for

1) measuring tensions and restringing any problem wires

est- 3 hours/week

2) assisting in leak test measurements and correcting any problems.

Estimate 3 hours/week

3) Assisting in preparation of the modules for gain testing- this

includes HV preparation with gas flow and determination of low

current draw

estimate 2 hours/week

4) Assist in gain scanning

estimate 8 hours/week

5) restringing or removal of wires with out-of-spec gain

estimate 2 hours/week

6) Set up of gas and HV for long term HV running, and monitoring running.

Estimate 2hours/week

For a total of about 20hours/week assisting with each module-

$30K/yearDetails of Estimate:

$1.5K for trip( FY03-2 trips

FY04( 2 trips, FY05 2 trips

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 10 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:16 PM

WBS 	3.2.1.1.1.2	Description:	equipment

Institution :	Contact	Not available

Equipment needs for checkout of

module in BLDG 154 after they

arrive at CERN.

multi channel tension- $6KDetails of Estimate:

Gas leak tester- $7K

HV breakdow test-$6k

Gas Gain-$65K

HV training- $15K

Storage, support-$22K

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Page 11 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:16 PM

WBS 	3.2.1.1.1.2.1	Description:	gas leak tester

Institution :	Indiana U.	Contact	Not available

Leak tester supplied by Indiana University.

$7K for Details of Estimate:

total cost of leak tester

and computer interface.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 12 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:16 PM

WBS 	3.2.1.1.1.2.2	Description:	multi channel tension

Institution :	Duke University	Contact	Not available

Tesnsion tester supplied by Duke University

$6K for 16 ch tension testerDetails of Estimate:

and computer interfaces.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 13 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:17 PM

WBS 	3.2.1.1.1.2.3	Description:	HV breakdown test

Institution :	Duke University	Contact	Not available

Supplied by Duke University

$3K for HV supply and cablesDetails of Estimate:

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 14 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:17 PM

WBS 	3.2.1.1.1.2.4	Description:	gain mapper

Institution :	Hampton U.	Contact	Not available

This will be built by Hampton

Readout electronics has been

purchased from base fund.

$65KDetails of Estimate:

for xray source,

$12K

position conroller

$13k

Gas system

$4K

cabinet

$11K

slow controls

$7K

DAQ, mCA

$18K

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 15 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:17 PM

WBS 	3.2.1.1.1.2.5	Description:	HV training supplies, cables

Institution :	Duke University	Contact	Not available

This is the HV longterm conditioning

that will be necessary to qualify a module

prior to installation.

$15k for Details of Estimate:

8 HV supplies  $8K

and $7 K for distribution

and cabling for up to 45 modules.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 16 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:17 PM

WBS 	3.2.1.1.1.2.6	Description:	storage and support

Institution :	Indiana U.	Contact	Not available

Storage and support equiment

in Bldg 154

Details of Estimate:

storage racks.$9K

Tools - $3K

measurement equipment- $4K

supplies( for entire period)- 6K

total 22K

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 17 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:18 PM

WBS 	3.2.1.1.1.3	Description:	other technical support (russian tech, IU postdoc,

Institution :	BNL-M&O	Contact	Not available

Technical support in Bldg 154 during period

of FY03  and FY04

This is money for a CERN based technical

level assistant to work with the specailist

on all checkout activities.

Indiana will supply a postdoc (Kayumov)

and a staff scientist (Gagnon) for additional

work in 154.

This  technician  will be spending half of his time

in Bldg 154 doing the module checkout,( ( ~one module/week) and the other

half assisting with the installation of the modules in the spaceframe.

During the  checkout operation in Bldg 154 this specialized

technician will be responsible for

1) measuring tensions and restringing any problem wires

est- 6 hours/week

2) assisting in leak test measurements and correcting any problems.

Estimate 4 hours/week

3) Assisting in preparation of the modules for gain testing- this

includes HV preparation with gas flow and determination of low

current draw

estimate 4 hours/week

4) Assist in gain scanning

estimate 16 hours/week

5) restringing or removal of wires with out-of-spec gain

estimate 2 hours/week

6) Set up of gas and HV for long term HV running, and monitoring running.

Estimate 4 hours/week

For a total of about 40hours/week assisting with each module-

IU physicist and postdoc coveredDetails of Estimate:

from base.

Tech is on MC for F04

no travel needed

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 18 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:18 PM

WBS 	3.2.1.1.4	Description:	TRT-6 mod-check (2/04- 1/05)

Institution :	Contact

preoperation work on modules in space frame, check cooling attachments, electronic checks on 3-6 module groups.

Maintain operation of modules once installed

The module installation activity involves the actual mounting of the

TRT barrel  modules into the spaceframe in the SR building, and the

initial hookup of services to a six module gas and cooling manifold.

This preparation  activity starts in October, 03 and continues until January 05.

There are 16 six-module sectors. Upon completion of all 16 sectors,

the final gas and cooling manifolds will be attached and connected.

The installation starts November,03

The present estimate is that this operation will require  3 weeks/sector.

The detailed activites have been scheduled by the project engineer, they

include:

install check six modules                                1.2 days

Install cooling tubes and CO2 lines, check    1.2 days

Install electronics on front end                       3.4 days

Install cooling plates and tubing front end      1.2 days

Install sector manifolds front end                    1.2 days

Install electronics  on backend                      3.4 days

Install cooling plates and tubing back end     1.2 days

Install sector manifolds back end                   1.2 days.

Sector cooling hookup                                   1 day

The installation is only part of the activitity in the SR building.

Following these operations, the additional  testing of cooling, active gas, HV,

Low volgtage, and signal noise for each sector are part of the M&O operations.

Continual monitoring of installed modules is also covered in the M&O which span the same period.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

309	0	0	309	0	216	0	93	3.0	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  MR	0	0	1756	880	0	0	0	0	0	0	2636

0	0	73.014	36.59	0	0	0	0	0	0	109.604

MR Total	0	0	1756	880	0	0	0	0	0	0	2636

0	0	73.014	36.59	0	0	0	0	0	0	109.604

Mechanical Engineer  R	0	0	444	0	0	0	0	0	0	0	444

0	0	30.769	0	0	0	0	0	0	0	30.769

Technician  R	0	0	2208	0	0	0	0	0	0	0	2208

0	0	75.681	0	0	0	0	0	0	0	75.681

R Total	0	0	2652	0	0	0	0	0	0	0	2652

0	0	106.45	0	0	0	0	0	0	0	106.450

Page 19 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:18 PM

Total	0	0	4408	880	0	0	0	0	0	0	5288

0	0	179.464	36.59	0	0	0	0	0	0	216.054

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	17.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	36.652

MR Total	0.0	0.0	17.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	36.652

Travel  R	0.0	0.0	37.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	56.630

R Total	0.0	0.0	37.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	56.630

Total	0.0	0.0	54.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	93.282

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	262	47	0	0	0	0	0	0	309

Page 20 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:19 PM

WBS 	3.2.1.1.4.1	Description:	technical support  (Kline)

Institution :	Indiana U.	Contact

1 technician  for 0.75 FTE FY04

( rest of FY04 covered in installation)

1 technicians for 0.25 FTE FY05

(rest of FY05 coverd in 3.2.1.1.5)

This specialized assembly person will spend 75% of his

time in FY04 on the checkout of the installed modules and services.

The remaining 25% is time during the first quarter of Fy04, when he will

be assisting with the initial prepartion of the spaceframe for installation of

modules

This tech will be working with 1.5 other techs on the process. Many

of the operations will reqire two people, an unknown is the process is

time for problem solving during installation.

The detailed activites have been scheduled by the project engineer, they

include:

install check six modules                                1.2 days

Install cooling tubes and CO2 lines, check    1.2 days

Install electronics on front end                       3.4 days

Install cooling plates and tubing front end      1.2 days

Install sector manifolds front end                    1.2 days

Install electronics on backend                      3.4 days

Install cooling plates and tubing back end     1.2 days

Install sector manifolds back end                   1.2 days.

Sector cooling hookup                                   1 day

total                                                             15 days

$30K/y Details of Estimate:

1.5K/trip( 3 in FY04, 2 in FY05)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

31	0	0	31	0	16	0	16	0.3	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  R	0	0	440	0	0	0	0	0	0	0	440

0	0	15.523	0	0	0	0	0	0	0	15.523

R Total	0	0	440	0	0	0	0	0	0	0	440

0	0	15.523	0	0	0	0	0	0	0	15.523

Total	0	0	440	0	0	0	0	0	0	0	440

0	0	15.523	0	0	0	0	0	0	0	15.523

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	10.5	0.0	0.0	0.0	0.0	0.0	0.0	0.0	15.645

Page 21 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:19 PM

R Total	0.0	0.0	10.5	0.0	0.0	0.0	0.0	0.0	0.0	0.0	15.645

Total	0.0	0.0	10.5	0.0	0.0	0.0	0.0	0.0	0.0	0.0	15.645

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	31	0	0	0	0	0	0	0	31

Page 22 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:19 PM

WBS 	3.2.1.1.4.2	Description:	other technical support (Russian)

Institution :	Indiana U.	Contact	Not available

0.5 FTE russian support

( remaining FTE covered by endcaps)

support for module checking

in Bldg 154

Extra CERN based support during the time

that module check out and module installation are taking place simultaneously.

no extra travel moneyDetails of Estimate:

required

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

31	0	0	31	0	31	0	0	0.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  R	0	0	888	0	0	0	0	0	0	0	888

0	0	31.329	0	0	0	0	0	0	0	31.329

R Total	0	0	888	0	0	0	0	0	0	0	888

0	0	31.329	0	0	0	0	0	0	0	31.329

Total	0	0	888	0	0	0	0	0	0	0	888

0	0	31.329	0	0	0	0	0	0	0	31.329

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	31	0	0	0	0	0	0	0	31

Page 23 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:20 PM

WBS 	3.2.1.1.4.3	Description:	project engineer(Callahan)

Institution :	Indiana U.	Contact

MC   0.4 FTE  04

(remainder as CERN associate )

0.6 FTE 05

(remainder as 1/2 year CERN associate extension + 0.25 on M&O)

Project Engineer to oversee

the module insertion

In Fy04 the first 1/2 year is spent working on the completion of the space frame and the initial

instalation of the modules into the frame.

The remainder of the time, the Project Engineer will focus on the checkout of the

modules after installation.

2004 CERN assoc coversDetails of Estimate:

60%

1/2 year extension in FY05

and remainder on M&O with

travel.

$10K/y

1.5K/trip ( 3 Fy04, 2 FY05)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

48	0	0	48	0	31	0	17	0.3	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Mechanical Engineer  R	0	0	444	0	0	0	0	0	0	0	444

0	0	30.769	0	0	0	0	0	0	0	30.769

R Total	0	0	444	0	0	0	0	0	0	0	444

0	0	30.769	0	0	0	0	0	0	0	30.769

Total	0	0	444	0	0	0	0	0	0	0	444

0	0	30.769	0	0	0	0	0	0	0	30.769

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	11.5	0.0	0.0	0.0	0.0	0.0	0.0	0.0	17.135

R Total	0.0	0.0	11.5	0.0	0.0	0.0	0.0	0.0	0.0	0.0	17.135

Total	0.0	0.0	11.5	0.0	0.0	0.0	0.0	0.0	0.0	0.0	17.135

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 24 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:20 PM

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	48	0	0	0	0	0	0	0	48

Page 25 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:20 PM

WBS 	3.2.1.1.4.4	Description:	electronics technician(B. LeGeyt)

Institution :	U of Pennsylvania	Contact

electronic tech FTE 0.5 - FY04

0.25 FTE FY05

for work on module electronic

testing and repair once modules are

installed

This persion will be the primary electronics lead tech for

the items listed at ET

The detailed activites have been scheduled by the project engineer, they

include:

install check six modules                                1.2 days

Install cooling tubes and CO2 lines, check    1.2 days

Install electronics on front end                       3.4 days  EE

Install cooling plates and tubing front end      1.2 days  EE

Install sector manifolds front end                    1.2 days

Install electronics  on backend                      3.4 days  EE

Install cooling plates and tubing back end     1.2 days  EE

Install sector manifolds back end                   1.2 days.

Sector cooling hookup                                   1 day

Faraday sheild connection, testing                  4 days  EE

The electronic technicai will be 50% on the testing phase and 50% on the

installation of electronics.

$30K/yearDetails of Estimate:

$1.5K for trip ( two in FY04,

Two in Fy05)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

53	0	0	53	0	29	0	24	0.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  R	0	0	880	0	0	0	0	0	0	0	880

0	0	28.829	0	0	0	0	0	0	0	28.829

R Total	0	0	880	0	0	0	0	0	0	0	880

0	0	28.829	0	0	0	0	0	0	0	28.829

Total	0	0	880	0	0	0	0	0	0	0	880

0	0	28.829	0	0	0	0	0	0	0	28.829

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	15.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	23.850

Page 26 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:20 PM

R Total	0.0	0.0	15.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	23.850

Total	0.0	0.0	15.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	23.850

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	53	0	0	0	0	0	0	0	53

Page 27 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:21 PM

WBS 	3.2.1.1.4.5	Description:	Electronics tech- Yale

Institution :	Yale University	Contact	Not available

1 FTE 04, 1 FTE FY05, 0.5 FTE FY06

work with Penn on

certifying the electronics

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

146	0	0	146	0	110	0	37	1.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  MR	0	0	1756	880	0	0	0	0	0	0	2636

0	0	73.014	36.59	0	0	0	0	0	0	109.604

MR Total	0	0	1756	880	0	0	0	0	0	0	2636

0	0	73.014	36.59	0	0	0	0	0	0	109.604

Total	0	0	1756	880	0	0	0	0	0	0	2636

0	0	73.014	36.59	0	0	0	0	0	0	109.604

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	17.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	36.652

MR Total	0.0	0.0	17.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	36.652

Total	0.0	0.0	17.5	7.0	0.0	0.0	0.0	0.0	0.0	0.0	36.652

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	99	47	0	0	0	0	0	0	146

Page 28 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:21 PM

WBS 	3.2.1.1.4.9	Description:	HV distribution

Institution :	Duke University	Contact

HV distribution for six sector test to verify the operation of each unit and to maintain

modules in opearation after installation

10 HV supplies and racks- $27KDetails of Estimate:

cables $8K, connectors, and

associated supplies  $5K

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 29 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:21 PM

WBS 	3.2.1.1.4.10	Description:	Low Voltage system

Institution :	U of Pennsylvania	Contact

Electronics low voltage supplies and daq for initial testing of six module sector- core

item

Electronics, power supplies and associated equipment -$15,000Details of Estimate:

Cables, connectors, - $5,000

DAQ, and computer for sector tests-$15,000

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 30 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:22 PM

WBS 	3.2.1.1.4.11	Description:	system tests

Institution :	Indiana U.	Contact	Not available

Equipment and supplies

for system tests

supplies forDetails of Estimate:

system testing $5000

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 31 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:22 PM

WBS 	3.2.1.1.5	Description:	TRT- SCT in SR (1/05 - 9/05)

Institution :	Contact

Services checkout for completed barrel cooling, electronics, HV tests and surveying

(with final cooling manifolds, electronics.

Front end performance testing including the

time when the SCT is installed and joint testing is being carried out

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

1065	0	0	1065	0	868	0	197	10.3	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	3564	0	0	0	0	0	0	0	3564

0	0	275.108	0	0	0	0	0	0	0	275.108

Grad Student  B/I	0	0	2646	0	0	0	0	0	0	0	2646

0	0	43.341	0	0	0	0	0	0	0	43.341

Post Doc  B/I	0	0	3546	0	0	0	0	0	0	0	3546

0	0	111.698	0	0	0	0	0	0	0	111.698

Sr Research Scientist  B/I	0	0	3546	0	0	0	0	0	0	0	3546

0	0	223.398	0	0	0	0	0	0	0	223.398

B/I Total	0	0	13302	0	0	0	0	0	0	0	13302

0	0	653.545	0	0	0	0	0	0	0	653.545

Technician  MR	0	0	880	0	0	0	0	0	0	0	880

0	0	32.155	0	0	0	0	0	0	0	32.155

MR Total	0	0	880	0	0	0	0	0	0	0	880

0	0	32.155	0	0	0	0	0	0	0	32.155

Electrical Engineer  R	0	0	880	0	0	0	0	0	0	0	880

0	0	60.984	0	0	0	0	0	0	0	60.984

Mechanical Engineer  R	0	0	440	0	0	0	0	0	0	0	440

0	0	30.492	0	0	0	0	0	0	0	30.492

Technician  R	0	0	2640	0	0	0	0	0	0	0	2640

0	0	90.921	0	0	0	0	0	0	0	90.921

R Total	0	0	3960	0	0	0	0	0	0	0	3960

0	0	182.397	0	0	0	0	0	0	0	182.397

Total	0	0	18142	0	0	0	0	0	0	0	18142

0	0	868.097	0	0	0	0	0	0	0	868.097

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	30.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	47.700

Page 32 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:23 PM

MR Total	0.0	0.0	30.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	47.700

Other  R	0.0	0.0	30.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	47.200

Travel  R	0.0	0.0	66.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	102.140

R Total	0.0	0.0	96.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	149.340

Total	0.0	0.0	126.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	197.040

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	1065	0	0	0	0	0	0	0	1065

Page 33 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:23 PM

WBS 	3.2.1.1.5.1	Description:	technical support-Fowler

Institution :	Duke University	Contact

fowler-Duke

Assisting with the SCT-TRTbarrel test

program

Includes:

Final hook of complete faraday sheild

Large scale noise studies

with end cap

with SCT

X-ray alignment studies

$30K/yearDetails of Estimate:

$1.5K for trip( three trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

324	0	0	324	0	276	0	48	3.0	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	1788	0	0	0	0	0	0	0	1788

0	0	146.437	0	0	0	0	0	0	0	146.437

Grad Student  B/I	0	0	879	0	0	0	0	0	0	0	879

0	0	14.398	0	0	0	0	0	0	0	14.398

Post Doc  B/I	0	0	879	0	0	0	0	0	0	0	879

0	0	27.688	0	0	0	0	0	0	0	27.688

Sr Research Scientist  B/I	0	0	879	0	0	0	0	0	0	0	879

0	0	55.377	0	0	0	0	0	0	0	55.377

B/I Total	0	0	4425	0	0	0	0	0	0	0	4425

0	0	243.9	0	0	0	0	0	0	0	243.900

Technician  MR	0	0	880	0	0	0	0	0	0	0	880

0	0	32.155	0	0	0	0	0	0	0	32.155

MR Total	0	0	880	0	0	0	0	0	0	0	880

0	0	32.155	0	0	0	0	0	0	0	32.155

Total	0	0	5305	0	0	0	0	0	0	0	5305

0	0	276.055	0	0	0	0	0	0	0	276.055

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  MR	0.0	0.0	30.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	47.700

MR Total	0.0	0.0	30.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	47.700

Page 34 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:23 PM

Total	0.0	0.0	30.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	47.700

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	324	0	0	0	0	0	0	0	324

Page 35 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:23 PM

WBS 	3.2.1.1.5.2	Description:	Project Engineer(Callahan)

Institution :	Indiana U.	Contact

Project engineer0 0.25 FTE

support of the final testing of the barrel

and the SCT

Includes:

Final hook of complete faraday sheild

Large scale noise studies

with end cap

with SCT

X-ray alignment studies

0.5 CERN associateDetails of Estimate:

$10K/y travel

$1.5K trip (three trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

146	0	0	146	0	128	0	18	1.7	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Grad Student  B/I	0	0	879	0	0	0	0	0	0	0	879

0	0	14.398	0	0	0	0	0	0	0	14.398

Post Doc  B/I	0	0	879	0	0	0	0	0	0	0	879

0	0	27.688	0	0	0	0	0	0	0	27.688

Sr Research Scientist  B/I	0	0	879	0	0	0	0	0	0	0	879

0	0	55.377	0	0	0	0	0	0	0	55.377

B/I Total	0	0	2637	0	0	0	0	0	0	0	2637

0	0	97.463	0	0	0	0	0	0	0	97.463

Mechanical Engineer  R	0	0	440	0	0	0	0	0	0	0	440

0	0	30.492	0	0	0	0	0	0	0	30.492

R Total	0	0	440	0	0	0	0	0	0	0	440

0	0	30.492	0	0	0	0	0	0	0	30.492

Total	0	0	3077	0	0	0	0	0	0	0	3077

0	0	127.955	0	0	0	0	0	0	0	127.955

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	12.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	17.880

R Total	0.0	0.0	12.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	17.880

Total	0.0	0.0	12.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	17.880

Page 36 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:24 PM

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	146	0	0	0	0	0	0	0	146

Page 37 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:24 PM

WBS 	3.2.1.1.5.3	Description:	Technical support (Kline)

Institution :	Indiana U.	Contact	Not available

0.50  FTE  for

assistance in the final testing of

the Barrel and SCT

Includes:

Final hook of complete faraday sheild

Large scale noise studies

with end cap

with SCT

X-ray alignment studies

$30K/yearDetails of Estimate:

$1.5K for trip ( three trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

311	0	0	311	0	287	0	24	3.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	888	0	0	0	0	0	0	0	888

0	0	72.727	0	0	0	0	0	0	0	72.727

Grad Student  B/I	0	0	888	0	0	0	0	0	0	0	888

0	0	14.545	0	0	0	0	0	0	0	14.545

Post Doc  B/I	0	0	1788	0	0	0	0	0	0	0	1788

0	0	56.322	0	0	0	0	0	0	0	56.322

Sr Research Scientist  B/I	0	0	1788	0	0	0	0	0	0	0	1788

0	0	112.644	0	0	0	0	0	0	0	112.644

B/I Total	0	0	5352	0	0	0	0	0	0	0	5352

0	0	256.238	0	0	0	0	0	0	0	256.238

Technician  R	0	0	880	0	0	0	0	0	0	0	880

0	0	31.046	0	0	0	0	0	0	0	31.046

R Total	0	0	880	0	0	0	0	0	0	0	880

0	0	31.046	0	0	0	0	0	0	0	31.046

Total	0	0	6232	0	0	0	0	0	0	0	6232

0	0	287.284	0	0	0	0	0	0	0	287.284

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	16.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	23.840

Page 38 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:24 PM

R Total	0.0	0.0	16.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	23.840

Total	0.0	0.0	16.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	23.840

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	311	0	0	0	0	0	0	0	311

Page 39 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:24 PM

WBS 	3.2.1.1.5.4	Description:	Electrical Engineer(VanBerg)

Institution :	U of Pennsylvania	Contact

Electrical engineer 0.5 FTE(Van berg?)

For work on total system testing of

installed modules- HV, LV and DAQ

emphasis will be on

Final hook of complete faraday sheild

Large scale noise studies

with end cap

with SCT

Operation of electronics in several sectors

for

X-ray alignment studies

$30K/yearDetails of Estimate:

$1.5K for trip ( two trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

146	0	0	146	0	117	0	29	1.0	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	888	0	0	0	0	0	0	0	888

0	0	55.944	0	0	0	0	0	0	0	55.944

B/I Total	0	0	888	0	0	0	0	0	0	0	888

0	0	55.944	0	0	0	0	0	0	0	55.944

Electrical Engineer  R	0	0	880	0	0	0	0	0	0	0	880

0	0	60.984	0	0	0	0	0	0	0	60.984

R Total	0	0	880	0	0	0	0	0	0	0	880

0	0	60.984	0	0	0	0	0	0	0	60.984

Total	0	0	1768	0	0	0	0	0	0	0	1768

0	0	116.928	0	0	0	0	0	0	0	116.928

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	18.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	28.620

R Total	0.0	0.0	18.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	28.620

Total	0.0	0.0	18.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	28.620

Page 40 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:25 PM

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	146	0	0	0	0	0	0	0	146

Page 41 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:25 PM

WBS 	3.2.1.1.5.5	Description:	system electronics  tests

Institution :	Indiana U.	Contact

equipment and support

for multimodujle system tests

supply support Details of Estimate:

for tests $5000

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

7	0	0	7	0	0	0	7	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	5.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	7.450

R Total	0.0	0.0	5.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	7.450

Total	0.0	0.0	5.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	7.450

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	7	0	0	0	0	0	0	0	7

Page 42 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:25 PM

WBS 	3.2.1.1.5.6	Description:	testing equipment

Institution :	U of Pennsylvania	Contact

Testing equipment for completed

module system

medium high end oscilloscope- $11KDetails of Estimate:

1 analog pulser $9K

1 SMT solder/rework station 1k

1 mantis magnifier 1.5K

additional supplies for E. Tech. 2.5k

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

40	0	0	40	0	0	0	40	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	25.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	39.750

R Total	0.0	0.0	25.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	39.750

Total	0.0	0.0	25.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	39.750

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	40	0	0	0	0	0	0	0	40

Page 43 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:26 PM

WBS 	3.2.1.1.5.7	Description:	electronics tech(B. LeGeyt)

Institution :	U of Pennsylvania	Contact	Not available

0.50 FTE electronics tech FY05

Electronics emphasis will be on

Final hook of complete faraday sheild

Large scale noise studies

with end cap

with SCT

Operating and maintaining the electronics

X-ray alignment studies

$30K/yearDetails of Estimate:

$1.5K for trip (three trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

61	0	0	61	0	29	0	32	0.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  R	0	0	880	0	0	0	0	0	0	0	880

0	0	28.829	0	0	0	0	0	0	0	28.829

R Total	0	0	880	0	0	0	0	0	0	0	880

0	0	28.829	0	0	0	0	0	0	0	28.829

Total	0	0	880	0	0	0	0	0	0	0	880

0	0	28.829	0	0	0	0	0	0	0	28.829

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	31.800

R Total	0.0	0.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	31.800

Total	0.0	0.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	31.800

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	61	0	0	0	0	0	0	0	61

Page 44 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:26 PM

WBS 	3.2.1.1.5.8	Description:	Technical support (Russian)

Institution :	Indiana U.	Contact	Not available

assistance with barrel-sct integration and

assembly of barrel in detector

$30000/YEAR Details of Estimate:

2 trips $1500/trip

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

31	0	0	31	0	31	0	0	0.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  R	0	0	880	0	0	0	0	0	0	0	880

0	0	31.046	0	0	0	0	0	0	0	31.046

R Total	0	0	880	0	0	0	0	0	0	0	880

0	0	31.046	0	0	0	0	0	0	0	31.046

Total	0	0	880	0	0	0	0	0	0	0	880

0	0	31.046	0	0	0	0	0	0	0	31.046

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	31	0	0	0	0	0	0	0	31

Page 45 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:27 PM

WBS 	3.2.1.1.8	Description:	ID Integration( 10/05-4/07)

Institution :	Contact	Ogren

verify operation of  during the trasfer

to the detector, checkout  in magnet,

cable, cooling, LV, HV hook up in magnet,

system checkout, system tests, survey

monitor operations until run time.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

2318	0	0	2318	0	2163	0	155	26.7	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Computer Professional  B/I	0	0	0	888	888	0	0	0	0	0	1776

0	0	0	50.35	50.35	0	0	0	0	0	100.700

Faculty  B/I	0	0	4403	6159	888	0	0	0	0	0	11450

0	0	277.389	438.007	72.727	0	0	0	0	0	788.123

Grad Student  B/I	0	0	0	5711	2650	0	0	0	0	0	8361

0	0	0	93.547	43.406	0	0	0	0	0	136.953

Post Doc  B/I	0	0	0	5742	4438	0	0	0	0	0	10180

0	0	0	180.873	139.797	0	0	0	0	0	320.670

Sr Research Scientist  B/I	0	0	0	5742	4438	0	0	0	0	0	10180

0	0	0	328.532	257.418	0	0	0	0	0	585.950

B/I Total	0	0	4403	24242	13302	0	0	0	0	0	41947

0	0	277.389	1091.309	563.698	0	0	0	0	0	1932.396

Computer Professional  R	0	0	0	880	356	0	0	0	0	0	1236

0	0	0	49.896	20.185	0	0	0	0	0	70.081

Electrical Engineer  R	0	0	0	880	0	0	0	0	0	0	880

0	0	0	60.984	0	0	0	0	0	0	60.984

Technician  R	0	0	0	2666	220	0	0	0	0	0	2886

0	0	0	91.839	7.207	0	0	0	0	0	99.046

R Total	0	0	0	4426	576	0	0	0	0	0	5002

0	0	0	202.719	27.392	0	0	0	0	0	230.111

Total	0	0	4403	28668	13878	0	0	0	0	0	46949

0	0	277.389	1294.028	591.09	0	0	0	0	0	2162.507

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	0.0	25.0	0.0	0.0	0.0	0.0	0.0	0.0	38.750

Travel  R	0.0	0.0	0.0	54.0	19.2	0.0	0.0	0.0	0.0	0.0	116.388

R Total	0.0	0.0	0.0	79.0	19.2	0.0	0.0	0.0	0.0	0.0	155.138

Page 46 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:27 PM

Total	0.0	0.0	0.0	79.0	19.2	0.0	0.0	0.0	0.0	0.0	155.138

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	277	1419	622	0	0	0	0	0	2318

Page 47 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:27 PM

WBS 	3.2.1.1.8.1	Description:	Technical support (Duke)

Institution :	Duke University	Contact	Ogren

$30K/yearDetails of Estimate:

$1.5K for trip (two trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

389	0	0	389	0	389	0	0	4.8	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	0	1757	0	0	0	0	0	0	1757

0	0	0	143.898	0	0	0	0	0	0	143.898

Grad Student  B/I	0	0	0	1318	890	0	0	0	0	0	2208

0	0	0	21.589	14.578	0	0	0	0	0	36.167

Post Doc  B/I	0	0	0	1318	890	0	0	0	0	0	2208

0	0	0	41.517	28.035	0	0	0	0	0	69.552

Sr Research Scientist  B/I	0	0	0	1318	890	0	0	0	0	0	2208

0	0	0	83.034	56.07	0	0	0	0	0	139.104

B/I Total	0	0	0	5711	2670	0	0	0	0	0	8381

0	0	0	290.038	98.683	0	0	0	0	0	388.721

Total	0	0	0	5711	2670	0	0	0	0	0	8381

0	0	0	290.038	98.683	0	0	0	0	0	388.721

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	290	99	0	0	0	0	0	389

Page 48 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:28 PM

WBS 	3.2.1.1.8.2	Description:	Computer professional

Institution :	U of Pennsylvania	Contact	Ogren

0.5 FTE computer  professional 06 and 07

verify operation of  during the trasfer

to the detector, of elctronics once installed.

system checkout, system tests,

monitor operations until run time.

$30K/yearDetails of Estimate:

$1.5K for trip (two trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

548	0	0	548	0	507	0	40	6.4	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	1757	1757	0	0	0	0	0	0	3514

0	0	110.691	110.691	0	0	0	0	0	0	221.382

Grad Student  B/I	0	0	0	1318	880	0	0	0	0	0	2198

0	0	0	21.589	14.414	0	0	0	0	0	36.003

Post Doc  B/I	0	0	0	1318	880	0	0	0	0	0	2198

0	0	0	41.517	27.72	0	0	0	0	0	69.237

Sr Research Scientist  B/I	0	0	0	1318	880	0	0	0	0	0	2198

0	0	0	66.427	44.352	0	0	0	0	0	110.779

B/I Total	0	0	1757	5711	2640	0	0	0	0	0	10108

0	0	110.691	240.224	86.486	0	0	0	0	0	437.401

Computer Professional  R	0	0	0	880	356	0	0	0	0	0	1236

0	0	0	49.896	20.185	0	0	0	0	0	70.081

R Total	0	0	0	880	356	0	0	0	0	0	1236

0	0	0	49.896	20.185	0	0	0	0	0	70.081

Total	0	0	1757	6591	2996	0	0	0	0	0	11344

0	0	110.691	290.12	106.671	0	0	0	0	0	507.482

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	18.0	7.2	0.0	0.0	0.0	0.0	0.0	40.068

R Total	0.0	0.0	0.0	18.0	7.2	0.0	0.0	0.0	0.0	0.0	40.068

Total	0.0	0.0	0.0	18.0	7.2	0.0	0.0	0.0	0.0	0.0	40.068

Page 49 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:28 PM

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	111	319	118	0	0	0	0	0	548

Page 50 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:28 PM

WBS 	3.2.1.1.8.3	Description:	electronics tech(B.LeGeyt)

Institution :	U of Pennsylvania	Contact	Ogren

1 FTE electronics technician FY06

0.25 FTE electronics tech FY07

verify operation of  electronics after  the trasfer

to the detector

cable, cooling, LV, HV hook up in magnet,

system checkout, system tests,

monitor operations until run time.

$30K/yearDetails of Estimate:

$1.5K for trip ( two trips FY06,

Three trips FY07

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

521	0	0	521	0	473	0	48	6.4	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	1757	1757	0	0	0	0	0	0	3514

0	0	110.691	110.691	0	0	0	0	0	0	221.382

Grad Student  B/I	0	0	0	1318	880	0	0	0	0	0	2198

0	0	0	21.589	14.414	0	0	0	0	0	36.003

Post Doc  B/I	0	0	0	1318	880	0	0	0	0	0	2198

0	0	0	41.517	27.72	0	0	0	0	0	69.237

Sr Research Scientist  B/I	0	0	0	1318	880	0	0	0	0	0	2198

0	0	0	66.427	44.352	0	0	0	0	0	110.779

B/I Total	0	0	1757	5711	2640	0	0	0	0	0	10108

0	0	110.691	240.224	86.486	0	0	0	0	0	437.401

Technician  R	0	0	0	880	220	0	0	0	0	0	1100

0	0	0	28.829	7.207	0	0	0	0	0	36.036

R Total	0	0	0	880	220	0	0	0	0	0	1100

0	0	0	28.829	7.207	0	0	0	0	0	36.036

Total	0	0	1757	6591	2860	0	0	0	0	0	11208

0	0	110.691	269.053	93.693	0	0	0	0	0	473.437

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	18.0	12.0	0.0	0.0	0.0	0.0	0.0	47.700

R Total	0.0	0.0	0.0	18.0	12.0	0.0	0.0	0.0	0.0	0.0	47.700

Total	0.0	0.0	0.0	18.0	12.0	0.0	0.0	0.0	0.0	0.0	47.700

Page 51 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:29 PM

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	111	298	113	0	0	0	0	0	521

Page 52 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:29 PM

WBS 	3.2.1.1.8.4	Description:	electrical Engineer(VanBerg)

Institution :	U of Pennsylvania	Contact	Ogren

0.5  Electrical Engineer- FY06

Organize and set up operations to verify electronics after the trasfer

to the detector,  such as  cable hookup and testing, cooling,

hook up and checkout of LV, HV hook up in magnet,

system checkout, system tests

monitor operations until run time.

$30K/yearDetails of Estimate:

$1.5K for trip ( two trips)

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

275	0	0	275	0	246	0	29	3.0	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Computer Professional  B/I	0	0	0	888	888	0	0	0	0	0	1776

0	0	0	50.35	50.35	0	0	0	0	0	100.700

Faculty  B/I	0	0	889	0	0	0	0	0	0	0	889

0	0	56.007	0	0	0	0	0	0	0	56.007

Grad Student  B/I	0	0	0	1757	0	0	0	0	0	0	1757

0	0	0	28.78	0	0	0	0	0	0	28.780

B/I Total	0	0	889	2645	888	0	0	0	0	0	4422

0	0	56.007	79.13	50.35	0	0	0	0	0	185.487

Electrical Engineer  R	0	0	0	880	0	0	0	0	0	0	880

0	0	0	60.984	0	0	0	0	0	0	60.984

R Total	0	0	0	880	0	0	0	0	0	0	880

0	0	0	60.984	0	0	0	0	0	0	60.984

Total	0	0	889	3525	888	0	0	0	0	0	5302

0	0	56.007	140.114	50.35	0	0	0	0	0	246.471

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	18.0	0.0	0.0	0.0	0.0	0.0	0.0	28.620

R Total	0.0	0.0	0.0	18.0	0.0	0.0	0.0	0.0	0.0	0.0	28.620

Total	0.0	0.0	0.0	18.0	0.0	0.0	0.0	0.0	0.0	0.0	28.620

Page 53 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:29 PM

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	56	169	50	0	0	0	0	0	275

Page 54 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:29 PM

WBS 	3.2.1.1.8.5	Description:	testing equipment

Institution :	U of Pennsylvania	Contact	Ogren

Testing equipment

for checkout of ID

9U VME Crate $7500Details of Estimate:

2 Single board interface boards $6k

2 Monitor workstaions and Software $3000

2 cosmic ray trigger boards $4000

HV distributor $3.5K

supplies for E tech $1K

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

24	0	0	24	0	0	0	24	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	0.0	15.0	0.0	0.0	0.0	0.0	0.0	0.0	23.850

R Total	0.0	0.0	0.0	15.0	0.0	0.0	0.0	0.0	0.0	0.0	23.850

Total	0.0	0.0	0.0	15.0	0.0	0.0	0.0	0.0	0.0	0.0	23.850

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	24	0	0	0	0	0	0	24

Page 55 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:30 PM

WBS 	3.2.1.1.8.6	Description:	 system tests

Institution :	Indiana U.	Contact	Ogren

Support for system tests

support and supplies forDetails of Estimate:

tests $10000

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

15	0	0	15	0	0	0	15	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	0.0	10.0	0.0	0.0	0.0	0.0	0.0	0.0	14.900

R Total	0.0	0.0	0.0	10.0	0.0	0.0	0.0	0.0	0.0	0.0	14.900

Total	0.0	0.0	0.0	10.0	0.0	0.0	0.0	0.0	0.0	0.0	14.900

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	15	0	0	0	0	0	0	15

Page 56 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:30 PM

WBS 	3.2.1.1.8.7	Description:	technical support (Russian)

Institution :	Indiana U.	Contact	Ogren

1.0 FTE 2006

verify operation of  during the trasfer

to the detector, checkout  in magnet,

cable, cooling, LV, HV hook up in magnet,

system checkout, system tests, survey

monitor operations until run time.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

546	0	0	546	0	546	0	0	6.1	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	0	888	888	0	0	0	0	0	1776

0	0	0	72.727	72.727	0	0	0	0	0	145.454

Post Doc  B/I	0	0	0	1788	1788	0	0	0	0	0	3576

0	0	0	56.322	56.322	0	0	0	0	0	112.644

Sr Research Scientist  B/I	0	0	0	1788	1788	0	0	0	0	0	3576

0	0	0	112.644	112.644	0	0	0	0	0	225.288

B/I Total	0	0	0	4464	4464	0	0	0	0	0	8928

0	0	0	241.693	241.693	0	0	0	0	0	483.386

Technician  R	0	0	0	1786	0	0	0	0	0	0	1786

0	0	0	63.01	0	0	0	0	0	0	63.010

R Total	0	0	0	1786	0	0	0	0	0	0	1786

0	0	0	63.01	0	0	0	0	0	0	63.010

Total	0	0	0	6250	4464	0	0	0	0	0	10714

0	0	0	304.703	241.693	0	0	0	0	0	546.396

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	305	242	0	0	0	0	0	546

Page 57 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:31 PM

WBS 	3.2.1.2	Description:	Operations

Institution :	Contact

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

2201	0	0	2201	0	2058	0	143	42.8	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Grad Student  B/I	0	0	0	4402	5271	5271	5271	5271	5271	5271	36028

0	0	0	72.105	86.34	86.34	86.34	86.34	86.34	86.34	590.145

Post Doc  B/I	0	0	0	3515	3514	3514	3514	3514	3514	3514	24599

0	0	0	110.722	110.691	110.691	110.691	110.691	110.691	110.691	774.868

Sr Research Scientist  B/I	0	0	0	879	870	870	879	879	879	879	6135

0	0	0	55.377	54.81	54.81	55.377	55.377	55.377	55.377	386.505

B/I Total	0	0	0	8796	9655	9655	9664	9664	9664	9664	66762

0	0	0	238.204	251.841	251.841	252.408	252.408	252.408	252.408	1751.518

Computer Professional  R	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

Technician  R	0	0	0	0	1320	1320	1320	1320	1320	1320	7920

0	0	0	0	45.46	45.46	45.46	45.46	45.46	45.46	272.760

R Total	0	0	0	0	1420	1420	1420	1420	1420	1420	8520

0	0	0	0	51.13	51.13	51.13	51.13	51.13	51.13	306.780

Total	0	0	0	8796	11075	11075	11084	11084	11084	11084	75282

0	0	0	238.204	302.971	302.971	303.538	303.538	303.538	303.538	2058.298

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	0.0	15.0	15.0	15.0	15.0	15.0	15.0	143.100

R Total	0.0	0.0	0.0	0.0	15.0	15.0	15.0	15.0	15.0	15.0	143.100

Total	0.0	0.0	0.0	0.0	15.0	15.0	15.0	15.0	15.0	15.0	143.100

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	238	327	327	327	327	327	327	2201

Page 58 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:31 PM

WBS 	3.2.1.2.1	Description:	Runtime activities

Institution :	Contact

M&O Activities during data taking

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

2201	0	0	2201	0	2058	0	143	42.8	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Grad Student  B/I	0	0	0	4402	5271	5271	5271	5271	5271	5271	36028

0	0	0	72.105	86.34	86.34	86.34	86.34	86.34	86.34	590.145

Post Doc  B/I	0	0	0	3515	3514	3514	3514	3514	3514	3514	24599

0	0	0	110.722	110.691	110.691	110.691	110.691	110.691	110.691	774.868

Sr Research Scientist  B/I	0	0	0	879	870	870	879	879	879	879	6135

0	0	0	55.377	54.81	54.81	55.377	55.377	55.377	55.377	386.505

B/I Total	0	0	0	8796	9655	9655	9664	9664	9664	9664	66762

0	0	0	238.204	251.841	251.841	252.408	252.408	252.408	252.408	1751.518

Computer Professional  R	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

Technician  R	0	0	0	0	1320	1320	1320	1320	1320	1320	7920

0	0	0	0	45.46	45.46	45.46	45.46	45.46	45.46	272.760

R Total	0	0	0	0	1420	1420	1420	1420	1420	1420	8520

0	0	0	0	51.13	51.13	51.13	51.13	51.13	51.13	306.780

Total	0	0	0	8796	11075	11075	11084	11084	11084	11084	75282

0	0	0	238.204	302.971	302.971	303.538	303.538	303.538	303.538	2058.298

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	0.0	15.0	15.0	15.0	15.0	15.0	15.0	143.100

R Total	0.0	0.0	0.0	0.0	15.0	15.0	15.0	15.0	15.0	15.0	143.100

Total	0.0	0.0	0.0	0.0	15.0	15.0	15.0	15.0	15.0	15.0	143.100

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	238	327	327	327	327	327	327	2201

Page 59 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:32 PM

WBS 	3.2.1.2.1.1	Description:	technical support (Russian)

Institution :	Indiana U.	Contact

0.50 technician FY07-FY12

This would be a fraction of a TRT russian technician  to

be responsible for the maintensce of the TRT system  during

runtime periods. This woulc include maintenance

of the acvtive gas system and recirculator, the

CO2 flushing gas system, and flourinert cooling

system.

The other half of his time is scheduled under shutdown maintenance

no extra travelDetails of Estimate:

Russian at CERN

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

954	0	0	954	0	954	0	0	16.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Grad Student  B/I	0	0	0	888	1757	1757	1757	1757	1757	1757	11430

0	0	0	14.545	28.78	28.78	28.78	28.78	28.78	28.78	187.225

Post Doc  B/I	0	0	0	879	878	878	878	878	878	878	6147

0	0	0	27.688	27.657	27.657	27.657	27.657	27.657	27.657	193.630

Sr Research Scientist  B/I	0	0	0	879	870	870	879	879	879	879	6135

0	0	0	55.377	54.81	54.81	55.377	55.377	55.377	55.377	386.505

B/I Total	0	0	0	2646	3505	3505	3514	3514	3514	3514	23712

0	0	0	97.61	111.247	111.247	111.814	111.814	111.814	111.814	767.360

Technician  R	0	0	0	0	880	880	880	880	880	880	5280

0	0	0	0	31.046	31.046	31.046	31.046	31.046	31.046	186.276

R Total	0	0	0	0	880	880	880	880	880	880	5280

0	0	0	0	31.046	31.046	31.046	31.046	31.046	31.046	186.276

Total	0	0	0	2646	4385	4385	4394	4394	4394	4394	28992

0	0	0	97.61	142.293	142.293	142.86	142.86	142.86	142.86	953.636

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	98	142	142	143	143	143	143	954

Page 60 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:32 PM

WBS 	3.2.1.2.1.3	Description:	computer professional

Institution :	U of Pennsylvania	Contact

Computer professional to work on DAQ

and Readout interfacing.

a  graduate student and

0.5 FTE  post doctoral physicist

( from the base program) will also

work on bringing up the

DAQ system and maintaniing it.

$60K/yearDetails of Estimate:

$1.5K for trip

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

477	0	0	477	0	429	0	48	10.8	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Grad Student  B/I	0	0	0	1757	1757	1757	1757	1757	1757	1757	12299

0	0	0	28.78	28.78	28.78	28.78	28.78	28.78	28.78	201.460

Post Doc  B/I	0	0	0	879	879	879	879	879	879	879	6153

0	0	0	27.688	27.688	27.688	27.688	27.688	27.688	27.688	193.816

B/I Total	0	0	0	2636	2636	2636	2636	2636	2636	2636	18452

0	0	0	56.468	56.468	56.468	56.468	56.468	56.468	56.468	395.276

Computer Professional  R	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

R Total	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

Total	0	0	0	2636	2736	2736	2736	2736	2736	2736	19052

0	0	0	56.468	62.138	62.138	62.138	62.138	62.138	62.138	429.296

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	0.0	5.0	5.0	5.0	5.0	5.0	5.0	47.700

R Total	0.0	0.0	0.0	0.0	5.0	5.0	5.0	5.0	5.0	5.0	47.700

Total	0.0	0.0	0.0	0.0	5.0	5.0	5.0	5.0	5.0	5.0	47.700

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 61 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:33 PM

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	56	70	70	70	70	70	70	477

Page 62 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:33 PM

WBS 	3.2.1.2.1.4	Description:	electronics technician

Institution :	U of Pennsylvania	Contact

0.25 FTE electronics technician

The work is focused on the electronics

system such as HV supplies, Low voltage supplies

for the front end cards, and assisting  the TRT

engineers on the total DAQ system maintenance.

It is anticipated that this will be a partime position with

special responsibilites for the Barrel TRT during shutdowns.

The remainder of the technicans time when not on the

TRT would be covered by the base program either on TRT or

other programs at the university.

$60K/yearDetails of Estimate:

$2K for trip-5trips

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

771	0	0	771	0	675	0	95	15.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Grad Student  B/I	0	0	0	1757	1757	1757	1757	1757	1757	1757	12299

0	0	0	28.78	28.78	28.78	28.78	28.78	28.78	28.78	201.460

Post Doc  B/I	0	0	0	1757	1757	1757	1757	1757	1757	1757	12299

0	0	0	55.346	55.346	55.346	55.346	55.346	55.346	55.346	387.422

B/I Total	0	0	0	3514	3514	3514	3514	3514	3514	3514	24598

0	0	0	84.126	84.126	84.126	84.126	84.126	84.126	84.126	588.882

Technician  R	0	0	0	0	440	440	440	440	440	440	2640

0	0	0	0	14.414	14.414	14.414	14.414	14.414	14.414	86.484

R Total	0	0	0	0	440	440	440	440	440	440	2640

0	0	0	0	14.414	14.414	14.414	14.414	14.414	14.414	86.484

Total	0	0	0	3514	3954	3954	3954	3954	3954	3954	27238

0	0	0	84.126	98.54	98.54	98.54	98.54	98.54	98.54	675.366

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	0.0	10.0	10.0	10.0	10.0	10.0	10.0	95.400

R Total	0.0	0.0	0.0	0.0	10.0	10.0	10.0	10.0	10.0	10.0	95.400

Total	0.0	0.0	0.0	0.0	10.0	10.0	10.0	10.0	10.0	10.0	95.400

Page 63 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:33 PM

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	84	114	114	114	114	114	114	771

Page 64 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:34 PM

WBS 	3.2.1.2.1.6	Description:	Testing equipment

Institution :	Indiana U.	Contact

previously available

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 65 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:34 PM

WBS 	3.2.1.3	Description:	TRT Maintenance

Institution :	Contact

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

1481	0	0	1481	0	1174	0	308	13.4	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	0	0	0	888	888	888	888	888	4440

0	0	0	0	0	72.727	72.727	72.727	72.727	72.727	363.635

Post Doc  B/I	0	0	0	0	888	888	888	888	888	888	5328

0	0	0	0	27.972	27.972	27.972	27.972	27.972	27.972	167.832

Sr Research Scientist  B/I	0	0	0	0	888	888	888	888	888	888	5328

0	0	0	0	55.944	55.944	55.944	55.944	55.944	55.944	335.664

B/I Total	0	0	0	0	1776	2664	2664	2664	2664	2664	15096

0	0	0	0	83.916	156.643	156.643	156.643	156.643	156.643	867.131

Computer Professional  R	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

Technician  R	0	0	0	0	1320	1320	1320	1320	1320	1320	7920

0	0	0	0	45.46	45.46	45.46	45.46	45.46	45.46	272.760

R Total	0	0	0	0	1420	1420	1420	1420	1420	1420	8520

0	0	0	0	51.13	51.13	51.13	51.13	51.13	51.13	306.780

Total	0	0	0	0	3196	4084	4084	4084	4084	4084	23616

0	0	0	0	135.046	207.773	207.773	207.773	207.773	207.773	1173.911

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	30.0	45.0	15.0	0.0	0.0	0.0	0.0	0.0	113.600

Travel  R	0.0	0.0	0.0	0.0	12.0	22.0	22.0	22.0	22.0	22.0	193.980

R Total	0.0	0.0	30.0	45.0	27.0	22.0	22.0	22.0	22.0	22.0	307.580

Total	0.0	0.0	30.0	45.0	27.0	22.0	22.0	22.0	22.0	22.0	307.580

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	30	60	178	243	243	243	243	243	1481

Page 66 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:34 PM

WBS 	3.2.1.3.1	Description:	 Shutdown maintenance activities

Institution :	Contact

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

1431	0	0	1431	0	1174	0	258	13.4	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	0	0	0	888	888	888	888	888	4440

0	0	0	0	0	72.727	72.727	72.727	72.727	72.727	363.635

Post Doc  B/I	0	0	0	0	888	888	888	888	888	888	5328

0	0	0	0	27.972	27.972	27.972	27.972	27.972	27.972	167.832

Sr Research Scientist  B/I	0	0	0	0	888	888	888	888	888	888	5328

0	0	0	0	55.944	55.944	55.944	55.944	55.944	55.944	335.664

B/I Total	0	0	0	0	1776	2664	2664	2664	2664	2664	15096

0	0	0	0	83.916	156.643	156.643	156.643	156.643	156.643	867.131

Computer Professional  R	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

Technician  R	0	0	0	0	1320	1320	1320	1320	1320	1320	7920

0	0	0	0	45.46	45.46	45.46	45.46	45.46	45.46	272.760

R Total	0	0	0	0	1420	1420	1420	1420	1420	1420	8520

0	0	0	0	51.13	51.13	51.13	51.13	51.13	51.13	306.780

Total	0	0	0	0	3196	4084	4084	4084	4084	4084	23616

0	0	0	0	135.046	207.773	207.773	207.773	207.773	207.773	1173.911

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	0.0	25.0	15.0	0.0	0.0	0.0	0.0	0.0	63.600

Travel  R	0.0	0.0	0.0	0.0	12.0	22.0	22.0	22.0	22.0	22.0	193.980

R Total	0.0	0.0	0.0	25.0	27.0	22.0	22.0	22.0	22.0	22.0	257.580

Total	0.0	0.0	0.0	25.0	27.0	22.0	22.0	22.0	22.0	22.0	257.580

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	40	178	243	243	243	243	243	1431

Page 67 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:35 PM

WBS 	3.2.1.3.1.1	Description:	technical support  (Russian)

Institution :	Indiana U.	Contact

This will be the TRT Barrel

0.5 FTE fraction of a russian technician assigned to the TRT system,

but during shutdowns, would cover the

short time stay of a more expert person from

one of the universities.

Russian at CERNDetails of Estimate:

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

1053	0	0	1053	0	1053	0	0	11.6	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Faculty  B/I	0	0	0	0	0	888	888	888	888	888	4440

0	0	0	0	0	72.727	72.727	72.727	72.727	72.727	363.635

Post Doc  B/I	0	0	0	0	888	888	888	888	888	888	5328

0	0	0	0	27.972	27.972	27.972	27.972	27.972	27.972	167.832

Sr Research Scientist  B/I	0	0	0	0	888	888	888	888	888	888	5328

0	0	0	0	55.944	55.944	55.944	55.944	55.944	55.944	335.664

B/I Total	0	0	0	0	1776	2664	2664	2664	2664	2664	15096

0	0	0	0	83.916	156.643	156.643	156.643	156.643	156.643	867.131

Technician  R	0	0	0	0	880	880	880	880	880	880	5280

0	0	0	0	31.046	31.046	31.046	31.046	31.046	31.046	186.276

R Total	0	0	0	0	880	880	880	880	880	880	5280

0	0	0	0	31.046	31.046	31.046	31.046	31.046	31.046	186.276

Total	0	0	0	0	2656	3544	3544	3544	3544	3544	20376

0	0	0	0	114.962	187.689	187.689	187.689	187.689	187.689	1053.407

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	0	115	188	188	188	188	188	1053

Page 68 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:35 PM

WBS 	3.2.1.3.1.3	Description:	Computer Professional

Institution :	U of Pennsylvania	Contact

0.25 computer professional each year

(assigned for running, also)

This person would be assigned for a total of

1/2 time on the TRT, and would be covered by the

university base program on this program or another reseach

program for the remainder of the time.

This computer professional will foucus on maintaining the

DAQ system for the TRT barrel during shutdown.

Work will include testing modifying data aquisistion units

such as the RODs as welll as the DTMROC interfaces.

In addition to the DAQ this person will maintain the

low controls system and keep it up-to-date.

$60K/yearDetails of Estimate:

$5K for trip 5 trips

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

114	0	0	114	0	34	0	80	0.3	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Computer Professional  R	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

R Total	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

Total	0	0	0	0	100	100	100	100	100	100	600

0	0	0	0	5.67	5.67	5.67	5.67	5.67	5.67	34.020

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	0.0	0.0	10.0	10.0	10.0	10.0	10.0	79.500

R Total	0.0	0.0	0.0	0.0	0.0	10.0	10.0	10.0	10.0	10.0	79.500

Total	0.0	0.0	0.0	0.0	0.0	10.0	10.0	10.0	10.0	10.0	79.500

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 69 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:36 PM

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	0	6	22	22	22	22	22	114

Page 70 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:36 PM

WBS 	3.2.1.3.1.4	Description:	electronics technician

Institution :	U of Pennsylvania	Contact

Electronics technician 0.25 for FY07-FY12

(also assigned to work during run-time)

The TRT Barrel work directly is focused on the electronics

system such as HV supplies, Low voltage supplies

for the front end cards, and working with the TRT

engineers on the total DAQ system maintenance.

It is anticipated that this will be a partime position with

special responsibilites for the Barrel TRT during shutdowns.

The remainder of the technican's time when not on the

TRT would be covered by the base program either on TRT or

other programs at the university.

$30K/yearDetails of Estimate:

$1.5K for trip

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

201	0	0	201	0	86	0	114	1.5	0.0

FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

MANPOWER	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)	(hrs)

(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

SUMMARY:

Technician  R	0	0	0	0	440	440	440	440	440	440	2640

0	0	0	0	14.414	14.414	14.414	14.414	14.414	14.414	86.484

R Total	0	0	0	0	440	440	440	440	440	440	2640

0	0	0	0	14.414	14.414	14.414	14.414	14.414	14.414	86.484

Total	0	0	0	0	440	440	440	440	440	440	2640

0	0	0	0	14.414	14.414	14.414	14.414	14.414	14.414	86.484

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Travel  R	0.0	0.0	0.0	0.0	12.0	12.0	12.0	12.0	12.0	12.0	114.480

R Total	0.0	0.0	0.0	0.0	12.0	12.0	12.0	12.0	12.0	12.0	114.480

Total	0.0	0.0	0.0	0.0	12.0	12.0	12.0	12.0	12.0	12.0	114.480

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 71 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:36 PM

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	0	33	33	33	33	33	33	201

Page 72 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:36 PM

WBS 	3.2.1.3.1.6	Description:	Testing equipment

Institution :	Duke University	Contact

Test equipment for monitoring TRT

1 monitoring computer, electrical test tools- $4kDetails of Estimate:

and supplies  for the mechanical and electrical technicians. $6,000 per year

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

32	0	0	32	0	0	0	32	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	0.0	10.0	10.0	0.0	0.0	0.0	0.0	0.0	31.800

R Total	0.0	0.0	0.0	10.0	10.0	0.0	0.0	0.0	0.0	0.0	31.800

Total	0.0	0.0	0.0	10.0	10.0	0.0	0.0	0.0	0.0	0.0	31.800

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	16	16	0	0	0	0	0	32

Page 73 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:37 PM

WBS 	3.2.1.3.1.7	Description:	Maintenance equipment

Institution :	U of Pennsylvania	Contact

Equipment items needed for

maintenance

US contribution equimentDetails of Estimate:

One additional oscilloscope $15000 FY06

One new data logic tester

$5000 FY07

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

32	0	0	32	0	0	0	32	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	0.0	15.0	5.0	0.0	0.0	0.0	0.0	0.0	31.800

R Total	0.0	0.0	0.0	15.0	5.0	0.0	0.0	0.0	0.0	0.0	31.800

Total	0.0	0.0	0.0	15.0	5.0	0.0	0.0	0.0	0.0	0.0	31.800

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	0	24	8	0	0	0	0	0	32

Page 74 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:37 PM

WBS 	3.2.1.3.2	Description:	spares

Institution :	Contact

Electronics spares due to end-of-life chip buy

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

50	0	0	50	0	0	0	50	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	30.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	50.000

R Total	0.0	0.0	30.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	50.000

Total	0.0	0.0	30.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	50.000

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	30	20	0	0	0	0	0	0	50

Page 75 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:38 PM

WBS 	3.2.1.3.2.4	Description:	circuit board spares

Institution :	U of Pennsylvania	Contact	Not available

electronics spares

Printed circuit board spares for

the Barrel and Endcaps.

Engineering judgementBasis of Estimate:

electronics spares estimatedDetails of Estimate:

costs for boards and cables.

Spare capacitor sets.

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

50	0	0	50	0	0	0	50	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	30.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	50.000

R Total	0.0	0.0	30.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	50.000

Total	0.0	0.0	30.0	20.0	0.0	0.0	0.0	0.0	0.0	0.0	50.000

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	30	20	0	0	0	0	0	0	50

Page 76 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:38 PM

WBS 	3.2.2	Description:	Common TRT/ID

Institution :	Contact	Ogren

U.S. ATLAS % share of 	7.00%

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

1329	0	0	1329	0	0	0	1329	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	44.9	84.6	132.4	248.8	229.7	260.9	197.3	130.5	1329.100

R Total	0.0	0.0	44.9	84.6	132.4	248.8	229.7	260.9	197.3	130.5	1329.100

Total	0.0	0.0	44.9	84.6	132.4	248.8	229.7	260.9	197.3	130.5	1329.100

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	45	85	132	249	230	261	197	131	1329

Page 77 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:38 PM

WBS 	3.2.2.1	Description:	 Pre-Operations

Institution :	Indiana U.	Contact	Ogren

Derived from ATLAS_B_june04.xls, ID sharing agreement (14% Silicon/7% TRT), and US sharing percentage

Engineering judgementBasis of Estimate:

M&O(B)Details of Estimate:

U.S. ATLAS % share of 	7.00%

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 78 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:39 PM

WBS 	3.2.2.2	Description:	Maintenance and operations (IU)

Institution :	Indiana U.	Contact	Ogren

TRT fraction of ID costs

split between TRT, SCT, Pixel

Engineering judgementBasis of Estimate:

M&O(B) and C&I(B) during runningDetails of Estimate:

U.S. ATLAS % share of 	7.00%

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

1329	0	0	1329	0	0	0	1329	0.0	0.0

Total w/

MATERIAL	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	overhead

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

Other  R	0.0	0.0	44.9	84.6	132.4	248.8	229.7	260.9	197.3	130.5	1329.100

R Total	0.0	0.0	44.9	84.6	132.4	248.8	229.7	260.9	197.3	130.5	1329.100

Total	0.0	0.0	44.9	84.6	132.4	248.8	229.7	260.9	197.3	130.5	1329.100

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

PROFILE  	FY 03	FY 04	FY 05	FY 06	FY 07	FY 08	FY 09	FY 10	FY 11	FY 12	Total

SUMMARY:	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)	(k$)

0	0	45	85	132	249	230	261	197	131	1329

Page 79 of 80

U.S. ATLAS M&&O Estimate Cost 	1/23/2005 12:51:39 PM

WBS 	3.2.2.3	Description:	Maintenance and operations (Nevis)

Institution :	Columbia  U.  (Nevis  Laboratory)	Contact	Ogren

TRT fraction of ID costs

split between TRT, SCT, Pixel

M&O(B) and C&I(B) during runningDetails of Estimate:

U.S. ATLAS % share of 	7.00%

Base	Cont	Total	EDIA	Mfg	EDIA	Mfg	FTEs  	FTEs

Cost	Cost	Cost	Cont   	Cost	Labor	Labor	Matls	Matls	All	Other

Summary:	(k$)	(k$)	%   	(k$)	(k$)	(k$)	(k$)	(k$)

(All)

0	0	0	0	0	0	0	0	0.0	0.0

Risk	Weight

CONTINGENCY	Cont %

FACTORS:	Technical	C o s t	Schedule	Des i gn	Technical	C o s t	Schedule

0	0	0	0	0	0	0	0

Page 80 of 80