CMS Milestones

(issue 2.1, 26’th August 1999)

This document lists the milestones used to monitor the construction and

assembly of the CMS experiment.

The milestones give a simplified picture of the principal tasks involved, their sequence and their estimated completion dates, consistent with current planning. Revisions and additions are to be expected as the project evolves, within the constraints imposed by the target date for completing installation of the detector.

For sub-detectors which have not completed an Engineering Design Review, the milestones are provisional and incomplete. In these cases, short-term milestones are given if available.

Milestone Levels:

Level 1 milestones are derived from the overall planning for  CMS assembly.

Level 2 milestones are defined by sub-system managers and represent key benchmarks in sub-detector progress towards the relevant level 1 milestones.

Level 3 milestones are defined by sub-system managers to complement the level 1 and 2 milestones by providing a more detailed breakdown of objectives and a mechanism for intermediate monitoring of major tasks in progress.  Frequent revisions and additions are anticipated as the detailed planning is adapted to reflect growing experience and changing circumstances.

Milestone reporting:

Level 1 : in writing to CMS Steering Committee and LHCC

Level 2 : in writing to CMS Steering Committee and LHCC

Level 3 : verbally to CMS Steering Committee and

to LHCC referees by CMS Technical Coordination

Key to Milestone Listings:

Level-3         - Black Font size 12 ,

Level-2     - Blue Font size 14 , Bold

LEVEL-1  - Red Font size 14, Bold and Capital

Italics - New milestones since last issue

Level 1 Milestones

# Surface Hall (SX5) ready	01/00

Submit Trigger TDR	11/00

Submit DAQ TDR	12/01

### End Assembly of Barrel Yoke	06/01

End Assembly of Endcap Yoke					       01/02

End Assembly of HE (on YE) in SX5				       05/02

End Assembly of HB in SX5					       07/02

Underground Hall (UX5) Ready	01/03

#### End Assembly of Coil	02/03

Slide Coil into Vac-tank	04/03

#### End Trial Insertion of HB in Vac Tank	07/03

End Trial Mounting of EB Super Module on HB	08/03

Start Cool-down of Coil	08/03

Close Yoke, and Start Magnet Test in SX5	09/03

### Start Lowering Magnet Parts into UX 5 	01/04

#### End Installation and Test of HB in UX5	05/04

End Cabling and Test of HE in UX5	07/04

### End Installation, Testing and Debugging of EB in UX5	10/04

### End Installation, Test & Debug. of EE & Preshower in UX5	5/05

Transport Tracker to SX5	12/04

### End Installation of MB Stations in Yoke Wheels in UX5	03/05

#### End Installation of ME Stations in YE in UX5	03/05

End Installation and Test of Tracker in UX5	06/05

End Installation and Test of  HF in UX5	06/05

Magnet Milestones

Extrude 150  m of 36 strand Insert	11/98

Engineering Design Review	12/98

C: Definition of ultrasonic scanning system	01/99

EC: Launch tender for external cryogenics	02/99

C: Write the conductor specification	03/99

Place order for Electron Beam Welding Line	03/99

E: Write the winding specification	04/99

W: Launch tender for winding	04/99

E: Engineer the swivelling system	06/99

E: Write Control and Safety system UR	06/99

C: Award contract for wire	06/99

E: Preparation of junction test station	07/99

EC: Contract for external cryogenics	07/99

E: Engineer the thermal screen	07/99

C: Award contract for pure Al	08/99

E: Write swivelling tool specification	09/99

E: Write specification for discharge resistors	09/99

E: Write specification for power supply	09/99

E: Write thermal screen specification	09/99

C: Award contract Al Alloy	09/99

C: Award contract for cabling	09/99

M: Finish prelim. design of control and power supply	10/99

Award contract for winding	10/99

C: Procure and extrude 200m of 32 strand insert (final strands)	11/99

C: Award contract for co-extrusion	11/99

End of Engineering Phase	11/99

Major contracts for conductor placed	11/99

M: Technical specification and tender of Control System	03/00

Delivery of 1 km conductor demonstration length	07/00

End of construction of winding line	08/00

W: Commission winding machine	09/00

#### End Assembly of yoke ring YB-2	10/00

End Assembly of YB-1	12/00

Prototype impregnated in industry	02/01

#### W: Winding prototype finished	02/01

End Assembly of YB-0	03/01

End Assembly of YB+1	05/01

End Assembly of YB+2	06/01

End Assembly of YE-3	05/01

End Assembly of YE-2	06/01

END ASSEMBLY OF BARREL YOKE	06/01

EC: Begin installation of external cryogenics on the surface	07/01

1st coil module wound in industry	07/01

End Assembly of YE-1	08/01

#### A: Install coil assembly platform	09/01

End Assembly of YE+3	10/01

End Assembly of YE+2	11/01

#### W: 2nd module wound	11/01

#### Install coil module –2 on assembly platform 			          01/02

End Assembly of YE+1	01/02

END ASSEMBLY OF ENDCAP YOKE	01/02

3rd coil module wound in industry	03/02

Assemble coil modules (-2 and  -1) at CERN	04/02

M: End procurement of magnet control and power supply	06/02

Start test of cryoplant in SX5	06/02

#### A: Adapt Ferris wheel for swivelling	06/02

#### W: 4th module wound	07/02

Assemble 3rd coil module (0) at CERN			         08/02

End of 5th coil module winding in industry	11/02

M: Commission magnet control and power supply 	12/02

#### A: Assemble coil module+1	01/03

End coil module assembly (+2) at CERN	02/03

END ASSEMBLY OF COIL	02/03

#### A: Swivelling	04/03

#### A: Enter coil in the outer vactank	04/03

#### A: Swivel inner vactank shell	05/03

#### A: Enter inner vactank shell	06/03

SLIDE COIL into VAC-TANK END	06/03

M: Test of magnet control and power supply on surface 	07/03

#### A: Vacuum test of the vactank	07/03

END COOLDOWN of COIL	09/03

CLOSE YOKE & START MAGNET TEST in SX5	09/03

START LOWERING MAGNET PARTS into UX5	01/04

End lowering magnet parts into UX5	04/04

E – Engineering, C-Conductor, W-Winding, A-Assembly, EC-External Cryogenics, M-Magnet Control and Power Supply

Tracker Milestones

Detector

Pixels

Prototype Design Runs of Readout Chip	up to 10/99

Define Control and Interface Block of Readout Chip	08/99

Full-size Readout Chip - submissions	02/00,10/00

Pixel Sensor Arrays – submissions	12/98, 12/99

Final-size Sensors - Submission	01/01

Final Full-size Readout Chip submission	02/01

### Micropattern/Si

SI: Final Sensor Design	11/99

Prototype 0 modules	11/99

Mechanics: cylinder + disk	11/99

Verification of Industrial Production of MSGCs	08/99

End Test of above MSGCs in PSI Beam	11/99

Full-scale Prototypes of Barrel and Endcap Mechanics	11/99

Review & Decision on technologies and layout		12/99

Engineering Design Review of Sensors			02/00

Define construction milestones up to 2005			03/00

Tracking System Test in an LHC-like Beam			05/00

Begin sensor module construction					10/00

Note: In preparation for the 12/99 review a full set of level 2 and level 3 milestones exists for the current baseline tracker. A similar set will be

prepared for the alternative “all-silicon” design.

Electronics

Deliver Front-end Chips for Prototype Construction	02/99

Intermediate System Review	07/99

Irradiation Studies of Candidate Technologies	07/99

Tender for Front-end Electronics & Optical Links	11/99

Final Pre-Production Review	01/00

Define construction milestones	03/00

TRANSPORT TRACKER TO SX5	12/04

END INSTALLATION and TEST	06/05

ECAL Milestones

Choice of APD	06/98

#### Multiple 28-fold Crystal Pulling Furnace in China	12/98

1000 Crystals produce by BTCP (Russia)

and lab. tested	06/99

Mechanical Engineering Design Review (Barrel)	07/99

EDR follow-up (EB)	 09/99

500 Electronics Channels Test	12/99

Module 0 (400 channels) prototype complete	12/99

250 SE sensors from Russia	12/99

Choice of VPT 	12/99

1000 Crystals produced in China and lab tested	03/00

1’st Module produced at Rome regional centre	04/00

ECAL  front end electronics production launched	04/00

Supermodule 1 completed	06/00

Mechanical Engineering Design Review (Endcap)	06/00

Preshower Pre-production 50/100 Si Detectors	07/00

Preshower (SE) Engineering Design Review	10/00

Preliminary evaluation of supermodule 1 complete	11/00

EB supermodule active storage area ready	12/00

50/100 SE detectors from each production centre	12/00

Preshower PACE front-end design finished	06/00

15,000 EB crystals delivered & tested	01/01

30,000 APD’s delivered	02/01

Supermodule 1 calibration and testing ends	08/01

Preshower : 500 front-end chips delivered	12/01

EE regional centre (CERN) ready	12/01

8000 VPT’s delivered	12/01

30,000 EB crystals delivered & tested	01/02

60,000 APD’s delivered	02/02

9 supermodules calibrated*	05/02

Half-barrel (18 supermodules) calibrated*	9/02

1st Endcap Dee produced and calibrated	9/02

45,000 EB crystals delivered & tested	01/03

8,000 EE crystals delivered & tested	03/03

All VPT’s delivered	06/03

END TEST of MOUNTING of

EB SUPERMODULE 1 ON HB	08/03

27 super-modules calibrated	08/03

Endcap Dee 2 produced (and calibrated)	11/03 (5/04)

Start EB underground installation	02/04

1’st preshower endcap completed	02/04

All APD’s delivered	02/04

16,000 EE crystals delivered & tested	04/04

ECAL  front-end electronics production complete	05/04

Full Barrel (36 Supermodules) calibrated	06/04

Endcap Dee 3 and 4 produced & calibrated	9/04

END INSTALLATION, TESTING

and DEBUGGING of EB 	10/04

End Installation, Testing and Debugging

EE+1,Preshower +1	11/04

2’nd preshower endcap completed	02/05

END INSTALLATION, TESTING

and DEBUGGING of EE and PRESHOWER 	05/05

* calibration dependent on availability of beam.

HCAL Milestones

Barrel (HB)

HB: PPP1 absorber delivered to CERN	10/98

HB: Mechanical Engineering Design Review	11/98

HB: Start optics production	01/99

HB: PPP2 absorber delivered to CERN	04/99

HB: Start readout box production                       	09/99

HB: Start absorber production                            	10/99

HB: Start HPD procurement                               	10/99

HB & HE: End Beam Test of PPP	10/99

HB EDR_3 (tooling & follow-up)	10/99

HB-1 optical assemblies 50% complete	12/99

HB-1 optical assemblies 100% complete	07/00

HB- HPD’s at FNAL	09/00

HB-1 barrel cradle complete	10/00

HB: Start optics installation in absorber	11/00

HB-1 absorber delivered to CERN	11/00

QIE ASIC production run 1	04/01

HB+1 optical assemblies 50% complete	05/01

End Front-end Electronics Production 	06/01

HB- readout boxes delivered to CERN	07/01

HB: Start readout box installation on absorber           	08/01

HB+1 HPD’s at FNAL	08/01

HB-1 optics installation complete	10/01

HB+1 barrel cradle complete	10/01

QIE ASIC production run 2	10/01

HB+1 absorber delivered to CERN	12/01

HB+1 optical assemblies 100% complete	12/01

HB: End electronics installation in readout boxes 	01/02

HB: End optics installation in absorber 	06/02

HB: End readout box installation on absorber 	06/02

HB-1 End assembly in SX5 	07/02

HB+1 End assembly in SX5 	07/02

HB: END ASSEMBLY IN SX5	07/02

HB: TRIAL INSERTION IN VACTANK	07/03

HB+1 Lower into UX5	02/04

HB-1 Lower into UX5	03/04

HB: End Installation in Solenoid in UX5	03/04

HB: 1’st layer scintillator installation complete	04/04

HB: END INSTALLATION & TESTS IN UX5	05/04

Outer Barrel (HO)

HO Engineering Design Review	06/99

HO: End Test Beam Study 	08/99

HO: Start optics production	10/99

#### HO: optics production complete				       10/01

HO: Start HPD procurement	06/01

HO: Start readout box production	10/01

HO: HPD’s delivered to FNAL	05/02

HO: Start optics installation on YB 	05/03

HO Optics Installation on YB completed	06/03

HO: Start readout box installation on YB 	11/03

HO: End electronics installation in readout boxes 	12/03

HO: End readout box installation on YB 	01/05

HO End Installation and Tests in UX5	04/05

Endcap (HE)

HE: PPP1 absorber delivered to CERN	10/98

###### HE Mechanical EDR	09/99

HE: End Beam Test of PPP	10/99

HE: Start optics pre-production	10/99

HE: Start absorber production                             	01/00

HE: Start optics bulk production	02/00

HE: Start HPD procurement 	04/00

HE: Start readout box production 	07/00

HE HPD’s delivered to FNAL	04/01

HE : optics production complete	07/01

HE-1 absorber delivered to CERN	07/01

HE: start assembling HE absorber/optics on endcap yokes	09/01

HE+1 absorber delivered to CERN	10/01

HE: Start readout/source box installation on absorber 	11/01

HE-1 absorber assembly complete 	12/01

HE-1  optics installation in absorber complete	01/02

HE: End electronics installation in readout boxes 	02/02

HE: End readout box installation on absorber 	05/02

HE+1 absorber assembly complete	05/02

HE: End optics installation in absorber 	06/02

HE: End readout box installation on absorber 	06/02

HE: END ASSEMBLY in SX5	03/03

HE: END INSTALLATION and TEST in UX5	7/04

Forward (HF)

HF-PPP absorber delivered to CERN                      	07/99

#### HF Engineering design workshop					10/99

#### HF Engineering Design Review complete           	10/00

### HF define intermediate manufacturing milestones			11/00

(all subsequent milestones are provisional and subject to redefinition after the EDR)

HF absorber production start                            		01/01

HF: Define Fibre Diameter     		01/01

HF- Support Frame Comp.                            		03/01

HF readout box production start                         		04/01

HF optics (fiber) procurement start                     		05/01

HF+ Support Frame Comp.                            		08/01

HF: Q1 and Q2 absorber delivered to CERN			10/01

HF PMT procurement start                                		10/01

HF optics (fiber) installation in absorber start        		11/01

HF: Q3 and Q4 absorber delivered to CERN			01/02

HF: Q5 and Q6 absorber delivered to CERN			12/02

HF: Q7 and Q8 absorber delivered to CERN			01/03

HF electronics installation in readout boxes complete        	09/03

HF readout box installation start                       		12/03

HF optics (fiber) installation in absorber complete     		02/04

HF readout box installation complete                    		05/04

HF: End Assembly in SX5                             		02/05

HF: END INSTALLATION & TESTS in UX5		06/05

PPP - Pre-Production Prototype

Muon System Milestones

#### Barrel Drift Tubes

DT Engineering Design Review	11/98

Review of Final Assembly Tooling Drawings 	12/98

1st Assembly Line Set up in CIEMAT 	06/99

Production of  Superlayer prototypes finished	10/99

Follow-up MB EDR, Planning for DTs and RPCs	07/99

Final Review of assembly and chambers	07/99

E: Begin Production of HV Boards	07/99

1’st Assembly line set-up at Legnaro	08/99

E: Begin production of FE and FE Boards	09/99

Set up 1st line at Aachen	12/99

Begin mass production	01/00

1’st Assembly line set-up at Torino	07/00

10% of chambers assembled	01/01

ISR active storage area ready	12/00

Start mass active storage at CERN	03/01

35% of chambers assembled	01/02

60% of chambers assembled	01/03

85% of chambers assembled	01/04

Chamber assembly complete	08/04

½ chambers installed in yoke (SX5)	07/03

END MB INSTALLATION IN YOKE (UX5)	03/05

Cathode Strip Chambers (ME1/1)

###### End Beam Tests of Full-size Prototype (P4)	10/98

###### Engineering Design Review	07/99

#### Begin Material procurement						  	    09/99

#### Begin panel manufacture							    01/00

#### Begin CSC assembly							  06/01

#### 15 chambers delivered to CERN						   09/02

#### 30 chambers	delivered to CERN						   03/03

45 chambers delivered to CERN						   09/03

One ME1/1 endcap installed in yoke (SX) 					   03/04

60 chambers delivered to CERN						   03/04

ALL chambers delivered to CERN					 09/04

END INSTALLATION of ME1/1 in YE+/YE-                     03/05

Cathode Strip Chambers (All except ME1/1)

Engineering Design Review	12/98

Begin Mass Production of CSC parts (Panels) 	04/99

EDR_2 follow-up	07/99

Delivery of pre-production ASICs for anode front-end	08/99

Delivery of  pre-production ASICs for cathode front-end	09/99

Check panel production rate	09/99

Begin Assembly of CSCs at FNAL	10/99

Pre-production ASICs ready	11/99

Begin Mass Production of Electronics Boards	08/00

Begin mounting electronics and testing at UCLA/UF	09/00

Begin CSC Assembly at PNPI/St. Petersburg

and IHEP/Beijing	01/01

40 ME1/2,3 Chambers assembled(+electrs) and tested at IHEP	12/01

20 ME2,3/1 Chambers assembled(+electrs)  and tested at PNPI	12/01

24 ME2,3/1 Chambers assembled(+electrs)  and tested at UF	12/01

24 ME2,3/1 Chambers assembled(+electrs)  and tested at UC	12/01

88 ME1/2,3 Chambers assembled(+electrs) and tested at IHEP	12/02

46 ME2,3/1 Chambers assembled(+electrs)  and tested at PNPI	12/02

56 ME2,3/1 Chambers assembled(+electrs)  and tested at UF	12/02

56 ME2,3/1 Chambers assembled(+electrs)  and tested at UC	12/02

50% of the chambers installed (SX)	07/03

All Large Chambers assembled and tested	10/03

148ME1/2,3 Chambers assembled(+electrs) and tested at IHEP	12/03

76 ME2,3/1 Chambers assembled(+electrs)  and tested at PNPI	12/03

All Chambers Installed	03/04

END INSTALLATION of ME STATIONS

IN YE IN UX5	03/05

Total no. of chambers: (ME1/1,2,3 = 72), (ME2,3/1 = 36), (ME2,3,4/2 = 276)

Resistive Plate Chambers

### Barrel

Produce Full-size Barrel Chamber Prototype	05/99

RPC EDR (bakelite plates and barrel mounting)	06/99

Begin Mass Production of the bakelite plates	08/99

Begin single gap production	10/99

Chamber mass production start  (after EDR  follow-up)	06/00

50% of chambers complete	12/01

ALL chambers complete	06/03

### Endcap

Produce Full-size Chamber						  07/99

Fix Design Parameters	12/99

Begin Mass Production of Bakelite plates	01/00

Pre-series Chambers produced	06/00

(Define further milestones once the manufacturing responsibilities are clarified)

### Common

End Irradiation Tests	03/99

Electronics–FE Boards final prototype submission	07/99

Electronics System Review	12/00

### Alignment

ALMY Prototype Test report					   06/99

Minimal Barrel Test (6 cameras)	10/99

Electronics Prototype	12/99

Begin full-scale test in the ISR tunnel	12/99

ALMY  technology selection	04/00

Alignment EDR	06/00

Define manufacturing milestones	07/00

Software and Computing Milestones

Hardware Milestones:

a) Regional Centres

- Identify initial candidates          	06/00

- Turn on functional centres           	12/02

- Fully operational centres            	06/05

b) Central Systems

- Functional prototype                 	12/02

- Turn on initial systems              	12/03

- Fully operational system             	06/05

Software Milestones:

a) Core Software                          	Proof of  Funct.  Fully   Prod.

concept   proto.  funct.  syst

- End of FORTRAN development        06/98

- GEANT4 simulation of CMS            	 06/98     12/99   06/01   12/03

- Reconstruction/analysis framework  06/98     12/99   12/01   12/03

- Detector reconstruction             	 12/98     12/99   06/02   06/04

- Physics object reconstruction        	 03/99     06/00   12/02   12/04

- User analysis environment            	 12/98     06/00   12/02   12/04

b) Database

- Use of ODBMS for testbeam            	  12/97

- Evt storage/retrieval from ODBMS   06/98     12/99   12/01   12/03

- Data organisation/access strategy   	  12/98

- Filling ODBMS at 100MB/s             	  06/99

- Simulation of data access patterns    12/00

- Integration of ODBMS and MSS       12/00

- Choice of vendor of ODBMS              12/01

- Installation of ODBMS and MSS      12/02

Trigger Milestones

Complete Initial Muon, Calorimeter and

Global (M/C/G) Trigger Design			11/98

RPC: Preliminary review of the Readout Board design	      		06/99

(conceptual) (Warsaw)

RPC: Preliminary review of the Trigger Crate design		      		06/99

(conceptual) (Warsaw)

CSC: Sector Receiver Initial System Design Document (UCLA)    		03/99

TK: Sector Processor Initial System Design Document (Florida)		03/99

DT : TSM ASIC 1st prototype (Bologna)				        		09/99

CSC: Muon Port Card Prototype Design (Rice)					05/99

GLOBAL: PSB prototype production and electronic tests			06/99

finished (Vienna)

CSC: Muon Port Card Prototype Delivery (Rice)				09/99

CSC: Sector Receiver Prototype Design (UCLA)				09/99

TK: Sector Processor Prototype Design (Florida)				09/99

RPC: Interim review of the Trigger Board design		      		11/99

(barrel+endcap) (Warsaw)

RPC: Interim review of the TTC+Sorter Board design				11/99

(barrel+endcap) (Warsaw)

TK: Interim Design Review (Vienna)			11/99

CAL: Review of test of Trigger Primitives System 2-towers 			11/99

prototype board.

Review of test with ECAL readout boards. (Lisbon, Palaiseau)

CAL: Review of tests of Regional Trigger Prototype Boards			11/99

and ASICs  (Wisconsin)

CAL: Review of calorimeter trigger control and readout software		11/99

Review of calorimeter trigger control and readout prototypes

(Lisbon)

CAL: Review of integration of the calorimeter trigger prototypes		11/99

(Palaiseau, Lisbon, Helsinki, Wisconsin)

CAL: Design of final Sort ASIC							11/99

Demonstrate link technologies to Regional Cal Trigger

and Global Trigger (Bristol)

GLOBAL: PSB prototype functional tests finished				11/99

GTL prototype design and production Ended (except GmuT)

GTF prototype design Ended (Vienna)

Complete Phase 1 Prototype Design			11/99

Technical Design Report – First Draft 			05/00

#### Technical Design Report			11/00

(EDR date and construction schedule to be agreed after TDR)

DAQ Milestones

Readout Unit prototype 2 designed 		05/99

Event Builder Prototype 1 complete		05/99

Readout Unit prototype 2 complete		11/99

Filter Unit Prototype 1		11/99

Vertical DAQ chain prototype 		11/99

High Level Trigger prototype 1		11/99

CMS specs for SCADA (controls) tender agreed 		12/99

Technologies choice preparation: scale 1:N DAQ		05/00

Full DAQ prototype tests		11/00

Technical Design Report first draft		05/01

Technical Design Report		11/01

( EDR date and construction schedule to be agreed after TDR)