Lesson Info

- Lesson Number: 	FPPD-LL-0051

- Lesson Date: 	11-Jan-2001

- Submitting Organization: GSFC (543)

- Submitted by: 	Daniel Helfrich

Subject/Title/Topic(s):

Landsat Solar Array Deployment Testing

Description of Driving Event:

The Landsat 7 (L7) solar array (S/A) is an assembly of four rigid aluminum honeycomb panels and an aluminum yoke with a total length of 8.5 m (335 in). The g-negation deployment ground support equipment (GSE) included: 1.) a deployment surface, which in the beginning, at least, was a poured epoxy floor, 2.) four solar array supports stands, each on a set of four air pads, for a total of 16 air pads, and 3.) a solar array mounting interface simulator mounted on a three-axis positioner.  When GSE problems arose during deployment qualification tests, what originally was a test effort planned for 6 months became twice that in duration.

Testing of the GSE with solar array mockups in the second half of CY1997 gave the first indications that the GSE was not 100% ready. Some simple adjustments were attempted at that time. The first full deployment of the S/A assembly on 6 Nov 97—a manual operation before its installation on the spacecraft—showed problems with the uneven epoxy floor and the square air pads. GSE repairs were made, and on 28 Apr 98, the first electrically-initiated deployment including the firing of live cable cutters was attempted. The S/A released only partially due to inadequate extraction of some of the restraint cables. Improper cable pre-load was later found to be a root cause, along with a lack of control of friction in the device. Subsequent manual deployment attempts demonstrated the epoxy floor was still a problem.

Lesson(s) Learned:

The preload of the restraint cable was a critical element of the design that was not fully appreciated nor documented. Minor design modifications and seemingly trivial discrepancies in key dimensions of the restraint system parts caused the unnoticed loss of preload in the initial test. Direct measurement of the preload through the use of load washers or from strain-gaged hardware elements is essential when the system preload is critical such as with a solar array release/restraint system.

Judicious testing of deployable devices early in satellite development is a cost effective tactic of developing complex and critical mechanism subsystems. The mechanism function is often independent of the primary operational function of the subsystem, allowing testing of the mechanism function using low cost mockups representing only the properties relevant to test objectives. These mockups often allow additional cost savings in handling environments. Subtle details in the implementation of the design of the deployable--and in the GSE with which it is tested--often lead to unexpected results in the initial functional tests of the mechanism, and often only the test itself is revealing. If the choice had been made to defer the Landsat 7 S/A deployment test until later in the flow, shipment could have easily been shifted out in time, ultimately leading to a slipped launch date and severe cost impacts.

Using a rigid granite deployment surface (even if it is comprised of several large granite blocks with seams) beats a cheap epoxy floor.  Precision honeycomb panels supported precisely can also provide superior performance. Elevated surfaces are easier to clean and stay cleaner.

Recommendation(s):

Load washers or strain-gages can be a very helpful element for assurance of cable preload when this is a critical element of a restraint/release system. Don’t rely on nut torque alone when preload is critical, as it often is.

Test g-negation GSE ahead of time, and even so, be ready for problems, especially when taking a new approach or implementing modifications to a proven approach. Don’t ignore or brush off seemingly minor checkout issues with GSE unless there is more than enough time to correct unforeseen problems when it’s used with the flight hardware for the first time. For GSE checked out far in advance, make adequate plans to fully protect the GSE while it’s in storage.

When testing large deployable devices on air pads, be sure the pads are round, the air flow is strong, and the air supply tubing is flexible yet strong.  Also be sure that the table is flat and level within acceptable tolerances that depend primarily on the available torque of the deployment hinges.

Evidence of Recurrence Control Effectiveness:

With many issues from the April deployment test failure resolved, on 24 Aug 98, the S/A was successfully deployed off the spacecraft with only minor issues found with the restraint system. A third pyrotechnic deployment on 8 Dec 98 was completely nominal, and on 15 Apr 99, the S/A deployed perfectly on-orbit.

Applicable NASA Enterprise(s):

Earth Science

Human Exploration and Development of Space

Space Science

Applicable Crosscutting Process(es):

Provide Aerospace Prods & Capabilities: Implementation

Additional Key Phrase(s):

Facilities

Ground Equipment

Test Facility

Test & Verification

Can this lesson be included in the International Safety Lessons Learned (ISLL) Database? 	No

Submitted by:			Daniel Helfrich

Mail Stop/Code:		GSFC 543

Lesson Author (if different):

Phone Number:		301-286-8481

E-Mail Address:	helfrich@gsfc.nasa.gov

Lesson Date:			01 / 11 / 2001