# MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief – March 15-19, 2004

Date:		March 19, 2004

Highlights:

During the FEL Upgrade commissioning activities this week the following kept us very busy: 
(1) during the optimization of the FEL performance using our 2.7% outcoupling optic we achieved both a new power output record (2.25 kW CW and 3 kW pulsed at 6 microns) and a new record for the power of the circulating laser beam in the optical cavity (84kW). This latter value is very close to the stored circulating power we need to demonstrate (100 kW) when we outcouple 10 kW with final outcouplers.  (2) Our low loss 6 micron  (8%) outcoupling optics that was installed last week was found to be free of distortion but unfortunately was cut to the wrong radius of curvature (14.5m vs 16m ) by the manufacturer.  (It is being returned for regrinding and recoating with a promised return to us in ~3 weeks).  (3) The octupole magnets that were installed in the 2nd recirculation arc last weekend worked extremely well.  After tuning the energy recovery phase and the extraction dump bend, we were, by exciting the octupoles and using sextupoles in two families to manage path length and nonlinear dispersion, able to recover and compress the full beam energy spread (over 8%, perhaps as much as 10%) generated when lasing quite strongly, even when backing up the sharp end of the detuning curve at high currents.

The power supply currents required in all elements is low enough (1.6 A sextupoles, 5.5 A octupoles, at ~90 MeV) that operation at energies provided by three modules (>140 MeV)is quite likely possible with the presently installed magnets and power supplies.  (4) We completed the initial commissioning of the 3rd cryomodule; all 8 cavities perform at specifications above what is needed delivering a total energy gain of > 85 MeV; (5) we had a successful final design review for the "Laser Microengineering Station" that will be delivered to the FEL User Labs next year by the Aerospace Corporation as a key component for the AFRL funded UV FEL Upgrade program. (6) Today we held a design review for the permanent magnet wiggler, 2 weeks ahead of schedule and approved the manufacturing drawings for release.

Commissioning Summary (by D.Douglas):

1.	Monday, we touched up the linac-to-recirculator match using a WesCam  based quad scan, providing reasonably good beam quality through the system. Results were consistent with those obtained from a cursory multimonitor measurement down the linac and indicate the "balanced gradient" injector configuration is yielding quite good emittances of order 15 mm-mrad horizontal and 10 mm-mrad vertical.

2.	Dependence of momentum spread in injector was checked as a function of buncher gradient. At recent gradient operating points of 3.4 MV/m, the injected momentum spread was of order 100 keV; this leads to ~1% full dp/p after acceleration, indicating an injected full bunch length of ~8 psec. The bunch length at the wiggler for this setpoint is and has been for some time around 750 fsec FWHM. If the accelerator is compressing the injected beam properly, this is just about exactly what is to be expected. As observed for some time, the beam momentum spread is (charge independently) an asymmetric function of linac phase - the quoted 1% is at the operating point of 10 degrees off crest, while at -10 degrees off crest, it grows to ~2%

If the buncher gradient is reduced to ~3 MV/m, the injected momentum spread drops to 50 keV. One would then anticipate the bunch length at injection would grow, but that it would, as a consequence of the smaller momentum spread, decrease after compression to 400 fsec FWHM or so.  HOWEVER, we observe that the final momentum spread DECREASES to 2/3% to 3/4% or so (indicating that the injected bunch length has fallen to 6 psec full), and the bunch length after compression INCREASES to 1 psec FWHM. Morever, the factor of 2 asymmetry in final momentum spread around crest persists.

As noted previously, various compression checks (compressing using energy slew from all cavities, single modules, and single cavities) have failed to isolate any cause for either the longish bunch or the asymmetry. On Thursday, we therefore performed an "anticavity" check on the first module, in which compression was performed by the whole linac, but with individual cavities turned off in sequence. Data is undergoing evaluation, and the tests will be extended to the 2nd module during operation today. We found, during the tests, that turning off the third cavity in the first module ("#6" - the third seen by the beam) reduced the bunch length from 1 psec to 750 fsec. Turning off the first cavity ("#8") reduced it from 1 psec to 850 fsec. It was not possible to turn of the 2nd cavity ("#7"). Yes, you read it right. The module WOULD NOT RUN without power to the 2nd cavity. It crashed to filaments when the cavity was off. If individual cavities were powered up, it crashed to filaments when the third cavity (#6) was powered up. We (well, okay, Richard Walker) found that it could be run with power on with a zero gradient setpoint. In this condition, the measured gradient was ~1.7 MV/m, unless the gradient set points of the adjacent cavities were zeroed, in which case the measured gradient reduced to 0.4 MV/m. With all cavities but the second at nominal gradient and the second at zero gradient set, we found the Happek device gave, at one point, a totally unphysical, antisymmetric bunch length scan and the BPM system said the energy was drifting around, even though the beam exhibited little or no motion on either the  2F08 synchrotron light monitor or the Happek viewer.  Hmm. Very weird, right? But these weird results probably provide the clues we need to solve this bunch length mystery.

Thursday was further subsumed with difference orbit measurements (delayed by 21/2 hrs due to an unauthorized cable movement!). Preliminary review of a bit of the data suggests this particularly mind numbing activity may have actually proven useful, inasmuch as the early reaction to the data suggests the machine is reasonable well decoupled. "Well", you ask, "why not? Didn't you claim you decoupled the machine six months ago?”. Yes, we did.

And we have no reason to believe the skew quad at the front end of the linac, which corrects the skew quad RF field in the HOM couplers of the first 4 cavities, has suddenly decided to get three times stronger. However, when the "balanced gradient" injector was set up, Steve Benson attempted to alleviate obvious H/V coupling in the beam not only by adjusting the single injector skew, but by using the 1st linac skew as well. It is, after all, BEFORE injection, is it not? He found that a reduction of the first skew quad in the linac by about 70% in strength (from 99 g to 29 g gradient integral) would give nice, upright spots through the system. So we've run this way, deciding to eat the orbit coupling that this change should produce.

Except that it DIDN'T PRODUCE orbit coupling - the orbit is fairly well decoupled, despite the fact the quad was set, some time back, by decoupling the orbits. Enquiring minds want to know: "what changed" - either the magnet did, or something in RF did. Given the above whiney discussion about the RF in the front of the 1st module, the reader may hazard a guess as to this author's opinion.

Investigation of this mystery continues. It is rumored a castle full of French knights has both the Holy Grail and a piece of the True Cross. We will journey to this site as soon as the swallows (either European or African) bring us new coconuts.

3.	Suspicious that we were recovering too close to trough, and thereby creating a noncompressed high energy tail at the dump, egged on Monday by the encouragement of one Mr. Benson, we increased the extraction buss excitation and  backed the energy recovery phase away from trough,  raising the energy of the exhaust beam and bending the highest energy components harder around the corner into the dump. The exhaust energy went up to about 9.7 MeV (injection buss = 9.2 MeV/c = 10600 g-cm, extraction buss now at

11200 g-cm) - so the energy recovery is "incomplete" to the tune of 1/2 kW/mA overall, or about 30 W/cavity/mA additional forward power consumption - well within the available klystron output and probably smaller than you would measure if you weren't either really interested or being really anal. This configuration moves the high energy tail of the beam fully into the trough (rather than drooping across it) so that there is "leverage" for the RF waveform to compress it. This also provides better coupling to the momentum compaction, which was immediately seized upon, during high power FEL operation, as an opportunity to use the recently installed octupoles. With the core beam compressing more completely into the dump, the tails were treated to a healthy does of octupolar field - modifying the lattice and linac longitudinal torsion and alleviating beam loss after energy recovery while lasing strongly.

As a consequence of the dump resteer/path-length-linac recovery rephase/octupole activation (or perhaps only purely coincidentally, though the machine DOES trip off if you fiddle the octupoles too far away from their set point - for example, if you turn them off, and Alex Dragt always used to say that "a little octupole is a good thing"), it became possible to run high current while lasing quite hard. Thus for example, Photonmeister Benson could generate 3 kW of light during 5 mA in 1 msec long trains of pulsed beam at 60 Hz whilst surviving both RF and FEL turnon transients; similarly he could back UP the steep side of the FEL detuning curve running high CW current - a stunt that worked in the Demo only on very, very good days of operation. The reader is referred to statements by knowledgeable parties for the details.

Management:

We held the final design review on March 18th for the Laser Microfabrication Station that is being designed and fabricated by the Aerospace Corporation.  This station will be a very versatile laser microengineering device that will be installed approximately 1 year from now in User Lab 4 to take advantage of the output of the UV FEL Upgrade.  Its capabilities are unparalleled in the micro machining world with the ability to microengineer 3D components with write speeds of 400 mm/sec over a field of 0.5m.  We congratulate Henry Helvajian and his team at Aerospace for a very successful review, which completes the final milestone of this phase of the Aerospace subcontract. 

On Friday March 19th, we held a design review by teleconference with the engineering team at STI, Inc. that is designing and building the short wavelength, permanent magnet wiggler for the IR Upgrade. The review was successful and the release of drawings for manufacturing was granted. 

On Wednesday, March 17th we conducted a tour and briefing for a delegation from Hawaii that is interested in the economic development aspects of a facility much like JLab's FEL facility. 

On March 16-17, SURA hosted a workshop on the applications of terahertz radiation attended by a mixture of industry, government and university representatives.

WBS 4 (Injector):

After the fourth re-cesiation performed early Wednesday morning on the January 27 cathode, the DC Photocathode Gun delivered up to 4.8 mA of CW beam for high power lasing operations that set a new FEL power record.  The total charge delivered by the cathode at the end of the day was about 40 Coulombs.  After the re-cesiation the cathode QE increased from 0.5 to 3%.

The Gun HVPS will be modified to run both drive stacks under voltage control, when there are several days available to make the changes and test the new configuration disconnected from the Gun.

WBS 6 (RF)

All RF systems are operating normally, except for cavity 2-7 which trips the zone back to Filaments when it is turned off.  The obvious masks were turned on, but to no avail.  This problem is being pursued today.

The commissioning of the FL03 cryomodule is making good progress.  High RF power has been run into all cavities to measure the maximum gradient available, the various Q's, and the GMES probe calibration factors.  Tasks for today and next week include:  checking the HOM filters in the RF Control Module, installing the Y Heater cables, operating the RF under EPICS control, checking the cavity piezoelectric tuners for turn-on control, and running the zone at gradient for 8 continuous hours for stability and tuner tracking tests. The results from all 8 cavities are as follows:

Cavity        Max Gradient, MV/m        Qo e+9 @12MV/m

1		17.1				8.2

2		15.0				6.4

3		17.1				8.2

4		17.1				8.1

5		12.0				7.0

6		15.1				6.4

7		15.0				7.9

8		15.3				7.4

Total		  123.7 MV/m

Cavity Length		 0.7 m

Max Accel.	      86.6 MeV    (Note :new RF Control Modules will be required to control this maximum available acceleration.)

WBS 8 (Instrumentation):

Much of this week was spent in support of operations while the Air Force design review was in session.  Another week brings another "fresh" idea from Michelle and George on an XPM (eXtreme Power Monitor) for the FEL. This one is designed to fit into the same 4" holder as the wasted CaFl (near) Brewster window pickoff. We're mounting a grid of 100 micron Tungsten wires on 1mm centers as another try on a high power pickoff.  If we burn up this one at least it will look pretty cool (HOT) before it goes... 
   Final connections to the Octupole magnets and power supplies were completed, Dave seems, well, pleased... 
   Effort continued on the design of the Pre-Amp chassis. This solves the problem of sharing the Stanford Research pre-amp between the two bunch length instruments. Continued fabrication of the 6th Stepper Motor chassis. We're looking into raising the output of the mirror heater chassis to increase the available ROC control. The new DC-DC converters are in for the third cryomodule piezo tuners. These convert 0 to 12 volts to 0 to 200 volts (2.5mAmp) and are less than one cubic inch in size. These PCB's are in the cue to be designed and laid out. Several new color cameras have been built for various systems monitoring applications in the FEL. Preparation for reinstallation of new SF6 pump system has begun. Additional video links were installed in the Output Coupler region. 
   Update on the Enterprise Linux Kernel: Red Hat has seemingly changed some of the kernel source code that is the foundation of the memory operations for this pci driver. The problem has been associated with the now inability to perform memory copies equal to those of Red Hat 9. A test program has been written to exploit this memory problem to prove that it was not due to an error by the coder. Red Hat support is going to be contacted to find the fix for the kernel. Anthony Cuffe is going to help setup an account with the proper group to talk to at Red Hat. Until Red Hat comes up with a solution, we will run Red Hat 9 as a secondary kernel on the new machine. This will also provide a safe rollback along with the continued testing and operation of the framegrabber. 
   Configuration Control Database - A major update to the configuration control database (https://laser.jlab.org) has been posted. The majority of the changes made will not be immediately evident (aside from the obvious formatting changes), however, the required internal programming changes have been implemented to allow for a seamless integration of FEL system status [high-level(WBS) and low-level (component) status], equipment servicing and preventive maintenance, item history, data archiving and operations scheduling as well as the usual flogs. Currently, the workstations in the FEL control room are running a 'very-old' build of UNIX and are not capable of running the system. This situation is being remedied by the computer center.

WBS 9 (Beam Transport):

Sextupole Lite Re-coiling to obtain higher field 
•	The drawings for the recoiling of the Sextupole Lites with 50% more turns are being  checked. 
Octupole (OT) 
•	The magnets were installed last weekend. I believe it was wise to fund their manufacture early in the fiscal year as we did. (See the report from Operations for this week) 
Wiggler 
Electromagnetic Wiggler for 2.8µ 
•	Process Equipment Company (PECo) was successful in having their water jet cutter subcontractor make two of the Type A conductors (one of 6 style variations of conductor) using water jet cutting. This effort is part of a separate prototyping effort to get a jump on problems. The parts came out beautifully and their concerns that the 8 foot pieces may be difficult to handle were laid to rest. 
•	They will now start water jet cutting the actual insulator sheets next week since that have material. They prototyped earlier. 
•	They started machining the core pieces. 
•	They are tack brazing the cooling tubes to the prototype cooling plates today in anticipation of proving out the full brazing by the brazing subcontractor over the weekend or early next week. 
•	Their comments today were: “For a project that started out (as tenuous) as just a series of sketches, it looks like we can complete it as anticipated. There don’t seem to be any showstoppers. Both the brazing subcontractor and the water jet subcontractor are very enthusiastic about this project and are being a great help” 
•	We obtained bids for making the ancillary parts in two batches by local vendors. The order for one batch, the manifolds, was placed. 
•	In the design area, we are down to the parts that make the wiggler mate well with the existing wiggler strong back and generating the final assembly from the 3-D model. 
•	The shop is welding up a sample junction on the new beam chamber for the 2.8 Micron Wigglers before they weld the final assembly. All the full tube parts are ready for welding. 
 Sextupole (SF) 
•	Procurement on hold pending 10 kW efforts

WBS 10 (Wiggler):
STI Optronics continues to make excellent progress on the new permanent magnet wiggler.  We had the mechanical design review today. This is two weeks before the deadline originally agreed to.  No serious issues were found.  The design looks simple, robust and well thought out.  The approval for the first progress payment was made this week as well.  The detailed end magnet design was completed this week and parts are being ordered.  The effective number of periods is 30.6 according to B2E.  Calculations by STI Optronics show a shorter length but they use a different ideal model than we do.   The bottom line is that the wiggler is about a long as one can get for the number of poles used.

WBS 11 (Optics):

Plan A is to obtain low loss 6 um optics.
  
2 figured Si mirrors that will be used for HRs were sent to the vendor that produced a very low (200 ppm) HR coating.  More OC mirror substrates, using the lowest loss material available, are at the vendor for fabrication.
 
Our three Plan B's had the following progress:
 
Scraper outcoupler:  The first article was brazed Thursday evening, and sent to the vendor for final machining.  It will return early next week for polishing, the final brazing of the cooling tubes, and then coating.  George Biallas reported: "Cooling tubes and their standoffs are made and in assembly. Don Bullard made a mock–up of the scraper piece that he will use next week to prove out the “rolling’ of the flex for cooling that are in the chamber beneath the beam line. These are the features that allow the scraper to withdraw from the beam-line, allowing lasing at shorter wavelengths to continue."

Cryomirror:
A holder that would thermally isolate a 3" mirror in a 4" holder was designed and is in fab.  This will be pressed into service if need be.  
 
George Biallas had this report:
The major parts for the flexible mirror mount and its hose assemblies continue in fabrication. The parts that will allow cryo cooling of the existing mirrors within the OC Can are done. 
•	A mock up part that resembles the membrane-like .015 thick tube that is the heart of the flexible mirror mount design was made by wire Electro Discharge Machining. The brittle molybdenum shattered far too easily to be a reliable part. However, the parallel manufacture of a niobium substitute by deep drawing is going well. The part was made, but has .002" wrinkles on part of the surface. We will work on eliminating the wrinkles for a short time more, but they may be OK as is.
•	The work on the cryo cooling liquid flow advanced. Two methods are being pursued in parallel, Dewar pressurization and pumped. Consulting the charts for nitrogen at cryogenic temperatures shows that flows of 0.09 GPM of liquid nitrogen would remove the 50 watts anticipated without boiling. Initial look at the state of flow indicates it is between laminar and turbulent through the mirror cooling assembly. Calculations continue to make this aspect more clear. 
•	The pressurization of a Dewar of liquid nitrogen to supply fluid is simple. It may drift up in temperature to the high 80’s K during pressurization and the flow is lost. The pumped circulation loop system would maintain the 77 K but is more complicated. We have received the circulation system’s pump and it is being modified for cryo service. We are ordering valves and working on the transfer lines for both systems.

2.8 micron mirrors:  In fabrication.  We expect mirror holders to mount them in from the vendor in about a week.

Other activities:  As mentioned in the commissioning summary, when we failed to lase after achieving gain ~ 3X the outcoupling, we used part of a swing shift to do some in situ checks of the ROC with the OCMMS.  Measurements showed an ROC of 14.5 m, deviating substantially from the 16.0m spec., despite the manufacturer’s certification. A reanalysis of the ROC determination of the test plate images turned up a flaw in the calculation we used during our in-coming QA inspection, which resulted in almost perfect agreement with the in situ determination.  The optics have been returned to the fabricating subcontractor, who promises quick turnaround, then they will be recoated and returned to us.  We returned to our old standby, the OC with low (~ 2.7%), and lased at sufficiently high power to calibrate our various laser power probes.  Agreement was within 10% (at worst) for all three.  We also had an IR camera that imaged one of the power probe surfaces, which gave us a sense of the beam size as a function of lasing.  When we ran higher amounts of power (> 1.5 kW), we noted a slight decreasing in beam size, consistent with the predicted thermal lensing.  After this excursion we saw patterns consistent with the pickoff window cleaving, so we withdrew it and continued lasing, achieving 2.25 kW at 5.7-5.8 um.  The new version of the diagnostic beam dump worked as advertised, with much faster response than the prototype, but it was still a bit slow to optimize the laser with.  Today we connected the 4 RTDs that are embedded in the wall of the dump, these should give us the response (and position information) we want.  We discovered the pickoff window had cleaved.  Our suspicion is that we had missteered to the point that we hit one of the stainless steel mounts, and that heated the optic unequally, causing sufficient stress that it made the optic cleave.  We temporarily removed the PSD (position sensitive detectors) in the OCMMS and replaced them with cameras, so we can follow the evolution (and position) of the return reflection over a larger range.

We cleaned the cavity optics in the drive laser.  It still has lower output than desired, so more work will need to be done.

Terahertz Project:

Shipments of beamline material continued to arrive.  This week both Jefferson Lab and Advanced Energy Systems participated in a THz applications symposium in Washington, DC, sponsored by the Southeastern Universities Research Association (SURA), the company that manages Jefferson Lab.  The meeting provided an opportunity to meet many of the people involved with THz remote sensing, and to make them aware of our facility and our source development work.  Several collaborations were discussed including with DARPA.