## Sheet1
STANDARD AMS SYSTEM MILESTONES |  |  | Applicability Legend: F= Full Scale Development C= Commercial Off The Shelf N= Non-Development Items |  | WBS MAPPING AND DECISION AUTHORITY
Milestone | Milestone Description | Level | AMS Phase | Applicability | WBS Description | Decision Authority
S1 | Readiness for concept and requirements definition decision - The enterprise architecture roadmaps prioritize and describe capability shortfalls and opportunities for the FAA. All investment opportunities that enter the AMS lifecycle must be in response to a priority service need found in an enterprise architecture roadmap. | 1 | Mission analysis | F,C,N | WBS 1 Mission Analysis All activities associated with data collection, analysis, and concept exploration and development required to satisfy existing and emerging demand for services. | Joint Resources Council approves the enterprise architecture including its roadmaps. The Vice President (ATO) or Director (non-ATO) makes the readiness for concept and requirements definition decision once all entrance criteria are satisfied.
S2 | Preliminary program requirements (pPR) approved - Preliminary program requirements are developed during concept and requirements definition and recorded in Attachment 1 to the Exhibit 300 program baseline (XPB). Program requirements are revised during initial investment analysis and finalized during final investment analysis. | 3 | Mission Analysis | F,C,N | WBS 1.5 Initial Requirements Definition All activities associated with translating information in the MNS into an initial requirements document (iRD), consistent with the operational concept. This includes research and development activities required to evaluate and develop initial requirements. It also includes the Requirements Correlation Matrix and the Mission Need Correlation Matrix. | Vice Presidents (ATO) or Directors (non-ATO) of the implementing and operating service organizations.
S3 | Plan for initial investment decision analysis approved - Plan approval occurs before the readiness for investment analysis decision. It defines what will be done during initial investment analysis and the participating organizations. | 3 | Initial investment analysis | F,C,N | 2.1.1 : Initial Investment Decision - Planning All activities associated with forming an investment analysis team, developing an investment analysis plan, identifying what metrics are affected by the planned investment, and coordinating the planned activities. | Vice Presidents (ATO) or Directors (non-ATO) of the service organization with the mission need and the operating service organization approve the plan for initial investment analysis after obtaining concurrence from the ATO senior vice president for finance.
S4 | Readiness for investment analysis decision - This decision occurs after completion of concept and requirements definition. It verifies that preliminary requirements are well-defined and identifies the preliminary alternatives that will be evaluated during initial investment analysis. | 1 | Readiness for investment analysis decision | F,C,N | None | Chief Operating Officer (ATO) or Associate or Assistant Administrator (non-ATO).
S5 | Exhibit 300 program baseline attachment 1 program requirements update approved - Program requirements are revised to reflect the results of initial investment analysis. | 3 | Initial investment analysis | F,C,N | None | Vice Presidents (ATO) or Directors (non-ATO) of the service organization with the mission need and the operating service organization(s).
S6 | Preliminary Exhibit 300 program baseline attachment 2: business case analysis report (BCAR) approved - The investment analysis team prepares the preliminary BCAR during initial investment analysis. This report defines the investment alternatives and quantifies the costs and benefits associated with each. | 3 | Initial investment analysis | F,C,N | WBS 2.1.2 : Initial Investment Decision - Analysis All activities associated with data collection, industry day activities, market surveys, and modeling to support quantitative and qualitative analyses of the activities identified in the investment analysis plan. This includes the technical, operational, lifecycle cost, benefits, risk, and return on investment analysis of the alternatives. For each alternative, human factors, safety, security, architecture, and affordability assessments will also be performed where appropriate. It also includes activities such as business case development for the preferred alternative and coordination of the analysis and findings with the sponsor, JRC members, and stakeholder organizations. | Vice President (ATO) or Director (non-ATO) of the service organization with the mission need.
S7 | Preliminary Exhibit 300 program baseline approved - Preliminary baseline is developed before the initial investment decision. The preliminary baseline includes the performance, alternatives analysis, Enterprise Architecture, and President's Management Agenda sections. | 3 | Initial investment analysis | F,C,N | WBS 2.1.3 : Initial Investment Decision - Documentation All activities associated with completing initial investment analysis which includes the following documents: JRC briefing package, updated iRD, initial acquisition program baseline (XPB), initial acquisition strategy, and the initial investment analysis report (with exit criteria) for the final Investment decision. | Acquisition Executive, Chief Operating Officer (ATO) or Associate or Assistant Administrator (non-ATO) of the line of business, Chief Financial Officer, Chief Information Officer, ATO Senior Vice President for finance.
S8 | Plan for final investment analysis approved - The investment analysis plan defines the actions, resources, schedules, roles and responsibilities, documentation, and exit criteria for final investment analysis. The plan includes any risk-reduction effort that may be necessary such as modeling, analysis, simulation, or research. | 3 | Initial investment analysis | F,C,N | WBS 2.2.1 : Final Investment Decision - Planning All activities associated with forming an investment analysis team, developing an investment analysis plan, and coordinating the planned activities. | Vice President (ATO) or Director (non-ATO) of the service organization with the mission need.
S9 | Initial investment decision - The JRC selects a solution for implementation at the initial investment decision and authorizes entry into final investment analysis for detailed planning and development of the XPB. The decision document is the preliminary XPB, including attachment 1 (preliminary program requirements) and Attachment 2 (business case analysis report). | 1 | Initial investment analysis | F,C,N | WBS 2.1.3 : Initial Investment Decision - Documentation All activities associated with completing initial investment analysis which includes the following documents: JRC briefing package, updated iRD, initial acquisition program baseline (APB), initial acquisition strategy, and the initial investment analysis report (with exit criteria) for the final Investment decision. | Joint Resources Council
S10 | System contract specification approved - The specification is approved before issuing the final screening information request. | 3 | Final investment analysis | F,N | WBS 2.2.2 : Final Investment Decision - Analysis All activities associated with conducting detailed technical, operational, lifecycle costs, benefits, risk, and return on investment analyses to finalize he XPB of the preferred alternative. Human factors, safety, security, architecture, and affordability assessments will also be performed as required. This also includes activities like the business case for the proposed acquisition, coordination of the analysis, findings, and final XPB with the sponsor, JRC members, and stakeholder organizations prior to contract award. This also includes activities related to preparing requests for information, requests for offer, and evaluating proposals from industry, academia, and other government laboratories. | Service team leader
S11 | Screening information request (SIR) released - There are three types of SIRs: qualification information which qualifies vendors for inclusion on the qualified vendors list; screening information which requests information from vendors to support a down-selection process (can be used iteratively); and request for offer (RFO) which requests binding offers from vendors (takes the place of the RFP). SIRs are developed and released during final investment analysis. Vendor responses are a basis for cost and schedule baselines in the XPB. | 3 | Final investment analysis | F,C,N | WBS 2.2.2 : Final Investment Decision - Analysis All activities associated with conducting detailed technical, operational, lifecycle costs, benefits, risk, and return on investment analyses to finalize he XPB of the preferred alternative. Human factors, safety, security, architecture, and affordability assessments will also be performed as required. This also includes activities like the business case for the proposed acquisition, coordination of the analysis, findings, and final XPB with the sponsor, JRC members, and stakeholder organizations prior to Contract Award. This also includes activities related to preparing requests for information, requests for offer, and evaluating proposals from industry, academia, and other government laboratories. | Service team leader
S12 | Operational capability demonstration (OCD) completed - Before a production contract award or decision to procure COTS or NDI, the investment analysis team may choose to evaluate a vendor's COTS hardware/software or an entire NDI subsystem to ensure it can meet specified functional and performance requirements. An OCD may occur during concept and requirements definition or initial investment analysis as part of the search solutions to mission need or as part of the source evaluation process during final investment analysis. | 2 | Concept and requirements definition and / or initial or final investment analysis | C,N | None | Service team leader
S13 | In-service review (ISR) checklist completed: The ISR process begins early in final investment analysis. It is initiated by a meeting between the ATO-S in-service review staff and cognizant service team members. | 3 | Final investment analysis | F,C,N | None | Service team leader
S14 | Exhibit 300 program baseline attachment 1 program requirements final approval - Final approved program requirements are required for the final investment decision. | 3 | Final investment analysis | F,C,N | 2.2.3 : Final Investment Decision - Documentation All activities associated with completing the final investment decision which includes the following documents: JRC briefing package, revalidated MNS, final requirements document, final XPB, final acquisition strategy, final integrated program plan (with risk management plan), and the final investment analysis report. | Vice Presidents (ATO) or Directors (non-ATO) of the service organization with the mission need and the operating service organization(s).
S15 | Exhibit 300 program baseline attachment 2 BCAR final approval - Revised BCAR is required for the final investment decision. The final BCAR reflects final costs, benefits, schedule, and performance for the alternative selected for implementation. | 3 | Final investment analysis | F,C,N | 2.2.3 : Final Investment Decision - Documentation All activities associated with completing the final investment decision which includes the following documents: JRC briefing package, revalidated MNS, final requirements document, final XPB, final acquisition strategy, final integrated program plan (with risk management plan), and the final investment analysis report. | Vice Presidents (ATO) or Director (non-ATO) of the service organization with the mission need
S16 | Exhibit 300 program baseline, attachment 3 - implementation strategy and planning (ISP) approval - The ISP defines the overall planning by which the service team will execute an investment program during solution implementation and support fielded products during in-service management Part 1 is a strategic overview of the service team's technical, management, procurement, and lifecycle management approach. Part 2 provides detailed actions that will be implemented for the phase approved for implementation by the Joint Resources Council at the final investment decision. For those investment programs designated for Independent Operational Testing & Evaluation (IOT&E), IOT&E planning is incorporated into the ISP. ATO-S identifies programs which are to receive IOT&E, and develops and co-approves the IOT&E section of the ISP. | 3 | Final investment analysis | F,C,N | WBS 2.2.3 : Final Investment Decision - Documentation All activities associated with completing the final investment decision which includes the following documents: JRC briefing package, revalidated MNS, final requirements document, final APB, final acquisition strategy, final integrated program plan (with risk management plan), and the final investment analysis report. | Vice Presidents (ATO) or Directors (non-ATO) of the service organization with the mission need and the operating service organization(s).
S17 | Final Exhibit 300 Program Baseline completed - The XPB establishes the performance, cost, schedule and benefits boundaries for implementing an investment program. The investment analysis team develops the XPB during final investment analysis for the solution selected for implementation at the initial investment decision. The service team that will implement the investment program develops cost and schedule baselines. | 3 | Final investment analysis | F,C,N | WBS 2.2.3 : Final Investment Decision - Documentation All activities associated with completing the final investment decision which includes the following documents: JRC briefing package, revalidated MNS, final requirements document, final APB, final acquisition strategy, final integrated program plan (with risk management plan), and the final investment analysis report. | Acquisition Executive, Chief Operating Officer (ATO) or Associate or Assistant Administrator (non-ATO) of the line of business, Chief Financial Officer, Chief Information Officer, ATO Senior Vice President for finance.
S18 | Final investment decision - The JRC approves and baselines an investment program at the final investment decision. The decision document is the XPB and its planning attachments | 1 | Final investment analysis | F,C,N | WBS 2.2.3 : Final Investment Decision - Documentation All activities associated with completing the final investment decision which includes the following documents: JRC briefing package, revalidated MNS, final requirements document, final XPB, final acquisition strategy, final integrated program plan (with risk management plan), and the final investment analysis report. | Joint Resources Council
S19 | Integrated baseline review completed - The IBR conduct is complete and the service team and leader agree on action items. | 2 | Solution implementation | F,C,N | WBS 3.1.1 : Solution Implementation - Program Planning, Authorization, Management and Control All activities associated with developing the strategy for implementing and executing the overall program. All activities associated with planning, authorizing, and managing all actions and activities that must be accomplished for successful program development, which includes preparation of the acquisition strategy paper and the integrated program plan, and the project-specific input to agency-level planning documents, such as the call for estimates and the NAS architecture. It also includes all activities required to ensure that all cost, schedule, performance, and benefit objectives are met. | Service team leader
S20 | Contract award - This event occurs when the contract is signed by the contracting officer. For a new investment program, contract award occurs early in solution implementation soon after the final investment decision. | 2 | Solution implementation | F,C,N | WBS 3.1.2 : Contract and Grant Management All activities associated with awarding, issuing, modifying, monitoring, and managing project-related contracts, grants, partnerships, cooperative research and development agreements, interagency agreements, foreign partnerships, memoranda of understanding, and memoranda of agreements. | Source selection officer
S21 | Systems requirements review (SRR) completed - The SRR occurs when the service team meets with the contractor design team to clarify functional, performance, test, and interface requirements, as contained in the contract and specification. The SRR is complete when the service team determines that action items resulting from the review are sufficiently completed. | 3 | Solution implementation | F,C,N | WBS 3.2.2 : Solution Development - System Requirements and Definition All activities associated with transforming the performance requirements of a final requirements document into specifications and a preferred solution configuration. This system engineering effort, which is applicable to each component of the solution throughout the program lifecycle, includes developing and maintaining design criteria, and preparing and maintaining system-level data flows, block diagrams, change proposals, and documentation trees. It includes the following activities: | Service team leader
S22 | System design review (SDR) completed - This review is conducted when the design definition effort has proceeded to the point where system characteristics are defined and configuration items are identified. The focus of the SDR is to evaluate the optimization, traceability, correlation, completeness, and risk of the system-level design to fulfill system functional baseline requirements. The service team determines when this review is complete. | 3 | Solution implementation | F,N | WBS 3.2.3 : Solution Development - Analysis, Design, and Integration All activities associated with the overall analysis, design, test, and integration of the solution, (e.g., hardware system, software, facility, and telecommunications ). This includes design, integrity, test and analysis, intra- and inter-system compatibility assurance (interface identification, analysis, and design), and the integration and balancing of reliability, maintainability, producibility, safety, and survivability. Design includes allocating functions to appropriate elements (e.g., hardware, software, telecommunications, user functions, services, facilities, etc.), and presenting prepared design information at identified design reviews. | Service team leader
S23 | System specification review (SSR) completed - The SSR is a formal review of configuration item requirements as specified in the hardware and software requirements specification. Its purpose is to establish the allocated baseline for preliminary design by demonstrating the adequacy of hardware and software requirements specification. The SSR is complete when the service team determines that action items resulting from the review are sufficiently completed. | 3 | Solution implementation | F,N | WBS 3.2.3 : Solution Development - Analysis, Design, and Integration All activities associated with the overall analysis, design, test, and integration of the solution, (e.g., hardware system, software, facility, and telecommunications ). This includes design, integrity, test and analysis, intra- and inter-system compatibility assurance (interface identification, analysis, and design), and the integration and balancing of reliability, maintainability, producibility, safety, and survivability. Design includes allocating functions to appropriate elements (e.g., hardware, software, telecommunications, user functions, services, facilities, etc.), and presenting prepared design information at identified design reviews. | Service team leader
S24 | Preliminary design review (PDR) completed - PDR is conducted by the service team to determine conformity of functional characteristics of the design to baseline requirements. The PDR represents approval to begin detailed design. The PDR is complete when the service team determines that action items resulting from the review are sufficiently completed and the contracting officer authorizes the contractor to proceed. | 2 | Solution implementation | F,N | WBS 3.2.3 : Solution Development - Analysis, Design, and Integration All activities associated with the overall analysis, design, test, and integration of the solution, (e.g., hardware system, software, facility, and telecommunications ). This includes design, integrity, test and analysis, intra- and inter-system compatibility assurance (interface identification, analysis, and design), and the integration and balancing of reliability, maintainability, producibility, safety, and survivability. Design includes allocating functions to appropriate elements (e.g., hardware, software, telecommunications, user functions, services, facilities, etc.), and presenting prepared design information at identified design reviews. | The service team leader
S25 | Critical design review (CDR) completed - CDR is the service team's evaluation of contractor product design. It is conducted for each HWCI and CSCI when all engineering drawings are complete. This is the last major review before authorization to fabricate a first article. For CSCIs, the CDR is conducted before coding and informal software testing. For large, complex systems, it may be a progressive or incremental review that culminates in a system-level CDR. The CDR is complete when the service team determines the action items resulting from the review are sufficiently completed. | 2 | Solution implementation | F,N | WBS 3.2.3 : Solution Development - Analysis, Design, and Integration All activities associated with the overall analysis, design, test, and integration of the solution, (e.g., hardware system, software, facility, and telecommunications ). This includes design, integrity, test and analysis, intra- and inter-system compatibility assurance (interface identification, analysis, and design), and the integration and balancing of reliability, maintainability, producibility, safety, and survivability. Design includes allocating functions to appropriate elements (e.g., hardware, software, telecommunications, user functions, services, facilities, etc.), and presenting prepared design information at identified design reviews. | Service team leader
S26 | Product demonstration decision - This decision occurs after completion of critical design review. Decision criteria are: engineering drawings are complete, system design and functionality satisfy customer requirements, key product characteristics are defined, system design reviews are complete, RMA goals and planning are complete, failure modes and effects analysis is complete, critical manufacturing processes are identified, and stakeholders agree that design is complete and producible. | 1 | Solution implementation | F,C,N | None | Vice president (ATO) or director (non-ATO) of the implementing service organization
S27 | Provisioning technical documentation delivered - This occurs when provisioning documents are delivered to the FAA by the contractor and accepted in final form. | 3 | Solution implementation | F,C,N | WBS 3.2.5 : Solution Development - Supportability, Maintainability, and Reliability Engineering All engineering activities and analyses undertaken during solution development as part of the engineering and design effort, to assist in complying with supportability and other logistics support objectives. All activities associated with supportability analyses to identify how to most cost effectively support the system over its entire life cycle. | Service team leader
S28 | System delivered to test and evaluation site - In most cases, this will be the William J. Hughes Technical Center. This occurs when the equipment, spares, test equipment, and software physically arrive at the test site. | 2 | Solution implementation | F,C,N | WBS 3.5.1 : System Development Test and Evaluation All activities associated with contractor conducted testing (e.g., factory acceptance testing) performed during the system development process to verify the new system is operating properly in order to achieve government acceptance. These are conducted to demonstrate that all engineering design and development activities are complete, and that the system will meet specifications, security certification, and authorization criteria. Development test and evaluation includes contractor and in-house activities associated with this effort, e.g., software validation and verification, and system and software access controls. It includes all support activities (e.g., technical assistance, maintenance, labor, material, support elements and testing spares, etc.) required during this phase of testing are included. It also includes the development and construction of those special test facilities, test simulators, test beds, and models required to perform developmental tests in order to verify the design and reliability of the system or subsystem. | Service team leader
S29 | Test readiness review (TRR) completed - The TRR is a multi-disciplined technical review to ensure the subsystem or system under review is ready to proceed into system-level developmental test. The TRR determines the completeness of test procedures and their compliance with test plans and descriptions. | 3 | Solution implementation | F,C,N | WBS 3.5.1 : System Development Test and Evaluation All activities associated with contractor conducted testing (e.g., factory acceptance testing) performed during the system development process to verify the new system is operating properly in order to achieve government acceptance. These are conducted to demonstrate that all engineering design and development activities are complete, and that the system will meet specifications, security certification, and authorization criteria. Development test and evaluation includes contractor and in-house activities associated with this effort, e.g., software validation and verification, and system and software access controls. It includes all support activities (e.g., technical assistance, maintenance, labor, material, support elements and testing spares, etc.) required during this phase of testing are included. It also includes the development and construction of those special test facilities, test simulators, test beds, and models required to perform developmental tests in order to verify the design and reliability of the system or subsystem. | Service team leader
S30 | Development test and evaluation completed (DT&E) - DT&E ensures the fielding of an effective and supportable system. This formal testing is performed by the contractor and witnessed by the FAA at the test and evaluation site. It is normally done at the William J. Hughes Technical Center where the product can be interfaced to other FAA systems and tested without the risk of service outage. | 2 | Solution implementation | F,C,N | WBS 3.5.1 : System Development Test and Evaluation All activities associated with contractor conducted testing (e.g., factory acceptance testing) performed during the system development process to verify the new system is operating properly in order to achieve government acceptance. These are conducted to demonstrate that all engineering design and development activities are complete, and that the system will meet specifications, security certification, and authorization criteria. Development test and evaluation includes contractor and in-house activities associated with this effort, e.g., software validation and verification, and system and software access controls. It includes all support activities (e.g., technical assistance, maintenance, labor, material, support elements and testing spares, etc.) required during this phase of testing are included. It also includes the development and construction of those special test facilities, test simulators, test beds, and models required to perform developmental tests in order to verify the design and reliability of the system or subsystem. | Service team leader
S31 | Operational test & evaluation (OT&E) Completed: OT&E is conducted in an B38environment as operationally realistic as possible. This milestone is completed when government integration and shakedown testing has been performed at the test and evaluation site. It occurs when all test procedures have been successfully completed per the test plan. | 2 | Solution implementation | F,C,N | WBS 3.5.2 : System Operational Test and Evaluation All activities associated with tests and evaluations conducted to assess the prospective system’s utility, operational effectiveness, operational suitability, and logistics supportability (including compatibility, interoperability, reliability, maintainability, logistics requirements, security administration, etc.). It includes all support activities (e.g., technical assistance, maintenance, labor, material, support elements and testing spares etc.) required during this phase of testing. All activities associated with development and construction of those special test facilities, test simulators, test beds, and models required for performance of the operational tests. | OT&E team leader (WJHTC)
S32 | Functional configuration audit (FCA) completed - The FCA formally examines the "as tested" characteristics of a configuration item. It is conducted on test data from a representative production unit to verify actual performance. The FCA is complete when the service team determines that discrepancies resulting from the audit are corrected. | 3 | Solution implementation | F,N,C | WBS 3.2.7 : Configuration Management All activities associated with establishing and maintaining consistency of a product’s performance, functional, and physical attributes with its requirements, design, and operational information throughout its life. This includes the establishment, monitoring, and administration of change control procedures, including collecting, processing, distributing, and tracking modification request forms; establishment and administration of change control boards, and formal audits to compare product to documentation. It also includes configuration management of hardware, software, facilities, data, interfaces, tools, and documentation. | Service team leader
S33 | Physical configuration audit (PCA) completed - The PCA formally examines the "as built" physical product configuration or "as coded" total system software against design documentation. The PCA is complete when the service team determines that discrepancies resulting from the audit are corrected. | 3 | Solution implementation | F,N,C | WBS 3.2.7 : Configuration Management All activities associated with establishing and maintaining consistency of a product’s performance, functional, and physical attributes with its requirements, design, and operational information throughout its life. This includes the establishment, monitoring, and administration of change control procedures, including collecting, processing, distributing, and tracking modification request forms; establishment and administration of change control boards, and formal audits to compare product to documentation. It also includes configuration management of hardware, software, facilities, data, interfaces, tools, and documentation. | Service team leader
S34 | Production readiness review (PRR) completed - The PRR determines if production engineering problems have been resolved, adequate planning accomplished, and the design is ready for production. The review evaluates the complete production-configured system to determine if it correctly and completely implements all system requirements. It determines whether system requirements are traceable to the final production system. | 2 | Solution implementation | F,C,N | WBS 3.3.5 : Procurement/Production All procurement associated with the project including electronic equipment and project material not included in other engineering and construction contracts (e.g., commercial off-the-shelf (COTS) or non-developmental items [NDI]). This includes procurement of hardware and software for technology refreshment. All activities associated with full-scale production necessary to fulfill quantity requirements for solution implementation. This includes all activities related to contractor-conducted testing performed on each end item before it leaves the factory to verify that the end item conforms to applicable specifications, and is free from manufacturing defects. It also includes any non-recurring production start-up costs associated with the production of the solution (e.g., facility expansion or construction, retooling or production equipment acquisition or modification, etc.). | Service team leader
S35 | Production decision - The production decision freezes the design and authorizes the program to move into full-scale production of the product. It occurs after successful operational test and evaluation and when stakeholders agree manufacturing processes are in sufficient statistical control to achieve product RMA requirements. | 1 | Solution implementation | F,C,N | WBS 3.3.5 : Procurement/Production All procurement associated with the project including electronic equipment and project material not included in other engineering and construction contracts (e.g., commercial off-the-shelf (COTS) or non-developmental items [NDI]). This includes procurement of hardware and software for technology refreshment. All activities associated with full-scale production necessary to fulfill quantity requirements for solution implementation. This includes all activities related to contractor-conducted testing performed on each end item before it leaves the factory to verify that the end item conforms to applicable specifications, and is free from manufacturing defects. It also includes any non-recurring production start-up costs associated with the production of the solution (e.g., facility expansion or construction, retooling or production equipment acquisition or modification, etc.). | Vice President (ATO) or Director (non-ATO) of the service organization unless reserved for the JRC or other decision authority (determined at the final investment decision).
S36 | Factory acceptance testing (FAT) completed - FAT is formal testing conducted by the contractor (usually) at the contractor facility. The FAT verifies the production item conforms to all contract specifications, is free from manufacturing defects, and meets all specification requirements. Completion is determined by the service team. | 2 | Solution implementation | F,N,C | WBS 3.3.5 : Procurement/Production All procurement associated with the project including electronic equipment and project material not included in other engineering and construction contracts (e.g., commercial off-the-shelf (COTS) or non-developmental items [NDI]). This includes procurement of hardware and software for technology refreshment. All activities associated with full-scale production necessary to fulfill quantity requirements for solution implementation. This includes all activities related to contractor-conducted testing performed on each end item before it leaves the factory to verify that the end item conforms to applicable specifications, and is free from manufacturing defects. It also includes any non-recurring production start-up costs associated with the production of the solution (e.g., facility expansion or construction, retooling or production equipment acquisition or modification, etc.). | Service team leader
S37 | Operator/maintenance training begins - Training begins at the inception of the first formal course sanctioned by FAA Academy. | 3 | Solution implementation | F,C,N | WBS 3.7.8 : Initial Training All activities associated with designing, developing, and delivering training services, aids, and materials for initial, attrition, and refresher training of site technicians, depot technicians, engineers, air traffic controllers, security administrators, technical on-site representatives, aviation safety inspectors, implementation personnel, and other personnel. | Service team leader
S38 | First-site preparation completed - This occurs when all work is completed that enables the contractor to deliver and install the new system in the designated space and enables it to be interfaced into the NAS. | 3 | Solution implementation | F,C,N | WBS 4.6 : Site Preparation, Installation, Test, and Checkout All activities associated with site preparation, installation, site acceptance testing, and checkout of hardware, software, and equipment at the site in order to achieve operational status. This includes coordination with all applicable organizations, unions and the public during installation and transition. | Service team leader
S39 | First-site delivery - This milestone occurs when product hardware, software, and support items (including instruction manuals and training material) physically arrive at the key site. Milestone may not be needed if the test & evaluation site and first operational site are the same. | 2 | Solution implementation | F,C,N | WBS 4.6 : Site Preparation, Installation, Test, and Checkout All activities associated with site preparation, installation, site acceptance testing, and checkout of hardware, software, and equipment at the site in order to achieve operational status. This includes coordination with all applicable organizations, unions and the public during installation and transition. | Service team leader
S40 | First-site training material delivered - This milestone occurs when FAA-approved training materials are delivered to the first site. | 3 | Solution implementation | F,C,N | WBS 4.9 : Implementation Training All activities associated with the delivery of initial, refresher, and attrition training for implementation personnel. This includes contractor costs associated with specific training. Training costs include course conduct (including instructor and facilities costs), travel, and per diem costs for students. | Service team leader
S41 | Independent operational test & evaluation (IOT&E) completed - IOT&E is a user/operator evaluation of the product in an operational environment. It provides decision-makers with an independent determination of operational readiness in support of the in-service decision. IOT&E testing is complete when verification is made of the operational effectiveness and suitability of the equipment with user participation, as defined in the Program Requirements Attachment to the XPB (e.g., reliability, maintainability, degraded operations, stress and NAS load-testing, system-man-machine interface, human factors, safety and security, site adaptation, transition switchover). | 2 | Solution implementation | F,C,N | WBS 3.5.4 : Independent Operational Test and Evaluation All activities associated with independent test and evaluation conducted by organizations other than the developer in a realistic environment to confirm operational readiness (suitability and effectiveness of the system to satisfy requirements) of FAA systems to become part of the NAS. It also includes all support activities. | IOT&E Team
S42 | Final in-service review (ISR) report delivered - This is the final report to support the in-service decision. This decision is made by the in-service decision authority. | 2 | Solution implementation | F,C,N | WBS 4.1.1 : Program Planning, Authorization, Management and Control All activities associated with program control, contract management, business and administrative activities such as planning, organizing, directing, coordinating, estimating, scheduling, and controlling, and approval actions designed to accomplish overall program objectives. It also includes all deployment planning activities required to support the deployment of the solution. It includes development and dissemination of deployment planning information to regional and site personnel; tailoring the in-service review (ISR) checklist template; conducting ISR checklist status reviews; developing action plans and briefing package to obtain In-Service Decision; conducting stakeholder meetings; obtaining the in-service decision; tracking ISD action plans; and updating the IPP. | The designated -n-service decision authority approved by the JRC and documented in the ISP.
S43 | In-Service Decision - This milestone represents the decision to accept a product or service for operational use during the solution implementation. This decision allows deployment activities to commence, such as installing products at each site and certifying them for operational use. | 1 | Solution implementation | F,C,N | WBS 4.1.1 : Program Planning, Authorization, Management and Control All activities associated with program control, contract management, business and administrative activities such as planning, organizing, directing, coordinating, estimating, scheduling, and controlling, and approval actions designed to accomplish overall program objectives. It also includes all deployment planning activities required to support the deployment of the solution. It includes development and dissemination of deployment planning information to regional and site personnel; tailoring the in-service review (ISR) checklist template; conducting ISR checklist status reviews; developing action plans and briefing package to obtain In-Service Decision; conducting stakeholder meetings; obtaining the in-service decision; tracking ISD action plans; and updating the IPP. | The designated -n-service decision authority approved by the JRC and documented in the ISP.
S44 | Contractor acceptance/inspection completed - This milestone is complete when the service team determines that equipment hardware and software have been successfully installed, tested, and shown to meet the requirements of the contract. The functional and physical configuration audits must be complete. This milestone marks the day when the contractor transfers ownership of the product to the FAA. It usually results in signing of form 256, which includes exceptions that must be remedied. | 2 | Solution implementation | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Service team leader
S45 | Site acceptance testing completed - Site acceptance testing confirms the acquired system is able to interface into the environment in which it will operate.
S46 | First-site initial operational capability date (IOC) - First-site IOC occurs when the first operational system satisfies FAA joint acceptance inspection, construction, installation, performance, operation, and maintenance criteria and is ready to be placed into operational use. This includes training for technician and air traffic specialist and full provisioning. | 2 | Solution implementation | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel
S47 | First-site operational readiness demonstration (ORD) completed - This milestone is reached when air transportation operational personnel complete a shakedown of the new system and are satisfied it can support full and sustainable air transportation operations. The milestone occurs when the site air transportation official signs the facility log making the new system the primary system for air transportation operations. The replaced system is usually left powered on in a backup mode for approximately 30 days and then removed. | 2 | Solution implementation |  | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel
S48 | First-site commissioning - The first system, subsystem, or equipment is commissioned when it is formally accepted and placed into operational service and the Technical Operations sector has assumed maintenance responsibility. For products to which the flying public have access, commissioning requires written confirmation to airmen and the aviation industry via a notice to airmen (NOTAM) | 3 | In-service management | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel
S49 | Site operational readiness date (ORD) 25% complete - 25% site ORD occurs when the site that represents 25% of planned deployments satisfies FAA joint acceptance inspection, construction, installation, performance, operation, and maintenance criteria and is ready to be placed into operational use. | 2 | In-service management | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel
S50 | Site operational readiness date (ORD) 50% complete - 50% site ORD occurs when the site that represents 50% of the planned deployments satisfies FAA joint acceptance inspection, construction, installation, performance, operation, and maintenance criteria and is ready to be placed into operational use. | 2 | In-service management | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel
S51 | Site operational readiness date (ORD) 75% complete - 75% site ORD occurs when the Site that represents 75% of the planned deployments satisfies FAA joint acceptance inspection, construction, installation, performance, operation, and maintenance criteria and is ready to be placed into operational use. | 2 | In-service management | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel
S52 | Last-site operational readiness date (ORD) - Last ORD occurs when the last operational product satisfies FAA joint acceptance inspection construction, installation, performance, operation, and maintenance criteria and is ready to be place into operational use. | 2 | In-service management | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel
S53 | Last-site commissioning - The last facility, system, subsystem or equipment is considered to be commissioned when it has been formally accepted and placed into operational service in the NAS, and its controlling technical operations sector has assumed maintenance responsibility. With completion of this milestone, the transition into in-service management is complete. | 2 | In-service management | F,C,N | WBS 4.7 : Joint Acceptance Inspection/Commissioning/Closeout All activities associated with preparing for and achieving declaration of operational readiness, initial operational capability, full operational capability, joint acceptance inspection, service availability, and commissioning. This includes operational procedure development or modification, Notice to Airmen (NOTAM) issuance, field familiarization activities, preliminary and final commissioning, flight inspections, and other applicable testing. It also includes initial certification activities, initial standards testing and evaluation, and initial publication of certification standards. | Site technical and operational personnel

## Sheet2
FACILITIES | MILESTONES
Milestone | Milestone Description | AMS Phase | Level
F1 | Service-Level Mission Need Decision: The SLMNS prioritizes and describes the capability shortfalls and opportunities for a service organization. It is the basis for all investment opportunities that enter the AMS lifecycle management process. The Chief Operating Officer (ATO) or Associate or Assistant Administrator (non-ATO) approve the SLMNS, which is reviewed annually and updated as needed. | Mission analysis | 1
F2 | Program Requirements (PR) Approval: Preliminary program requirements are developed during concept and requirements definition and recorded in Attachment 1 to the Exhibit 300 Program Baseline (XPB). Program requirements are revised during initial investment analysis and finalized during final investment analysis. They are approved by the Vice Presidents (ATO) or Directors (non-ATO) of the implementing and operating service organizations. | Concept and requirements definition | 1
F3 | Readiness for Investment Analysis Decision. This decision occurs after completion of CRD. It verifies preliminary requirements are well-defined and identifies the preliminary alternatives that will be evaluated during initial investment analysis. The decision authority is the Chief Operating Officer (ATO) or Associate or Assistant Administrator (non-ATO) of the line of business with the mission need. | Concept and requirements definition | 1
F4 | Business Case Analysis Report (BCAR) Approval: The Investment Analysis Team prepares the BCAR during initial investment analysis. This report defines the investment alternatives and quantifies the costs and benefits associated with each. The BCAR is Attachment 2 of the XPB, and is approved by the ATO Vice President for Finance. | Initial investment analysis | 1
F5 | Initial Investment Decision: The JRC selects a solution for implementation at the initial investment decision and authorizes entry into final investment analysis for detailed planning and development of the X300 Program baseline. The decision document is the preliminary X300 Program Baseline, including attachment 1 (Preliminary Program Requirements) and Attachment 2 (Business Case Analysis Report) | Initial investment analysis | 1
F6 | Exhibit 300 Program Baseline (XPB) Approval: The XPB establishes the performance, cost, schedule and benefits boundaries for implementing an investment program. The Investment Analysis Team develops the XPB during final investment analysis for the solution selected for implementation at the initial investment decision. The service team that will implement the investment program develops cost and schedule baselines. The JRC approves the XPB at the final investment decision. All baseline changes require JRC approval. | Final investment analysis | 1
F7 | Implementation Strategy and Planning (ISP) Attachment Approval: The ISP defines the overall strategy by which the service team will execute an investment program during the solution implementation and support fielded products during in-service management Part 1 is a high-level, strategic overview of the service team's technical, management, procurement, and lifecycle management approach. Part 2 provides detailed actions that will be implemented for the phase approved for implementation by the Joint Resources Council at the final investment decision. The ISP is approved by the Vice Presidents (ATO) or Directors (non-ATO0 of the implementing and operating service organizations. | Final investment analysis | 1
F8 | Site Selection/Acquisition Assessment Completed. Includes collection of all site-selection data such as: real estate appraisals and zoning restrictions, legal concerns such as title search and property status, and environmental assessments+B14 | Final investment analysis | 1
F9 | Facility Conceptual Design Completed. For a major facility the conceptual design effort encompasses an Architectural/Engineering contract of approximately one year with incremental design reviews at 30%, 50% and 100%. When all review comments are incorporated into design plans and specifications, the conceptual design is completed. | Solution implementation | 1
F10 | Memo of Agreements (MOA) With Equipment Suppliers Completed. The facility program office has completed MOAs with all equipment/software suppliers (service teams); e.g., automation, communications, surveillance systems. | Solution implementation | 1
F11 | Contract Award For Site-Specific Detail Design. Using the approved conceptual design, award a site-specific detail design contract to an A/E firm to adapt the design to a specific site that will be used in the Invitation For Bid (IFB) document for construction. | Solution implementation | 2
F12. | Facility Design Completed. The site-specific detailed design of the facility, including plans and specifications, is 100% completed. | Solution implementation | 1
F13 | Site(s) Acquisition. Site(s) selected, procurement negotiated, and real estate purchase completed. | Solution implementation | 1
F14 | Facility Procurement Request(s) (PR) To Regional Logistics Completed. The Regional Engineering Office in consonance with the Regional Logistics Office has completed the procurement requests(s) and submitted it to the Contracting Officer for acquisition. The procurement request(s) is accompanied by the plans, specifications, statement of work, etc. | Solution implementation | 2
F15 | Invitation(s) For Bid (IFB) Issued. Building construction funds have been received by the Regional Office and prospective bidders are forwarded an Invitation for Bid, which includes a complete procurement package (construction plans, specifications, statement of work, and standard procurement documentation). | Solution implementation | 1
F16 | Regional Construction Contracts Awarded. Bid opening has been completed, bidder's price has been verified, the bidder has been determined to be responsive, and the contract is awarded. | Solution implementation | 1
F17 | Facility Construction Begun. The Contracting Officer has issued a Notice to Proceed to the successful bidder. | Solution implementation | 1
F18 | Beneficial Occupancy Date. The date a preselected portion of the building is occupied early for FAA use; e.g., electronic equipment rooms, operations room. | Solution implementation | 1
F19 | Facility Construction Completed. The facility has been inspected and is determined to be in compliance with the contract and is approved for FAA occupancy. | Solution implementation | 1