## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.0
| Agency Name: | Social Security Administration
| Week Start Date: | 2009-03-02
| Submitter Name: | Mark Silvestri
| Submitter Contact Info: | 410-965-0017 mark.silvestri@ssa.gov
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Total Appropriation | Total Obligations | Total Disbursements
1 | 28 | 418 | 09/11
2 | 28 | 417 | 09/11 | 90000000
3 | 28 | 417 | x | 500000000
4 | 28 | 417 | 09/10 | 500000000
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
Weekly Update Report Data (sheet 2 of 2)
No. | Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
| General Recovery Act Implementation | General Recovery Act Implementation
| 2/24 Established an SSA Recovery Act website at http://socialsecurity.gov/recovery/. | 3/3 Ongoing work with OMB to interpret Recovery Act implementation guidance.
| 2/24 Posted first major communication report. | 3/3 Meet with OMB on Recovery Act plans and risk management plans.
3/3 Posted first weekly financial and planned action report.
1 | One-Time Economic Recovery Payments (ERP) | One-time Economic Recovery Payments (ERP)
| 3/3 Established Treasury symbol 28 9/11 0418 to track funding of ERP payments. | 3/3 Apply for a CFDA number through GSA for ERP payments.
2 | 3/3 Established Treasury symbol 28 9/11 0417 to track funding for administrative costs of making ERP payments. | 3/3 Receive approved apportionment request.
| 3/3 Modified national 800 number to provide general upfront message. | 3/3 Issue funding to SSA components.
3 | 3/3 Issued an Administrative Message to SSA's internal Policy Net. | 3/3 Award printing contract for ERP advance information mailer.
4 | 3/3 Modified http://socialsecurity.gov/payment/ for ERP information. | 3/3 Modify http://socialsecurity.gov/payment/ with additional FAQs.
5 | 3/3 Weekly meeting with RRB and VA on ERP data matching to eliminate duplicate payments. | 3/3 Send an advance information mailer in late April to those who will receive the one-time ERP.
6 | 3/3 Held internal SSA meetings to review implementation plan and identify issues. | 3/3 Meet with component lead to start development of program-specific Recovery Act plans.
7 | 3/3 Submitted apportionment request for ERP funding.
8 | 3/3 Met with advocates on ERP.
9 | 3/3 Solicited bids through GPO for ERP notice.
10 | 3/3 Established an Agency lead to develop program specific Recovery Act plans.
11
12 | Replace the National Computer Center (NCC) | Replace the National Computer Center (NCC)
13 | 3/3 Established Treasury fund symbol 28 x 0417 to track construction and IT equipment purchases separately. | 3/3 Receive approved apportionment request.
14 | 3/3 Submitted apportionment request for NCC funding. | 3/3 Issue funding to SSA components.
| 3/3 Held kickoff meeting with SSA, GSA and OMB to discuss implementation plans. | 3/3 Meet with component leads to start development of program-specific Recovery Act plans.
3/3 Established an Agency lead to develop program specific Recovery Act plans.
15
| Additional Disability and Retirement Workloads | Additional Disability and Retirement Workloads
16 | 3/3 Established Treasury fund symbol 28 9/10 0417 to track these workloads. | 3/3 Receive approved apportionment request.
17 | 3/3 Submitted apportionment request for workload funding. | 3/3 Issue funding to SSA components.
| 3/3 Established an Agency lead to develop program-specific Recovery Act plans. | 3/3 Meet with component leads to start development of program-specific Recovery Act plans.
18
| Program Oversight and Audit Work | Program Oversight and Audit Work
19 | 3/3 Established Treasury fund symbol 28 9/12 0403 to track oversight and audit work separately. | 3/3 Receive approved apportionment request.
20 | 3/3 Submitted apportionment request for audit & oversight funding. | 3/3 Issue funding to SSA OIG.
21 |  | 3/3 All future OIG activity will be reported on SSA's Office of the Inspector General website.
22
23
24
25
26
27
28 | .
29