Guidelines for a WBS

Number: 580-GL-031-03					Approved By: (signature)

Effective Date: August 31, 2007				Name: John Donohue

Expiration Date: August 31, 2011				Title: Assoc. Chief, ISD

Responsible Office: 580/Information Systems Division (ISD)	Asset Type:  Guideline

Title:  Guidelines for a WBS					PAL Number:  1.2.4.1

| Purpose | The purpose of this document is to provide uniform guidance for developing the mission software project’s Work Breakdown Structure (WBS), which is a mechanism used to formulate the project plan, report progress against the plan, and facilitate communication of and commitment to the plan among members of the project team and ISD management. |
| --- | --- |

| Scope | This guideline should be used by all mission software projects and should align with the Software Project Planning process. It should also align with the process used for the Project Monitoring and Control. |
| --- | --- |

| Guideline | The following are in no particular order and are numbered for reference purposes only: A project WBS may be tailored and constructed to reflect unique characteristics of the product effort as appropriate. The WBS is a tree-structured, activity-oriented list of all work needed to meet the requirements of the project. The WBS is organized by product or service such that activities for a product (or sub-product or service) are normally grouped within a section of the WBS. The WBS provides a mechanism for the collection of cost and schedule data on a product-by-product (or service) basis, as well as for the project overall. It provides a framework for identifying material, services, schedules, staffing, and costs associated with each work element of the project. It addresses all work required, including organizing, planning, monitoring, controlling, and reporting the status of all work elements across the project. The WBS is used as the set of activities to be scheduled for the project. Estimation of resources required is also frequently based on the work defined in the WBS. If there is work you must do that is not reflected in your WBS, it is likely to have no schedule or resources. It will probably result in a schedule and/or cost variance. The WBS is defined based on project requirements during the project planning process. Use the list the WBS checklist at http://software.gsfc.nasa.gov/toolsDetail.cfm?selTool=1.2.4.0 as a checklist for your WBS and include any item that is appropriate for your project. The checklist provides a list of most high-level activities that a project may have to perform. It includes a WBS Dictionary to assist in selecting the appropriate items. Use the example of a project WBS in Addendum A as a guide in creating, formatting, and documenting your WBS. Your WBS will have many different WBS items, but will need many of the same items as in the example. Also see Resources for a link to the Flight Software Branch (FSB) WBS Standard. Although the WBS is product or service based, remember to include management and process activities (e.g., reporting, integration, training, requirements management) that must be accomplished to meet the project requirements. These must be included as WBS elements or they will not be scheduled and they will have no resources allocated to them. Some of the management processes that must be covered are: planning; monitoring and control; measurement and analysis; CM; PPQA; requirements management; acquisition management; and risk management. Organize the specific work elements that must be accomplished into successively smaller work elements such that: The subdivisions (or decomposition) of work elements are referenced in terms of levels. The highest levels usually reflect the major deliverable work areas or phases of the project. Higher WBS levels are sub-divided to a sufficient level of detail (depth) to permit accurate planning and monitoring without undue maintenance, data collection and reporting burden. High risk activities (or those requiring higher accuracy of planning and estimation) should be driven to a lower level of detail. A sufficient level of detail is usually at least one level lower than management reporting requirements. To break each WBS item down further, identify the steps defined for each applicable process and include the steps as lower level WBS items where appropriate. Ensure that each WBS element summarizes all WBS elements below it and that each WBS element has only one parent. Each element should have further explanatory information about it in a WBS Dictionary with task descriptions. A unique labeling scheme for each WBS element should be used that clearly denotes the hierarchical nature of the WBS. Labeling is normally accomplished through a hierarchical numeric structure. Each WBS element should have a documented completion criteria that can be used to assess whether or not all aspects of the work element have been completed (i.e., all work requirements of the sub-product, product, or service have been successfully accomplished.) The WBS should be used as the basis for your schedule. Each WBS element is scheduled and assigned resources. The cost can then be estimated based on the work elements defined in the WBS. This planning is iterative. As the planning process progresses, detailed scheduling, estimation, and costing may result in modifications, deletions, or additions to the initial set of WBS elements. Because the WBS is not just for planning, consider how it will be used to facilitate reporting, monitoring, and controlling activities on the project. Adjust the WBS structure to facilitate the reporting and monitoring activities. Each WBS element should be mapped to the individual or group within the project or task that is responsible for completing the work. This mapping should be noted in the Product Plan. Each WBS element should also have appropriate time keeping and accounting structures defined. The WBS should be available to appropriate involved parties during planning – to solicit input and to document commitment. Cost and schedule data should be available for appropriate WBS elements/level (sufficient detail and “roll-ups”/summary, but not to the lowest level of the WBS) |
| --- | --- |

| Tools and Templates | The following tools are available. Others may exist for the local project. |
| --- | --- |
|  | Name | Description |
|  | WBS Checklist | Provides a list of WBS elements that will normally cover all aspects of a development project. See http://software.gsfc.nasa.gov/toolsDetail.cfm?selTool=1.2.4.0 |
|  | FSB WBS Standard | General high level WBS applicable to all FSB Software Projects. |

| Change History | Version | Date | Description of Improvements |
| --- | --- | --- | --- |
|  | 1.0 | June 20, 2005 | Initial approved version by CCB |
|  | 2.0 | 4/2/07 | Example WBS replaced with a better WBS checklist in response to DCR 31 |
|  | 3.0 | 8/28/07 | DCR 48 - WBS Checklist replaced with a pointer to the WBS Checklist web page to avoid having to update the checklist in two places. |

Addendum A

Example WBS for a Project

Use the example shown as a guideline in possible WBS tailoring as you develop and format your WBS. You will need many of the WBS elements shown below. Some of the WBS elements in this example you will not need. In addition, you will likely need additional WBS elements that are specific to your project. Make sure that ALL work you must do is reflected in your WBS.

| PROJECT WORK BREAKDOWN STRUCTURE AND DATA DICTIONARY |
| --- |
| 1 MANAGEMENT |
| 1 | Software Management | Technical and management oversight by project of all aspects of all software to be developed |
| 1.1 | Plan Software |  |
| 1.1.1 | Plan Technical Approach | Plan the technical approach |
| 1.1.1.1 | Refine Project WBS | Development and refinement of WBS |
| 1.1.1.2 | Perform Init Make/Buy/Reuse Analysis | Make-buy studies for technical approach |
| 1.1.1.3 | Refine Life-Cycle for project | Establish project life cycle |
| 1.1.1.4 | Plan Acquisitions / Receivables | Identify and schedule acquisitions and receivables |
| 1.1.1.5 | Plan Life Cycle Phases | Plan each life cycle phase |
| 1.1.1.6 | Plan Builds | Identify basic build contents and schedule |
| 1.1.2 | Plan Management Approach | Plan the management approach |
| 1.1.2.1 | Establish Organization | Establish organizational structure |
| 1.1.2.2 | Plan Metrics Approach | Establish the metrics approach with objectives, metrics, and collection/storage approach |
| 1.1.2.3 | Plan Stakeholder Approach | Identify stakeholders, their roles, and monitoring approach |
| 1.1.2.4 | Plan Data Mgmt Approach | Identify what data will be kept, who will keep it, where it will be kept, and how it will be monitored |
| 1.1.2.5 | Plan Training Approach | Identify what training is needed, by whom it is needed, how it will be obtained |
| 1.1.2.6 | Plan Risk Mgmt Approach | Establish the risk strategy, identify the initial risks, classify the risks and place them in the risk tool, and develop mitigation plans |
| 1.1.3 | Estimate / Re-estimate Cost | Estimate (and re-estimate) project costs |
| 1.1.4 | Plan / Revise Staffing | Plan (and replan) the project staff |
| 1.1.5 | Plan/Revise Schedule | Establish (and revise) the work schedule |
| 1.1.8 | Plan / Revise Build Contents | Create (and maintain) the Product Plan |
| 1.2 | Monitor & Control Activities | Monitor and control the project activities |
| 1.2.1 | Install Metrics Tools / ID Repositories | Install the metric tools and repositories as needed |
| 1.2.2 | Load Plan / Revised Plan Data | Load planned data (and revisions) into spreadsheet tools |
| 1.2.3 | Collect Metrics Actuals | Collect and store metric data monthly |
| 1.2.4 | Assess Plan vs. Actuals | Compare actual data to plan monthly |
| 1.2.5 | Analyze Technical Metrics | Analyze metric data monthly |
| 1.2.6 | Obtain TL's Status | Get status from task leads weekly |
| 1.2.7 | Review Action Items | Review issues and action items on a weekly or monthly basis |
| 1.2.8 | Review / Update Risks | Review the risks and update status at least monthly |
| 1.2.9 | Monitor DM Collections | Verify that data management activities are ongoing |
| 1.2.10 | Track Receivables | track receivables against the schedule |
| 1.2.11 | Prepare and Report | Track issues and actions, and report status to stakeholders |
| 1.2.11.1 | Track and Resolve Issues and Actions | Identify, track, and resolve issues and actions |
| 1.2.11.2 | Status To Code 400 Project | Report monthly to Code 400 project |
| 1.2.11.3 | Status To Branch Head | Report monthly to the Branch Management |
| 1.2.11.4 | Status To Code 500 Champion | Report quarterly to the Code 500 Champion |
| 1.2.11.5 | Lessons Learned to repository | Identify lessons learned bi annually |
| 1.3 | Manage Configurations | Perform CM activities |
| 1.3.1 | Plan CM Approach | Plan the CM approach (you may tailor an organizational approach) |
| 1.3.1.1 | Identify Controlled Items | Identify the controlled items |
| 1.3.1.2 | Charter an Internal Review Board (IRB) | Set up an IRB (like a CCB), how it works, who is on it, and when it meets |
| 1.3.2 | Create / Update CM Plan | Write (and maintain ) the CM Plan |
| 1.3.3 | Select / Instantiate CM Tools | Select, obtain, and install the CM tools to be used |
| 1.3.4 | Conduct IRBs | Conduct IRB meetings on a regular basis to assess and manage requirement change requests, and to assess, assign, track, and disposition DCRs |
| 1.3.5 | Configure / Baseline CIs | Configure and baseline the configuration items |
| 1.3.6 | Audit CI Configurations | Conduct and support CI audits |
| 1.3.7 | Address CM Audit Findings | Address audit findings |
| 1.4 | Support Quality Assurance | Perform SQA support activities |
| 1.4.1 | Negotiate Activities with Code 300 | Negotiate for SQA activities with Code 300 |
| 1.4.2 | Review SQAP | Review the Code 300 SQAP |
| 1.4.3 | Schedule FY Proc/Prod Assessments | Schedule process and product quality assessments |
| 1.4.4 | Prepare for QA audits | Prepare for SQA audits |
| 1.4.5 | Address QA Audit Findings | Address audit findings |
| 1.5 | Stakeholder Coordination | Perform stakeholder coordination |
| 1.5.1 | Negotiate Commitments | Negotiate with stakeholders for commitments |
| 1.5.2 | Provide Liaison & Support as needed | Provide Liaison & Support as needed |
| 1.5.3 | Monitor/Verify S/H Involvement Monthly | Monitor/Verify S/H Involvement Monthly |
| 1.5.4 | Monitor/Verify S/H Commitments Monthly | Monitor/Verify S/H Commitments Monthly |
| 1.6 | Manage Acquisitions |  |
| 1.6.1 | Determine Acquisition Needs | Identify all hardware and software that will be procured by the project to the extent possible. |
| 1.6.2 | Select Suppliers | Identify the desired supplier for each item to be procured. Supplier may be sole source (justification needed) or selected based on item availability, cost, or other reasonable criteria. |
| 1.6.3 | Issue Procurements | Create or support the creation of procurement documents based on the governing processes from the Mission Project or the Procurement Office, as applicable. |
| 1.6.4 | Accept Products | Receive hardware or software; verify it is the correct item in the proper quantity, and in good condition; install the item in the appropriate environment. |
| 1.6.5 – 1.6.13 | Process Additional Procurement Needs | Assess and process any additional procurement needs, quarterly at a minimum |
| 2 ENGINEERING |
| 2 | Engineering |  |
| 2.1 | Systems Engineering | Perform Systems Engineering |
| 2.1.1 | Develop Software System Concept | Develop the project software concept |
| 2.1.2 | Define Interface Requirements | Receive and review all ICDs related to the project software |
| 2.2 | Dev/Test Environment Eng | Perform development and test environment engineering |
| 2.2.1 | Configure Tools | Configure Development Tools needed by the project |
| 2.2.2 | Integrate Proc F Test String | Integrate Proc F Test String |
| 2.2.3 | Integrate Main Processor Test String | Integrate Main Processor Test String |
| 3 SYSTEM DEVELOPMENT |
| 3 | Subsystem Development |  |
| 3.1 | Architecture Design | Perform architecture design |
| 3.1.1 | Define Requirements | Meet Stakeholders to understand, analyze, and allocate level 3 requirements to subsystems; baseline level 3 requirements, conduct the Software Requirements Review (SRR), and capture and track SRR RFAs |
| 3.1.2 | Develop Preliminary Design Pkg | Develop the preliminary design and conduct the PDR |
| 3.1.3 | Develop Detailed Design Pkg | Develop the critical design and conduct the CDR |
| 3.2 | Develop Main Processor Subsystem |  |
| 3.2.1 | Develop Main Processor Level 4 Requirements | Meet Stakeholders to understand, analyze, and define level 4 Main Processor requirements, allocate level 4 requirements to tasks, and conduct Main Processor requirements peer reviews |
| 3.2.2 | Develop Main Processor Software | Develop the Proc A, Proc B, Main Processor, and Common Software builds and develop the documentation |
| 3.2.2.1 | Proc A Build 1.0 |  |
| 3.2.2.2 | Proc A Build 2.0 |  |
| 3.2.2.3 | Proc A Build 3.0 |  |
| 3.2.2.4 | Create/Update Proc A User’s Guide |  |
| 3.2.2.5 | Proc B Build 1.0 |  |
| 3.2.2.6 | Proc B Build 2.0 |  |
| 3.2.2.7 | Proc B Build 3.0 |  |
| 3.2.2.8 | Create/Update Proc B User’s Guide |  |
| 3.2.2.9 | Main Proc Main Proc Build 1 |  |
| 3.2.2.10 | Main Proc Main Proc Build 2 |  |
| 3.2.2.11 | Main Proc Main Proc Build 3 |  |
| 3.2.2.12 | Create / Update Main Processor User’s Guide |  |
| 3.2.2.13 | Common SW Build 1 |  |
| 3.2.2.14 | Common SW Build 2 |  |
| 3.2.2.15 | Create / Update Common SW User’s Guide |  |
| 3.2.3 | Develop Proc C Subsystem |  |
| 3.2.3.1 | Develop Proc C Level 4 Requirements | Meet Stakeholders to understand, analyze, and define level 4 Proc F requirements, allocate level 4 requirements to tasks, and conduct Proc C requirements peer reviews |
| 3.2.3.2 | Develop Proc C Software | Develop the Proc D, Proc E, and Proc F builds and develop the documentation |
| 3.2.3.2.1 | Proc D Build 1.0 |  |
| 3.2.3.2.2 | Proc D Build 2.0 |  |
| 3.2.3.2.3 | Create/Update Proc D User’s Guide |  |
| 3.2.3.2.4 | Proc E Build 1.0 |  |
| 3.2.3.2.5 | Proc E Build 2.0 |  |
| 3.2.3.2.6 | Create/Update Proc E User’s Guide |  |
| 3.2.3.2.7 | Proc F Build 1.0 |  |
| 3.2.3.2.8 | Proc F Build 2.0 |  |
| 3.2.3.2.9 | Proc F Build 3.0 |  |
| 3.2.3.2.10 | Create/Update Proc F User’s Guide |  |
| 3.2.4 | Develop Diagnostic Software |  |
| 3.2.4.1 | Develop Diagnostic Software Requirements | Meet Stakeholders to understand, analyze, and define diagnostic requirements, allocate requirements to tasks, and conduct requirements peer reviews |
| 3.2.4.2 | Develop and Test Diagnostic Software | Develop and test diagnostic software |
| 4 TEST SOFTWARE |
| 4 | Test Software |  |
| 4.1 | Plan Test Program | Plan the overall test program |
| 4.1.1 | Load L 4 Requirements into Req Tool | Put level 4 requirements into Req Tool |
| 4.1.2 | Configure Test Environment for Test | Configure Test Environment for test |
| 4.1.3 | Create Test Plan | Develop and update the test plan , conduct plan walkthrough(s) with the Team, and obtain plan approvals |
| 4.2 | Plan Build Test Scenarios and Procs | Build the test scenarios and test procedures for each build |
| 4.2.1 | Proc A Build 1.0 |  |
| 4.2.3 | Proc A Build 2.0 |  |
| 4.2.4 | Proc A Build 3.0 |  |
| 4.2.5 | Proc B Build 1.0 |  |
| 4.2.6 | Proc B Build 2.0 |  |
| 4.2.7 | Proc B Build 3.0 |  |
| 4.2.8 | Main Proc Build 1 |  |
| 4.2.9 | Main Proc Build 2 |  |
| 4.2.10 | Main Proc Build 3 |  |
| 4.2.11 | Common SW Build 2 |  |
| 4.2.12 | Proc D Build 1 |  |
| 4.2.13 | Proc D Build 2 |  |
| 4.2.14 | Proc E Build 1 |  |
| 4.2.15 | Proc E Build 2 |  |
| 4.2.16 | Proc F Build 1.0 |  |
| 4.2.17 | Proc F Build 2.0 |  |
| 4.2.18 | Proc F Build 3.0 |  |
| 4.3 | Build Verification Test and Report | Conduct build tests and report results for each build |
| 4.3.1 | Verification Test Main Processor |  |
| 4.3.1.1 | Proc A Build 1.0 |  |
| 4.3.1.2 | Proc A Build 2.0 |  |
| 4.3.1.3 | Proc A Build 3.0 |  |
| 4.3.1.4 | Proc B Build 1.0 |  |
| 4.3.1.5 | Proc B Build 2.0 |  |
| 4.3.1.6 | Proc B Build 3.0 |  |
| 4.3.1.7 | Main Proc Build 1 |  |
| 4.3.1.8 | Main Proc Build 2 |  |
| 4.3.1.9 | Main Proc Build 3 |  |
| 4.3.1.10 | Common SW Build 2 |  |
| 4.3.2 | Verification Test Proc C |  |
| 4.3.2.1 | Proc D Build 1 |  |
| 4.3.2.2 | Proc D Build 2 |  |
| 4.3.2.3 | Proc E Build 1 |  |
| 4.3.2.4 | Proc E Build 2 |  |
| 4.3.2.5 | Proc F Build 1.0 |  |
| 4.3.2.6 | Proc F Build 2.0 |  |
| 4.3.2.7 | Proc F Build 3.0 |  |
| 4.4 | Perform System/Acceptance Testing |  |
| 4.4.1 | Conduct Sys Test Readiness Rev | Conduct a Test Readiness Review for the software |
| 4.4.2 | Validation Test System | Perform validation testing |
| 4.4.3 | Acceptance Test System | Perform acceptance testing |
| 4.4.4 | Conduct Accept Test Results Rev | Conduct an acceptance test results review |
| 4.4.5 | Create System/Acceptance Test Report | Complete the system acceptance test report |