Family Justice Project

Project # 263-0294

2nd Quarter Report

FY 2008

January 1st – March 31st, 2008

Ambassador Moushira Khattab visits NGO Grantee in Giza

Table of Contents

Executive Summary	3

Task One: Strengthening Capacity to Mediate Family Disputes	5

Component 1 – Family Justice Training	5

1.1 Training of Trainers	5

1.2 Nationwide Training of Family Court Mediators	5

1.3 Ongoing technical assistance and training in pilot courts	6

Component 2 - Infrastructure Repairs in Family Courts	7

2.1 Infrastructure Repairs in Family Mediation Offices – Minya Governorate	7

2.2 Infrastructure Repairs in Family Mediation Offices – Giza Governorate	8

Component 3 – Media Support for MOJ	8

3.1 MOJ Headquarters	8

3.2 Mediation Offices	9

Task Two:  Increasing Access to Information on Family Court Legal Services	10

Component 1 - NGOs Grants Program	10

1.1 Ongoing support/technical assistance/training to current grantees	10

1.2 New Grant Awards	13

Component 2 - Media Community Awareness (NCCM)	13

2.1. National	13

2.2. Pilot Regions Community-based (Giza, Minya and Port Said)	14

Annexes	15

Annex (1):  Agenda for Skills Enhancement Training	17

Annex (2): National Training Plan	21

Annex (3): List of Grantees from FY07 to date	22

Annex (4): Quarterly M&E Report	26

# Executive Summary

To support Egypt's determination to strengthen access to justice, enhance family stability, and protect the rights of children, USAID, in cooperation with the Government of Egypt, established the Family Justice Project (FJP) and chose Management Sciences for Development, Inc. (MSD), as its implementing partner.  The purpose of the FJP is to enhance access to justice for families.  Specifically, the Project supports the implementation of Law Number 10 of 2004, pertaining to family court mediation and works closely with the Ministry of Justice (MOJ) and The National Council for Childhood and Motherhood (NCCM).

During the second quarter of FY2008, the FJP continued to achieve its objective by supporting both the mediation and NGO components of the Project.  FJP continues to work closely with its partners to complete the activities outlined in the FY2008 workplan.  This quarterly report continues to track progress against the activities previously elaborated in that workplan and follows the same format.  Some of the highlights for this quarter include:

- Completion of skills enhancement trainings for 144 specialists from the three Pilot governorates

- Completion of training for mediators and mediation staff in Sohag, Qena and Aswan as part of the nationwide training program

- Completion of two legal specialist workshop for 39 participants from 14 Giza NGOs and 79 participants from 10 Minya NGOs in cooperation with MOJ and NCCM

- Award of two additional grants and four extensions, bringing the total awarded to more than 1.7 million USD

- Completion of 179 public awareness events for 10,831 participants by NGO grantees to promote family stability and support the mediation process

- Visit by Ambassador Khattab, Secretary General of NCCM, to NGO for inspection of services, program about achievements, and press coverage

- Completed capacity building activities for NGO grantees in areas of legal, financial and programmatic support

- Completion of significant portion of repairs at El Saaf mediation offices

- Settlement of 2,539 cases by 52 NGO counseling centers

Task One

During this quarter, nationwide training for mediation office personnel continued with the completion of Sohag, Qena, and Aswan, for a total of 285 participants.  FJP also completed skills enhancement training for 144 participants as a follow-up to the pilot trainings completed last year.  These trainings were held in Port Said, Minya, and Giza and resulted in concrete information about additional needs and plans for continued technical support of the pilot mediation offices.

FJP began and completed most of the required repairs at El Saaf mediation offices.  The repairs will be completed in April.  Preparations for repairs at other locations in Giza and Minya continued with draft drawings of all Minya locations completed.  The MOJ decided to forego repairs at El Wahat due to its remote location and low case load.

Task Two

During this quarter, Task Two awarded two additional grants bringing the total NGOs receiving funding to 26.  An additional four extensions were signed bringing the total funding to $1.7 million.  NGO grantees successfully implemented program activities focusing on counseling services for families, community awareness and education efforts. FJP provided capacity building training for NGO grantees in key areas including legal, financial training and program implementation to ensure quality services and sustainability of activities beyond the life of the project.

FJP organized follow-up legal training in cooperation with NCCM and MOJ for NGO partners in both Giza and Minya.  The training program included presentations by MOJ and NCCM personnel and discussed Law 10 and its application as well as the proposed amendments to the child law.

Activities planned for next quarter

In the third quarter of FY2008, FJP will complete mediation training for offices in Benha, Shebin El Komm, Damietta, and Zagazig.  FJP will also complete two train-the-trainers programs, one for judges and one for mediators, as well as conducting roundtable discussions for mediators from the pilot regions. Repairs to rural Giza courts will be completed and repairs to Minya locations will be underway by the end of next quarter.

Task Two will continue to strengthen the “safety net” for families in the pilot communities by awarding additional grants and providing on-going training and technical assistance to new NGO grantees and follow-up support to those NGOs whose contracts have expired but have fulfilled their previous grant agreements. FJP will complete the training methodology and manual to be utilized by NGOs and will conduct training for NGOs to familiarize them with the messages and methods to ensure consistent training activities.  The community awareness and media activities will also continue with media events on a regular basis to emphasize the work of the mediation offices and the NGOs.  The media component will also support NGO grantees to develop and disseminate messages on family justice to children, youth, parents and community leaders.

# Task One: Strengthening Capacity to Mediate Family Disputes

During the 2nd quarter of FY2008, the Family Justice Project (FJP) continued to execute the National Training Plan for mediation office personnel. Skills enhancement training for the pilot regions was completed in all three regions. Repairs and upgrades to pilot region mediation offices are well underway. Most work to the El Saaf mediation offices was completed during the quarter and will be finalized in April.

## Component 1 – Family Justice Training

## 1.1 Training of Trainers

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 1.1.1 | Recruit and conduct TOT in Southern region | MOJ/Academic Insitutions | 10 trainers trained to serve Sourthern region |  |  | ( |

Two train-of-trainers (TOT) programs are planned for next quarter, based on discussions and agreement with the MOJ.  The MOJ has requested one session for family court judges and another for mediators. The MOJ will nominate the appropriate personnel to attend the training program. Due to the nationwide training schedule and the follow-up training for the pilot regions, MOJ requested to have this training in May and June rather than March, as originally scheduled.

### 1.2 Nationwide Training of Family Court Mediators

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 1.2.1 | Assuit Training (continued) | MOJ | 37 trained | ( |  |  |
| 1.2.2 | Sohag Training | MOJ | 135 trained | ( | ( |  |
| 1.2.3 | Qena Training | MOJ | 92 trained |  | ( | ( |
| 1.2.4 | Aswan Training | MOJ | 21 trained |  |  | ( |

Nationwide mediation training continued with the completion of the last session for the Assuit mediation offices.  Nationwide mediation training was completed for Sohag with four sessions, Qena with four sessions and two sessions for Aswan.  In total, 285 participants including 13 mediation offices in Assuit, 12 mediation offices in Sohag, 16 mediation offices in Qena and 5 mediation offices in Aswan completed the training.  The participants included 46 psychological, 84 social, 112 legal and 43 administrative personnel.  The training programs included one day of legal aspects where the participants were introduced to implementation of Law 10 and were able to discuss related issues with MOJ representatives.  The remaining 3 days focused on mediation techniques including the steps of mediation, understanding family conflict, advanced communication skills, and report writing.  During the training, the concept of team building was emphasized by helping participants understand the role of each of the mediators (i.e. legal, social and psychological) and how they inter-relate.

The MOJ made a decision to send only specialists to the nationwide training and exclude administrative personnel who were previously being allowed to attend.  This decision took effect during the final training of the quarter in Aswan.  FJP personnel discussed this issue with MOJ personnel and encouraged them to send administrative staff to the program since these employees receive no training and have little understanding of Law 10 and its implication, and lack skills on interviewing family members.  A special one day session to run simultaneously with the nationwide training program was also recommended to MOJ by FJP personnel to ensure that these employees can provide the appropriate support for mediators.  However, the MOJ has not yet agreed to this program or to allowing the administrative personnel to attend the full session as before, preferring to keep the training specific to the specialists.  FJP will continue to pursue possible avenues for training administrative personnel.  Based on this change, which decreased the number of planned participants, FJP has updated the national training plan and it is contained herein as Annex 2.

Nationwide Training in Qena

### 1.3 Ongoing technical assistance and training in pilot courts

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 1.3.1 | Conduct 1 one-day booster training and technical assistance in Port Said | MOJ | 18 trained |  | ( |  |
| 1.3.2 | Conduct 1 one-day booster training and technical assistance in Giza | MOJ | 58 trained |  |  | ( |
| 1.3.3 | Conduct 1 one-day booster training and technical assistance in Minya | MOJ | 68 trained |  |  | ( |

In parallel with the National Training Schedule, FJP in coordination with the MOJ technical team developed skills enhancement training as a follow-on to training previously provided for the pilot locations of Giza, Minya and Port Said.  The first of these trainings took place in Port Said on February 26th with 18 participants, all of whom previously received mediation skills training.  Giza training took place on March 17th – 19th with 58 participants and in Minya on March 25th – 27th with 68 participants completing the program.  These programs were designed to continue providing technical support and assess the impact of the trainings conducted in 2007 in the Pilot governorates.

The agenda for the 1-day workshop (See annex 1) included one session on legal issues where mediators were able to discuss with MOJ representatives the procedural and legal problems they are facing.  The MOJ representative provided trainees with updates on regulations and also addressed problem areas and lessons learned, to improve the effectiveness of family mediation.  Trainees also completed a session to further their mediation skills and learn more about the practical approach to mediation.  The final session included developing communication skills and team building techniques.

During the training program, the mediation specialists also completed a qualitative and quantitative assessment of their prior training. In addition to completing a written assessment, the participants had break-out brainstorming sessions about how they benefited from the training, the skills they were able to implement, and the additional support they needed to be effective.  The results of these sessions were reported in a plenary session for all participants to share their lessons learned.

Skills Enhancement Training – Port Said

Training reports for each governorate were compiled and provided to USAID, as well as the MOJ, who requested the information in order to support the needs of the mediators.  Some of the skills that mediators improved included clarification of their specific roles, negotiation skills, exercising neutrality and keeping their personal opinions to themselves, using the problem tree technique (i.e. getting to the real root of the problem), enhanced teamwork, better communication skills, and report writing.

Specialists reported a significant increase in the number of visits to their office and attributed that to increased public awareness through media outlets, increased trust based on experience with the specialists, and a general reputation that certain offices move cases quickly.  Some of the obstacles they noted were lack of proper equipment and private space to hold confidential mediations, manipulation of parties by lawyers, clients attempting to manipulate facts to influence the mediator’s judgment, and lack of attendance by one of the parties.  The participants requested more contact with the National Council on Childhood and Motherhood to share updates, more contact with MOJ to ensure they are executing the law and procedures properly, increased security at their offices to protect themselves and clients, and additional training to continue improving their skill level.

## Component 2 - Infrastructure Repairs in Family Courts

Based on the previously conducted assessments and discussions with MOJ personnel, including Counselor Attawaya, El Saaf was chosen as the first location for repairs followed by 6th of October.   The MOJ has also requested upgrades to their technical offices located at MOJ headquarters and an assessment visit is scheduled for early April.

### 2.1 Infrastructure Repairs in Family Mediation Offices – Minya Governorate

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 2.1.1 | Preparations of RFPs for constructions, electric, sanitary and A/C contractors to execute repairs | MOJ | Site drawings and specifications completed RFP has been made |  | ( | ( |

Preparatory work is underway for the 8 Minya locations serving 9 Family Courts.  Early this quarter FJP contracted an A&E firm to survey all of the Minya locations and prepare drawings of the mediation offices.  The first draft of these drawings have been completed and delivered to FJP.  The FJP Engineer will verify the drawings and complete final versions to be shared with AOJSII and the MOJ.  As soon as the drawings are complete, FJP will complete timelines, similar to those prepared for the Giza locations, to share with MOJ and AOJS II, to ensure coordination of work.

### 2.2 Infrastructure Repairs in Family Mediation Offices – Giza Governorate

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Jan.08 | Feb.08 | Mar.08 |
| 2.2.1 | Preparation of RFPs for construction, electirc, sanitray and A/C contractors to exucute repairs | MOJ | ( | ( | ( |
| 2.2.2 | Contract with construction, electric, sanitary and A/C contractors for Giza | MOJ | ( | ( |  |
| 2.2.3 | Supervise ongoing work of contractors for Quality Assurance | MOJ | ( | ( | ( |

During the 1st quarter FJP, AOJSII and MOJ engineers completed site visits to all five mediation offices and El Saaf was chosen as the first location for repairs, followed by 6th of October.  The MOJ decided to forego work at El Wahat due to its remote location and the extremely small caseload there.  FJP developed timelines for each location with specific activities and completion dates which were shared with AOJSII and the MOJ.  During this quarter repairs for El Saaf began and were almost complete, with final completion expected in April.  Repairs were delayed due to damaged piping from the second floor which caused leaking into the area where FJP is upgrading the mediation offices.  The upgrades to the mediation offices provide more working space for employees and easier access for families to the mediation offices.  A private mediation room will now be available to ensure confidentiality of proceedings.

Preliminary work is underway for the Sixth of October location.  This Family Court building is a relatively new and the need for additional office space was not necessary, though some upgrades are needed to have appropriate space for mediation.  The drawing, sanitary and electric layouts, and timeline has been developed and construction work will begin early in the third quarter.  These drawing, timelines, and layout have been provided to AOJSII and the MOJ.

## Component 3 – Media Support for MOJ

### 3.1 MOJ Headquarters

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 3.1.1 | Develop materials on family justice for MOJ | MOJ | Flyers, brochure, posters, Q&A booklet | ( | ( | ( |
| 3.1.2 | Provide technical assistance to develop a database for journalists and media professionals. | MOJ | Database for MOJ Press Office | ( | ( | ( |
| 3.1.3 | Develop and implement a public relations plan to deliver defined messages of the mediation offices and MOJ | MOJ | PR message |  | ( | ( |
| 3.1.4 | Train appropriate senior MOJ officials on handling media interviews | MOJ | Senior MOJ officials trained | ( | ( | ( |

The media team, in close coordination with the MOJ’s Administrative Services Department, completed the production of signage for the mediation offices.  Three types were developed to accommodate the various locations (i.e. inside, outside, on walls), all of which have been delivered to the MOJ who is now distributing those to the offices, along with the instructional posters.  These posters provide a step by step process for litigants to follow in processing their family law claims.

The media team is working with psychological experts to develop a manual of key messages for both NGOs and MOJ to utilize in media activities.  This activity will result in a technical manual and specialized training to ensure that messages to families and children in particular are focused and responsive to the psychological needs of that group.

The media team is working with “El-Birnamig El-Aam” or General Program Radio to complete 30 sessions focused on family law issues.  The topics for the programs have been developed and representatives from both the MOJ and NCCM will participate in the program to answer specific questions from call in listeners.    MOJ and NCCM representatives, along with the FJP Sr. Legal Expert, are coordinating to ensure that the content is accurate and typical of family law disputes in Egypt and properly addresses the solutions, both legally and psychologically.

### 3.2 Mediation Offices

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 3.2.1 | Identify outlets for promoting MOJ messages | MOJ | Media Outlets | ( | ( | ( |
| 3.2.3 | Develop 5-minute film about process of infrastructure repairs | MOJ | Documentary film | ( | ( | ( |

FJP completed a video shoot in both Minya and Giza with NGOs and their beneficiaries as part of the documentary being developed on family counseling centers.  This video builds on the original documentary shown in the first press conference and will be used to educate the media about mediation and the work of the NGOs.  A video shoot was also completed at the El Saaf court where repairs are currently underway to the mediation offices to illustrate the before and after progress.

# Task Two:  Increasing Access to Information on Family Court Legal Services

During the 2nd quarter of FY2008, Task Two successfully completed the following activities: 1) signed two new grant agreements with NGOs from Port Said, 2) completed four extensions of current grantees, 3) completed capacity building training for legal specialists in Giza and Minya, 4) conducted financial orientations and reporting workshops for Giza and Minya NGOs, and 5) conducted a site visit to FJP grantee in collaboration with NCCM.

## Component 1 - NGOs Grants Program

### 1.1 Ongoing support/technical assistance/training to current grantees

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 1.1.1 | Capacity building workshops on human rights approach to strengthening families for NGOs. (Giza, Minya, Port Said) | NCCM | Training provided to legal specialists in Giza and Minya | ( | ( | ( |
| 1.1.2 | Training workshop on managerial and financial skills (Giza, Minya Port Said) | NCCM | 2 new NGO grantees trained | ( | ( |  |
| 1.1.3 | Financial Auditing | NCCM | Increased capacity to monitor financially |  | ( |  |
| 1.1.4 | Technical Assistance | NCCM | No. of field visits and progress recorded | ( | ( | ( |

USAID Mission Director, Dr. Hilda Arellano conducted a site visit to the USAID project offices located at the National Council for Childhood and Motherhood, including FJP.  During the visit FJP staff presented activities and accomplishments to date as well as an overview of services offered by NGO grantees.  During the USAID visit, Ambassador Khattab, Director of NCCM, expressed her satisfaction with the work of the project, especially the capacity building for NGOs.  Ambassador Khattab noted that the FJP team has established a successful review and monitoring system that is considered a model for other projects at NCCM. The Mission Director thanked FJP for their successful efforts and noted that she is looking forward to field visits to observe first hand the services offered by the NGO community through FJP grants.

On March 10th, Ambassador Khattab of NCCM visited the family counseling center of the Islamic Charity Society, a partner with the New Horizons NGO.  Ambassador Khattab toured the premises and reviewed the services being provided.  A short program was conducted,                         Amb. Khattab reviews NGO files and activities

highlighting the various activities and achievements of the center, followed by a song selection from children who attend the center.  Ambassador Khattab provided closing remarks expressing her satisfaction with the services being provided and the capacity building being conducted for the NGOs.

On March 13th, the Minya Businessmen Association and its four partner NGOs concluded their grant activities with an event held in Minya and attended by Ambassador Khattab and Mr. Fouad Saad El Din, Minya, governor and Secretary General of the Governorate.  The event included 140 participants from the community, media and representatives of other Minya NGOs.  The event highlighted the accomplishments made through the grant and the effect of the services on beneficiaries. The event also served to raise public awareness in the community about the services offered and their benefits to children and families.

Amb. Khattab and Minya Governor at NGO program

In support of FJP’s NGO capacity building activities, Task Two completed legal specialist workshops for both Giza and Minya grantees.  Thirty nine participants completed the one-day workshop for Giza NGOs which was held on January 13, 2008, at the NCCM premises.   Ambassador Sadr of NCCM, Margaret Groarke of USAID and Teresa Cannady, FJP COP provided opening remarks. This program was a follow-up to the program held in November during which NGOs requested additional information and training on both Law 10 and the proposed amendments to the child law.  Representatives from both NCCM and the MOJ provided sessions on these topics, discussing openly with participants their concerns and suggestions to improve the system.

This legal workshop was repeated in Minya on February 12, with 79 participants from 10 Minya grantees, sub-grantees and partners completing the program.  One of the major outcomes from these events was that participants provided recommendations on the amendments to the child laws, which were compiled by FJP and provided to NCCM for further discussion and action by the amendment committee.  At least one of the suggestions made regarding medical check-ups prior to marriage was incorporated by the committee into the proposed amendments.

Additional capacity building activities included a financial orientation workshop for four Minya NGOs on February 14.  It was attended by accountants, financial managers and NGO treasurers. FJP also completed an orientation workshop at NCCM for recent Giza NGO grantees; Society of Local Community Development at Warak Al Hadar and Azhar Al Karma Foundation.  An orientation workshop was completed for 22 participants of 3 Port Said grantees on March 5th. These workshops outlined procedures and guidelines for technical and financial reporting to ensure compliance with FJP standards and forms.

On March 16th – 17th, the Alliance for Arab	Women completed training for 35 social workers from its counseling centers located in all three Pilot governorates. Dr. Hoda Badran conducted the training sessions on “Components of Family Counseling.” The event allowed participants an opportunity to share ideas and discuss mutual problems they are facing.

Some of the results achieved by the NGO grantees during this quarter include the following:

Minya:

- 75 participants received FJP reporting and financial training in order to assure their effectiveness in gathering information and maintaining FJP standards.

- 2,783 individuals visited FJP sponsored NGOs and counseling centers to obtain family counseling or information regarding family law and family dispute settlements.

- 16 trainings were held by NGOs reaching 303 participants across Minya; trainings provided citizens with the legal background regarding Law No. 10 and family courts.  Other training included the concept of counseling centers, media training, and mediation office services training.

- 102 awareness raising events were held reaching 6,889 participants.  The events discussed the importance of developing healthy family relationships and provided information on mediation office centers and NGO counseling centers throughout Minya.

- 3,986 home visits were conducted by NGOs to deliver messages about the benefit of family cohesiveness.

- 678 children received sponsorship to support their education and ensure that children who previously were school dropouts due to family disputes and in poor economic conditions to remain enrolled in educational programs.

Giza:

NGOs attend orientation workshop

- 46 participants attended FJP Reporting and Financial Training workshops in order to assure their effectiveness in gathering information and maintaining FJP standards.

- 17 trainings were held by NGOs reaching 366 participants in Giza; trainings provided attendees with legal background regarding Law No. 10 and family courts.  Other training included the concept of counseling centers, media training, and mediation office services training.

- 77 awareness raising events took place during the quarter reaching 3,942 individuals across Giza.  Some of the events helped promote counseling centers hosted by the NGOs while other events raised awareness around promoting healthy family environments and family law.

- 1,980 citizens visited FJP sponsored NGOs and counseling centers to obtain family counseling or information regarding family law and family dispute settlements.

- 992 children received sponsorship to support their education

### 1.2 New Grant Awards

FJP signed two new NGO grant agreements and four grant extensions.  The new NGO grantees are Port Fouad Child & Family Care Society and Organizations of Civilized Development at Port Fouad (El Hadareya).   Grant extensions were also issued to New Horizons Foundation of Giza and Social Services & Integrated Development, Egypt Renaissance Foundation, and The Good Shepherd of Minya.

Also, FJP is currently working with several NGOs and NCCM to provide extensions for additional successful grantees whose agreements are scheduled to end 2nd quarter FY2008.  Currently, FJP has awarded 30 grants totaling 1,722,000 USD (see Annex 2 for complete list of NGO grantees list).  Orientation workshops were provided to new grantees to familiarize them with FJP reporting requirements.  Currently, Task Two is evaluating additional NGO funding and awaiting NCCM feedback before submitting the new grant proposals for USAID approval.

## Component 2 - Media Community Awareness (NCCM)

### 2.1. National

| FY08 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 2.1.1 | Establish committee of experts on child development, psycho-social and family dynamics. | NCCM | Ongoing expert advice and review of media messages development | ( | ( | ( |
| 2.1.2 | Develop concepts for radio and TV programs. | NCCM | Participate and provide experts input on children for Radio and TV |  |  | ( |
| 2.1.3 | Develop children’s Sesame Street episodes (Alam Semsem) | NCCM | Use content developed by children committee to produce visual educational episodes to be aired on TV and used by NGOs for raising awareness |  | ( | ( |
| 2.1.5 | Develop flyers, posters Q&A booklet. | NCCM | Material developed to serve communication needs of the project | ( | ( | ( |

On March 10th, 2008 a media event at the Islamic Charity NGO, a sub-grantee of New Horizons was held.  Ambassador Khattab of NCCM and a representative from the Governors office in Giza attended and spoke at the event.  A short documentary film about mediation centers in the governorate of Giza was presented, followed by presentations from NGO representatives who provided highlights and accomplishments of the NGO, as well as testimonials from clients.  Also, a press conference was held to inform the media about family law issues and the work of the NGOs.  Guests were encouraged to visit the facilities and observe the daily activities of the NGO.  The event was later aired on two local television channels after the evening news.

During this quarter the media team worked closely with Ms. Amany El Sayaad, Head of the Women Programs at “El Bernamig El Aam” (General Program), a local radio station.  The episodes and time slots are being finalized with concepts already completed.  Also, FJP continues to coordinate with Alam Semsem (Sesame Street) to develop 12 segments for children on handling family disputes.  Their production cycles operate on a yearly basis; therefore these segments are being developed for the next cycle of programming set for 2009.

### 2.2. Pilot Regions Community-based (Giza, Minya and Port Said)

| FY2008 WorkPlan Activities for Q2 | Q2 |
| --- | --- |
|  | Activities | Counterpart | Output | Jan.08 | Feb.08 | Mar.08 |
| 2.2.1 | Campaign to promote counseling centers (1 event per governorate): Material development Opening ceremony | NCCM | Coordinating with individual NGOs, an estimated 500 attendees at each event | ( | ( | ( |
| 2.2.2 | Initiate youth work Materials developed | NCCM | Definition of youth target audience, age, gender and geographical distribution Main message to be developed to target audience Different channels of intervention |  | ( | ( |

FJP’s media team completed site visits to Giza and Minya NGOs throughout the quarter to document and film activities for a short video.  The video depicts the work being completed by NGOs in the community to provide public awareness and counseling centers.  The NGOs helped organize visits to the counseling centers and NGO offices, as well as interviews with beneficiaries and clients.  The media team visited rural villages which are benefiting from FJP sponsored NGO activities.  The first screening of this video was held during the media event previously described herein at a local NGO partner in Giza.  FJP will continue to develop the video with future activities and accomplishments to enlighten both the public and media about family law issues and responses.

Annexes

# Annex (1):  Agenda

# Mediation Skills Enhancement Training Program

# For Pilot Governorates

# Sofitel Hotel - Giza

# March 17-19, 2008

| 8.30 – 9.00 | Registration |
| --- | --- |
| 9.00 – 10.00 | Introduction Objectives Review /Assessment of the Pilot Training conducted 2007 Dr. Mohamed Khalil / Dr. Adel Madany |
| 10.30 – 12:00 | Session One: Legal Matters / Mediation Offices Regulations Open Discussion: Significant Practical Issues Counselor Wasseim Swielam, Member of the Technical Office, MOJ |
| 12:00 – 1:30 | Coffee Break |
|  | Session Two: Mediation Skills, Types of Mediation, and Mediation Steps from a Practical Approach Open Discussion: Significant Practical Issues Dr. Mohamed Khalil / Dr. Adel Madany |
| 2.00 – 2.30 | Coffee Break |
| 2.30 – 4.30 | Session Three: Communication Skills and Team Building Open Discussion: Significant Practical Issues Dr. Mohamed Khalil / Dr. Adel Madany |
| 4.30 – 5.00 | Lunch |

National Training Plan 2007-2008

| From | To | Total No. of Trainees | Average No. of Trainees per session | Training Location | Remarks / Proposed Training Venue |
| --- | --- | --- | --- | --- | --- |
| July 30, 2007 | August 2, 2007 | 104 | 35 | Cairo North | Triumph Hotel |
| August 6, 2007 | August 9, 2007 |  | 34 | Cairo North | Triumph Hotel |
| August 13, 2007 | August 16, 2007 |  | 35 | Cairo North | Triumph Hotel |
| August 20, 2007 | August 23, 2007 | 105 | 35 | Cairo South | Pyramisa Dokki |
| August 27, 2007 | August 30, 2007 |  | 35 | Cairo South | Pyramisa Dokki |
| September 3, 2007 | September 6, 2007 |  | 35 | Cairo South | Pyramisa Dokki |
| October 22, 2007 | October 25, 2007 | 62 | 31 | Beni Suef | Conference & Hotel center |
| October 29, 2007 | November 1, 2007 |  | 31 | Beni Suef | Conference & Hotel center |
| December 3, 2007 | December 6, 2007 | 109 | 37 | Assiut | Dal El Diafa, Assiut University |
| December 10, 2007 | December 13, 2007 |  | 36 | Assiut | Dal El Diafa, Assiut University |
| January 14, 2008 | January 17, 2008 |  | 36 | Assiut | Dal El Diafa, Assiut University |
| January 21, 2008 | January 24, 2008 | 124 | 31 | Sohag | El Safa Hotel |
| January 28, 2008 | January 31, 2008 |  | 31 | Sohag | El Safa Hotel |
| February 4, 2008 | February 7, 2008 |  | 31 | Sohag | El Safa Hotel |
| February 11, 2007 | February 14, 2008 |  | 31 | Sohag | El Safa Hotel |
| February 18, 2008 | February 21, 2008 | 150 | 37 | Qena | Iberotel |
| February 25, 2008 | February 28, 2008 |  | 38 | Qena | Iberotel |
| March 3, 2008 | March 6, 2008 |  | 37 | Qena | Iberotel |
| March 10, 2008 | March 13, 2008 |  | 38 | Qena | Iberotel |
| March 24, 2008 | March 27, 2008 | 48 | 24 | Aswan | Marhaba |
| March 31, 2008 | April 3, 2008 |  | 24 | Aswan | Isis Island |
| April 7, 2008 | April 10, 2008 | 71 | 36 | Benha | Sheaphard |
| April 21, 2008 | April 24, 2008 |  | 35 | Benha | Sheaphard |
| May 5, 2008 | May 8, 2008 | 85 | 28 | Shebin El Komm | Venecia Village |
| May 12, 2008 | May 15, 2008 |  | 29 | Shebin El Komm | Venecia Village |
| May 19, 2008 | May 22, 2008 |  | 28 | Shebin El Komm | Venecia Village |
| May 26, 2008 | May 29, 2008 | 29 | 29 | Damietta | Helnan Port Said |
| June 2, 2008 | June 5, 2008 | 38 | 38 | Fayoum | Helnan |
| June 9, 2008 | June 12, 2008 | 118 | 30 | Zagazig | Mercure Ismailia |
| June 16, 2008 | June 19, 2008 |  | 29 | Zagazig | Mercure Ismailia |
| June 23, 2008 | June 26, 2008 |  | 30 | Zagazig | Mercure Ismailia |
| June 30, 2008 | July 3, 2008 |  | 29 | Zagazig | Mercure Ismailia |
| July 7, 2008 | July 10, 2008 | 28 | 28 | Ismailia - N. Sinai | Mercure Ismailia |
| July 14, 2008 | July 18, 2008 | 14 | 14 | Suez -S. Sinai | Mercure Ismailia |
| August 4, 2008 | August 7, 2008 | 117 | 30 | Alex | Sofitel - Cecil |
| August 11, 2008 | August 14, 2008 |  | 29 | Alex | Sofitel - Cecil |
| August 18, 2008 | August 21, 2008 |  | 29 | Alex | Sofitel - Cecil |
| August 25, 2008 | August 28, 2008 |  | 29 | Alex | Sofitel - Cecil |
| October 13, 2008 | October 16, 2008 | 170 | 34 | Damanhour | Sofitel - Cecil |
| October 20, 2008 | October 23, 2008 |  | 34 | Damanhour | Sofitel - Cecil |
| October 27, 2008 | October 30, 2008 |  | 34 | Damanhour | Sofitel - Cecil |
| November 3, 2008 | November 6, 2008 |  | 34 | Damanhour | Sofitel - Cecil |
| November 10, 2008 | November 13, 2008 |  | 34 | Damanhour | Sofitel - Cecil |
| November 17, 2008 | November 20, 2008 | 129 | 32 | Tanta | Panorama |
| November 24, 2008 | November 27, 2008 |  | 32 | Tanta | Panorama |
| December 1, 2008 | December 4, 2008 |  | 32 | Tanta | Panorama |
| December 8, 2008 | December 11, 2008 |  | 33 | Tanta | Panorama |
| December 15, 2008 | December 18, 2008 | 131 | 32 | Mansoura | Ramada |
| January 12, 2009 | January 15, 2009 |  | 33 | Mansoura | Ramada |
| January 26, 2009 | January 29, 2008 |  | 33 | Mansoura | Ramada |
| February 2, 2009 | February 5, 2009 |  | 33 | Mansoura | Ramada |
| February 9, 2009 | February 12, 2009 | 61 | 31 | Kafr El Sheikh |  |
| February 23, 2009 | February 26, 2009 |  | 30 | Kafr El Sheikh |  |
|  |  | 1693 | 1693 |  |  |

# Annex (2): List of Grantees from FY07 to date

Grantees List

FY07-FY08 to date

| # | Proposal # | Grant # | NGO Name / Program Title | Program Location | Grant Duration (Months) / Start Date | Approx. Grant Amount ($000) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 111-71M22 | GA-263-06-01-00 | Minya Businessmen Association Family Justice Offices Program | Minya | 12 (17Dec 06) | 45 |
| 2 | 1-36O16 | GA-263-06-02-00 | New Horizons Foundation Interaction Program | Giza / Minya | 12 (1 Jan 07) | 48 |
| 3 | 1-4M1 | GA-263-06-03-00 | Samalut Culture Palace Pioneers Culture & Family | Minya | 12 (1 Jan 07) | 31 |
| 4 | 1-81M32 | GA-263-06-04-00 | Minya Coalition of Health NGOs Family Rights & Society Welfare | Minya | 24 (1 Jan 07) | 153 |
| 5 | 1-46G11 | GA-263-06-05-00 | Future Girls’ Association Justice Awareness & Empowerment for Family and Child | Giza | 12 (1 Jan 07) | 48 |
| 6 | 1-37G26 | GA-263-07-06-00 | National Association for the Defense of Rights and Freedoms Legal & Social Counseling for the Egyptian Family | Giza | 12 (1 Feb 07) | 25 |
| 7 | 1-72M23 | GA-263-07-07-00 | New Vision Association for Development Family Stability & Justice Enhancement | Minya | 12 (1 Feb 07) | 35 |
| 8 | 1-62M13 | GA-263-07-08-00 | Social Services & Integrated Development Family Support in Minya | Minya | 12 (1 Feb 07) | 31 |
| 9 | 1-66M17 | GA-263-07-09-00 | Egypt Renaissance Foundation Supporting Children Rights & Women Issues in Egyptian Family | Minya | 12 (11 Feb 07) | 37 |
| 10 | 1-70M21 | GA-263-07-10-00 | The Good Shepherd Liberty Children | Minya | 12 (1 April 07) | 21 |
| 11 | 1-20G7 | GA-263-07-11-00 | Hawaa Al-Mostakbal Society for Family & Environmental Community Cooperation against Family Violence | Giza | 12 (1 April 07) | 53 |
| 12 | 1-57G22 | GA-263-07-12-00 | Shemou’ Association for Human Rights & Local Development Enhancing the Bonds of Family Stability | Giza | 12 (1 April 07) | 45 |
| 13 | 1-41O20 | GA-263-07-13-00 | Center for Egyptian Family Development Happy Egyptian Family Program | Giza | 12 (1 April 07) Award Declined* | - |
| 14 | 1-33O13 | GA-263-07-14-00 | Alliance for Arab Women Supporting the Family Court | Giza, Minya, Port Said | 24 (1 June 07) | 257 |
| 15 | 1-5M2 | GA-263-07-15-00 | The Evangelical Association for sustainable Development Better Practice Towards minimizing Family Conflict | Minya | 12 (8 August 07) | 57 |
| 16 | 1-7M4 | GA-263-07-16-00 | Future Eve Happy Family void of Discrimination and Domestic Violence | Minya | 12 (8 August 07) | 32 |
| 17 | 1-69M20 | GA-263-07-17-00 | Sydat Misr Society for Women's Affairs Supporting Family Stability | Minya | 12 (8 August 07) | 27 |
| 18 | 1-31O11 | GA-263-07-18-00 | Masr El Mahroosa Baladi Association Towards Better Marriage | Giza | 15 (1 Sep. 07) | 77 |
| 19 | 1-32O12 | GA-263-07-19-00 | Caritas Egypt/Seti Center Stable Family Challenging Disability by Counsel and Empowerment | Giza | 12 (23 Sep. 07) | 70 |
| 20 | 1-16G3 | GA-263-07-20-00 | Al Tawan Association for Developing Local Community (Yad b Yad) Family Stability is the Base for Society Development | Giza | 12 (25 Sep. 07) | 36 |
| 21 | 1-26O6 | GA-263-07-21-00 | Heya Foundation for Women Accord for Family Safety | Giza | 12 (26 Sep. 07) | 46 |
| 22 | 1-48G13 | GA-263-07-22-00 | Egyptian Foundation for Family Development Mediation System Support | Giza | 12 (27Sep. 07) | 30 |
| 23 | 1-52G13 | GA-263-07-23-00 | Light of Life Association for Family & Child Family & Child Legal Protection | Giza | 12 (27 Sep. 07) | 52 |
| 24 | 1-58G23 | GA-263-08-01-00 | Society of Local Community Development at Warak AL Hadar Family legal & social services support | Giza | 12 (23 Dec. 07) | 82 |
| 25 | 1-34O14 | GA-263-08-02-00 | Azhhar AlKarma Foundation Better Life Program | Giza | 12 (23 Dec. 07) | 76 |
| 26 | MSS Recommendation /Orientation | GA-263-08-03-00 | Port Fouad Child & Family Care Society Family Justice | Port Said | 12 (25 Feb. 08) | 45 |
| 27 | MSS Recommendation /Orientation | GA-263-08-04-00 | Organization of Civilized Development at Port Fouad (El Hadareya) Stability & Better Future | Port Said | 12 (25 Feb. 08) | 65 |
| 28 | 1-36O16 | GA-263-06-02-02 | New Horizons Foundation Interaction Program | Giza | 12 (1 Apr 08) | 56 |
| 29 | 1-62M13 | GA-263-07-08-02 | Social Services & Integrated Development Family Support in Minya | Minya | 12 (1 Apr 08) | 60 |
| 30 | 1-66M17 | GA-263-07-09-02 | Egypt Renaissance Foundation Supporting Children Rights & Women Issues in Egyptian Family | Minya | 12 (1 Apr 08) | 31 |
| 31 | 1-70M21 | GA-263-07-10-01 | The Good Shepherd Liberty Children | Minya | 18 (1 April 08) | 51 |
| Total | 1,722,000 |

# Annex (3): Quarterly M&E Report

Summary of Project Performance

| Event | Output | Explanation |
| --- | --- | --- |
| Task 1 |  |  |
| Nationwide Mediation Training | 285 | Target for this quarter was 334 (portion of the Aswan training carried over into the 3rd quarter and will be reported on next quarter) |
| On going technical assistance: Booster Training (Pilot governorates) | 144 |  |
| Task II |  |  |
| New Grant Awards | 2 grants agreements signed | Current total is 30 grants/extensions |
| FJP Capacity Building Training | 3 trainings/132 participants |  |
| NGO Training Programs | 33 trainings/669 participants |  |
| NGO Activities | 4763 Counseling Center Visits 2539 Cases settled 1670 Children Supported 1005 Families Economically Empowered 203 Children at Risk Committees 4303 Home Visits 179 Awareness Raising events attended by 10,831 participants |  |
| Infrastructure |  |  |
| Giza | El Saaf at 90% completion, to be finished early 3rd quarter. RFP construction work issued for other sites. |  |
| Media |  |  |
| MOJ HQ Press Manual | In Progress |  |
| Documentary Film | On-going | Film continues to be updated for future use |
| Campaign to promote counseling centers |  | First of three events too place in Giza |

NGO M & E Details by Month

| 2.2.5 | NGO Capacity Building |  |  | Jan. | Feb. | Mar. | Q 2 Totals |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Training Activities |  |  |  |  |  |  |
|  | _ | No. of MSD Capacity Bldg. trainings conducted |  | 1 | 1 | 1 | 3 |
|  | _ | Number of attending trainees |  | 46 | 75 | 11 | 132 |
|  | _ | Number of NGO trainings conducted |  | 11 | 13 | 9 | 33 |
|  | _ | Number of attending trainees |  | 274 | 204 | 191 | 669 |
|  | Awareness raising events |  |  |  |  |  |
|  | _ | Number of Awareness events |  | 49 | 71 | 59 | 179 |
|  | _ | Number of Awareness event attendees |  | 2,075 | 6,143 | 2,613 | 10,831 |
| 2.2.6 | Monitoring & Evaluation |  |  |  |  |  |  |
|  | NGO Grantees Information |  |  |  |  |  |  |
|  | _ | Number of Sub Grantees and Partner Organizations |  |  |  |  | 43 |
|  | _ | Number Of Counseling Centers |  |  |  |  | 52 |
|  | NGO Performance |  |  |  |  |  |  |  |  |
|  | _ | Number Of Visits received |  |  | 1572 | 1486 | 1705 | 4763 |
|  | _ | Number of cases settled |  | 532 | 1011 | 996 | 2539 |
|  | _ | Number of children supported |  | 527 | 836 | 307 | 1670 |
|  | _ | Number of Family Econ. empowered |  | 159 | 337 | 509 | 1005 |
|  | _ | Number of (Child AT RISK) Committees |  | 73 | 113 | 17 | 203 |
|  | _ | Number of home visits conducted |  | 1852 | 915 | 1536 | 4303 |

Yellow highlights – numbers that feed into USAID Common Indicators

Mediation Training Details

| Nationwide training of court Mediators |  |  | Jan. | Feb. | Mar. |  | M | F | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | # trainees |  |  |  |  |
|  | LOCATION |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Assiut |  |  |  |  |  |  |  |  |  | 44 | 24 | 68 |
| 1.2.4 | Sohag |  |  |  |  |  | 62 | 62 |  |  | 42 | 93 | 135 |
| 1.2.5 | Qena |  |  |  |  |  |  | 75 | 75 |  | 62 | 30 | 92 |
| 1.2.6 | Aswan |  |  |  |  |  |  |  | 24 |  | 28 | 14 | 42 |
|  |  |  |  |  |  |  |  |  |  | Total | 176 | 161 | 337 |
| Skill Enhancement Training for Pilot Regions | Sessions | # of Trainings |  |  |  |  |
| 1.3.1 | P. Said | 3/26/08 | One 1-day |  | 15 |  |  |  | 5 | 13 | 18 |
| 1.3.2 | Giza | 3/17-3/19/08 | Three 1-day |  |  | 80 |  |  | 22 | 36 | 58 |
| 1.3.3 | Minya | 3/25-3/27/08 | Three 1-day |  |  |  | 80 |  | 50 | 18 | 68 |
|  |  | 17-19 Nov |  |  |  |  |  | Total | 77 | 67 | 144 |

MOJ Mediation Offices Visits

| Mediation OFFICES |
| --- |
| RECEIVED VISITS |
| A. Pilot Governorates |  |  |
| Pilot | Jan. | Feb. | March |
| P. SAID | 590 | 563 | 590 |
| MINYA | 1516 | 1621 | 1500 |
| GIZA | 2137 | 2407 | 2200 |
| TOTALS | 4243 | 4591 | 4290 |
| B. Nation wide training* |  |
| North Cairo |  |  |  |
| South Cairo |  |  |  |
| Beni Suef |  |  |  |
| Fayoum |  |  |  |
| Assiut |  |  |  |
| Sohag |  |  |  |
| Qena |  |  |  |
| Aswan |  |  |  |
| Benha |  |  |  |
| Shebin El Kom |  |  |  |
| Damietta |  |  |  |
| Zagazig |  |  |  |
| Ismailia-North Sinai |  |  |  |
| Suez South Sinai |  |  |  |
| Alexandria |  |  |  |
| TOTALS |  |  |  |
| Total/Month | 4243 | 4591 | 4290 |
| Q2 Total | 13124 | VISITS* |
| * Did not receive complete numbers from MOJ for all locations. |  |

# Text boxes

Annex (1): Agenda for Skills Enhancement Training

Annex (2): National Training Plan

Annex (4): M&E Report

Annex (3): List of Grantees