## FSIS Re-design

## Weekly Status – February 13th, 2004

Tasks completed this week:

- Provided feedback and approval on content development submissions - 296 submitted, 285 approved (see content approval tracker below).

- Continued development and testing of the 296 pages defined as in scope.

- Continued development and testing of the 75 pages additional to the 296 defined as in scope.

- Roger Baker continued structure review and analysis of the advisory committee sections and the FOIA reading room sections to determine if these areas can be better organized.

- Continued work on the vRep tool.  A total of 743 questions exist in the tool, 18 questions were accepted by content administrators, and 2 questions are in review.

- Barbara O’Brien and Diane Van received refresher training on the vRep approval process.

- Met with Dean Bramell to refine the Careers and HR Support areas of the site map.  The site map is updated with changes agreed upon in the meeting. Dean, assisted by Maria Miranda, is proceeding with development of content worksheets for the new pages about veterinary careers.

- OPAEO web staff and representatives of the FSIS e-government working group met with Phil Kinnison of the USDA Web Presence team to review and provide comments and changes to the USDA Web Presence migration strategy presentation.  The presentation will be updated and sent to all FSIS staff present in the meeting.

- Linda Eckrich presented a project overview and the re-designed FSIS test site to the usda.gov working group to show the progress of the effort and discuss lessons learned. She was asked to give a brief presentation at the next USDA webmasters meeting February 27.

- Maria Miranda provided initial Spanish translation of promotional graphics and drafted content for 14 pages identified for the re-designed En Espanol section.

Tasks for next week:

- Maria Miranda will refine content for the re-designed En Espanol section based on comments from FSES bilingual specialists Olga Catter and Maribel Machin.

- Bessie Berry will receive a vRep approval process refresher course on Wednesday, February 18.

- Continue development (adding approved content) and testing of the 296 pages defined as in scope.

- Complete development and testing of the 75 pages additional to the 296 defined as in scope.

- Continue to provide feedback and approval on content development submissions.

- Code the search results page to retrieve pages from the old and new site using indexing in IIS.

- Complete updates of the site map with changes that arose from the content development process.  Site map will indicate which pages or groups of pages will be left in the old look and feel at the time of launch.

- Identify additional pages for development.

- Initiate planning and scheduling of the FSIS Site Maintenance training.

- Initiate planning and scheduling of the Marketing and Communications Strategy Session.

- Initiate creation of the re-direct strategy document.

Issues:

- The vRep tool will be offline Thursday, February 12 and Friday, February 13 due to system updates being made by Native Minds.

- Need to finalize an internal FSIS, final content approval process for all pages with new content on the re-designed site.

- The USDA Meat & Poultry Hotline staff is responsible for adding and updating content in the vRep tool.  The approval piece is not working and the Re-design team is working with Native Minds to resolve the issue. A work around has been established that allows approvers to approve content by changing their user ID settings.

- Deadline for content development of 306 pages on Friday, December 12 was not met by FSIS content developers.  Development of all pages with approved content was not complete by the end of the task order on 1/23/03.  Content submissions and approvals have progressed slowly since the deadline and currently 97% of the in scope pages are approved by the Re-design team.

| CONTENT DEVELOPERS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name | # of Pages | # Submitted | # Approved | % Complete |
| Linda Eckrich | 75 | 75 | 75 | 100% |
| Ben Dinsmore | 30 | 30 | 29 | 97% |
| Dean Bramell | 35 | 35 | 35 | 100% |
| Pat Basu | 31 | 31 | 21 | 68% |
| Maria Miranda | 61 | 61 | 61 | 100% |
| Carol Blake/Noreen McGuirk | 18 | 18 | 18 | 100% |
| Ellen Matten | 13 | 13 | 13 | 100% |
| Hany Sidrak | 7 | 7 | 7 | 100% |
| David Reiners | 3 | 3 | 3 | 100% |
| N/A | 4 | 4 | 4 | 100% |
| Donna Robey/Roger Baker | 19 | 19 | 19 | 100% |
| Total | 296 | 296 | 285 | 106% |