## FSIS Re-design

## Weekly Status – January 8th, 2004

Tasks completed this week:

- Provided feedback and approval on content development submissions - 214 submitted, 171 approved (see content approval tracker below).

- Continued development and testing of the 306 pages defined as in scope.

- Continued development and testing of the pages additional to the 306 defined as in scope.

- Created white paper for the task order extension and reviewed with Sandy Facinoli.

- Scheduled meetings with Bryce Quick and Clif Gonzalez to discuss the extension task order.

Tasks for next week:

- Continue development and testing of the 306 pages defined as in scope.

- Continue development and testing of the pages additional to the 306 defined as in scope.

- Select final images for the promotional graphics.

- Continue to provide feedback and approval on content development submissions.

- Work with Bryce Quick to determine final content approval process.

- Complete FSIS Style Guide and send to design team for review.

- Meet with Bryce Quick and Clif Gonzalez to discuss the extension task order.

Issues:

- Deadline for content development of 306 pages on Friday, December 12 was not met by FSIS content developers.

- Development of all pages with approved content will not be complete by the end of the task order on 01/23/03.