# COMMUNICATIONS MISSION SUPPORT SCHEDULE

# prepared i.a.w ids-gycc-014

# SUPPORT INFO KEY

| 1 | V/S | QA | QUALITY |
| --- | --- | --- | --- |
| 2 | W/B | (r) | RECORDINGS (V/S) |
| 3 | PAO AUDIO/VIDEO | H | HAZARDOUS TEST |
| 4 | WTB | * | NEW TEST |
| 5 | OTV (39 AREA) | ** | CHANGE IN TEST |
| 6 | unassigned | (TEST TT) | REQUIRES TEST TROUBLE TICKET |
| 7 | OTV (IND AREA) | LI | KICS LINE ITEM |
| 8 | CABLE | M | KICS MINI |
| 9 | UNASSIGNED | C | CONTINGENCY |
| 10 | SHOP |  |  |

# FLOW AGENDA

|  |  | OPF 1 | OPF 2 | OPF 3 | VAB 1 | VAB 2 | VAB 3 | VAB 4 | PAD A | PAD B | FLIGHT | MISC. | PAYLOAD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MSN | (1) | (3) | (2) | (1) | (1) | (3) | (4) | (2) | (1) |  |  |  |
| DISCOVERY OV-103 | (2) |  |  | X |  |  |  |  |  |  | sts-121 | OPF-3 LCC-2 | ISS-23- 10A |
| ATLANTIS OV-104 | (1) |  |  |  | x |  |  |  |  |  | STS-114 | vab-1 LCC-1 | ISS-17- ULF1 |
| ENDEAVOUR OV-105 | (3) |  | x |  |  |  |  |  |  |  | sts-115 | opf-2 LCC-3 | iss-18- 12a |
| MLP-1 |  |  |  |  |  |  |  |  |  |  |  | e.refurb |  |
| MLP-2 |  |  |  |  |  |  |  |  |  |  |  | W.refurb |  |
| MLP-3 | (1) |  |  |  | x |  |  |  |  |  | STS-114 | VAB-1 |  |

# FOR QUESTIONS/ADDITIONS/DELETIONS ON THE MSSCHED, call 867-7640

friday   03/07/2003

# TABLE OF CONTENTS

SUPPORT INFO KEY	1

FLOW AGENDA	1

TABLE OF CONTENTS	2

PLANNED TEST FORECAST (PTF)	3

MISSION SUPPORT PLAN (MSP) STS-114	4

MISSION SUPPORT PLAN (MSP) STS-115	5

PLANNED TEST FORECAST (PTF)RECURRING SUPPORT	6

EXPENDABLE LAUNCH VEHICLE(ELV) SUPPORT	6

LAUNCH FORECAST (STS)	7

LAUNCH FORECAST (ER)	7

OIS-D SYSTEM CONFIGURATION	8

PRETEST BRIEFINGS/READINESS REVIEW	8

NASCOM 2000/CKT/SYSTEM DOWNTIME	8

OPF-1/opf-2/opf-3	9

VAB AREA	10

CX-39 AREA MISCELLANEOUS	11

PAD-A/PAD-B	12

PAYLOAD OPERATIONS	13

O&C MBR/auditorium	17

IND AREA/hmf/ER/SLF	18

recurring support	20

comm omi’s	22

# PLANNED TEST FORECAST (PTF)

NEXT LAUNCH:  STS-114

C = COMPLETED

| sts-114 | c | 01/29 | s5023 orb to vab |
| --- | --- | --- | --- |
| opf-1 | c | 01/29-02/04 | s0004 orb/et mate |
| vab-1/mlp-3 | c | 02/03-02/04 | s0008 sit test at vab |
| ov-104 | c | 01/29 | s0044 sim run |
|  |  | 03/10 | S0030S ORB/ET DEMATE |
|  |  | 03/13 | v5112.010 RETURN TO OPF-1 |
| pad-b/msn-1 |  | tbd | a5214 xfer to pad b cts: |
| grandparent |  | tbd | s0009 pad val |
| mwo 292227 |  | tbd | v1308/v1046.001 eng/ball seal lk cks |
|  |  | tbd | s0017 tcdt |
|  |  | tbd | s0024 prelaunch prop load |
|  |  | tbd | cryo sim |
|  |  | tbd | s5009 part iii ord instl |
|  |  | tbd | s0024 vol 2 hyper press/closeout |
|  |  | tbd | s0007 launch countdown |
|  |  | tbd | launch t-0:tbd window:tbd |
|  |  | tbd | s0028 ksc landing:tbd |

| sts-115 |  | TBD | s5023 orb to vab |
| --- | --- | --- | --- |
| opf-2 |  | TBD | s0004 orb/et mate |
| vab-1/mlp-2 |  | TBD | s0008 sit test at vab |
| ov-105 |  | TBD | s0044 sim run |
| pad-b/msn 3 |  | TBD | a5214 xfer to pad cts:tbd |
| grandparent |  | TBD | s0009 pad val |
| mwo 305055 |  | TBD | v1308/v1046.001 eng/ball seal lk cks |
|  |  | TBD | s0017 tcdt |
|  |  | TBD | s0024 prelaunch prop load |
|  |  | TBD | cryo sim |
|  |  | TBD | s5009 part iii ord instl |
|  |  | TBD | s0024 vol 2 hyper press/closeout |
|  |  | TBD | s0007 launch countdown |
|  |  | TBD | launch t-0:TBD window:TBD |
|  |  | TBD | s0028 ksc landing:TBD |

MISSION SUPPORT PLAN (MSP) STS-114

(OV104),OPF-1(MSN-1)/VAB-1/MLP-3(MSN-1)PAD-b(MSN-1)

| 292227 voice | 292227 wide band | 292227 video | status | sts-114(ov104) mission support plan(msp)grandparent mwo 292227 |
| --- | --- | --- | --- | --- |
| 297697 | 306554 | 297178 |  | SYSTEM PARENT MWO |
| 297698 |  | 297179 | comp | V9001 ORBITER POWER UP/DOWN OPF-1 |
| 297699 |  | 297180 | comp | A3206 MLP-3 MOVE FROM PAD-B TO VAB HB-3 |
| 297700 |  | 297181 | comp | B5303 STACKING AND ALIGNMENT OPERATIONS |
| 297701 |  | 297182 | comp | S0003 ET MOVE AND MATE SRB’S |
|  |  | 297183-pre 303724-post |  | B2038 HYDRAZINE SERVICE CART LOADING & DRAIN |
|  |  | 297184 |  | v2073 ORBITER ACCESS ARM LPS CHECKOUT PAD-B |
|  |  | 297185 |  | V2200 PAD-B HYPERGOLIC FUEL STORAGE AREA SERV(LPS) |
| 297702 |  | 297186 |  | A2202 SOUND SUPPRESSION WATER FLOW TEST PAD-B |
|  |  | 297187 |  | G2211 LH2 TANK PRESSURIZATION TEST USING LPS |
|  |  | 297188 |  | V2388 FLEXHOSE HYDROSTAT: HINGE COLUMN FSS/RSS PAD-B |
|  |  | 297189-pre 303728-post |  | V7234 OXID/FUEL FLOWMETER CALIBRATION |
| 297703 |  | 297190 | comp | s5023.001 ORB/ots transport ops – opf-1 to vab-3 |
| 297704 | 306555 | 297191 |  | S0044 SHUTTLE FINAL COUNTDOWN PHASE SIMULATION(LPS) |
| 297706 | 306556 | 297192 | comp | S0004 ORBITER MATE-VAB |
| 297707 | 306557 | 297193 | comp | S0008 SHUTTLE INTERFACE TEST-VAB |
| 297708 |  | 297194 |  | S9001 ORBITER POWER UP/DOWN-VAB/PAD |
| 297729 |  |  |  | MCSP MISSION CONFIGURATION SUPPORT PLAN |
| 297709 | 306558 | 297195 |  | A5214 SHUTTLE TRANSFER TO PAD-B |
| 297710 | 306559 | 297196 |  | S0009 SHUTTLE LAUNCH PAD-B VALIDATIONS |
| 297713 | 306560 | 297197 |  | S0024 PRELAUNCH PROPELLANT SERVICING/OMS/RCS |
|  |  | 297198 |  | B1016 SRB HYDRAZINE SYSTEM SERVICING PAD-B |
| 297714-v/s 297715-pao | 306561 | 297199 |  | S0017 TERMINAL COUNTDOWN DEMONSTRATION TEST (TCDT) |
| 297716 |  | 297200 |  | S1025 FLIGHT & GROUND CREW EMERGENCY EGRESS |
| 297717 | 306562 | 297201 |  | S5009 FINAL ORDNANCE INSTALL/CONNECT & C/O |
| 297718-v/s 297719-pao 297720-shp | 306563 | 297202 otv 297203 pao |  | S0007 SHUTTLE COUNTDOWN |
| 297721 | 306564 | 297204 |  | 6009 STS-114 FLIGHT |
| 297724 |  |  |  | S2005 POST LAUNCH PAD SECURING |
| 297725-v/s 297726-pao 297727-shp | 306566 | 297205 otv 297206 pao |  | S0028 STS-114 SHUTTLE LANDING/POST LANDING CONVOY OPS-SLF |
| 297728 | 306567 | 297207 |  | 10X00 CARGO SUPPORT |
| 297730 |  | 297208 |  | A3204 MOBILE LAUNCHER PLATFORM TRANSFER-PAD-B TO VAB/REFURB |

MISSION SUPPORT PLAN (MSP) STS-115

(OV105),OPF-2 msn(2),VAB-1/MLP-2 msn(3)PAD-B/MSN(3)

| 305055 voice | 305055 wide band | 305055 video | status | sts-115(ov105) mission support plan(msp)grandparent mwo 305055 |
| --- | --- | --- | --- | --- |
| 315420 | 308552 | 307089 |  | SYSTEM PARENT MWO |
| 315421 |  | 307090 |  | V9001 ORBITER POWER UP/DOWN OPF-2 |
| 315422 |  | 307091 |  | A3206 MLP-2 MOVE FROM E.REFURB TO VAB HB-1 |
| 315423 |  | 307092 |  | B5303 STACKING AND ALIGNMENT OPERATIONS |
| 315424 |  | 307093 |  | S0003 ET MOVE AND MATE SRB’S |
| 315425 |  |  |  | A2202 SOUND SUPRESSION WATER FLOW TESTING PAD-B |
|  |  | 307095-PRE 307122-POST |  | B2038 HYDRAZINE SERVICE CART LOADING & DRAIN |
|  |  | 307096 |  | v2073 ORBITER ACCESS ARM LPS CHECKOUT PAD-B |
|  |  | 307097 |  | V2200 PAD-B HYPERGOLIC FUEL STORAGE AREA SERV(LPS) |
|  |  | 307098 |  | A2202 SOUND SUPPRESSION WATER FLOW TEST PAD-B |
|  |  | 307099 |  | G2211 LH2 TANK PRESSURIZATION TEST USING LPS |
|  |  | 307100 |  | V2388 FLEXHOSE HYDROSTAT: HINGE COLUMN FSS/RSS PAD-B |
|  |  | 307102-PRE 307123-POST |  | V7234 OXID/FUEL FLOWMETER CALIBRATION pad-B |
| 315426 |  | 307103 |  | s5023.001 ORB/ots transport ops – opf to vab |
| 315427 | 308553 | 307104 |  | S0044 SHUTTLE FINAL COUNTDOWN PHASE SIMULATION(LPS) |
| 315428 | 308554 | 307105 |  | S0004 ORBITER MATE-VAB |
| 315429 | 308555 | 307106 |  | S0008 SHUTTLE INTERFACE TEST-VAB |
| 315431 |  | 307107 |  | S9001 ORBITER POWER UP/DOWN-VAB/PAD |
| 315449 |  |  |  | mcsp mission configuration support plan |
| 315432 | 308556 | 307108 |  | A5214 SHUTTLE TRANSFER TO PAD-B |
| 315433 | 308557 | 307109 |  | S0009 SHUTTLE LAUNCH PAD-X VALIDATIONS |
| 315434 | 308558 | 307110 |  | S0024 PRELAUNCH PROPELLANT SERVICING/OMS/RCS |
|  |  | 307111 |  | B1016 SRB HYDRAZINE SYSTEM SERVICING PAD-B |
| 315435-V/S 315436-PAO | 308560 | 307112 |  | S0017 TERMINAL COUNTDOWN DEMONSTRATION TEST (TCDT) |
| 315437 |  | 307113 |  | S1025 FLIGHT & GROUND CREW EMERGENCY EGRESS |
| 315438 | 308562 | 307114 |  | S5009 FINAL ORDNANCE INSTALL/CONNECT & C/O |
| 315439-V/S 315440-PAO 315441-SHP | 308563 | 307116-OTV 307116-PAO |  | S0007 SHUTTLE COUNTDOWN |
| 315442 | 308564 | 307117 |  | 6009 STS-115 FLIGHT |
| 315443 |  |  |  | S2005 POST LAUNCH PAD SECURING |
| 315444-V/S 315445-PAO 315447-SHP | 308565 | 307118-OTV 307119-PAO |  | S0028 STS-115 SHUTTLE LANDING/POST LANDING CONVOY OPS-SLF |
| 315448 | 308566 | 307120 |  | 10X00 CARGO SUPPORT |
| 315450 |  | 307121 |  | a3204 mlp transfer from pad-X to e.refurb |

PLANNED TEST FORECAST (PTF)RECURRING SUPPORT

01/01/2003 – 12/31/2003

MWO

| voice 312107 | wide band 312107 | video 312107 | test number | grandparent mwo 312107 |
| --- | --- | --- | --- | --- |
| 312555 | 311815 | 312027 | xxxxxxxxxx | parent mwo |
| 312559 | 311762 | 312028 | y-2279 | sd10010a pao support |
|  | 311780 | 312029 | y-1020 | sd10030b daily support |
|  |  | 312030 | y-1021 | sd10030c weekend lightning coverage |
|  |  | 312032 | y-1001 | sd0018b lightning monitoring and data collection |
|  | 311802 |  | y-1991 | SD10000 data systems continuous support |
| 312561 | 311486 |  |  | RD160 – KSC SUPPORT FOR ETR TITAN PROGRAM |
| 312561 | 311756 |  |  | RD160 – KSC SUPPORT FOR ETR ATLAS PROGRAM |
| 312561 | 311757 |  |  | RD160 – KSC SUPPORT FOR ETR DELTA PROGRAM |
| 312561 | 311759 |  |  | RD160 – KSC SUPPORT FOR ETR PEGASUS PROGRAM |
| 312561 | 311885 |  |  | RD160 – KSC SUPPORT FOR ETR SHUTTLE SUPPORT |
| 312563 |  |  |  | NASA SELECT AUDIO ON OIS 235/OIS MULTI-CHANNEL XMIT |
| 270116 |  |  |  | V9001 (OPF) POWER UP OF UNDEFINED OR FUTURE MISSIONS |

EXPENDABLE LAUNCH VEHICLE(ELV) SUPPORT

01/01/2003 – 12/31/2003

mwo

| VOICE (1) | WIDE BAND (2) | t-0 | TEST # | DESCRIPTION |
| --- | --- | --- | --- | --- |
| 318117 |  | 04/04/03 | F-8170 | PEGASUS/GALEX (T/C C7600C1 – C7600C7) |
| 322868 | 303877 | 04/15/03 | F-8615 | SIRTF/DELTA II |
| 313385 |  |  |  | titan iv b-35 |
| 319110 |  |  |  | MARS EXPLORATORY ROVER-1 (MER-1) |
| 319107 |  |  |  | MARS EXPLORATORY ROVER-2 (MER-2) |
| 312000 |  |  |  | proseds |

# LAUNCH FORECAST (STS)

| C | FLT STS | ORB OV- | LAUNCH DATE | LAND AT: | LANDING DATE | PAYLOAD | PAD | VAB HB | OPF | MLP | CREW | LCC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| c | 109 | 102 | 3/01/02 | ksc | 3/12/02 | hst sm 3b | a | 3 | 3 | 2 | 7 | 2/1 |
| c | 110 | 104 | 4/08/02 | ksc | 4/19/02 | iss-13-8a | b | 1 | 2 | 3 | 7 | 2/3 |
| C | 111 | 105 | 6/05/02 | DRD | 6/19/02 | iss-14-uf2 | a | 3 | 1 | 1 | 7 | 2/1 |
| C | 112 | 104 | 10/07/02 | KSC | 10/18/02 | ISS-15-9A/S1 | b | 3 | 1 | 3 | 6 | 2/3 |
| c | 113 | 105 | 11/23/02 | KSC | 12/07/02 | ISS-16-11A | a | 1 | 1 | 2 | 6 | 2/1 |
|  | 107 | 102 | 01/16/03 |  |  | freestar | A | 3 | 2 | 1 | 7 | 2/3 |
|  | 114 | 104 | TBD | KSC | TBD | ISS-17-ULF1 | B | 3 | 1 | 3 | 7 | 2/1 |
|  | 115 | 105 | TBD | KSC | TBD | ISS-18-12A | B | 1 | 2 | 2 | 6 | 2/3 |
|  | 116 | 104 | TBD | KSC | TBD | ISS-19-12A.1 | B | 3 | 1 | 1 | 7 | 2/ |
|  | 117 | 105 | TBD | KSC | TBD | ISS-20-13A | A | 1 | 2 | 3 | 6 | 2/ |
|  | 118 | 102 | TBD | KSC | TBD | ISS-21-13A.1 | B | 3 | 1 | 2 | 6 | 2/ |

# LAUNCH FORECAST (ER)

| C | VEHICLE | PAYLOAD | CX | WINDOW | OPR # |
| --- | --- | --- | --- | --- | --- |
| C | pegasus | SORCE(NASA) | L1011 | 01/25/1510e – 1608e | F-8451 |
| C | delta ii | gps iir-8 | 17b | 01/29/1306e – 1320e | a-7957 |
|  | delta iv | dscs-1 | 37b | 03/08/1844e – 2002e | f-7265 |
|  | atlas v | hellasat | 41 | 03/14/1600e – 1800e | g-4402 |
|  | PEGASUS | GALEX(NASA) | L1011 | 03/25/0650e – 0850e | F-8170 |
|  | delta ii | gps iir-9 | 17a | 03/29/1700e – 1717e | a-7962 |
|  | TITAN IV | B-35 (NO IUS) | 40 | 04/06/0951E – 1351E | F-9101 |
|  | ATLAS IIIB | ASIASAT 4 | 36B | 04/10/1900E - 2100E | F-6155 |
|  | DELTA II | SIRTF (NASA) | 17B | 04/15/0534E | F-8615 |
|  | atlas v | rainbow | 41 | 05/08/0700e – 0900e | g-4303 |
|  | delta ii | mars rover a nasa | 17a | 05/30/0000 | f-7326 |
|  | titan iv | b-36 nrol-19 | 40 | 06/09/0000 | f-9069 |
|  | delta ii | mars rover b nasa | 17b | 06/25/0000 | f-7336 |
|  | delta iv | dscs-2 | 37 | 07/01/0000 | f-8315 |
|  | delta ii | gps iir-10 | 17a | 07/18/0000 | a-8758 |
|  | atlas iias | syperbird-6 | 36a | 09/03/0000 | g-4409 |

# OIS-D SYSTEM CONFIGURATION

| PERM | TEST OR EVENT i/a | ASSIGN DATE/TIME |
| --- | --- | --- |
| DAILY_158 | M12_TDRS TO SAEF II | 11/05/0800E |
| DAILY_159 | UR 2 TO PLM1/UR 6 TO DAILY A | 12/17/0730E |
| daily_160 | sts-107 support msn (3) | 01/15/1200e |

| PERM | TEST OR EVENT LC-39 | ASSIGN DATE/TIME |
| --- | --- | --- |
| 2DAILY_STS114 | OPF-1 TO MSN (1) | 02/14/0830E |
| 4DAILY_STS114 | OPF-3/PAD-A/LCC-2 TO MSN(2), OPF-2 TO MSN(3) | 02/24/0001E |
| 5daily_sts114 | vab-1 to msn (1) | 02/25/0001e |
| 6DAILY_STS114 | VAB-3 TO MSN (3) | 02/26/0001E |
| 7daily_sts114 | pad-a/mlp-1 to msn (3) | 03/04/0001e |
| 8daily_sts114 | pad-a to msn (2) | 03/05/0001e |

# PRETEST BRIEFINGS/READINESS REVIEW

# NASCOM 2000/CKT/SYSTEM DOWNTIME

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS CX-39 AREA TEST EVENTS OPF-1/opf-2/opf-3 | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| y-4164 (1)315421 (5)307090 li 2008 | v9001.102a1 power up sts-115 (ov-105) area:opf-2 support per mwos msn (3) | 12 |  |  | 12 | 12 | 12 | 12 |
| Y-1165 (1)(R) LI 2070 | V1014.001C FCL 1/2 RADIATOR FLOW CONTROL C/O AREA:OPF-2 RCRD OIS CH 132,143,232 MSN(3) | 12 |  |  | 12 | 12 |  |  |
| y-1175 (1)(r) li 2051 | V1078.001A01(run 2)APU 1/2/3 LUBE OIS SERVICING AREA:OPF-2 RCRD OIS CH 182 MSN (3) |  |  |  |  |  | 1 |  |
| y-1181 (1)(r)(5)qa m 02-1 | V5011.002Z RH OMS POD INSTALL AREA:OPF-2 RCRD OIS CH 111,117,142,232 MSN (3) PROVIDE 2 PORT OIS-D UNITS IN XFER AISLE OTV PROVIDE CAM 95A PURGE AND PRESSURES REQUIRED COMM LOCKOUT:TBD COMM RESTORE:TBD |  |  |  |  |  |  | 12 h |
| *y-1184 (5) (1)mwo-tbd m 01-1 | V5112.010 ORBITER TRANSPORT VAB TO OPF-1 (STS-114) V/S SUPPORT PER MWO MSN (1) OTV RECORD CAM 081,082 |  |  |  |  |  |  | 1 H |

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS CX-39 AREA TEST EVENTS VAB AREA | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Y-1041 1 r/t | VAB DAILY SUPPORT AREA: VAB PROVIDE 1 UHF RADIO CONTACT: D. SMITH 1-5108 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1176 (1)297708 (5)297194 LI 5007 | S9001 VEH PWR UP/SYS SNAPSHOTS AREA:VAB-1,MLP-3 (STS-114) SUPPORT PER MWO’S MSN (1) |  |  |  | 1 |  |  |  |
| Y-1177 (1)(R)(5) M V-15 | S0030S ORB/ET DEMATE AREA:VAB-1,MLP-3 (STS-114) RCRD OIS CH 111,114,117,131, 136,138,142,146,232 MSN (1) OTV RECORD CAM 82,83,84,85 cts:11/0800e | 12 |  |  | 1 | 12 | 312 hh |  |

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS CX-39 AREA TEST EVENTS CX-39 AREA MISCELLANEOUS | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Y-1341 (1) VSCSD3 | LC-39 AREA BCDS CONFIGURATION AREA:LC-39 CONFIG PRIME M1, ALSO ASSIGN THE FOLLOWING: CH FREQ OIS-D 30 153.4 3156** 31 153.5 3166** 32 153.6 3176 33 153.7 2151 34 153.8 2156 35 153.9 2166 36 154.0 2176 37 154.1 1176 38 154.2 1177** 39 154.3 1187** 40 154.4 3155** CONTACT:SCHEDULER 7-7640 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |

| test numberS SUPPORT infO SOURCE | OPERATIONS CX-39 AREA TEST EVENTS PAD-A/PAD-B | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

blank page

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS CX-39 & INDUSTRIAL AREAS PAYLOAD OPERATIONS | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| y-1120 (1)319107 (1)319110 (1)320772 | mars exploration rovers (Mer 1&2) support per mwo’s t/c a3 | 312 |  |  | 312 | 312 | 312 | 312 |
| Y-1153 G4006 (2) | PRO-SEDS WIDEBAND CONFIG AREAS:AE,XY,CD&SC,VPF PROVIDE XY TO VPF CKTS: 6TVC3805/6TVM4021 6TVC3808/6TVM4022 6TVC3809/6TVM4023 6TVC3811/6TVM4680 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1058 (1) | SSPF CR1 (ROOM 2397) CONFIG (J1) 207-07 52D (J2) 204-27 52D (J3) 205-27 52D (J4) 204-48 52D (J5) 205048 52D (J6) 206-48 52D (J7) 207-48 52D (J8) 204-67 52D (J9) 205-67 52D (J10) 206-68 53D (J11) 207-68 53D (J12) 206-56 52D | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| y-1314 (1) | sspf CR2 (ROOM 2393) CONFIG ptd 204-26 51d ptc 205-26 51d (j1) 206-27 52d (j2) 207-27 52d (j3) 204-47 52d (j4) 205-47 52d (j5) 206-47 52d (j6) 207-47 52d (j7) 204-66 52d (j8) 205-66 52d (j9) 206-67 52d (j10) 207-67 52d | 312 | 312 | 312 | 312 | 312 | 312 | 312 |

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS CX-39 & INDUSTRIAL AREAS PAYLOAD OPERATIONS | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| y-1315 (1) | sspf CR3 (ROOM 2387) CONFIG ptd 204-07 51d ptc 205-07 51d (j1) 205-25 52d (j2) 206-26 52d (j3) 207-26 52d (j4) 204-46 52d (j5) 205-46 52d (j6) 206-46 52d (j8) 204-65 52d (j9) 205-65 52d | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1537 (1) | SSPF CR9 (room 2353) CONFIG PTD 207-20 51D PTC 206-40 51D (J1) 204-57 52D (J2) 205-76 52D (J3) 206-76 52D (J4) 207-76 52D (J5) 204-20 52D (J6) 205-20 52D (J7) 206-20 52D (J8) 204-40 52D | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1538 (1) | SSPF QTMR (room 2398) CONFIG (J1) 206-62 52D (J2) 207-62 52D (J3) 204-18 52D (J4) 205-18 52D (J5) 206-58 53D | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| y-1091 G4851 (2) (1)(R)318117 t/c 7600c1, 7600c4 (1)315262 (1)319113 | galex ois-d configuration area:cd&sc,mppf,o&c,ae,gsfc, jpl v/s support per mwo’S W/B PATCH 6TVC3810/6TVM4222 & 6TVC4220/6TVC3905 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS CX-39 & INDUSTRIAL AREAS PAYLOAD OPERATIONS | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| y-1317 (1) | sspf high bay (FP) #4 config (j1) 206-0e lpis stand (j2) 207-0d lpis stand (j3) 204-2e lpis stand (j4) 205-2f lpis stand (j5) 206-2f lpis stand (j6) 207-2f lpis stand (j11) 204-6e lpis stand (j12) 205-6c lpis stand | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1145 (1) | SSPF HIGH BAY (FP) #7 COnFIG (j1) 206-31 (j2) 207-31 (j3) 204-51 (j4) 205-51 (j5) 206-51 (j6) 207-51 (j7) 204-70 (j8) 205-6E (j9) 206-6F (j10) 207-71 (j11) 204-12 (j12) 205-12 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1340 (1) | SSPF HIGH BAY (FP) #8 CONFIG (J1) 206-11 (J2) 207-10 (J3) 204-31 (J4) 205-31 (J5) 206-32 (J6) 207-32 (J7) 204-52 (J8) 205-52 (J9) 206-52 (J10) 207-52 (J11) 204-71 (J12) 205-6F (J1) 204-24 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS CX-39 & INDUSTRIAL AREAS PAYLOAD OPERATIONS | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Y-1338 (1) | SSPF INTERBAY #8 CONFIGURATION (J1) 204-33 P1 CEWS (J2) 205-33 P1 CEWS (J3) 206-34 P1 CEWS (J4) 207-34 P1 CEWS (J5) 204-54 P1 CEWS | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1277 (1) | SSPF INTERBAY #4 CONFIGURATION (J1) 204-32 USICU (J2) 205-32 USICU (J3) 205-35 USICU (J4) 206-14 USICU (J5) 205-57 USICU | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1827 (1) | SSPF INTERBAY #3 CONFIGURATION (J1) 206-12 USICU (J2) 207-11 USICU (J3) 206-74 USICU (J4) 205-73 USICU (J5) 206-55 USICU | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1667 (1) | SSPF INTERBAY #5 CONFIGURATION (J1) 206-33 PTCS (J2) 207-33 PTCS | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-4195 (1)(R) | HEATER CHANNEL TEST AREA:SSPF RCRD OIS CH 076 MSN (15) |  |  |  |  |  |  |  |

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS INDUSTRIAL AREA O&C MBR/auditorium | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

AUDITORIUM:

3/10	8:30 AM - 10:00 AM	BLOOD BORN PATHEGEN		LARRY DAVIS 7-2027

3/12	12:00 P - 4:00 PM	EEO DIVERSITY BRIEFING		CLARA ANDERSON 7-2087

3/14	1:00 PM - 2:00 PM	SOW REFINEMENT BRIEFING		PEGGY PARRISH 476-4000

| TEST number SUPPORT INFO source | OPERATIONS TEST EVENTS IND AREA/hmf/ER/SLF | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Y-1023 (1)270567 (2)311762 (3)312028 | NTV VIDEO FILE SUPPORT INCOMING (NASA HQ) AMC2 FEED (XP-9) PER mwo’s MON – FRI: 1200E – 1300E | 1 |  |  | 1 | 1 | 1 | 1 |
| y-2279 (1)270567 (2)311762 (3)312028 | iss expedition vi flight and docking coverage via jsc AMC2 xp9 support per mwo’s fully distribute iss expedition V commentary(audio and video) ksctv assign the iss a/g audio as received to ckts (321-867-4003) and (321-867-4920) no manning required | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-2088 (1)273503 | DELTA II SIRTF/JPL LINK SUPPORT PER MWO EXTEND KJPL63559 TO HANGAR AE FROM KSC NODE 04/15/29 TO HANGAR AE NODE 16/15/01 S:09/19/02-05/01/03 0800E-1600E MONDAY-FRIDAY | 1 |  |  | 1 | 1 | 1 | 1 |
| Y-1178 G-3880-G3886 (4) (1)312561 (2)311757 T/C A,B,C,D | DELTA IV F-1’S AREAS:RADAR 1914,LCC,TEL-IV,XY, AE,(UCS 1,2,3,7,8 & PB DOAMS), HRT/MCBR SUPPORT PER MWO’S S:07/0800E-1600E | 1 |  |  |  |  |  |  |

| TEST number SUPPORT INFO source | OPERATIONS TEST EVENTS IND AREA/hmf/ER/SLF | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Y-1179 F-7265 (4)(5) (1)312561 (2)311757 T/C A,B,C, D,F | DELTA IV LAUNCH AREAS:RADAR 1914,LCC,TEL-IV,XY, AE,(UCS 1,2,3,7,8 & PB DOAMS), HRT/MCBR,USB,O&C SUPPORT PER MWO’S JYVO PATCH 6TVM2124 TO 6TVC2285 S:08/1159E-2002E T-0:08/1844E manning required |  | 12 |  |  |  |  |  |
| *Y-1185 R1200/R1299 (1)312561 (2)311885 | EASTERN RANGE ISCF ACCEPTANCE TESTING AREAS:RADAR 1914,LCC,TEL-IV,XY, AE,(UCS 5,6,8 & PB DOAMS) SUPPORT PER MWO’S S:13/0800E-1210E |  |  |  |  |  |  | 1 |

| TEST number SUPPORT INFO source | OPERATIONS TEST EVENTS recurring support | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Y-1006 (1)(R) gary carr 867-2276 | LC39 AREA CRANE AND GENERAL POOL RADIO SUPPORT RECORD: 2RAM012, 2RAM014, 2RAM016, 2RAM017, 2RAM018, 2RAM021, 2RAM022, 2RAM023, 2RAM025, 2RAM027, 2RAM028 NO O/T MANNING REQ’D | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1009 (1)(R) | AUDIO RECORDING OF CH’S PER VSCSD6 ALSO RCRD OIS CH 132 MSN (2) & MSN (4) NO O/T MANNING REQ’D | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1010 (1)(R) | LETF TEST ACTIVITIES RCRD OIS CH 103 msn (14) CONTACT: VAN GUILDER, 867-4422 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Y-1011 (1)(R) | TEST CELL/POD PWR ON TESTING AREAS: M7-961e & W, M7-1212 RCRD OIS CH 001-006 msn (5) | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| y-1012 (1)(r) | o&c crane radio support rcrd uhf 2ram001,2ram004 & 2ram007 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1014 (1)(R) | MMSE CANISTER OPERATIONS RCRD I/A UHF CH 6 (2RAC600)OIS CH 235 MSN (15) ALSO RCRD 2RAM500 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1016 (1)269724 | MULTI-CHANNEL TRANSMISSION AREAS:LCC 1P9,1P10 SUPPORT PER MWO | 312 | 312 | 312 | 312 | 312 | 312 | 312 |

| TEST number SUPPORT INFO source | OPERATIONS TEST EVENTS RECURRING SUPPORT | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Y-1007 (2)311780 | MINOR SUPPORT per mwo AREAS: TEL-4, CDSC, MILA CONTACT MILA PRIOR TO ANY CKT RECONFIGURATION ON THIS mwo NO O/T MANNING REQ’D | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1991 (2)311802 | DATA SYSTEMS CONTINUOUS SUPPORT W/B SUPPORT PER MWO NO O/T MANNING REQ’D | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1004 (5)312029 | daily support/CAPE WX OTV SUPPORT PER mwo CONTACT: JOHN MADURA, 867-2666 | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1001 (5)312032 | S0018 WEATHER SUPPORT/BIRD WATCH SUPPORT OTV SUPPORT PER MWO | 312 | 312 | 312 | 312 | 312 | 312 | 312 |
| Y-1021 (5)312030 | WEEKEND OTV CAM COVERAGE AREAS: PAD-A,PAD-B,VAB, OPF-1/2/3 SUPPORT PER mwo S:3RD SHIFT & WEEKENDS | 3 | 312 | 312 | 3 | 3 | 3 | 3 |

| TEST NUMBERS SUPPORT INFO SOURCE | OPERATIONS comm omi’s | fr 07 | Sa 08 | su 09 | mo 10 | tu 11 | we 12 | th 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| d6121c pads a/b | seq. 15 otv pressure checks qa required | 12 |  |  | 12 | 12 | 12 | 12 |
| D6121C HMF | SEQ. 15 OTV PRESSURE CHECKS EVERY TUESDAY-QA REQUIRED |  |  |  |  | 12 |  |  |