# MEMORANDUM

To:		Distribution

From:		George R. Neil

Subject:	FEL Upgrade Project Weekly Brief - March 26-30, 2007

Date:		March 30, 2007

Highlights:

We performed an extensive series of tests of harmonic production for JTO supported work for SAIC.  We also were able to conclude the week with some initial measurements aimed at resolving the source and dependence of CSR and/or longitudinal space charge induced energy spread in our second arc.  We were also able to provide some beam time after-hours for the nanotube setup, off resonant optical trap, and Aerospace microengineering station.

Management:

We held two coordination meetings to plan the up-coming installation of the high Q cryomirror and cooled wiggler chamber.   That installation is now scheduled to commence late next week barring any unknown hardware fabrication issues in final assembly of either item.

We worked with lab management to provide DOE with budget requests in support of a new Infrastructure initiative and reviewed the JLab response plan for Avian Flu.

We continued work with Integrated Safety Management to assess our readiness to support the safety audit scheduled for this summer similar to that recently completed by SLAC.

Michelle Shinn attended a review of the Colorado State University (CSU) - led proposal on optics and coating development that was submitted in response to an ONR solicitation

Operations:

It was a busy week with operations going into the evening most days.   On Monday we completed the work on the new 1 micron high reflector and started setting up for 2.8 micron operations for harmonic studies for SAIC.  We set up the harmonic energy measurement on Monday afternoon and took data on Tuesday.  We had one problem with a translation stage for this setup that prevented us from optimizing the energy throughput through the slits.  We were able to get data of the harmonic energy vs. cavity length detuning for harmonics up to the 6th.  We still need to calibrate the system to get the ratio of the power at the detector to the power in the resonator.  Once this is done we will have good numbers for the harmonic energy vs. the  fundamental  We did see a sharp spike in the harmonic intensity for  the 2nd, 3rd, and 5th harmonics at the synchronous point.  This is similar to what we saw in the IR Demo. 
    On Wednesday and Thursday we ran 1.06 micron at low power for the FORT experiment conducted for Old Dominion University.  This was a good test of the stability of our optical transport system.  We found that the transport drifted with steering errors on the order of 10 microradians at the collimator.  We will have to do better than this to deliver beam for damage tests in user lab 2.  The beam quality for 1 micron lasing was not very good since the mirror tended to distort  badly as soon as it heated up.

Wednesday and Thursday evening were spent on running for modulation measurements in the injector and boron nitride nanotube production in User Lab 1.  Today we are taking data on CSR/LSC induced emittance growth in the optical chicane.  We want to be able to compare the energy distribution in the second arc as a function of the bunching.

Injector Diagnostic Development

This week we took a fair amount of data investigating new possibilities for beam diagnostics in the injector.

We turned on the modulation of buncher gradient, cavity 1-3 and cavity 1-4, modulating different elements at different frequencies, i.e., 3 kHz, 4 kHz and 5 kHz. With very small modulation on the gradient of the 1-3 and 1-4 we got a very good measurable signal in the 0F06a BPM.

We repeated the Drive Laser phase scan. We found again that the zero crossing of the buncher determined by the new technique we are developing is different from the zero crossing as determined by our present procedure. We need to do some data analysis to understand the difference. To do so, we took additional measurements of the bunch length at the two different phases of the drive laser. Next we investigated the dependence of the transverse beam position modulation downstream of the ¼ cryo unit as a function of the beam trajectory through the buncher cavity. We clearly can see that a small trajectory change affects the beam modulation amplitude fairly strongly so that the effects of the transversal beam kick by the buncher and the energy modulation by the buncher measured at the 0F06a BPM are comparable.

Finally, a set of measurements was made changing cavity 1-3 phase and measuring the beam position modulation at the 0F06a BPM. Presently we are analyzing the data.

Injector:

The photocathode gun has delivered about 12 Coulombs and 8 hours of CW beam time during the week with a QE drop of about 0.5%. A task hazard analysis for the calibration of the photocathode QE scanner was prepared and on-the-field practices reviewed by Patty Hunt from the ESH&Q Division.

Gun Test Stand
Blank Conflat Flanges have been collected and are being prepared to be mounted to the gun chamber for vacuum firing. We prepared initial documentation required for the installation of the Personal Safety System and an initial task schedule. Electrical work and purchase of components is in progress after power requirements were specified to the proper parties in the Engineering Division. Hazard analysis documentation is in progress.

Instrumentation & Controls:

Major efforts continue in the new Gun Test Stand (GTS). Installation of the network cabling for the GTS control room (room 217) has been scheduled to begin the week of 4/9. The network switch has been purchased and configured along with additional patch cables and patch panels. Work has begun on some light refurbishing of the GTS HV tank. Since we are designing much of our instrumentation and controls for the Gun Test Stand around the 3U General Purpose Processor Card and the Single Board IOC, we decided to make some modifications to the SBIOC design to make it easier to do some of the simpler functions. We took one of the blank pcbs that we had and assembled it according to the modifications. This board with these modifications is currently under testing. The new gun’s quantum efficiency scanner has also been ordered. This is a galvo unit purchased from http://gs-scanners.com/ 
   Testing continued this week with the 4-Ch Charge/Dump Current Monitor. Many of the circuits that are used on this PCB are also used on the High Voltage Power Supply(HVPS) Analog I/O module. Testing was completed on all of the circuits needed for the analog module and these circuits are being incorporated into the analog module design. Currently the schematic for this board is well underway. The overall functionality and design goals have been planned out so some of the design details are still being worked out though. The design goals for the Digital I/O module are clear as well but many of the design details still need to be cleared up as well. 
To support the High Q Mirror Test, the parts needed to break out the Silicon Diode Temperature sensors to a precision ADC are all being assembled and planned out. We have a test fixture assembled to simulate the diodes at the temperature of 40K and we can track the voltage over several days to get a noise calibration of the entire system. The breakout system to patch the required signals into the ADC has been assembled and is ready for installation. This will be installed along with all of the cabling early in the upcoming down to get as much time for the noise calibration and system check out as possible. 
The script for shutting down the FEL has been heavily modified. As the requirements changed the existing application lacked sufficient flexibility to easily meet those needs. The application is now highly flexible and new modes of shutting down can be added without generating a lot of code. Time on Monday has been allotted to shake out the new code and determine where changes may need to be made. 
   Work continues on the Laser Personnel Safety System. All the door monitors for the LPSS were installed this week. Additionally, we have decided it is more cost efficient to design a board for the LPSS PA system than it is to purchase the pre-made board, so design of the PA board is starting today. It will utilize the Winbond Chipcorder 17150 package for the sound record/playback. The chip will be programmed using the Winbond ES17XX_USB Evaluation board. The sound amplification for the system will be done using the ST-PA6 audio amplifier made by Radio Design Labs. 
   Work also continues on the Single Board IOC. The 20 I/O pins were connected between the ColdFire and the FPGA and the prototype board was modified for this connection. The code was programmed for the connection and loaded on the FPGA. With these 20 I/O pins, the Single Board IOC will have more functions for digital I/O controls. Also added the signals (TIP and TS) from the Coldfire to the FPGA. These two signals are used for Chip Select function that the ColdFire controls the FPGA through the bridge. The ColdFire-FPGA bridge was updated and loaded on the FPGA. The bridge works great and the ColdFire can read and write the data from the RAM on FPGA. The revised Single Board IOC is under debuging. After the testing, we will make new version and will start to use it for Beam View control. 
   The FELWiki website is now available for offsite access at: http://fel.jlab.org/wiki. Access requires your CUE username and password as does each users wiki account login for editing. (i.e. no registration required - just log in and edit) In preparing the new FEL wiki site, the PHP maintenance scripts were written to generate and import 12,569+ new wiki articles as "reserved" in order to maintain a 1:1 correspondence with the existing Devlore database. Everyone is invited to add and modify content. Off-site file uploads are also possible.

Beam Transport:

Improvements and Upgrades

New Gun Test Stand

• 	In calculating the stresses on the flange of the gun chamber when attached to the SF6 Tank, I have concluded that superposing the many cases of closed form calculations is very complicated.  I don’t believe I can create a reviewable set of documents. Instead, a FEA analysis using the ANSYS workbench software can do a far better job.  Mike Bevins of the Engineering Group led me through a preliminary version of the flange using an IDEAs model made by Ron Lassiter.  At week’s end I have arranged with Ed Daly to utilize the overview services of Robby Hicks while I enhance the analysis using ANSYS mounted to Fred Dylla’s old PC.

•  The Gun Chamber is in a position to be baked as soon as we finish the new wiggler chamber

SF Sextupole Magnet Testing

• 	The Accelerator Division’s Power Supply Group continues their commissioning of the CANBUS control of the new power supplies.  They have solved the communication problem and are working on getting the internal ramp to work reliably.  As soon as this is working, Scott Higgins can complete the control software and we can start our plan to test the magnets with the power supplies in Magnet Test with the actual software.

Cooled and less resistive Wiggler Chamber

• 	Don Bullard of the Injector Group did a first copper sputter in the Test Chamber.  The test was not as successful as we hoped.  The test pointed out the difficulties of maintaining the plasma in the right portions of the chamber.  The ceramic insulators we used to isolate the central copper strip also got plated with copper, eventually causing shoring and instability in maintaining the plasma.  Our conclusion is that evaporation may be a quicker option.  At week’s end we are working on a demonstration sample.

• 	In parallel, the source lab folks made the copper cooling tubes and the chamber had a solder bead run on the top and bottom edges and cleaned to eliminate any flux.

Optics:

FEL Mirror Development

Measurements of the harmonic content were made early this week and, with the new configuration, worked well.  We collected data on the energy in the 2nd through 6th harmonic as a function of cavity length detuning.  The transmission of the setup needs to be determined before the ratios can be determined.

Michelle Shinn attended a review of the Colorado State University (CSU) - led proposal on optics and coating development that was submitted in response to an ONR solicitation.  While there she met with two members of the Optics Improvement collaboration.  She also gave an update to some of the LIPSS (Dark Matter particle search) consortium members on the FEL performance during the two physics runs, and proposed future paths.

The work with a student, Anne Watson, on modeling and measuring the efficacy of apodization on our edge-outcoupled mirror is making excellent progress.  We are now able to quickly simulate the effect of changing the feature parameters on the far- and near-field intensity pattern.

#### Cavity/Optical Transport

This week was primarily devoted to preparing for the 1.6um High-Q cavity cryo-mirror work. We received two brazed cryo-frames from T. Elliott. Of the two, one was leak tight and the other had a leak along the ID. The first we slowly cryo-cycled down to ~80K and the other was sent back for a second braze. The cryo-cycle opened a leak on one of the cooling tube to frame junctions and was sent back for another braze run. The result of the second braze was two leak tight mounts. When they where cryo-cycled the first remained leak tight and the second now has a leak along the OD. The later is with T. Elliott for a third attempt. We received a Boron Nitride plate that was machined to fit the gold target for reforming. This was placed it the vacuum furnace overnight, we await news of its success. This target will be used to sputter both the cryo-frame and the perimeter of the 1.6um optics. A design for a cryo-diode support that should provide a faster and more accurate helium temperature readback was sent to the Machine Shop for machining. We expect to receive it later today. The backscatter shields for both cavity ends as well as the collimator mirror were received early this week. We want to thank G. Biallas, who quickly brazed the cooling tube to the shields. The shields were sent out for laser black, light absorbing plating. We anticipate receipt late next week. The CPU board for the Optical Beam Position Monitor was ordered. The vacuum can is ready for installation. The electronics should be ready by mid next week. Cryo-diodes were ordered for the cryo-mirror tests. A harness to bring the cryo-diode signals outside of the vacuum chamber is being readied. We will have eight helium temperature diodes in the OC vessel. Half of these are redundant with half for inflow and the others for outflow. Additional inline cooling water thermometry for the HR is being readied as the RTDs are very fragile and take a few days to cure.

#### Optic’s Student Activities

The majority of activities this week were geared toward preparing for the upcoming machine down. The pump carts have been pumping all week and the problem with one of the RGA's seems to be fixed. It is believed to have something to do with how they are shut down. All on our carts are in working order and test fine.

Assistance was also given to C. Gould in association with the cryo mirror installation. The cryo-frame assemblies were cryo-cycled and leaked checked during the week. Tools will be cleaned this afternoon in prep for their use next week, along with gathering of other materials such as gloves, isopropanol, acetone, etc.

#### Lasers and Diagnostics

The investigation and search for a suitable drive laser for the Gun Test Stand continues. We are searching for one with the lowest possible cost while keeping the required specifications. We have contacted many laser vendors. Some discussions were held within the FEL team and a decision will be made after a bit more work is done. We also held a meeting to discuss the upcoming EO sampling experiment for bunch longitudinal tomography and a schedule was made. We have started preparing the EO sampling laser system for a safe move into location in Lab 3. We supported the ODU user on their FORT experiment.

Terahertz:

This week, the new design for the gas cell to be used in Harvey Rutt’s double resonance experiments by was finalized.  The new design allows the mid IR beam to enter and exit the cell at Brewster’s angle through the silicon windows to eliminate the interference effects from the spectrum.  The difficulty is that the angle is very severe, making the design and fabrication of the cell very complex.  We also were able to make more measurements of the incoherent visible synchrotron light with the Vigo detector.  This is the detector that is used for measuring both the mid IR spectrum and to detect the modulation of the spectral components induced by the THz pulses.  This is important because it gives us an absolute phase reference through the sample (gas cell or solid phase sample). 

Also, plans were made this week to move forward on the electro-optic (EO) measurements to be performed in the THz lab.  This will require the installation of a Ti:Sapphire oscillator enclosed in a local laser hutch enclosure just outside of the THz hutch wall.  An enclosed beam transport line will also have to be made to deliver the laser beam into the THz hutch.  The goal is to make some baseline measurements and to perform some straightforward EO measurements in the THz hutch to gain experience that will be valuable in determining how to implement a more permanent long term system.