## FSIS Re-design

## Weekly Status – February 26th, 2004

Tasks completed this week:

- Completed feedback and approval on content development submissions - 384 submitted, 384 approved (includes pages that did not require new content development, see content approval tracker below).

- Continued development and testing of the 384 pages defined as in scope for phase I.

- Completed development schedule detailing 61 pages for content and HTML/ASP development in this extension.  Distributed content assignments to content developers with a deadline of March 5.

- Provided feedback and approval of extension content development submissions – 13 submitted, 2 approved (see content approval tracker below).

- Continued creation of re-direct strategy document.

- Scheduled Web site maintenance training for March 2nd, 3rd, and 4th from 9:00 – 12:00pm.

- Created Web site maintenance manual for reference during the Web site maintenance training.

- Conducted a train the trainer session with Linda Eckrich to prepare her for conducting functional Web site maintenance training.

- Scheduled meeting with AISD to discuss the timeline of the extension and the migration to production.

- Facilitated the marketing and communications strategy session.

- Roger Baker analyzed the Advisory Committee section and recommended the addition of one page that has been added to the site map and phase II development.

- Continued work on the vRep tool.  A total of 792 questions exist in the tool and 49 questions were approved, 9 categories were added.

- Dean Bramell and Maria Miranda created content for 4 of 7 newly identified veterinary pages.

Tasks for next week:

- Conduct Web site maintenance training on March 2nd, 3rd, and 4th from 9:00 – 12:00pm.

- Complete Web site maintenance manual to be used as reference materials for future development and maintenance of the site.

- Install MS Powerpoint, Defect Tracking Tool, and purchased IFilter for SHTML on the development server.

- Complete development (adding approved content) and testing of the 288 pages defined as in scope.

- Complete development and testing of the 75 pages additional to the 288 defined as in scope.

- Provide feedback and approval on content development submissions.

- Facilitate meeting with AISD to discuss the timeline of the extension and the migration to production.

- Complete re-direct strategy document.

- Create marketing and communications plan based on ideas and suggestions captured in the marketing and communications strategy session.

- Initiate creation of marketing and communications materials: web promos, HTML email, and postcard based on feedback received in the marketing and communications strategy session.

Issues:

- Need to finalize an internal FSIS, final content approval process for all pages with new content on the re-designed site.

- Need to install Microsoft Powerpoint and custom built defect tracking tool on the development server.

- Need to purchase IFilter for SHTML and Visual SourceSafe.