# DOWNLOADED AND/OR HARD COPY UNCONTROLLED

# Verify that this is the correct version before use.

| APPROVAL SIGNATURES | DATE |
| --- | --- |
| Gregory Blaney (original signature on file) | IMS Representative | 12/03/2007 |

| REVISION HISTORY |
| --- |
| Rev No. | Description of Change | Author | Effective Date |
| Basic | Initial Release | Greg Blaney IT/387 | 01/30/1998 |
| A | Numerous changes in content throughout entire document | Greg Blaney IT/387 | 04/07/1998 |
| B | Changed document format and added sections 6.3.5 & 6.3.6 | Greg Blaney IT/387 | 05/06/1998 |
| C | Added new terms in Section 3.0 Definitions. Added two new sections called “Inspection and Test of Product” as section 6.5.1.3 and “Inspection and Test Status” as section 6.5.1.4. The “Control of Nonconforming Product” section changed from 6.5.1.3 to 6.5.1.5; and Added references to SLPs IVV 09-1, IVV 09-2, and IVV 09-3. Added notes in sections 6.3, 6.4, and 6.5.2 referring to the OSMA SLP IVV 09-3 when areas of this SLP did not apply. | Greg Blaney IT/387 | 07/24/1998 |
| D | Quality Record - format changes | Greg Blaney IT/387 | 08/26/1998 |
| E | Section 6.2 – Removed electronic file req. Sections 6.5.1.3 & 6.5.1.4 – Added reference to the 5-day grace period and added “Deliverable Acceptability Status” email req. Section 6.5.2 – Added “Monthly Financial Assessment” email req. Section 8 – Added both records mentioned above. | Greg Blaney IT/387 | 09/11/1998 |
| F | Added IVV 01 to Referenced Docs. Sections 6.3.4, 6.4.1, 6.5.1.2, 6.5.1.4, and 8.0 are modified as follows: added a Formal Agreement checklist, a new section, some references, and changed the Concurrence Sheet responsibility. | Greg Blaney IT/387 | 01/20/1999 |
| G | Added definition for Senior Staff (section 3.4), and modified section 6.5.1.4 to include a Senior Staff review process for high level documents. | Greg Blaney IT/387 | 04/14/1999 |
| H | References to Ames Quality Manual replaced with references to IV&V Facility Quality Manual and Added Section 3.11 | Greg Blaney IT/387 | 09/10/1999 |
| I | Format and Number changes; Delete Reference to Ames Research Center | John Griggs | 12/06/2000 |
| J | Significant re-write to accommodate current PM process based upon transition to GSFC | Greg Blaney | 04/03/2001 |
| K | Clarify requirement for Project Managers to maintain copies of task orders. | John Gatto | 05/15/2002 |
| L | Remove COTR requirements and include instructions for Mission Tracking Matrix. | John Gatto | 10/31/2002 |
| M | Expanded Control of Nonconforming Product and added information regarding PMRs. | John Gatto | 03/24/2003 |
| N | Expanded Control of Nonconforming Products to include information regarding nonconformance’s discovered by the organization. | John Gatto | 06/02/2003 |
| O | Added Senior lead duties, updated procedure flowchart and Metrics reference. | Raju Raymond | 09/26/2003 |
| P | Added references to New Business Lead and Deputy PM. Use of PM Tool and TOMS are identified. Added new Mission Model updating process. Expanded PM’s responsibility to manage and monitor Customer-supplied data (Section 6.9). Added reporting of Project related risks in Section 6.13. Included references to Customer funded and IBD funded projects; added req. for annual review of Customer agreements; rewrote the section for controlling the nonconforming products; added new req. of monthly PMR updates; and updated the Evaluation of Deliverables section for clarity. | Stephanie Ferguson Raju Raymond Ken Vorndran | 03/27/2004 |
| Q | Clarified sections 6.3 and 6.4 to clearly state what information the PM is responsible for updating. Deleted “Facility cover page” from 6.12. Changed insure to ensure throughout document. | Stephanie Ferguson Steve Raque | 4/21/2004 |
| R | DCR 240 CARs 13260, 13261 PARs 13041, 13103, 13163, 13335, 13777, 13789 Deleted Mission Tracking Sheet requirements due to change in requirements by New Business Lead. Updated Sec 3.0 for definitions unique to this SLP only Updated Sec 5.0 to include responsibilities for all applicable roles to this SLP New Process Flow Diagram to represent new organization of this SLP Deleted the PM Tool description section and added PM Tool to Section 3.0 | Melissa Schmidt | 11/2/2004 |
| S | Section Change PAR: 2005-P-111 Change Sections: 6.1.3.3 PAR: 2005-P-140 Change Sections: 5.5, 6.7, 6.8 Annual Review Updates Sections: 3.0, 6.6.2, 8.0 | John Marinaro | 02/28/2005 |
| T | Update for organizational changes. Added to/refined list of external presentations/reviews. Clarified FA dependencies. | Steve Raque | 09/08/2005 |
| U | Updated to implement CMMI initiative (IV&V Services Baseline definition, Requirements Management section, Inspection of Product from Contractor section), Updated definitions, added references to IVVP Template, removed Establish Contractor Tasking section (now in IVV 09-8), updated list of items that are captured in PM Tool, complete rework of Records section. | Steve Raque | 07/26/2006 |
| V | Update process flow diagrams to align with Facility Management paradigm | Stephanie Ferguson | 09/21/2007 |
| W | Update Quarterly/Annual Responsibilities flow to reflect correct PMER input intervals | Raju Raymond | 12/05/2007 |

| REFERENCE DOCUMENTS |
| --- |
| Document Number | Document Title |
| Current versions posted by NASA | Federal Acquisition Regulations (FARs) and Supplements |
| Current version posted by NASA | IV&V Export Control Policy/Procedure |
| Form 1007 | Concurrence Sheet |
| IVV QM | IV&V Quality Manual |
| IVV 07 | Financial Data Control |
| IVV 08 | Contracting Officer Technical Representative (COTR) |
| IVV 09-4-1 | IV&V Services Risk Management |
| IVV 09-8 | Project Startup |
| IVV 14 | Corrective and Preventative Action |
| IVV 16 | Control of Quality Records |
| NPR 1441.1 | NASA Records Retention Schedules |
| T2101 | MOA Template |
| T2103 | IPEP Template |

# Purpose

The purpose of this system level procedure (SLP) is to establish a consistent and documented method of performing project management at the NASA IV&V Facility.

# Scope

This SLP applies to all IV&V Services personnel who perform project management for IV&V or system/software engineering tasks for the NASA IV&V Facility.

# Definitions & Acronyms

Official NASA IV&V Facility roles and terms are defined in the Quality Manual.  Specialized definitions identified in this SLP are defined below.

## Deliverable

A Deliverable is a product identified as a deliverable within task orders, contracts, or IV&V Project Execution Plans (IPEPs).

## Milestone

A Milestone is an event in the life cycle of a project that is generally denoted by a formal, project-led review with IV&V participation (e.g., Preliminary Design Review).

## Project Artifacts

Project Artifacts are those products delivered to or by the NASA IV&V Facility for use in performing IV&V or documenting the IV&V efforts on a project.

## Acronyms

CAR		Corrective Action Request

COTR		Contracting Officer Technical Representative

FA		Formal Agreement

FY		Fiscal Year

GSFC		Goddard Space Flight Center

IBD		IV&V Board of Directors

IMS		NASA IV&V Facility Management System

IPEP		IV&V Project Execution Plan

MOA		Memorandum of Agreement

MSR		Monthly Status Review

NetOps	Network Operations

NPR		NASA Procedural Requirements

PM		Project Manager

PMER		Performance Monitor Evaluation Report

PMR		Project Management Review

POC		Point of Contact

QM		Quality Manual

RAC		Resource Allocation Committee

RMO		Resource Management Office

SLP		System Level Procedure

SMSR		Safety and Mission Success Review

# Process Flow Diagrams

The following diagrams depict processes described in this document, and the responsibilities and actions that shall be performed by process participants.

## Project Life Cycle

For IV&V Project initiation, the Project Manager (PM) shall follow IVV 09-8, Project Startup.  During the life cycle of the project, lessons learned, if any, should be compiled.

Once an IV&V Project has been closed and all the tasks are completed for the Customer according to the IPEP, the PM shall ensure that the following closeout activities are completed:

- Catalog and archive the Customer and Project Artifacts.  For artifacts stored on the Shared Network Drive, inform Network Operations (NetOps) staff of the location of the artifacts to be archived (NetOps staff shall move the artifacts to the appropriate write-protected location).

- Work with the appropriate Contracting Officer’s Technical Representative (COTR) to initiate task order closeout process.

## Establish Formal Agreement (FA)

The Formal Agreement (FA) will document the managerial, technical, and business aspects of the tasks to be performed for the Customer.  The FA will also describe the type of agreement (e.g., Memorandum of Agreement (MOA), a task agreement, an Interagency Agreement, contract), the type of funding for the project (e.g., Customer-funded, IV&V Board of Directors [IBD]-funded), and the amount of funding by fiscal year (FY) for the life of the IV&V Project.  Refer to T2101, MOA Template, for information regarding MOA preparation.

The FA shall contain, but not be limited to, the following information:

      - Purpose

      - Duration

      - Points of Contact (POCs)

      - Roles and Responsibilities

      - Budget (for Customer-funded efforts)

      - Issue resolution protocol

      - Signature lines for both parties (NASA IV&V Facility and Customer)

The PM shall review FAs annually.  If modifications to FAs are needed, the PM shall follow the process described in this section of this document.

## Establish Baseline Revision/IV&V Project Execution Plan (IPEP)

The PM shall review/update the Baseline Revision and IPEP semi-annually.  Refer to T2103, IPEP Template, for information regarding IPEP preparation.  Refer to IVV 07, Financial Data Control, for information regarding Baseline Revision preparation.

## Deliverable Processing and Distribution

### Control of Customer Supplied Product, Product Identification, and Traceability

The PM shall ensure that appropriate Customer-supplied products (e.g., documents, code, databases) are used when performing tasks and that the Contractor identifies the product used in the resulting report/output (e.g., version, date).  In addition, the PM shall identify and adhere to any privacy and/or security related requirements associated with Customer-supplied products, which includes NASA Export Control Regulations (see IV&V Export Control Policy located on the NASA IV&V Facility Services Web Site at http://services.ivv.nasa.gov/docs.html).  The PM shall relay this information to the Contractor and ensure that the Contractor is following the appropriate procedures.  For additional information, refer to IVV 08, Contracting Officer’s Technical Representative.

### Inspection of Product from Contractor

The PM shall objectively evaluate all IV&V Project-related products required by a contract or task order that are delivered to the NASA IV&V Facility within ten working days of delivery.  The PM shall objectively evaluate such products for quality using applicable criteria including, but not limited to, those identified in the contract and/or task order requirements.  Results of these evaluation efforts shall be recorded in the PM Tool.

### Control of a Nonconforming Product

If the NASA IV&V Facility identifies a problem with a product that has already been delivered to the Customer Project, the PM shall immediately inform the Customer Project of the problem. If the Customer identifies a product produced by the NASA IV&V Facility as nonconforming (e.g., an inappropriate format or because it was performed on the wrong Customer product), the PM shall resolve the issue with the Customer.  Regardless of how the problem has been identified:

  - The PM shall complete a Corrective Action Request (CAR) form per IVV 14, Corrective and Preventive Action.

  - The PM shall ensure that the problem is resolved and that the Customer is provided a full explanation of events.

  - The nonconforming product shall be subjected to its established verification process once the nonconforming product has been corrected.

  - The PM shall request closure of the CAR once the nonconforming product has been approved and sent to the Customer.

## Review and Approval Process

The PM shall submit products for review and approval using Form 1007, Concurrence Sheet.  Approval must be obtained prior to officially submitting the product to the Customer.

| Type of Product | Originator | Reviewers | Approver |
| --- | --- | --- | --- |
| FAs: Customer Project-Funded | PM | Appropriate COTR RMO IV&V Services Lead | Facility Management |
| FAs: IBD-Funded | PM | IV&V Services Lead | Facility Management |
| Customer Deliverables | Contractor Name (No Signature) | None | PM |
| IV&V Presentations for Customer Project Milestone Reviews | PM | None | IV&V Services Lead |
| Safety and Mission Success Review (SMSR) | PM | IV&V Services Lead | Facility Management |
| Final Readiness Review | PM | IV&V Services Lead | Facility Management |
| IPEP | PM | IV&V Services Lead | IV&V Services Lead |

## Project Timetable

### Annual/Quarterly Responsibilities

### Monthly Responsibilities

The PM shall perform the following responsibilities on a monthly basis:

      - Review/approve deliverables

      - Create and present Project Management Review (PMR) presentation

      - Update Goddard Space Flight Center (GSFC) Monthly Status Report (MSR) inputs

      - Review Resource Allocation Committee (RAC) reports

      - Review/update risks per IVV 09-4-1, Work Instruction for IV&V Services Risk Management

### Weekly Responsibilities

The PM shall update the One-Liner file on a weekly basis.

# Metrics

Any metrics associated with this SLP are established and tracked within the NASA IV&V Facility Metrics Program.

# Records

The following records will be generated and filed in accordance with this SLP and IVV 16, Control of Quality Records, and in reference to NASA Procedural Requirements (NPR) 1441.1, NASA Records Retention Schedules.

| Record Name | Original | Vital | Responsible Person | Retention Requirement | Location |
| --- | --- | --- | --- | --- | --- |
| Concurrence Sheet for associated FA Submitted to Customer | Y | N | PM | Retire at close of program/project (8/101) | Filing System |
| FA signed by Customer | Y | Y | PM | Retire at close of program/project (8/101) | Filing System & Shared Network Drive |
| Concurrence Sheet for FA annual review | Y | N | PM | Destroy when 2 yrs old (8/109) | Filing System |
| IPEP | Y | Y | PM | Retire at close of program/project (8/101) | Filing System & Shared Network Drive |
| Customer Deliverable | Y | Y | PM | Retire at close of program/project (8/101) | Shared Network Drive |
| Concurrence Sheet for Customer Deliverables | Y | N | PM | Destroy when 2 yrs old (8/109) | Filing System |
| Concurrence Sheet for Review of IV&V Presentations | Y | N | PM | Destroy when 2 yrs old (8/109) | Filing System |