One Coordinated TA Plan –

Pilot, Circle of HOPE MO

Date:  09-07                                                   Report prepared by: Frank Rider, RTAC

# Introductory Information

- Community Name: Circle of H.O.P.E.

- Location: St. Joseph, MO

- Year Funded: 2006

- Project Officer: Elizabeth Sweet, SAMHSA - CMHS

- Regional Technical Assistance Coordinator: Frank Rider – Region III

TA Team Members:

- Family Resource Specialist: Gwen Palmer

- Youth Resource Specialist: Reyhan Reid

- TA Partnership Director/Resource Specialist: Regenia Hicks

- SOC Alumnus: Greg Bullard, Greenville SC (former project director):

- Communications Campaign Liaison: Erin Turner

- ORC Macro Evaluation Liaison: Connie Maples

- Other TA Support: Sandy Keenan, TA Partnership                                                           Mary Tierney MD, TA Partnership

One Coordinated TA report

Area 1

# Area of Focus 1 : Effective Collaboration - Partnerships with Education

- Description of Area of Focus: The Circle of HOPE is building a system of care for children and families that integrates primary health care, (public) education,  behavioral health care and other child serving systems in partnership with young people and their families.  Planning focused on partnerships involving education yielded the following:

- Strengths:

- Educators are substantially involved in the Circle of HOPE.  St. Joseph school district (12,000 students across 40 sites) and Humboldt Elementary School (an initial pilot site) are well represented in the initiative.

- Humboldt Elementary School has a long history of innovative best practice and partnership with mental health, has a community support worker, and aspires to a schoolwide behavior management approach.

- The former superintendent of the school district had signed the collaborative MOU, and the current administrative leadership is ready to participate substantially in the Circle of HOPE initiatives

- Improved school performance, attendance; decreases in expulsions and suspensions are reported widely in system of care communities.  These documented results can be effective motivators for education partnerships in the Circle of HOPE.

- All Title I Schools have family involvement coordinators.                                                     Action: The school district will share the names of these FICs with Joe Turner, KFC. Action: The Circle of HOPE will consider inviting FIC’s to participate in upcoming wraparound trainings.

- Action 1.1 RTAC to arrange a specific conference call with Sandy Keenan, Humboldt Elementary School representatives (e.g. Sara, Principal) and Circle of HOPE personnel, before 12/15/07, to help plan implementation of pilot activities.

  - TA Resources for Action 1.1

- "Toward A Shared Agenda" document, discusses Missouri and national-level partnerships among education systems, mental health systems and families; at: 
http://schoolmentalhealth.missouri.edu/focusgroup/agenda03.rtf

- National report, describing Missouri's role among six states that have received seed grants to support partnering among schools and mental health systems, at:
http://www.ideapartnership.org/report.cfm?reportid=47

- Positive Behavior Intervention and Supports resources:

  - Lucille Eber, Positive Behavior Interventions and Support - www.pbisillinois.org                (Ph: 708 482-4860)

  - National Center on PBIS, based in Portland OR – www.pbis.org

  - National Conference on Positive Behavior Supports – Chicago IL March 27-9, 2008 (see http://conference.apbs.org/)

  - New Hampshire’s graduated SOC initiative spread PBIS statewide, was successful, has published very positive outcomes.

- Sandy Keenan, TA Partnership – skeenan@air.org – will provide follow-up direct TA to educators in this community.

- In addition, Sandra will provide direct TA and facilitation in state-level activities to build partnership with the education system during Spring 2008; it is hoped that a current $7.5-million Legislative appropriation to support school-based mental health services will pass, and be a focal point of Sandra’s work (coordinate with Connie Cahalan, Missouri DMH).

Sandy Keenan’s initial technical assistance  call 9/12/07:

- Collaboration at multiple levels:

- Individual child/student level – school representatives are involved at the child/family team level.

- Needs of a group of children (6, 12, 15) e.g. individual or group therapy services on site at school, after school programs, programs after hours or co-located at school

- Schoolwide collaboration and support (e.g. schoolwide PBIS, MH provider assigned to school; school offers BH support center)

- District level support – comprehensive programming.

- Countywide or statewide level of implementation.

- Six specific promising practices emerged from early SOC work related to education:

- Use clinicians and other support providers in schools must work not only with children and families, but also with the staff of the school (consultation, professiona development, education for staff).

- School-based and school-focused wraparound processes tp support improved educational outcomes.

- School-based case management

- Schoolwide prevention and early intervention programs, and

- Creation of “centers” within a school (that is, physical places) around emotional and behavioral needs of children; and

- Use of family liaison and family advocate roles.

- Positive Behavior Interventions and Supports (PBIS):

- Universal (school wide) interventions and approaches

- Targetted interventions (10-15% of children may need special support, reminders, practice; and

- Chronic, longterm, intensively needy students need specific approaches.

- PBIS is a pretty comprehensive staff training and development initiative, might take 2-3 years, and can be used well beyond the schools, to after school programs, day care, in family homes, group homes, scouts, etc.

- Fits well with system of care: pre-referral/intervention team at school.

- Social/emotional learning and anti-bullying programs are also compatible with system of care values and approaches.

- Action 1.2 - Clarify legal and regulatory issues around the IEP process in particular, and around confidentiality/information sharing concerns of families and schools in general.

  - TA Resources for Action 1.2

Sandra Keenan will provide information, resources and forms to special education and non-special education personnel within the school district, to ensure that school-based wraparound processes, and school representatives’ participation in family support (a.k.a. wraparound) teams.

- Action 1.3 - Provide wraparound training to pilot site personnel (Humboldt Elementary School); implement and refine protocol with input from families and school personnel.  (See Area of Focus #5: Building Clinical Services and Supports.)

  - St. Louis Youth in Transitions’ CAS site is hosting wraparound training effort that Circle of HOPE constituents will access for initial training.

- Action 1.4 - Determine how best to involve the family involvement coordinators that the Title I schools already have in place, in the Circle of HOPE initiatives.

- Beth Berndt, McHenry Co. Family CARE (bberndt@mc708.org) – regarding family resource developer positions deployed in schools.

One Coordinate TA report

Area 2

Area of Focus 2 - Governance

- Strengths:

- Policy team participants have signed MOU

- Group Rules and Decision-Making Process have been developed

- Policy team has worked hard to coalesce, and to behave in accordance with the principles of “family-driven”

- Policy team bylaws require that families have 51% of the voting power.

- Policy team has engaged in intensive strategic planning (February and May 2007 sessions with outside facilitation), revisited initial goals and has revised, based on family and collective input, and has taken ownership of the Circle of HOPE initiative

- Team members have a long history of working together prior to this cooperative agreement.

- Commitment of participants is evident.  People are willing to make a substantial contribution.

- Challenges:

- Need to establish a process for conflict resolution that can be replicated at the agency/provider and the child/family team levels

- Need to increase ethnic/racial diversity on the Governing Board (e.g. to ensure effective proactive outreach to the emerging Latino population)

- Have not yet been able to organize youth to participate effectively in Governance

- Need to define Governance for this community.  Power/authority must be appropriately shared among Policy Team/Governance members, staff, private agencies, state agencies, etc.  See Theme #4 in GFA Crosswalk for its list of 20 key questions.

- Finding “win/win” solutions that take into account, and satisfy, the self-interest of members and their constituents (The “what’s in it for me?” question.

- Action 2.1- Develop a clear, limited set of local indicators of progress, success.   Publicize these, use them to galvanize the governance participants.  Consider developing a local version of the Missouri “Stats Blast.”

  - TA Resources for Action 2.1

  - Local and/or national evaluation team members.

  - Arizona example of four functional outcomes, and its statewide, published outcomes reporting

  - SAMHSA NOMS (National Outcome Measures)

- Action 2.2 - Continue to figure out where we need to go with further development of our governance structure.  Use the 20 questions from the GFA crosswalk as a tool to guide this process.  Identify goals, objectives mand strategies to address areas

  - TA Resources for Action 2.2

  - GFA and System of Care Implementation Crosswalk (TA Partnership, 2006), list of 20 key questions on Pages 17-19, at: http://www.tapartnership.org/download/GFA%20Crosswalk%20Year%20One%203%2014%2006%202.pdf

  - Bruce Strahl, TA Partnership and Sheryl Schrepf, project director, Sarasota FL have been identified by project director and RPT (10/07), with approval of principal investigator, as preferred external consultative resources to assist Circle of HOPE to strengthen governance practices in coming months.

  - Arrange a visit to, or by, one of the three team learning centers: Dawn Project, Wraparound Milwaukee, Westchester Co. NY:

The Dawn Project, Indiana, Knute Rotto, CEO - krotto@choicesteam.org

(also see www.kidwrap.org)

Westchester Community Network, NY - Michael Orth, Director -

www.westchestercommunitynetwork-

Wraparound  Milwaukee, Wisconsin - Bruce Kamradt, Director -

bkamrad@wrapmilw.org or bkamradt@milwcnty.com

  - Other communities that can provide useful teaching examples:

  - Cuyahoga County Tapestry Project – Beth Dague, Cleveland OH

  - McHenry Co. Family CARE, Crystal Lake IL – Todd Schroll, Project Director

- Action 2.3 - Develop a barriers identification and resolution process.

- Teach, motivate, incentivize FSA’s, care coordinators and agency partners to use this process.

- Empower youth and families to use this process.

- Motivate people to resolve conflicts at the lowest level possible.

- Analyze the barriers, develop systemic solutions when possible, and develop protocols that account for the majority.

- Incorporate this process into our MOU.

- Use this as an excellent starting place to apply meaningful youth voice.

- “Don’t Just Say No!”  Consider using mediation.

- TA Resources for Action 2.3

Arizona’s barriers identification and resolution procedures, provided by Frank Rider (frider@ffcmh.org), RTAC 10/07.

One Coordinated TA report

Area 3

## Area of Focus 3 – Strategic Planning

- Description of Area of Focus:

Policy Team has focused primarily on near-term tasks, and has not yet developed a longer-term strategic plan.  Ideally, would like to develop timely annual planning process to establish goals/objectives and make budgetary decisions in time to support annual reapplication for cooperative agreement funds.

- Strengths:

- Policy Team is actively applying the results of its concept mapping process in setting goals and objectives.

- Policy Team has developed and approved a nearterm workplan, which can be expanded upon and updated

- Policy Team has developed a logic model which can serve as primary basis for strategic planning.

- Challenges:

Policy Team has focused primarily on near-term tasks, and has not yet developed a longer-term strategic plan.

- Action 3.1 -  Describe a clear vision of a transformed system of care for St. Joseph; and ensure this is reflected in the Logic Model:

Schedule and facilitate strategic planning sessions for the Policy Team to establish a clear, shared vision, and a longer-term strategic plan.

  - TA Resources for Action 3.1

Community has identified Bruce Strahl, TA Partnership and Sheryl Schrepf, Sarasota FL project director as preferred external consultative resources to help facilitate this process (10/07).

One Coordinated TA report

Area 4

## Area of Focus 4 - Sustainability

- Description of Area of Focus:                                                                                        1. Securing, documenting matching resources                                                                    2. Determine which essential elements of the Circle of HOPE system of care will be sustained; and begin to determine strategies for sustainability (e.g. financial, structural, personnel, advocacy)

- Strengths:

- Two local legislators are champions for MH services.

- Child welfare is dedicating two children’s service worker staff positions to the philosophy of Circle of HOPE.  They work with intact families, in prevention.  Has an existing staff member dedicated already.

- Active, engaged family members can be key to advocating as needed in support of sustaining resources.

- Many Circle of HOPE goals are congruent with current local United Way goals.

- Several potential matching resources identified in brainstorming session: What are the enhancements to services and supports that become added to the local system of care?  Examples: Karate class at community college?                          College students volunteering time as youth mentors?   Student internships?                          Red Alert, Blue Alert? Time Banking?  “Eminem?”

- The community’s United Way has an Unmet Needs committee which could serve the Circle of HOPE’s flexible funds.  This was the arrangement in Greg’s SC community.

- Challenges: Matching funds requirements, given limited financial resources.

- Action 4.1 – Develop, implement a process to secure matching resources to meet the Maintenance of Effort and matching funds requirements of the cooperative agreement.

  - TA Resources for Action 4.1

  - Greg Bullard, SC’s suggested strategy to frontload longterm agreements with providers so that they contribute more in the later years, allowing the cooperative agreement to pay a greater portion in early years, ands a lesser portion in latter years of the cooperative agreement (e.g. the co-located MH person in the pediatrics clinic example).  To wit:

“ I would suggest 5 year contract with the grant providing staff/services free for the first 2/3 years(by all means, however, share your data with those contractors, and use your MIS systems to show the dollar amount of services provided, cost savings, etc, etc..).  The contract should, after the third year, start increasing the amount contributed by the contractor (e.g. $5,000 for the 4th year, $10,000 for the 5th year, $15,000-$20,000 in the 6th and 7th years).  My experience taught me that if I didn’t enter into long-term contracts, then  some system partners will fail to remember verbal commitments. Especially if I failed to provide them with meaningful data, or if there were key leadership changes for the contractor.”

  - Bazelon Center matching funds guide (already provided to community)

  - Matching funds scenarios prepared by Frank Rider, RTAC for NW Minnesota (provided 11/07)

  - Frank Rider to pull arrange conference call with project directors, CFOs from other communities (e.g. Beth Dague, Sue Bowler)

- Action 4.2 - Strategic Planning process to develop the budget needed to support the third year reapplication.  Make this an annual process that occurs in time to

prepare the next year’s reapplication process. (See Focus Area #3 for TA Resources).

- Action 4.3 – Strategic Sustainability Planning

- TA Resources for Action 4.3

Frank to furnish research and Ppt presentation by Beth Stroul on this topic to help guide

local planning (provided 11/07).

One Coordinated TA report

Area 5

## Area of Focus 5 – Building Clinical Services and Supports

- Strengths:

- A great service delivery team has been working hard and productively since May to develop a service delivery process for the first children and families.

- The community has identified three initial pilot sites, intending to identify and work through challenges on a small scale before expanding service delivery.

- Existing Misouri pilots around MST and FFT

- The service delivery team has developed an initial protocol, covering the following steps: engagement of the family, clinical assessment, immediate crisis stabilization, strengths needs and culture discovery, Family Support Team formation, team support plan development and implementation, ongoing crisis and safety planning, tracking and adapting, transition, and evaluation.

- Have developed job description for family support assistant role, and state

- Medicaid is expected to cover FSA activities in Missouri before end of 2007.  RTAC is assisting principal investigator with resources to facilitate this initiative (11/07)

- Challenges:

- Still need to figure out best service delivery “client flow” process (e.g. where does the CAFAS fit?).

- Need effective clinical approaches to address externalized (e.g. oppositional defiant disorder) behavior problems.

- Clinical services and supports for emerging Latino population

- Provide culturally sand linguistically appropriate assessment forms, and the provision of interpretor and/or translation services

- Different service delivery strategies may be needed to expand COH service delivery in rural communities, in contrast to strategies with St. Joseph’s urban hub

- Strategies to engage youth early in the service delivery process (consider the

- option that the youth coordinator, when hired, can do this.)

- Action 5.1 – Implement the dry run of the proposed intake/enrollment process for two volunteer families, and one youth, to test it for “family friendliness,” for cultural and linguistic sensitivity, and against the requirements of funding sources/agencies.

  - TA Resources for Action 5.1

- Regenia Hicks assisted Vickie on-site to help inform assessment process/tools (e.g. clinical interview) in regard to cultural sensitivity.

- Frank to furnish Family Guides to Wraparound Process from National Wraparound Initiative website (10/07); and from Cuyahoga County Tapestry, OH).

- Action 5.2 - Determine what kind of documentation Circle of HOPE personnel will meet.  For 10/1/07 start-up, use the Medicaid standard of documentation as the minimum.  Over time, account for the documentation of needs of all other major system partners, and incorporate into a revise, longer-term documentation procedure.

  - Completed – no TA Resourcesneeded

- Action 5.3 - Determine minimum staff training requirements.  The basic training curriculum should include:                                                                                                                 1. Understanding and applying key Circle of HOPE values, including:                                      family-driven, youth guided; interagency collaboration and coordination of care; accessibility of services; culturally and linguistically competent; and equity/non-discrimination                                                                                                                                        2. wraparound process                                                                                                                      3. strength/need based planning                                                                                                              4. explaining the new local processes, including the new role of family support assistants, and                                                                                                                     5. initial information to meet requirements of the national evaluation protocol.

- TA Resources for Action 5.3

- St. Charles has a good System of Care training curriculum model that can be adapted by Circle of HOPE to for this, per Gary Hammond.

- Frank Rider will furnish Elizabeth a sheet of practical suggestions to promote active youth participation in their own service planning, and in positive youth activities (FAX to Jayme Neal 11/07).

- Reyhan will review proposed training curriculum to help ensure it substantially addresses expectations for/how to support meaningful youth participation.

- National Wraparound Initiative website – tools, consultants; Arizona protocols and technical assistance documents on Child and Family Team Process have been provided by Frank Rider (Oct-Nov 2007)

- Communication Campaign has developed presentation templates about benefits of systems of care that could be adapted to help support training curriculum.

- Frank Rider, RTAC can provide several training presentations that could be adapted to help support training curriculum.

- Action 5.4 -  Determine how to incorporate consents and releases in the service delivery process.  Adequately meet the requirements (EDIF, NOMS) for national evaluation.  Test this during dry run.

- TA Resources for Action 5.4

- Local evaluation team, Connie Maples, service delivery team

- Show Me Kids, St. Louis Transitions, state of Missouri have consent forms/releases that

- can be adapted by Circle of HOPE.

- Action 5.5 - Develop clinical (best practice) capacity to address identified needs of children with externalized behavior problems, and their families.

- TA Resources for Action 5.5

- http://www.parenting.org/

- PCIT

- Incredible Years

- Strengthening Families curriculum

- the “Common Sense Parenting” curriculum developed by Boys & Girls Town (see http://www.girlsandboystown.org/pros/training/child_welfare/CSP_trainers.asp).

- Love & Logic training series, by Jim Fay and Foster Cline.

- See PBIS resources in Action 1.1

- The major evidence-based approaches that are demonstrated to work well with youth with externalized behavior problems who need intensive support include:

- Multi-systemic treatment

- Functional family therapy (see existing Missouri initiative in two counties)

- Multi-dimensional treatment foster care

- Treatment foster home model – Mary Grealish, existing Missouri DMH initiative

- Many other EBPs may be added to this list.

  - See SAMHSA’s National Registry of Evidence-Based Practices and Programs (NREPP) at http://www.nrepp.samhsa.gov/

  - The federal Office of Juvenile Justice and Delinquency Prevention (OJJDP) selected ten approaches that can be replicated (see “Blueprints for Violence Prevention” at http://www.colorado.edu/cspv/blueprints/).

- Research Bian Post

- Action 5.6 – Create a workforce development plan to ensure that there is sufficient capacity to facilitate the Family Support Team process as the demand grows beyond the initial pilot site.  Dimensions that need to be accounted for:

  - Buy-in to process by system partners, that the process works for each of the systems, connected to the identified outcomes (see Action 2.1)

  - Higher Education Partnership with Missouri Western State University (e.g. student intern program – with stipend support from KC?)

  - Invest in importing purveyors of high quality wraparound practice, and effective clinical services.

  - TA Resources for Action 5.6

    - San Diego wraparound institute model – Gwen Palmer to furnish.

    - Arizona Roll-Out strategies via Frank Rider

    - Connection to Missouri’s commitment to high fidelity wraparound (e.g. through Vroon VanDenBerg LLP and/or National Wraparound Initiative) – Frank Rider, RTAC is advising principal investigator on this effort (11/07) .

One Coordinated TA report

Area 6

## Area of Focus 6 – Management Information System (MIS)

- Description of Area of Focus:

- How can you put information management systems in place to track, measure, assess, and communicate your activities?

- How can you develop an MIS system to provide you with real time data to support more informed decision- making at the clinical, program, administrative and systems levels and to measure progress toward different level outcomes?

- What is the best approach to developing an MIS for systems of care:  build your own, purchase off the shelf, or a combination of approaches?

- Strengths:

- Has an active MIS committee with sophisticated membership across multiple dimensions.

- The MIS committee has studied its end users requirements, and developed a “wish list” as well: Family friendly, access from multiple portals, case management across systems, and incorporate best practices into system

- The MIS Committee has been exploring some alternatives (e.g. Missouri’s SERNA system) , and wants to learn from other communities’ experiences with MIS

- Missouri has been recently awarded a $5-million grant to plan around  electronic health information exchange.

- The St. Joseph School District has recently extended access to its school records to the students’ families.

- Matthew Heil from MIMH developed a web-based application for families involved with multiple systems.

- Missouri has already developed an informed consent/release of information template.

- Challenges:

- Meeting as many of the items on the User Requirement wish list as possible.

- Supporting the national evaluation protocol requirements (GPRA requirements, NOMS – examples: days lost from work, hospital admissions, days lost form school, and more recent ).

- We want an MIS that is easily accessible to all partners within the Circle of HOPE, that the families can access,

- Are schools able to generate the data that the national evaluation protocol requirements demand?

- Action 6.1- Understand federal reporting requirements: NOMS, GPRA and TRAC System – and develop evaluation processes that are family-friendly and efficient while meeting these requirements as well as local evaluation priorities.

  - TA Resources for Action 6.1

- Connie Maples, Frank Rider to provide weblinks and other source documents for NOMS, GPRA and TRAC system (11/07).

- Connie Maples, ORC Macro to explain/interpret national evaluation protocol requirements, and offer ideas from other communities.

- Action 6.2 - Understand strategies/options that can best support the stated values of the Circle of HOPE/families while meeting the requirements of HIPAA, FRPA.

  - Include release of medical information;

  - school-based health care clinic option; and

  - “informed assent” strategies to support youth participation in their own care (American Academy of Pediatrics)

  - Clarify status of involved community entities under state of Missouri’s statewide HIPAA approach.

  - Understand FRPA privacy requirements from education.

- TA Resources for Action 6.2

- Clarify status of involved community entities under state of Missouri HIPAA approach

- Secure “informed assent” forms/documents from Dr. Tierney.

- Share examples of consent/release forms that support cross-system sharing

- Missouri has developed cross-system consent forms, approved by attorneys general, and will share it with Andrea in support of the Family Support Team process. (completed by Judy Finnegan, Missouri DMH before 09/24/07).

- Action 6.3 - Service delivery committee to determine how to apply the EDIP data (about 16 questions)

- Action 6.4 - Establish ICN access to identified staff (Lisa, evaluation team will facilitate this)

Additional TA Resource on MIS Needs/Preferences of Circle of HOPE:

MIS should consider contacting Gabriel Cate, Bowman Systems (Ph: 318 213-8780 x116; toll-free 888 580-3831 x116; e-mail: gcate@bowmansystems.com)  concerning Service Point, the MIS used by the United Way (that we discussed during our visit), to explore customizing Service Point to address the well-described needs/ preferences of this community.

Additional Areas of Focus

7. Youth-Guided:

Description of Area: Preparing the system to effectively apply the authentic voices of youth - provide training for policy team about listening to youth; shaping the experience of policy team members through working with former youth” first.

Strengths:

- the youth at the group home are willing to offer input and feedback, and demonstrate skill in doing so.

- The social worker at the group home is very talented and committed.

- Youth coordinator Jayme Neal has been hired by Circle of HOPE, has been oriented by TA Partnership resource specialist and is actively involved in youth coordinator affinity processes among Region III communities (11/07)

Input from young people on 9/13/07 PM included:

- More respect for youth voice

- Understand us as specific, unique voices – we are not all the same

- Start with our children when they are young – do not wait

- Punish, protect us from child-molesting parents

- He need to know how to comfort and help young people having suicidal thoughts

- Children who act out as bullies may well be being bullied a home, or be reacting to other problems they are having

- Why should we have to pay for books and fees in order to be successful in school

- We need safe and supportive spaces for children.  What this might look like: can hang out together, talk to people about what happens in their lives, there are games to play; blend very different kinds of kids together, don’t put kids into compartments based on their differences.  Schools should be a safe place, too.

- Sexual education needs to be provided for children at a young enough age so that they can benefit from it before it is too late (e.g. sexually active)

- We would like to get involved in developing brochures, we want to be asked to contribute our ideas.  Incentives that would attract us to help include: money, the pleasure of both receiving, and giving, respect, gift cards, volunteer service hours, pay for our lunches at school sometimes.

- Deliver messages to youth in cool formats, like comic strips.

Action 7.1 - Examine policies and procedures related to hearing youth voices.

Action 7.2 - Youth coordinator can identify existing, natural safe spaces in the community.

TA Resources:

- Reyhan will share more complete notes back to the community from the youth (completed 9/16/07).

- Frank to furnish contact information for PhotoVoice project in Wyoming’s SAGE Initiative (see http://wyosage.org/photovoice.html).

8. Workforce/Workforce Development issues

Description of Area:

Bud Salansky described a very limited pool from which to draw for skilled staff in professional workforce.

TA Resource:

- Reference Annapolis Coalition report/recommendations at http://www.annapoliscoalition.org/national_strategic_planning.php.

9. Cultural and Linguistic Competency

Description of Area: Outreach to emerging new Latino population (e.g. being attracted to Triumph Foods, a new major local employer).

Strength: Circle of HOPE has hired new coordinator for Cultural & Linguistic Competence, Nicki Samson (11/07).  TA Partnership has begun providing orientation, and foundational information resources, to Nicki (11/07).

- Action 9.1: Identify a cultural broker to participate on the Policy Team to help ensure that decision making can account for cultural and linguistic needs of the population.   Work with Title I school personnel to learn what they understand to date about children and families in this population.

Resources: Spanish Language documents/translation: screening form, CAFAS, Arizona signage.  Consider outreach into Missouri Western State University for interpretor, translation resources.

- Action 9.2: Craft and implement outreach and service strategies to engage impoverished families.

TA Resources:

- Specific resources are sought about understanding the impacts of poverty:

  - Ruby Payne, national expert will be coming to provided training this fall.  Recommend strong participation by Circle of HOPE staff and constituents in Ruby’s training, and seek some consultation.

  - William C. Madsen (Guilford Press, 1999), Collaborative Therapy for Multi-Stressed Families book will be helpful.

  - Develop, provide training on identification of strengths and resiliency among poor people.

- Prepare available operational supports.

- Toward a Culturally Competent System of Care, 3 Volumes http://.gucchd.georgetown.edu

- Cultural Competence Standards in Managed Care - www.samhsa.gov

- Broward County CLC Plan (Frank provided a copy 11/07)

Some Practical Next Steps:

    - Community to prioritize some next action steps within its workplan.

    - Frank shared the single TA Plan document with Andrea by 10/1/07, and shared copies with other Circle of HOPE team members, program partners and federal project officer at same time.

    - Frank shared a draft update of the plan document with Andrea and TA coordinator Nicki Samson on 11/19/07.