Northern Plains Area Non-Funded Cooperative Agreement (NFCA) Process:   The proposed research must support the mission of ARS; be of mutual interest to all parties; supplement the program(s) of the scientist and unit; be fully documented and tracked.  All parties must mutually contribute to the research effort.

| ARS Scientist/Unit Support Staff Responsibilities: | Extramural Agreements Section Responsibilities: |
| --- | --- |
| Obtain the ARS-416/417/550a (no budget section) template from the Unit ARIS User; complete the templates and return to Unit ARIS User. Unit ARIS User: Enter the ARS-416/417/550a and obtain line management approval signatures (RL/LD/CD). Allow 2-4 weeks for NPS approval of the ARIS. Allow 30-90 days for the Cooperator to review and approve the Agreement language. The research cannot begin until all Agreement actions are completed and signed by all parties. Special Note: Do NOT engage, or make any plans for the relationship, with the Cooperator until NPS approval of the NFCA has been verified/confirmed. Although rare, there have been instances where the NPL(s) have disapproved a proposed NFCA. | Review and approve the ARS-416/417/550a. Release to NPS level for their review and approval. Provide Statement of Work example(s) upon request from the scientist. Contact Information: 970-492-7029 or jim.quaratino@ars.usda.gov 970-492-7022 or marcie.currie-gross@ars.usda.gov Monitor the ARIS for NPS approval. Notify the ARS scientist and Unit ARIS User when NPS approval is received. |
| Prepare the Statement of Work (SOW) for the proposed research. Mutual interest in the agreement's objective must be specifically stated in the SOW. E-mail the SOW to the Agreements Section. Sign and return the ADODR page to the Agreements Section within 10 working days of receipt. | Review the Statement of Work for the proposed research. Contact scientist if revisions are required. Upon NPS approval of the ARS-416/417/550a, prepare the Non-Funded Cooperative Agreement package and send it to the Cooperator for signature. Send a copy of the fully signed & executed Agreement document to the Cooperator, ARS scientist, RL/LD/CD, and LAO. |
| Obtain the Annual Performance Reports from the Cooperator's Principal Investigator by August 1 of each year. Forward the report to the Agreements Section. Prepare the Annual and/or Final Progress ARS-421 Report(s) for ARIS to document the research for the sibling CRIS project. Enter publications via the ARS-115 as applicable to the Cooperative Research Agreement. | Document the Annual and Final Performance Reports under the Terms and Conditions of the Agreement. Monitor the ARS-421 Annual/Final Progress Report system for the sibling CRIS project. Submit the Annual and Final Performance Reports prepared by the Cooperator's Principal Investigator to the Assistant Area Director for review and approval. Close the Agreement through appropriate channels. |
| For Amendments to the Agreement: Notify the Unit ARIS User of your wish to extend the time. Unit ARIS User: Create a work record of the existing ARIS and modify accordingly. Obtain line management approvals (RL/LD/CD). Prepare the expanded SOW. E-mail the SOW to the Agreements Section. | Review and approve the revised ARS-416/417/550a. Release to NPS level for their review and approval. Monitor the ARIS for NPS approval. Upon NPS approval of the ARS-416/417/550a, prepare the Agreement amendment document and send it to the Cooperator for signature. Send a copy of the fully signed & executed Agreement amendment document to the Cooperator, ARS scientist, RL/LD/CD, and LAO. |