1.  Last Gate: Gate 2  07/19/05

Disposition: APPROVED. Issue #1: Funding for implementation is available from AHPS and AWIPS sources. O&M costs (beginning in FY09) are currently TBD and unfunded. It is expected that the O&M funds would be covered within baseline AWIPS O&M funding. Note #1: This project has been working in parallel with the Distributed Hydrologic Modeling Project (OSIP #04-007) to bring GFE capabilities to RFCs. Note #2: Any future enhancements to GFE after the initial implementation will require a separate OSIP project. Note #3: With OSIP Gate 3 approval, the IWT requests that this project be redirected to the SREC for an OB 8.X build (8.2 or 8.3 as appropriate). Note #4: RFC representation has been added to OSIP #06-094 Improving GFE Smart Tool Capabilities.

2.  Solution Description:

Solution - Initial Implementation of Graphical Forecast Editor (GFE) capability for RFCs at 5km resolution. The recommended solution will entail the implementation of the GFE onto RFC AWIPS sites supporting preliminary RFC requirements (referred to as GFE “out of the box”). See Note #2 above. Positives: a) Still required by RFCs; b) Ideal for WFO and RFC coordination; c) Can introduce Distributed Hydrologic Modeling (DHM) grids at the RFCs; and d) Less risk in implementation delays. Negatives: a) Won’t initially support all operational/functional requirements for RFCs; b) Due to limited initial capabilities, will likely take longer to see the total benefits of this tool. This solution will deliver the GFE to all 13 RFCs and include enhancements to satisfy DHM requirements. Capabilities include adjustable horizontal resolution (some western RFCs are interested in 2.5km resolution) as well as malleable smart tool capabilities.

3.  Planned Activities:

During Next Stage: Coordinate with AWIPS SREC to target an AWIPS Release for operational deployment (as of 3/20/07 expected to be OB 8.2) Design, code, and test the solution (to meet performance measures) Link products generated from the GFE to the hydrologic modeling systems Schedule and conduct all AWIPS-mandated software development reviews Determine expected system resource usage (e.g., SBN, WAN, cpu) Conduct early field testing of solution at selected RFCs if conditions permit Deliver all artifacts (source code, documentation, other) for inclusion in the national baseline Conduct Software Integration Testing (SWIT) Conduct Beta Testing at selected RFCs Confirm funding for Deployment. Confirm AWIPS O&M funding for this capability. Execute implementation, including training on the system Deliver solution to RFCs via the AWIPS release process. Provide NCF support to resolve issues related to the solution Provide software maintenance support to resolve issues related to the solution Assess how well the solution works in full operations

4.  Performance Measures and Success Criteria:

| At End of Next Stage | Performance Measure | Baseline (Current) | Threshold for Success |
| --- | --- | --- | --- |
|  | NONE |  |  |
| At Project Completion | RFC to share and collaborate 5 km grids with neighboring RFCs and WFOs | 2 out of 13 RFCs | 13 out of 13 RFCs |
|  | RFC operational use of GFE | 2 out of 13 RFCs | 13 out of 13 RFCs |
|  | AWIPS performs to maximum standards at RFCs | 99.9 % | No degradation to AWIPS. In other words, AWIPS will operate at 99.9 % availability |
|  | Service Backup of software, including configuration files and grids using rsynch | 0% @ RFCs | 100% @ RFCs |

5.  Organizational Roles and Responsibilities:

| During Next Stage | Organization | Lead | Role | Responsibility |
| --- | --- | --- | --- | --- |
|  | OST/PPD | Douglas Hilderbrand | IWT Lead | OSIP POC |
|  | OST/SEC | Stowe Davison | IWT Member | Will ensure AWIPS system resources are adequate to meet project needs |
|  | GSD | Tom Lefebvre | Software Developer and Lead Training POC. | Will develop software solution; will prepare for and conduct all mandated AWIPS reviews; will help perform training for RFCs |
|  | SREC | Ed Mandel | Assigns project to AWIPS Release | Will review and recommend changes to the AWIPS software baseline |
|  | WR | Kevin Lynott | IWT Member | Document Review |
|  | OHD | Chris Dietz and Dieu Ai Vo | IWT Member | Will ensure project outcomes do not conflict with Distributed Hydrologic Modeling Project requirements |
|  | AWIPS Contractor | TBD | Operational Deployment and Hotline support; adaptive and corrective maintenance | Will deploy AWIPS Release to RFCs and provide 1st tier software support |

6.  Milestones and Schedule:

Note: Milestone dates marked with an asterix (*) are subject to possible change

| DuringNext Stage | Milestones | Date (Qtr/FY) | Lead Organization |
| --- | --- | --- | --- |
|  | Gate 3 approval and redirect to SREC for AWIPS OB8.X | 3/2007 | SREC |
|  | Begin Design, Code, and Test Software | 3/2007 | Dev Org |
|  | AWIPS User Interface Review | 3/2007 | Dev Org |
|  | AWIPS Design Review | 3/2007 | Dev Org |
|  | Code Review(s) | 3/2007 | Dev Org |
|  | Test Plan & Procedures Review | 3/2007 | Dev Org |
|  | GFS Handoff Readiness Review* | 3/2007 | Dev Org / AWIPS Contractor |
|  | Code/Software hand-off* | 3/2007 | Dev Org / AWIPS Contractor |
|  | Begin Software Integration Testing* | 4/2007 | AWIPS Contractor |
|  | Complete Software Integration Testing* | 4/2007 | AWIPS Contractor |
|  | Deploy software to all RFCs* | 4/2007 | AWIPS Contractor |
|  | Begin Recurring O&M | 1/2008 | OST |
|  | Conduct Assessment of deployed solution | 4/2008 | OST |

7a.   Resource Requirements by Organization:

| During Next Stage | Organization | Labor (Hours) | Non-Labor ($K) |
| --- | --- | --- | --- |
|  |  | Required | Delta | Required | Delta | Source |
|  | OST/SEC (1 FTE @ 3 hours/week for 26 weeks) | 78 | 0 |  |  |  |
|  | Dev Org (projected to be GSD) | 120 | 0 | 75 | 0 | AWIPS |
|  | SREC (meet approx once a month for 2 hours) | 14 | 0 |  |  |  |
|  | WR (1 FTE @ 1 day) | 8 | 0 |  |  |  |
|  | OHD (1 FTE @ 2 hours/week for 26 weeks) | 52 | 0 | 75 | 0 | AHPS |
|  | OOS (1 FTE @ 2 hours/week for 26 weeks) | 52 | 0 |  |  |  |
|  | AWIPS Contractor |  |  | TBD | TBD |  |
|  | AWIPS Data Management |  |  | TBD | TBD |  |

7b.   Resource Requirements by Activity and FY:

|  | FY 2006 |  |  |  |  |  | Cost to | Cost at |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ($ in Thousands)One-time Investments | & Prior | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | Complete | Completion |  |
| Software |  | 70K | 0 |  |  |  | 70K |  |  |
| Hardware Upgrade |  | 0 | 0 |  |  |  | 0 | - |  |
| Service Backup (provided by RFC) |  | 0 | 0 |  |  |  | 0 | - |  |
| Training (cost depend on # focal points/RFC) 13 RFC focal points plus 13 others @$2000 for 1 week in Boulder |  | 52-80 K | 0 |  |  |  | 80K | - |  |
| WAN Costs for additional gridded products transmitted |  | 0 | 0 |  |  |  | 0 |  | Steady State Recurring Costs |
| Sub-total, One-time Costs | - | - 150K | - 0 | - | - | - | 150K | - |  |
| Recurring Costs (O&M) |  |  |  |  |  |  |  |  |  |
| AWIPS standard operating O&M |  | 0 | 0 | TBD | TBD | TBD | TBD | - |  |
| Hydrologic Software Maintenance |  | 0 | 0 | TBD | TBD | TBD | TBD | - |  |
| Sub-total, Recurring | - 0 | 0 | 0 | - TBD | - TBD | - TBD | - TBD | - | - |
| TOTAL | - | 150 | - | - | - | - | 150K plus O&M | - |  |
| Difference/Program Adjustment | - | - | - | - | - | - | - | - |  |

8.  Acquisition Strategy:

| During Next Stage | Item | Strategy |
| --- | --- | --- |
|  | None |  |
| Beyond Next Stage | None |  |

9.  Assumptions and Constraints:

| During Next Stage | Assumption/Constraint | Description |
| --- | --- | --- |
|  | Functional requirements will be coordinated | DHM IWT and GFE/RFC IWT will partner on Phase 1 requirements per solution agreement |
|  | Not operationally feasible to consider dividing RFC domains. | Observation from RFCs |
|  | A delay or obstruction in software development (for any amount of time) could delay release date | Known problems must be assessed and prioritized accordingly (OHD or Dev Org) |
|  | Time for RFCs to spin-up will be short | Training will entail an intensive 4.5 days at the GSD facility in Boulder, CO for focal points from each RFC. Focal points will then train the forecasters and his/her respective RFC. |
|  | Capabilities must conform to the AWIPS technical and security architectural constraints | The tool will contain the necessary features and performance capabilities (to meet the needs of the RFCs) as the system allows |

10.  Risk Assessment and Mitigation:

|  | Type | Description | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| During Next Stage | Business | New AWIPS Contractor | High | Low | Work thoroughly with Raytheon to accommodate new or enhanced science and technology |
|  | Technical | Hardware not able to handle added data for RFC operations | Low | High | Demonstration in Kansas City on 1/31/07 addressed this concern. |
|  | Technical | Architecture not satisfying performance requirements | Low | High | Test to insure that performance requirements are satisfied |
|  | Cost | Competing for limited AWIPS funds | Low | Medium | AWIPS has provided development funding and O&M must be identified prior to implementation. |
|  | Technical | System Backup | Low | High | Both software and hardware support shall be provided as well as a system backup plan by deployment |
|  | Schedule | AWIPS OB.2 delivery schedule | Medium | Medium | Coordinate with OST on latest release schedule for AWIPS OB8.X and where this project fits in |
|  | Technical | RFCs not trained on new system | High | High | Training composes large portion of budget. Training at Boulder as well as internet-based training will be provided. |