New Britain – Hartford Busway

Hartford, Connecticut

(November 2007)

The Connecticut Department of Transportation (ConnDOT) is proposing to construct the New Britain-Hartford Busway, an 11-station, 9.4-mile exclusive bus rapid transit (BRT) system operating primarily in an existing and abandoned railroad right-of-way on a new two-way roadway between downtown New Britain and downtown Hartford’s Union Station.  The busway would run parallel to Interstate 84

(I-84), the primary transportation link between New Britain, West Hartford, and downtown Hartford.  The project’s operating plan calls for a number of bus routes to operate on the Busway, including services that enter and exit the facility to reach destinations well outside of the immediate corridor without the need for a transfer.  The project scope includes the procurement of 30 new buses and construction of five park-and-ride lots along the alignment.

I-84 is currently, and is forecast to remain, the region’s most congested highway.  In addition, the combined population of New Britain and Hartford accounts for just under 50 percent of the entire  metropolitan area’s zero-car households. The proposed busway project is intended to provide faster transit travel times between major activity centers throughout the corridor, improve mobility and accessibility for the corridor’s relatively large transit-dependent population, and promote redevelopment opportunities in older urban centers along the project alignment.

| Summary Description |
| --- |
| Proposed Project: | Bus Rapid Transit |
|  | 9.4 Miles 11 Stations |
| Total Capital Cost ($YOE): | $458.78 Million (Includes $11.16 million in finance charges) |
| Section 5309 New Starts Share ($YOE): | $275.27 Million (60.0%) |
| Annual Forecast Year Operating Cost: | $10.00 Million |
| Ridership Forecast (2030): | 15,200 Average Weekday Boardings |
|  | 4,500 Daily New Riders |
| Opening Year Ridership Forecast (2012): | 13,700 Average Weekday Boardings |
| FY 2008 Local Financial Commitment Rating: | Medium |
| FY 2008 Project Justification Rating: | Medium |
| FY 2008 Overall Project Rating: | Medium |

The New Britain-Hartford Busway is not a candidate for FY 2009 funding, so FTA is reporting the project’s most recent ratings (November 2006).  The project was approved into final design in October 2006 with a cost estimate of $458.78 million.  Since that time, ConnDOT has experienced cost growth which may push the project cost above $600 million.  ConnDOT has identified over $100 million in potential cost saving strategies.  Some of these strategies may result in additional environmental work which could result in delays in the project schedule; others may impact the anticipated transportation benefits of the project, thus requiring new travel demand forecasts.

The New Britain-Hartford Busway has been in the New Starts pipeline since January 2000, and has encountered significant schedule delays and cost increases over that period.  ConnDOT must: a) submit to FTA a revised project scope, schedule, budget, and financial plan to serve as the basis for any potential Full Funding Grant Agreement, by June 30, 2008; and b) sustain sufficient New Starts ratings by September 30, 2008, or be removed from the New Starts pipeline.

Project Development History and Current Status

The 1994 regional transportation plan prepared by the Capitol Region Council of Governments identified the I-84 corridor west of Hartford as one of the metropolitan area’s high priority corridors in need of improvement.  A major investment study in the corridor was completed in 1999, which resulted in the selection of a BRT system between New Britain and Hartford as the locally preferred alternative.  FTA approved the New Britain - Hartford Busway’s entrance into preliminary engineering (PE) in January 2000.  The project received a Federal environmental Record of Decision (ROD) in March 2002.  In order to address changes in project scope since issuance of the ROD, ConnDOT completed supplementary environmental work, which FTA approved in June 2006.  FTA approved final design for the project in October 2006.  ConnDOT is currently looking at a number of cost reduction strategies in order to mitigate increases in the capital cost estimate resulting from further design of the project.

Project Justification Rating: Medium

The Medium project justification rating is based upon the following measures and criteria ratings, which were evaluated and rated in November 2006, and assume a capital cost estimate of $458.78 million.

| Cost Effectiveness Rating: Medium |
| --- |
| Cost per Hour of Transportation System User Benefit Incremental Cost per Incremental Trip | New Start vs. Baseline $22.07* $19.63 |
| Mobility Improvements Rating: Medium-High |
| Average Per Station: Employment Low Income Households Transportation System User Benefit Per Project Passenger Mile (Minutes) | 5,900 420 New Start vs. Baseline 3.60 |
| Environmental Benefits Rating: High |
| Criteria Pollutant Status 8-Hour Ozone (O3) Carbon Monoxide (CO) | EPA Designation Moderate Non-attainment Area |
| Transit Supportive Land Use Rating: Medium |
| Existing Land Use | Medium-Low |
| Transit Supportive Plans and Policies | Medium |
| Performance and Impacts of Policies | Medium |

# *Indicates that measure is a component of Cost Effectiveness rating

# Local Financial Commitment Rating: Medium

The Medium local financial commitment rating is based on Medium ratings for the New Starts share of project costs and for both the operating and capital finance plans. The plan was evaluated and rated in November 2006, and assumes a capital cost estimate of $458.78 million.

| Locally Proposed Financial Plan |
| --- |
| Source of Funds | Total Funds ($million) | Percent of Total |
| Federal: Section 5309 New Starts Section 5307 Urbanized Area Formula Funds Section 5309 Fixed Guideway Modernization Funds Section 5309 Bus Discretionary FHWA Flexible Funds (CMAQ and STP) FHWA NHS Funds | $275.27 $12.98 $13.06 $22.06 $38.85 $6.00 | 60.0% 2.8% 2.9% 4.8% 8.5% 1.3% |
| State: Special Transportation Fund (STF) STF/Public Act 06-136 | $38.56 $52.00 | 8.4% 11.3% |
| Total: | $458.78 | 100.0% |

NOTE:  The financial plan reflected in this table has been developed by the project sponsor and does not reflect a commitment by DOT or FTA.  The sum of the figures may differ from the total as listed due to rounding.

MAP