## ANL-E
Laboratory: Argonne National Laboratory - East | [9 empty] | Modernization Needs
Project/Activity | Space Added (sq. ft.) | Space Removed (sq. ft.) | TEC | 2001 | 2002** | 2003** | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | FY02-FY13 | FY04-FY13
REAL PROPERTY MAINTENANCE |  |  |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 204 | 170
(% of RPV) |  |  |  |  | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5%
General Plant Projects (GPP)
Canal Water System Overhaul - Building 582/583 |  |  | 1.4 | 2002**: 0.645 | 0.645 | 0
Building 364 - 2400V Transformer T11 & T12 |  |  | 0.4 | 2002**: 0.4 | 0.4 | 0
Central Chilled Water System Upgrade, Bldg 371 |  |  | 2.98 | 2002**: 1.08; 2003**: 1.8 | 2.88 | 0
Upgrade Inadequate PA Systems Program |  |  | 0.5 | 2003**: 0.2; 2004: 0.3 | 0.5 | 0.3
Overhead Crane Modifications Program |  |  | 0.4 | 2003**: 0.1; 2004: 0.1; 2005: 0.1; 2006: 0.1 | 0.4 | 0.3
Elevator Improvements Program |  |  | 9.2 | [13 empty] | 9 | 8 | bar: 2001 to Modernization Needs 2013
Restroom Upgrade Program |  |  | 3.6 | 2005: 1.8; 2006: 0.6; Modernization Needs 2007: 0.6; Modernization Needs 2008: 0.6 | 3.6 | 3.6
Space Rehabilitation Program |  |  | 10.3 |  |  |  |  | 1 | 1 | 2 | 1.3 | 1 | 1 | 1 | 1 | 1 | 10.3 | 10.3
5 KV Distribution System |  |  | 1.5 | 2005: 1.5 | 1.5 | 1.5
Improve Central Chilled Water Dist. & CFC Compliance, Phase II |  |  | 2.23 | 2004: 2.23 | 2.23 | 2.23
Sewer Renovation Completion |  |  | 2.8 | Modernization Needs 2007: 2.8 | 2.8 | 2.8
Metasys Expansion - Phase II |  |  | 2 | 2004: 2 | 2 | 2
Main Steam & Condensate Upgrades |  |  | 2 | [13 empty] | 2 | 2 | bar: 2001 to Modernization Needs 2013
Site Wide Door & Window Upgrades |  |  | 6 | [13 empty] | 6 | 6 | bar: 2001 to Modernization Needs 2013
Building 364 Chiller Upgrades |  |  | 1.9 | 2005: 1.9 | 1.9 | 1.9
400 Area Chilled Water System Expansion |  |  | 7.5 | 2004: 3.3; 2006: 2.1; Modernization Needs 2008: 2.1 | 7.5 | 7.5 |  |  | 144000000
Replacement Instrument Calibration Facility |  |  | 1.5 | 2004: 1.5 | 1.5 | 1.5 |  |  | 120000000
Replacement Waste Storage Building |  |  | 2 | 2005: 2 | 2 | 2 |  |  | 198000000
Replacement Central Fire Facility |  |  | 4.3 | 2006: 4.3 | 4.3 | 4.3 |  | General Plant Projects | 143500000
Building 604 (Bath House) Replacement |  |  | 1.5 | Modernization Needs 2007: 1.5 | 1.5 | 1.5 |  | General Purpose Equipment | 120000000
Misc. GPP Projects (TEC<1.0M or TBD) |  |  |  |  | 3.295 | 1.8 | 2.57 | 3.1 | 3.4 | 6.7 | 8.5 | 11.5 | 11.5 | 11.5 | 13.5 | 13.5 | 90.865 | 85.77 |  | Line Item Projects | 198066773
Total GPP |  |  |  |  | 5.42 | 4.9 | 13 | 13.4 | 14.5 | 15.6 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 153.82 | 143.5 |  |  | 461566773
General Purpose Equipment (GPE)
[5 empty] | 0.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IT: Networking Facilities Needs | [6 empty] | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 26 | 26
IT: Conferencing and Collaboration Equipment | [6 empty] | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 11 | 11
IT: Digital Libraries and Information Management | [6 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | 40
IT: "Network Smart" Equipment Infrastructure | [6 empty] | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 13 | 13
Other GPE Priorities |  |  |  |  | 1.6 | 2.3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 33.9 | 30
Total GPE |  |  |  |  | 1.606 | 2.3 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 123.906 | 120
INFRASTRUCTURE LINE ITEM CONSTRUCTION (SLI) | [19 empty] | 52.6227
Fire Safety Improvements - Phase IV |  |  | 8.4 | 2002**: 2 | 2 | 0
Mechanical and Control Systems Upgrades - Phase I |  |  | 9 | 2002**: 0.8; 2003**: 3; 2004: 0 | 3.8 | 0
Building Roof Replacements |  |  | 16.5 | 2005: 16.5 | 16.5 | 16.5
Multiprogram Laboratory Office Building | 50000 |  | 11.9771 | 2005: 11.9771 | 11.9771 | 11.9771 |  |  | #REF! | New Facilities
Building Electrical Service Upgrades - Phase II |  |  | 9.1 | 2004: 0; 2005: 9.1 | 9.1 | 9.1
Mechanical and Control Systems Upgrades - Phase II |  |  | 10.5062 | 2005: 10.5062 | 10.5062 | 10.5062 |  |  | #REF! | Building Improvements
Building Electrical Service Upgrades - Phase III |  |  | 10.7689 | 2006: 10.7689 | 10.7689 | 10.7689 |  |  | #REF! | Infrastructure Improvements
Roads/Parking/Walks/Street Lighting Upgrade |  |  | 13.5 | 2006: 13.5 | 13.5 | 13.5 |  |  | #REF!
Fire Safety Improvements - Phase V |  |  | 6.2 | 2006: 6.2 | 6.2 | 6.2
Laboratory Space Upgrades - Phase I |  |  | 12.9227 | Modernization Needs 2007: 12.9227 | 12.9227 | 12.9227
Mechanical and Control Systems Upgrades - Phase III |  |  | 10.7689 | Modernization Needs 2008: 10.7689 | 10.7689 | 10.7689 |  |  | 52.6227 | Lab Space Upgrades
General Purpose Laboratory Facility | 25000 |  | 5.9229 | Modernization Needs 2008: 5.9229 | 5.9229 | 5.9229 |  |  | 31.1752 | Mech
Building 362 Asbestos Abatement |  |  | 5.4 | Modernization Needs 2008: 5.4 | 5.4 | 5.4 |  |  | 35.4689 | Elec
Building Electrical Service Upgrades - Phase IV |  |  | 7.7 | Modernization Needs 2009: 7.7 | 7.7 | 7.7
Electrical System Upgrade - Phase IV |  |  | 11.3 | Modernization Needs 2009: 11.3 | 11.3 | 11.3 |  |  | 119.2668
Laboratory Space Upgrades - Phase II |  |  | 13.6 | Modernization Needs 2010: 13.6 | 13.6 | 13.6
Central Heating Plant Auxiliaries Upgrade |  |  | 8 | Modernization Needs 2010: 8 | 8 | 8
Mechanical and Control Systems Upgrades - Phase IV |  |  | 9.9 | Modernization Needs 2011: 9.9 | 9.9 | 9.9 |  |  | #REF!
Building Electrical Service Upgrades - Phase V |  |  | 7.9 | Modernization Needs 2012: 7.9 | 7.9 | 7.9
Laboratory Space Upgrades - Phase III |  |  | 26.1 | Modernization Needs 2013: 26.1 | 26.1 | 26.1
[17 empty] | 0 | 0
Total Line Items |  |  |  |  | 2.8 | 3 | 0 | 48.0834 | 30.4689 | 12.9227 | 22.0918 | 19 | 21.6 | 9.9 | 7.9 | 26.1 | 203.8668 | 198.0668 |  |  | 779.6335 | Capital
Total GPP/GPE/GPF: |  |  |  |  | 9.826 | 10.2 | 25 | 73.4834 | 56.9689 | 40.5227 | 48.5918 | 45.5 | 48.1 | 36.4 | 34.4 | 52.6 | 481.5928 | 461.5668
*Funded project, not included in the total for modernization needs.
**Dollars shown to match DOE Infrastructure Cross-cut information provided to Congress, March 2002, where appropriate.
Programmatic Project
Multiprogram Computational Facility | 40000 |  | 32.3067 | Modernization Needs 2007: 32.3067 | 32.3067 | 32.3067
Laboratory: Argonne National Laboratory - East |  |  |  | Modernization Needs 2007: Modernization Needs
Project/Activity | Space Added (sq. ft.) | Space Removed (sq. ft.) | TEC | 2001 | 2002** | 2003** | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | FY02-FY13 | FY04-FY13
DOE Direct Funded Excess Facilities Clean-up and Disposition
Non or slightly contaminated: list any projects***
Non or Slightly Contaminated
Bldg. 205 Sample Carousel |  | 130 | 0.455 | 2002**: 0.455 | 0.455 | 0
Bldg. 315 Cell 6 Pit Cleanup |  | 576 | 0.21 | 2002**: 0.21 | 0.21 | 0
Bldg. 315 Radiochemistry Lab D&D |  | 600 | 0.145 | 2002**: 0.145 | 0.145 | 0
Bldg. 205 H-125/H-126 Cell Decontamination |  | 2360 | 0.351 | 2003**: 0.351 | 0.351 | 0
Bldg. 306 C132 A&B Decontamination |  | 130 | 0.349 | 2003**: 0.349 | 0.349 | 0
Bldg. 202 (Kennels) Partial Disposal |  | 8000 | 0.2 | 2003**: 0.2 | 0.2 | 0
Bldg. 306 Rm. D0001, Cell 2 Decontamination |  | 275 | 0.2 | 2003**: 0.2 | 0.2 | 0
Bldg. 203 Service Floor Radium Clean-up |  |  | 4 | 2004: 0.5; 2005: 2; 2006: 1.5 | 4 | 4
Bldg. 40 (Instrument Calibration) Disposal |  | 4929 | 0.5 | 2005: 0.5 | 0.5 | 0.5
Bldg. 329 Waste Storage Facility |  | 960 | 0.5 | 2006: 0.5 | 0.5 | 0.5
Bldg. 325C Waste Storage Facility |  | 700 | 0.3 | 2006: 0.3 | 0.3 | 0.3
Bldg. 374A Waste Storage Facility |  | 1596 | 0.7 | 2006: 0.7 | 0.7 | 0.7
Bldg. 333 (Central Fire Station) |  | 11382 | 0.1 | 2006: 0.1 | 0.1 | 0.1
Bldg. 604 |  | 560 | 0.1 | Modernization Needs 2007: 0.1 | 0.1 | 0.1
Subtotal for Non or Slightly Contaminated |  |  |  |  | 0.81 | 1.1 | 0.5 | 2.5 | 3.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 8.11 | 6.2
All Other Contaminated
Building 330 (Demolition) |  |  | 3.7 | 2004: 3.7 | 3.7 | 3.7 | 0 |  | 21.6 | EM Baseline
Building 301 (Demolition:Funds for S&M in EM Baseline) |  |  | 1 | [13 empty] | 1 | 1 | 0 |  | 10.63 | EM FY02-03 | bar: 2006
Hot Cells, Building 200 M-Wing D&D ( incl. Demolition) |  |  | 30 | 2005: 1; 2006: 10; Modernization Needs 2007: 10; Modernization Needs 2008: 9 | 30 | 30 |  |  |  | 30 | Bldg 200 M-Wing
Subtotal for All Other Contaminated |  |  |  |  | 0 | 0 | 3.7 | 1 | 11 | 10 | 9 | 0 | 0 | 0 | 0 | 0 | 34.7 | 34.7
Total Excess Facilities |  |  |  |  | 0.81 | 1.1 | 4.2 | 3.5 | 14.1 | 10.1 | 9 | 0 | 0 | 0 | 0 | 0 | 40.9 | 40.9 | 0
Environmental Management | [20 empty] | #REF! | All demolitions
Continued O&M Requirements, Contaminated Sites | [6 empty] | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 4.5 | 4.5
Hydrological Characterization | [5 empty] | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 0.12 | 1.32 | 1.2
Environmental Monitoring Program |  |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 18 | 15
Long Term Stewardship | [6 empty] | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 6 | 6
Wetlands Management |  |  |  |  | 0.13 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.955 | 0.75
Total for Environmental Management |  |  |  |  | 1.63 | 1.695 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 31.325 | 28
All other contaminated: list any projects*** | [16 empty] | 0
EM Funded Commitments, Baseline and Proposed
EM-Funded D&D Baseline Projects (Incl. S&M) |  |  |  | 2002**: 2.656; 2003**: 0.374; 2004: 7.2; 2005: 7.2; 2006: 7.2 | 24.63 | 21.6 |  |  | 21.6
EM Funded Environmental Remediation Activities (Projects) |  |  |  | 2002**: 3.8; 2003**: 3.8 | 7.6 | 0 |  |  | 187.35 | Proposed EM
[17 empty] | 0 | 0
Subtotal for EM Funded Commitments, Baseline and Proposed |  |  |  |  | 6.456 | 4.174 | 7.2 | 7.2 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[18 empty] | 6.2 | demo
Third Party Funding
Energy Savings Performance Contract Projects |  |  |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 10
Total Third Party |  |  |  |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 12 | 10
**Dollars shown to match DOE Infrastructure Cross-cut information provided to Congress, March 2002, where appropriate.