SAFEGUARDS AND SECURITY FOR PROJECT MANAGEMENT

[This Guide describes suggested non-mandatory approaches for meeting requirements.  Guides are not requirements documents and are not construed as requirements in any audit or appraisal for compliance with the parent Policy, Order, Notice, or Manual.]

FOREWORD

This Department of Energy Guide is for use by all DOE elements.

Beneficial comments (recommendations, additions, and deletions) and any pertinent data that may improve this document should be sent to the Director, Office of Policy, HS-71, U.S. Department of Energy, Washington, DC  20585, by letter or by sending the self-addressed Standardization Document Improvement Proposal (DOE F 1300.3).

This Guide is intended to provide approaches for implementing the safeguards and security requirements of DOE O 413.3A, Program and Project Management for the Acquisition of Capital Assets.  DOE Guides, which are part of the DOE Directives System, provide supplemental information for fulfilling requirements contained in rules, regulatory standards, and DOE directives.  Guides do not establish or invoke new requirements nor are they substitutes for requirements.

CONTENTS

SECTION I:  INTRODUCTION

- Goal

- Scope

- Objectives

4.	Applicability

SECTION II:  SAFEGUARDS AND SECURITY PROGRAM

SECTION III:  DESIGN CONSIDERATIONS & INTERFACES

- Design Philosophy

- Basis for Design Standards

- Applicability of Facility and Physical Protection Standards

- Federal and Local Building Codes and National Standards

- Site Planning and Architectural Design

- Security System Design

- Security System Alternatives Evaluation

SECTION IV:  PROJECT & PROGRAM MANAGEMENT CONTROLS

- Change Control Process

- Change Initiation and Documentation

- Contract Completion and Closeout

SECTION V:  SAFEGUARDS & SECURITY AND THE CRITICAL DECISION PROCESS

- Project Phases

- Time Frames

- Initiation Phase (Pre-Conceptual Planning)

- Definition Phase (Conceptual Design)

- Execution Phase I (Preliminary Design Phase)

- Execution Phase II (Final Design Phase)

- Transition/Closeout Phase (Construction)

- Operational Phase.

Attachment 1 – Safeguards and Security Project Checklist

Attachment 2 – References

SECTION I:  INTRODUCTION

- GOAL:  The goal is to ensure that safeguards and security requirements are identified and integrated into the project early and their implementation assessed throughout the project life cycle, specifically at each Critical Decision (CD).  Establishing safeguards and security requirements early is necessary for project planning and cost estimating and to prevent project impacts that can be expected when safeguards and security requirements are injected late into the design process or as part of the operational readiness review.  Additionally, due to potential conflicts in meeting safeguards and security requirements and the requirements of other critical disciplines (e.g., operations and safety), the integration of all requirements is critical to developing a cost effective solution, which satisfies all requirements and provides the best overall solution for the project.  The protection of an asset should consider the threat to the asset as a fundamental part of the design process, so that the Department can maximize safeguards and security effectiveness while minimizing safeguards and security costs.  The total cost of the project (design, construction, installation, training and maintenance) should be measured against the potential harm from loss or misuse of the asset being protected or controlled.

2.	SCOPE:  This Guide addresses the implementation steps for achieving safeguards and security systems that support the Department’s protection objectives.  It provides a logical process for the implementation of accepted safeguards and security principles, which are translated into system requirements and configuration with an auditable cost and schedule; from project/program initiation through the transition/closeout phases.

3.	OBJECTIVES:  This Guide is to provide safeguards and security advice to Federal Project Directors and Federal Program Managers in identifying and implementing key safeguards and security components of their projects and integrating safeguard and security consideration into each Acquisition Management Phase (Initiation, Definition, Execution and Transition/Closeout).

a.	Facilitate communication and interaction between security professionals and the other members of the project design team.

b.	Develop effective security which minimizes impact on operations.

c.	Ensure a federal security representative is identified to serve as design Point of Contact (POC) and member of the Integrated Project Team (IPT) during the entire project cycle.

4.	APPLICABILITY: This guide applies the term “DOE” to refer to all DOE elements, including the National Nuclear Security Administration (NNSA).  Additionally, as used in this guide, the term “security” refers to both safeguards and security as it is applicable to the project or facility regardless of the type of building, structure, or facility and whether new or a modification.

This Guide provides approaches for implementing the security provisions within the functional areas contained in DOE O 413.3A, Program and Project Management for the Acquisition of Capital Assets.  The DOE G 413.3-X series provides companion supplemental Project Management guidance.  These are listed in the attached References of this Guide. Specific regulatory citations are provided in the body of the Guide.  This Guide expands upon the regulatory requirements of DOE O 413.3A and provides explanations and examples for implementing the requirements.

Except for requirements established by a regulation, contract, or administrative means, the provisions in this Guide are DOE’s views on acceptable methods of program implementation and are not mandatory.  Conformance with this Guide will; however, create an inference of compliance with the related regulatory requirements.  Alternative methods that are demonstrated to provide an equivalent or better level of protection are acceptable.  DOE encourages its contractors to go beyond the minimum regulatory requirements and to pursue excellence in their programs.

The words “should” and “may” are used to denote optional program recommendations and allowable alternatives, respectively.  This Guide is applicable to all DOE activities that are subject to the requirements of DOE O 413.3A.

SECTION II:  Safeguards and Security PROGRAM

DOE assets are defined and protection standards outlined in the Department’s Design Basis Threat Policy.  Protection strategies, depending on the asset being protected, range from a combination of compliance with DOE security policies to specific performance standards that must be met.  This constitutes a graded and risk-based approach assuring the highest levels of protection for those assets where loss, theft, compromise, and/or unauthorized use would seriously affect the national security, the environment, Departmental programs, and/or health and safety of the public or employees.  Security related interests and assets include special nuclear material (SNM), other nuclear material, radiological material, biological assets, classified parts, classified and/or sensitive information, critical assets, and high cost or unique items.  For example, all radiological materials are under varying levels of compliance-based requirements (i.e., physical security; material control and accountability policies; protective force responses; etc) based on the categorization of the radiological material (both as individual items and as the aggregate of the items to a greater category).  For those assets designated as Threat Level – 1, 2, or 3, reference the DBT policy, additional security measures may be required.  These additional requirements are defined as performance-based security measures, and require the conduct of a vulnerability assessment (VA).  The VA process is performed by the respective site, and results in a determination of what, if any, additional security measures are necessary to achieve an integrated protection system consisting of sensing, assessment, communication, response, interruption, and neutralization.

The DOE O 470 Series of orders establish minimum design principals.  Adherence to these orders will ensure safeguards and security designs embellish the DOE tenants of providing graded security and establishing defense in-depth.  For example, a security area denotes a physically defined space containing departmental security assets and subject to physical protection and access controls.  Security areas are established per the requirements of DOE M 470.4-2, Physical Protection.  The type of security area established depends on the nature of the security interests to be protected, with the following types required for the protection of the listed security interests.  These are:  Property Protection Area (PPA); Limited Area; Exclusion Area; Protected Area (PA); Material Access Area (MAA), and Vital Area.  The PPA (an office building or administrative area) represents the least restrictive area with the most restrictive being a PA which is located within an MAA.  The descriptions are provided in DOE M 470.4-7, Safeguards and Security Program References.

DOE safeguards and security programs are established through DOE 470 series Orders and Manuals, examples of applicable Orders and Manuals are:

- DOE O 470.3A, Design Basis Threat Policy (U), dated 11/29/05,

- DOE O 470.4, Safeguards and Security Program, Performance Assurance, dated 08/26/05,

- DOE M 470.4-1, Chg 1, Safeguards and Security Program Planning and Management, dated 03/07/06,

- DOE M 470.4-2, Chg 1, Physical Protection, dated 03/07/06,

- DOE M 470.4-4, Information Security, dated 08/26/05,

- DOE M 470.4-6, Chg 1, Nuclear Material Control and Accountability, dated 08/14/06.

SECTION III:  DESIGN CONSIDERATIONS & INTERFACES

- DESIGN PHILOSOPHY:  Completed designs should meet the requirements of all disciplines associated with the project.  Effective project management strives for an integrated solution to the issues.  The best solution, achieving the goals of each discipline, should be the aim of the project.  This integrated approach facilitates a cost effective solution for the project.  Designs should be defensible in terms of scope, cost, and project, and supportability.

- BASIS FOR DESIGN STANDARDS:  DOE security interests are to be protected from theft or diversion, sabotage, espionage, loss or theft of classified matter or government property, and other hostile acts which could cause unacceptable adverse impacts on National security, program continuity, or the health and safety of employees, the public, or the environment.  Levels of protection appropriate to particular safeguards and security interests are to be provided in a graded fashion in accordance with potential risks to National security and the health and safety of employees and the public.  Protection programs are tailored to address site-specific characteristics on the basis of DOE Orders, DOE Manuals, and other requirements.  Site-specific protection programs describing the implementation of these requirements are documented in protection program plans and/or Site Security Plans.

The basis for each discipline standard should be addressed.  For example, nuclear safety rules do not address malevolent acts, sabotage, or terrorist activities, while security requirements are focused primarily on such actions.  However, successful design accounts for all requirements within the areas applicability and expected environmental conditions for the system to operate.  This will necessitate accommodating potential interactions and overlaps among applicable requirements, such as those that might be encountered between postulated security technologies and normal operation or accident conditions, such as those required to be evaluated for life safety.

- APPLICABILITY OF FACILITY AND PHYSICAL PROTECTION STANDARDS:  Planning, design, and installation of security systems should be determined in consultation with the cognizant DOE security authority and should comply with security policies.

A key role of the security professional assigned to the project team will be to ensure that the best approach to meeting policy requirements is identified.  The approach should provide a security solution that minimizes security’s impact on project cost, potential safety concerns, operational impact, and other important considerations while maintaining compliance with requirements and providing effective security.

- FEDERAL AND LOCAL BUILDING CODES AND NATIONAL STANDARDS:  The planning and design should consider those Federal and local municipal life safety and electrical codes and standards applicable to the specific site and facility commensurate with its configuration and operations, and support National model building codes, mandatory design standards, energy conservation and environmental standards.  In addition, the design should address the facility design requirements driven by facility operations, such as chemical, biological, and radiological safety.

- SITE PLANNING AND ARCHITECTURAL DESIGN:  All DOE facilities are evaluated for potential risks to the employees, the public, and the environment.  DOE M 470.4 series policy documents contain guidance for determining the level of protection, based on facility functions and potential security risks.  A preliminary security review should be initiated during the project conceptual design phase and further developed during the preliminary and final design phases.  In most situations, these reviews are included in the project planning and design documentation (e.g., in conceptual design reports, or Critical Decisions).  Facility design and construction features, identified as a result of security review, may be factored into the conceptual design before establishing the project cost estimate and requesting funding authorization for design and construction.  An appropriate security plan should be completed and approved prior to the start of construction (including site preparation), consistent with DOE M 470.4-1, Safeguards and Security Program Planning and Management.  The plan should be updated as appropriate to reflect changes affecting security that are made to the facility during its lifetime.

- SECURITY SYSTEM DESIGN:  Controls should be established to prevent unauthorized access to security areas, unauthorized activities within security areas, and removal of security interests.  The following considerations include:

  - Although building access points are often minimized for security reasons, personnel egress from security areas must meet the requirements of National Fire Protection Association (NFPA) 101 and the applicable portions of the project building code (e.g., International Building Codes or NFPA 5000).

  - Entrances to and exits from security areas should be designed for efficient, yet controlled, movement of personnel or vehicles through designated portals.

  - Due to the security limitations on exiting certain buildings, alternative life safety approaches, such as a safe haven, based on performance based compliance with the NFPA requirements, may be required to meet the requirements of both disciplines.

  - External and internal areas within security boundaries should be provided with infrastructure support (i.e., electrical power, alarm communications and control systems).

Where there are conflicts between the security requirements and those of other disciplines, these need to be defined as early in the project as practicable, so as to provide the time to reach the best overall solution to all requirements.

- SECURITY SYSTEM ALTERNATIVES EVALUATION:  During the conceptual and preliminary design phase, alternatives analysis of security system is performed along with the other major activities of the project, including the security implications of the various proposed sites.  To ensure consideration of all alternatives appropriate to the significance of the threat, the project team should consult departmental programs supporting the development or deployment of security technologies.  Currently these include the DOE Office of Health, Safety and Security and the NNSA Chief, Defense Nuclear Security.  These organizations will be able to provide technical and contact information for security technologies being developed, tested, or deployed by the Department or other agencies of the United States.  Care should be taken to avoid new untested systems.  They should not be installed at DOE facilities unless there is a conscious decision that the site will be a field test facility for those systems.

Project teams may request technical assistance from the Office of Health, Safety and Security.  Communication is essential to ensure that the facility is able to receive the technology and that its deployment is appropriate for the facility.

SECTION IV:  PROJECT & PROGRAM MANAGEMENT CONTROLS

- CHANGE CONTROL PROCESS:  Change control ensures that project changes are identified, evaluated, coordinated, controlled, reviewed, approved, and documented in a manner that best serves the project as depicted in Figure IV-1, Communication is the Key to Change Management.  Errors, problems, opportunities, new management, or the availability of new methods or tools can initiate project changes.  Uncontrolled changes can lead to serious, far-reaching problems, which could affect the project’s technical scope, schedule, and cost baseline, as well as effects on safety, risk, quality, and products.

Figure IV-1 – Communication is the Key to Change Management

Once a security system has been selected and approved by the program/project manager, project evolution and/or changes in requirements can impact that decision or specifics of the solution.  Therefore, it is critical to manage change.  This includes the impact that security system changes have on the rest of the project and impacts other element changes could have on the security system.

Due to the critical nature of the interface between security and the other project elements, project triggers for change management (including when DOE should approve the change) should be defined based on security requirements and not just on the traditional DOE O 413.3A cost and schedule baseline requirements.  Once the program/project manager has approved construction, this change management process should become more formalized and timely.

Examples of change management triggers that should cause a meeting of the project team to discuss overall impacts and issues as a result of changes in one area (safety, security, operations) that might result in changes in other areas are:

- Life safety requires the installation of fire doors in previously unobstructed hallways or corridors, thereby potentially impacting closed circuit television coverage, alarm sensor coverage, or applied security technology.

- Security designs incorporating active denial as the most cost effective solution, thereby resulting in the need for changes in operations and life safety approach through the addition of safe havens or additional emergency egress points.

- The planned operational environment of a room changes through the planned introduction of Radio Frequency-sensitive work or equipment, thereby potentially limiting the use of radios for life safety (fire and medical) and security (protective force and system maintenance).

- The selected facility design for processing nuclear material changes to incorporate additional processing quantities and/or material forms (e.g., oxide and chlorides, in addition to metal), thereby potentially changing the safeguards and security strategy, criticality safety, and nuclear facility safety approaches.

- The planned facility is changed from only handling general process unclassified information to incorporate handling and storage of sensitive and classified matter.

- CHANGE INITIATION AND DOCUMENTATION:  If there are changes during the course of a project, the project team will need to determine whether project changes are required.  If changes are needed, the project team should determine and document each of the alternatives with respect to security risk; safety risk; environmental impact; quality and other regulatory requirements; long-term programmatic costs; project risk, cost, and schedule; etc.  Alternative selection approval should be made at the appropriate management level, as documented by the Project Execution Plan.

The Integrated Project Team (IPT) needs to determine the correct timing for the identification and procurement of security technologies for the project.  Although early planning and interface evaluation within the project is the key to success, especially the evaluation of alternative protection and control strategies, it may be important to delay actual procurement of the technology until it is required.  This delay provides project options for using improved technologies and assuring that the chosen technology is not obsolete when the project is ready to begin operation.  This is especially important for projects taking years to complete.  In such cases, however, it will be necessary to provide the infrastructure to support these technologies.  In doing so it is important that the federal project security representative maintains close coordination with the DOE and NNSA security technology organizations.

- CONTRACT COMPLETION AND CLOSEOUT:  After installation of safeguards and security systems, an appropriate level of review needs to be conducted to ensure that the security features will be available when needed and ready to function as intended.  In particular, a mechanism needs to exist to ensure that the functionality of the mechanisms as implemented meets the required levels of performance.  In addition, the review needs to ensure the safety features related to the security system are properly installed, operationally tested to ensure safety features operate as planned, and that the safeguards and security systems fail-safe (duplicate or alternative system elements designed to enhance operational reliability ensuring continuing operation in the event of failure of the primary system element) ensuring adequate security while avoiding safety mishaps.  The level of review can be graded based on the significance of the installation as long as the review covers these key features.  Use of existing readiness review processes in place at the site is encouraged.  After installation, there is typically an acceptance period to discern if the installed system meets the technical requirement specified in the contract.  An acceptance test based upon required security performance levels should have been specified for all security-relevant systems in the contract document, along with the plan approval requirements.

Essential elements associated with security systems require routine testing of the system to ensure operability.  Safeguards and security system testing requirements should be identified during the system selection process and documented in the Project Execution Plan.  Before the facility becomes operational, testing requirements must be documented in the appropriate security plans and facility operating procedures, including a formal Performance Assurance Program Plan when required by DOE security directives.

Administrative security mechanisms and any related physical and/or administrative safety controls must be tested and the review needs to ensure appropriate procedures, training, and other activities are in place and effective.

DOE O 425.1 C, Start and Restart of Nuclear Facilities, is applicable for new nuclear facilities and modifications following shut down of a Hazardous Category (HC)-1 or HC-2 nuclear facility.  The requirements of this order specify a readiness review process that must, in all cases, demonstrate that it is safe to start (or restart) the applicable facility.  It is also required for new HC-3 nuclear facilities.  The order should be reviewed for applicability when deploying security technologies and for modifications within a nuclear facility.

SECTION V:  SAFEGUARDS & SECURITY AND THE CRITICAL DECISION PROCESS

- PROJECT PHASES.  The project consists of phases (Initiation, Definition, Execution, and Transition/Closeout) which incorporate and are separated by Critical Decisions, which act as hold points for DOE’s approval of the current project activities and the plans for the next phase.  These Critical Decisions provide DOE’s approval for the project to move into the next phase.  Four critical decisions are considered major milestones approved by the Acquisition Executive that establish mission need, recommended alternative(s), acquisition strategy, the performance baseline, and other essential elements required to ensure that the project meets applicable mission, design, security, and safety requirements.  Figure IV-1, Typical DOE Functions for Projects, depicts a typical DOE project approach.

Figure V-1 Typical DOE Project Timeline

- TIME FRAMES:  The amount of time to complete a phase leading to a successful Critical Decision and to transition to the next decision will vary on the project and its complexity.  The less complicated the project, the more likely that more than one critical decision may be approved simultaneously.  On the other hand, there may be a need to separate a critical decision into sub-elements.  The key security tasks associated with each project phase are presented in Table V-1.  Note that these tasks need to be finished to complete the phase and support the Critical Decision.  However, it is important to start these efforts early in the phase, providing time for project interaction in support of these tasks and to address project changes they drive.  The phases are described below.

- INITIATION PHASE (PRE-CONCEPTUAL PLANNING):  This phase includes all activities leading to a CD-0 Mission Need decision.  This phase is normally independent of a particular solution and should not be defined by equipment, facility, technological solution, or physical end-item.  The Initiation Phase allows flexibility to explore multiple solutions and not limit potential solutions.  For all projects, an early evaluation of probable security concerns and Design Basis Threat (DBT) assessment should be made.  When indicated by this evaluation, a security professional for the project should be identified to serve as technical advisor and consultant and IPT member to the project on security matters for the remainder of the project.  For additional details regarding the CD process from initiation through the closeout phase, see Table V-1, Overarching Areas of Consideration.

When determined that it is to be a classified project, the DOE program manager should determine, with assistance from the security staff, the actions necessary for identifying the level of security and the associated requirements cited in Part 2, Section I, Chapter VII, DOE M 470.4-1, Program Planning and Management.  This action should identify the scope of the access authorizations required for project personnel and the need for procedures for the processing the Facility Data and Approval Record and any subsequent changes.

- DEFINITION PHASE (CONCEPTUAL DESIGN):  Once the Mission Need is approved (CD-0), the Definition Phase begins with the Conceptual Design Phase.  Successful completion of the Conceptual Design Phase is identified by the approval of CD-1.  The Conceptual Design Phase is defined as an interactive process to define, analyze, and refine project concepts and alternatives.  Approval of CD-1 authorizes Project Engineering and Design funds.  The security team representative would begin to plan for the role of security within the project.  This represents a critical point for determining and defining the security involvement in the project.  During conceptual design, the security representative would document all security requirements (e.g. physical security devices and systems, nuclear materials safeguards, information security and any specialized security equipment) to ensure that all critical overarching security components are identified.  The security representative should summarize alternative protection and control strategies and provide the project manager with estimated ranges for capital and operating costs of alternatives which meet security policy requirements.  This would occur with most topical security areas to ensure that alternatives for protection and control of security risks are evaluated for effectiveness and for long-term costs.  At the conclusion of conceptual design (CD-1), the Program would know the impact of safeguards and security operations on the project and the overall security role (e.g., security’s impact on the project will be significant, minimal, or serve in an advisory role ensuring safeguards and security departmental requirements are identified).

- EXECUTION PHASE I (PRELIMINARY DESIGN PHASE):  Once CD-1 has been obtained and Project Engineering and Design funds authorized, the Preliminary Design Phase commences.  Successful completion of the Preliminary Design Phase is identified by the approval of CD-2.  Approval of CD-2 authorizes submission of a budget request for the total project cost.  Safeguards and security involvement in the Preliminary Design Phase would consist of activities such as conducting vulnerability assessments, refining security strategies, defining security system performance requirements, determining office, alarm station, and other infrastructure requirements; and preparing mature cost estimates.  Depending on the scope of, and assets associated with the project, the resources necessary to conduct vulnerability assessments and security technology option analyses might be significant and require the expenditure of Project Engineering and Design funds in support of the performance baseline.  Additionally, security designs and associated electrical; communications; heating, ventilation, and air conditioning; and other appropriate support infrastructures for the security features of the project should be integrated into the overall project design and engineering package.  Where possible, industry standards should be used to plan for future growth or technological changes in the security systems.

- EXECUTION PHASE II (FINAL DESIGN PHASE):  Once CD-2 has been obtained, the Final Design Phase is initiated.  Final drawings, specifications, and contract documents are prepared to solicit bids for asset construction or assembly.  Statements of Work are prepared to solicit and select needed contractor support and appropriate performance incentives are identified.  Testing requirements and acceptance criteria are prepared for security systems and for system components.  Acceptance tests based upon required performance levels should be specified for all security-relevant systems in the contract documents.  Security representatives of the Integrated Project Team should ensure approval of the selected security system design by both contractor and field office managers.  Foreign Ownership, Control, or Influence (FOCI) determinations are made and vendor and contractor management systems are examined.  Project status and earned value milestones and reporting controls are negotiated.  The configuration management program is established

Successful completion of the Final Design Phase is identified by the approval of CD-3.  CD-3 is authorization to complete all procurement, construction, and implementation activities.  Guidance on the project cost parameters are addressed in DOE O 413.3A.  CD-3 authorizes expenditure of all budgeted resources to execute the project.  When final design is completed, all known security concerns have been identified and addressed, and the project is ready to begin construction.  Following CD-3 security would support construction of necessary security initiatives, begin safeguards and security-identified training objectives, finalize organizational structure, and prepare appropriate security plans and procedures necessary to support the project.  There should be included the Acceptance Plan preparation and Approval and when system operation and maintenance training should take place.  This includes the supporting operations and maintenance manuals/procedures.

- TRANSITION/CLOSEOUT PHASE (CONSTRUCTION):  Once CD-3 has been completed, the project Transition /Closeout Phase begins.  Project activities that are in progress in parallel with construction include final preparation of plans and procedures for facility operations.  This includes acceptance testing of systems as construction is completed, and the facility is transferred from the project to operations.  Thus, during the Transition/Close-out, all system documentation is reviewed and an acceptance determination made.  System component and complete system acceptance testing is evaluated against the test and acceptance plan.  Action is taken to evaluate the storage of system source codes and updates.  Maintenance and spare parts requirements are assessed, and procedures and maintenance practices are tested.  For security, efforts leading to CD-4 would represent an approved security plan, procedures, trained security professionals on-hand, and a successful Operational Readiness Review.

- OPERATION PHASE:  At CD-4, the project is completed, and there is transition to the operations program/project manager for assumption of responsibility for operations and maintenance.  The facility/site Management and Operations Group takes over the responsibility for the management, operation, and associated support.

ATTACHMENTS

ATTACHMENT 1 – SAFEGUARDS AND SECURITY PROJECT CHECKLIST

The following checklists are meant to be used by the safeguards and security point of contact and project team lead as a guide for ensuring that safeguards and security is efficiently and effectively integrated into the project.  As used in this attachment,, the term “security” refers to both safeguards and security as it is applicable to the project or facility regardless of the type of building, structure, or facility and whether new or a modification..  These lists are not meant to be all-inclusive.

Initiation Phase

- Safeguards and security (S&S) Point of Contact (POC) designated as a member of the Integrated Project Team (IPT)and briefed on the parameters of the potential project or mission need:

  - New Facility or existing retrofit

  - Type of facility (e.g., research, production, administrative/computing facility, nuclear and/or radiological material storage, processing with or without classified parts)

  - Population of the facility (e.g., numbers and origin)

  - Potential locations for the facility

  - Existing facility or infrastructure upgrade project (e.g., fire safety upgrade, security systems upgrade, adding classified capabilities to a formally unclassified facility)

- Begin identification of potential security-related assets associated with the project

  - Special Nuclear Materials (SNM), other nuclear material, radiological material, biological assets (virus samples, etc.), classified and/or sensitive information or parts, critical assets, high cost or unique items, high availability items (fire station, Emergency Operations Center (EOC), etc.)

  - Potential physical size and location of the project

  - Potential for hazardous materials

  - Potential impacts to protective force(PF) size and posture

  - Potential interfaces with emergency management/response assets due to nature of the facility

  - Impacts on existing security infrastructure/operations

  - Assess the Design Basis Threat (DBT) guidance for application to the project

- Establish relationships with other team members or disciplines involved:

  - Operations

  - Safety

  - Engineering

  - Information/Cyber Security Technologies

  - Budget

- Rough out timeline for major security related milestones and associated resources:

  - Conduct of Vulnerability Assessment’s (VA)

  - Security System design initiated and completed

  - Security documentation prepared, updated and completed (e.g., VA, security plan, materials control and accountability (MC&A) plan, security clearances)

  - Security tests (all safeguards and security functions)

  - Security Operational Readiness Review (ORR)

Definition Phase

- Confirm the parameters of the project and mission need:

  - New Facility or existing retrofit

  - Type of facility, e.g. research, production, administrative/computing facility

  - Population of the facility

  - Potential locations for the facility

  - Existing facility or infrastructure upgrade project (e.g. fire safety upgrade, security systems upgrade, adding classified capabilities to a formally unclassified facility, electrical power distribution and communications)

  - Potential initial registration or revision/update to the Safeguards and Security Information Management System (SSIMS)

  - Validate the application of the DBT to the facility and its operation

  - Perform vulnerability analyses against the facility configuration.

- Confirm security related assets identified in initiation phase and identify any new security- related assets

  - SNM, other nuclear material, radiological material, biological assets (virus samples, etc.), classified and/or sensitive information or parts, critical assets, high cost or unique items, high availability items (fire station, EOC, etc.)

  - Potential physical size and location of the project

  - Potential for hazardous materials

  - Potential impacts to Safeguards and Security staffing

    - Protective force size and posture

    - MC&A staffing

    - Information Security staffing

  - Potential interfaces with emergency management/response assets due to nature of the facility

  - Integration with existing security infrastructure/operations

- Finalize security-related functional and operational requirements for inclusion in overall project functional and operational requirements document:

  - Identify general safeguards and security requirements, to include barriers, explosives, security communications, PF support, entry/access controls, intrusion detection/surveillance systems, and MC&A systems

  - Identify operational and infrastructure support needed for safeguards and security features

- Identify safeguards and security-related disciplines necessary to consult on the project (e.g., physical security, information security, MC&A, operations security (OPSEC), PF, personnel security, etc.

- Continue relationships with other team members or disciplines involved:

  - Operations

  - Safety

  - Engineering

  - Information/Cyber Security Technologies

  - Project Management with other members IPT

  - Emergency Management

- Begin to finalize timeline for major security-related milestones and associated resources:

  - Conduct of computer-based VAs of the system and its components.

  - Security system design initiated and completed

  - Security documentation updated and completed

  - Security performance/acceptance tests

  - Security ORR

  - System operations and training documentation

  - System source code documentation

- Begin to develop/review security-related costs and resources

  - Direct Project related

  - Security operations

  - Project support related

Execution Phase I (Title Design)

- Conduct security-related assessments based on the confirmed parameters of the project and mission need:

- New Facility or existing retrofit

- Type of facility (e.g. research, production, administrative/computing facility)

- Population of the facility

- Potential locations for the facility

- Existing facility or infrastructure upgrade project (e.g., fire safety upgrade, security systems upgrade, and adding classified capabilities to a formerly unclassified facility

- Conduct security-related assessments based on the DBT, security policies, and the confirmed security-related:

- SNM, other nuclear material, radiological material, biological assets (virus samples, etc.), classified and/or sensitive information or parts, critical assets, high cost or unique items, high availability items (fire station, EOC, etc.)

- Potential physical size and location of the project

- Potential for hazardous materials

- Potential impacts to protective force size and posture

- Potential interfaces with emergency management/response assets due to nature of the facility

- Impacts on existing security infrastructure/operations

- Associated security risks

- Conduct reviews of overall project documentation for:

  - General and specific security requirements inclusion in engineering and design packages (e.g., physical security, barriers, explosives, security communications, PF support, entry/access controls, intrusion detection/surveillance systems, MC&A systems; classified and/or unclassified sensitive information systems; cyber systems)

  - Operational and infrastructure support needed for security features

  - Interfaces and impacts to and from other sections of the engineering and design package (e.g. safety systems, general and specific layouts, operational descriptions, etc.)

- Provide tasking, as required, to security-related disciplines to consult on the project (e.g., physical security, information security, MC&A, OPSEC, PF, personnel security, etc.):

  - Begin development of security-related training strategies

  - Begin development of security-related operational strategies

  - Interface with safety and operational training development

- Continue relationships with other team members or disciplines involved:

- Operations

- Safety

- Engineering

- Training

- Information/Cyber Security Technologies

- Budget

- Execute and review/complete major security-related milestones:

- Conduct of VAs

- Security System design, including key technologies

- Security documentation

- Security performance tests

- Security ORR

- Review/Finalize security-related costs and resources:

- Direct Project related

- Security operations and staffing

- Project support related

Execution Phase II (Construction / Acquisition)

- Monitor construction and change control:

- Document reviews

- Project meeting attendance

- Construction site walkthroughs

- Participation/observation in security related acceptance testing

- Continue security related assessments based on the DBT, security policies, and the confirmed security-related:

- SNM, other nuclear material, radiological material, biological assets (virus samples, etc.), classified and/or sensitive information or parts, critical assets, high cost or unique items, high availability items (fire station, EOC, etc.)

- Potential physical size and location of the project

- Potential for hazardous materials

- Potential impacts to protective force size and posture

- Potential interfaces with emergency management/response assets due to nature of the facility

- Impacts on existing security infrastructure/operations

- Associated security risks

- Continue reviews of overall project documentation and construction for:

  - General and specific security requirements inclusion in engineering and design packages (e.g. barriers, explosives, security communications, PF support, entry/access controls, and intrusion detection/surveillance systems)

  - Operational and infrastructure support needed for security features

  - Interfaces and impacts to and from other sections of the engineering and design package (e.g., safety systems, general and specific layouts, operational descriptions, etc.)

- Provide tasking, as required, to security-related disciplines to consult on the project (e.g., physical security, information security, MC&A, OPSEC, PF, personnel security, etc.):

  - Begin development of security-related training strategies

  - Begin development of security-related operational strategies

  - Interface with safety and operational training development

- Continue relationships with other team members or disciplines involved:

  - Operations

  - Safety

  - Engineering

  - Training

  - Information/Cyber Security Technologies

  - Budget

- Complete documentation and analysis necessary to support major security-related milestones:

  - Conduct of VAs

  - Staffing plans

  - Security System installation, including security technology

  - Security documentation updated and completed

- Security plans, including Site Security Plan , Site Safeguards and Security Plan, MC&A

- Security procedures

- Operations/Maintenance plans

- Proposed operation/maintenance budgets

  - Security function and performance tests, (all safeguards and security functions)

  - Security ORR

  - Documentation in support of the SSIMS data registration

- Review/finalize security related costs and resources

- Direct Project related

- Security operations

- Project support related

Transition/Closeout Phase

- Monitor construction closeout and change control

- Transition security to an operational status

- Continue security-related assessments based on the DBT, security policies, and the confirmed security-related:

- SNM, other nuclear material, radiological material, biological assets (virus samples, etc.), classified and/or sensitive information or parts, critical assets, high cost or unique items, high availability items (fire station, EOC, etc.)

- Potential physical size and location of the project

- Potential for hazardous materials

- Potential impacts to protective force size and posture

- Potential interfaces with emergency management/response assets due to nature of the facility

- Impacts on existing security infrastructure/operations

- Associated security risks

- Review final project documentation and construction (As-built) and assist in the development of punch lists for:

  - General and specific security requirements inclusion in engineering and design packages (e.g., barriers, explosives, security communications, PF support, entry/access controls, intrusion detection/surveillance systems)

  - Operational and infrastructure support needed for security features

  - Interfaces and impacts to and from other sections of the engineering and design package (e.g., safety systems, general and specific layouts, operational descriptions, etc.)

- Provide tasking, as required, to security related disciplines to consult on the project (e.g., physical security, information security, MC&A, OPSEC, PF, etc.)

- Finalize/conduct security-related training

- Finalize/conduct security-related operational procedures

- Interface with safety and operational training development and conduct

- Interface with safety and operational procedures

- Continue relationships with other team members or disciplines involved

- Operations

- Safety

- Engineering

- Training

- Information/Cyber Security Technologies

- Budget

- Complete documentation and analysis necessary to support major security-related milestones:

- Conduct of VAs

- Staffing plans

- Security System installation

- Security documentation updated and completed

    - Security plans

    - Security procedures

    - Maintenance and test plans/procedures

    - Proposed operational budgets

- Security functional, performance/acceptance tests

- Security ORR

- Conduct/oversee security-related operational acceptance tests and performance-related tests:

- Finalize security-related costs, resources and reports

- Direct Project related

- Security operations

- Project support related

- SSIMS

ATTACHMENT 2 - REFERENCES

Legislation

42 U.S.C. 2011, et seq., Atomic Energy Act of 1954, as amended

42 U.S.C. 7101 to 7386k, Codification of Department of Energy Organization Act

42 U.S.C. 7144a, Establishment of Security, Counterintelligence, and Intelligence Policies

41 CFR 102.74, Facility Management

48 CFR 952.204-2, Security Requirements

Department Directives

DOE 205 Series:  Although separate from the safeguards and security (S&S) information security program, the Department’s cyber security program operates under the same basic protection principles.  The cyber security program (including both classified and unclassified cyber security) is administered by the Department’s Chief Information Officer.

DOE O 413.3A, Program and Project Management for the Acquisition of Capital Assets

DOE G 413.3-1, Management of Design and Construction

DOE G 413.3-2, Quality Assurance

DOE G 413.3-3, Safeguards and Security for Project Management

DOE G 413.3-4, Tailoring

DOE G 413.3-5, Performance Baselines & Baseline Management

DOE G 413.3-6, High Performance Sustainable Building

DOE G 413.3-7, Risk Management

DOE G 413.3-8, EM Clean-up Projects

DOE G 413.3-9, Project Reviews

DOE G 413.3-10, Earned Value Management

DOE G 413.3-11, Project Management Lesson Learned Process

DOE G 413.3-12, Cost Estimating

DOE G 413.3-13, Acquisition Strategies

DOE G 413.3-14, IT Projects

DOE G 413.3-15, Project Execution Plans

DOE G 413.3-16, CD-4

DOE G 413.3-17, Mission Need Statement

DOE G 413.3-18, Integrated Project Teams

DOE O 470.4, Safeguards and Security Program and DOE M 470.4-X Series of Manuals

Other Federal Directives

FC 4-010-01, Unified Facilities Criteria, DoD Minimum Antiterrorism Standards for Buildings

U.S. Army Corps of Engineers, Technical Manual 5-853-4, Electronic Security Systems; CEGS 13720 series guides, and the  PROSPECT Program

GSA Office of Government Policy, Federal Real Property Council Security Resource Guide

DOJ Vulnerability Assessment of Federal Buildings

# Text boxes

Safety

Security

Operations

Design

Project

Management

Contractor IPT

Federal IPT

QA

DOE

Approval