DO TITLE:  Development and Build of Trace Gas Analyzer (TGA) Flight Unit

DO Type:  _X _ CPFF     ___ FFP

DO Contact Information in Addition to the CRAVE Contract Specialist or CO:

TMR:	Ralph J. Marak					Phone:  (281) 483-9144

DO Manager:  Ralph J. Marak				Phone:  (281) 483-9144

DO Mgr. Alternate: Joe Gensler 			            Phone:  (281) 483-0025

Concurrences:

(Original Signed)             	(Original Signed)               	(Original Signed)

Ralph J. Marak	Harold Reimers	Joe Gensler

DO Manager			      DO Mgr. Management		COTR

(Original Signed)              	(Original Signed)               	__________                   _

Ralph J. Marak	Steve Miller

Division TMR		      S & MA

Task Contains Flight Hardware, Flight Software or GSE?   	__X_ Yes	___No

Program Supported:    	__Shuttle     _X_ISS	 _X _EVA    _ _Advanced -

---------------------------------------------------------------------------------------------------------------

WBS:  _X _ 1.0 EVA  __ 2.0 FCE   __ 3.0 EVR   __ ECLSS   __ 5.0 ATCS   __ 6.0 CHeCS

For purposes of complying with FAR 52.232-22, Limitation of Funds, the total amount allotted by the Government to contract is specified in clause B.6, Contract Funding.  The funding listed in B.6 is the amount allotted for all Delivery Orders on the contract combined.

All terms and conditions of the contract apply to this Delivery Order.  In the event of a conflict between the contract and this Delivery Order, the contract shall prevail.

WBS reporting shall be done in accordance with applicable WBS reporting categories, as shown above and in the contract within Section C, Table 1.

# Narrative Task Description

## Background / Problem Description:

- Objective

The objective of this Delivery Order (DO) is to design, develop, certify, and deliver a flight certified Trace Gas Analyzer to support ISS Flight 15A.  Task includes the following: (1) integration of a new sensor that is GFE provided; (2) Performance of acceptance testing and recertification of the TGA; and (3) Preparation of the documentation necessary for the configuration control and certification of the TGA.

- Background

Recovery of the single fault tolerance to the External Active Thermal Control System (EATCS) in the event of ammonia loss, and the subsequent repair of any leak, is dependent on the availability and functionally of the Trace Gas Analyzer (TGA). The current TGA (P/N SEG39135052-301, S/N 1001) development unit has a limited life that has been exceeded and other limited life issues with this hardware has deemed that refurbishment of this unit is not practical.  The availability of COTS hardware, as well as the ability to reduce crew time with increased function and reliability, has produced the need for a design upgrade. The new configuration will be based on the design of the development unit but will include upgrades to the pumping system, microprocessor, display and modification of the housing to enclose the existing and new components.

## Task Description:

The contractor shall provide personnel and facilities necessary for the design, manufacturing, and testing of a TGA. The tasks shall include:

Design and development of an upgraded TGA that includes a new pumping system, display, and microprocessor. The new design will be based on the design of the development TGA (P/N SEG39135052-301, S/N 1001) and the results of the investigations of a new pumping system, display, and microprocessor performed under NASA Contract # NNJ04HE06C, “ATCS Leak Detection and Repair Hardware”. The components that have been recommended for the  upgraded TGA are :

| Nomenclature | P/N | Manufacture |
| --- | --- | --- |
| Ion Pump (2) | 9190520 | Varian |
| Pole Piece Assembly | 9190038 | Varian |
| Getter | S5H0380 | SAES Getters |
| Microprocessor | 84-0027 | JK Microsystems |
| Test Display | OSD 1602-A | OSD (One Stop Displays) |
| Graphics Display | OSD 2401-4 | OSD (One Stop Displays) |

This task also includes the design and manufacture of any new circuit boards that will be required for interfacing the new microprocessor with the TGA and any that will be required for the new pumping system and display.  The contractor shall:

Design, development and test software/firmware associated with TGA and Quadrupole Mass Spectrometer (QMSA)

Prepare new CARD (DRL# 45), TGA Derived Requirements Specifications and Software Documentation that reflects the configuration and the acceptance/certification requirements of the new configuration. The CARD is to be tailored from the requirements that are stated in the CARD (JSC-40058A), the TGA Derived Requirements Specification (JSC-40136), and the Software Specification Document (JSC-40095) for the development TGA (P/N SEG39135052-301, S/N 1001) and the capabilities of the TGA with the new enhancements.

Design and manufacture of a new case that will house the existing and new components.

Coordinate with JPL for the manufacturing and delivery of the QMSA components that are necessary to assemble the flight TGA.

Assemble TGA using new components and integrate new QMSA.

Support JPL in the retuning of the QMSA, document the procedures and perform certification and acceptance testing.

Certify TGA and deliver with required data packages and documentation.

Coordinate with JPL to assist or prepare documentation necessary to identify the processes and procedures required to assemble and test the QMSA.

Prepare process documentation that is necessary to assemble and test components of the TGA (i.e. Overpressure Interlock System -OPIS).

Reconfigure GFP development TGA with new display, microprocessor and pumping system. This task includes manufacturing of new TGA case components, as required to assemble the TGA.

Support Human Thermal Vacuum HTV demonstration testing with prototype unit  (This task will be applicable only if a HTV test is scheduled during the performance of this DO).

Identify and procure sufficient spares of the limited life components that will be capable of supporting repairs of the TGA through CY 2010

Deliverables/Products:

| Product | Description | Qty | Due | Class |
| --- | --- | --- | --- | --- |
| Hardware |  |  |  |  |
| Mock Up |  |  |  |  |
| Prototype | Reconfigured Development unit (P/N SEG 39135052-301, S/N 1001) to Hi-Fi flight configuration | 1 | 6/20/06 | III |
| Certification | Utilize Flight item for certification |  |  |  |
| Flight | Upgraded TGA w/ new pumping system, display, and microprocessor | 1 | 3/30/07 | I |
| Training | Utilize Prototype unit |  |  |  |
| Other |  |  |  |  |
| Test |  |  |  |  |
| Software | Software/firmware associated with TGA and QMSA |  | 5/22/06 |  |
| Other Products |  |  |  |  |

SCHEDULE

Start Date:  Dec.  2, 2005			Finish Date: March 30, 2007

| ITERIM MILESTONES | DUE DATES |
| --- | --- |
| Combined SRR/PDR/CDR | 5/22/06 |
| Certification Complete | 3/23/07 |
| Deliver Hardware | 3/30/2007 |
| Milestones, along with subjective measurements, are to be used for measuring performance. For schedule detail see Microsoft Project file located on the CRAVE web site for this DO listed under the Government Cost Estimate below. |

Government Estimate Located in RFQ File in Microsoft Project File On CRAVE Web Site

The file is titled:

Total Government Estimate for this DO: $1.75M

TOTAL COST ESTIMATE FOR THIS DO:  $ (contractor complete)

FEE:  $ (contractor complete)  (If Applicable)

Changes to DRDs:

Since the level of maturity of the design for the TGA is past the PDR stage, the following DRDs are to be combined: DRD # 4, DRD #6,and DRD #18,  Submittals for the SRR Data packages and the PDR Data Packages shall only be required to identify the requirements and designs for the changes from the design of the TGA P/N SEG39135052-301, S/N 1001.

DATA REQUIREMENTS

| DRD # | DATA TYPE | DRD TITLE | DUE | FREQUENCY | REQUIRED FOR DO? Y/N | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Written Approval | FlightGFE Configuration Management Plan | With Proposal | Once | Attachment J-8 |  |
| 2 | Mandatory Submittal | Regular Status Report/ Summary Review | Thirty (30) days following contract start | Monthly | Y |  |
| 3 | Written Approval | Project Technical Requirements Specification | If Required for DO See Comments | Once with Revisions | N | Requirements identified in CARD (DRD #45) |
| 4 | Mandatory Submittal if Flt H/W | GFE Systems Requirements Data Package | If Required for DO See Comments | Once with Revisions | Y | Combine with CDR (DRD #18) |
| 5 | Written Approval | Flight GFE Projects Requirements & Verification Document | If Required for DO See Comments | Once with Revisions | N | Verification Requirements identified in CARD (DRD #45) |
| 6 | Mandatory Submittal if Flt H/W | Preliminary Design Review Data Package | If Required for DO See Comments | Once with Revisions | Y | Combine with CDR (DRD #18) |
| 7 | Written Approval | Flight GFE Workmanship Specifications List | If Required for DO See Comments | Once with Revisions | Y |  |
| 8 | Written Approval | Project Schedule | PDR or 10% effort complete Milestone (See Comments) | Once w/Revisions (due w/DO proposal, updates & details provided as DO progresses) | Y | Baseline scheduled provided at CDR |
| 9 | Written Approval | Flight GFE Interface Control Document | If Required for DO See Comments | Once with Revisions | N |  |
| 10 | Written Approval | GFE End Item Specification | If Required for DO See Comments | Once with Revisions | N |  |
| 11 | Mandatory Submittal if Flt H/W | Flight GFE Failure Analysis Report | If Required for DO See Comments | As Required | Y |  |
| 12 | Written Approval | Flight GFE Verification and Validation Plan | As Specified in EA-023 | Once with Revisions | N |  |
| 13 | Written Approval | GFE Software Requirements Specification | If Required for DO See Comments | Once with Revisions | N |  |
| 14 | Written Approval | GFE Software Development Plan | If Required for DO See Comments | Once with Revisions | N |  |
| 15 | Written Approval | GFE Software Design Document | If Required for DO See Comments | As Required | Y |  |
| 16 | Written Approval | Engineering Drawings | If Required for DO See Comments | Once with Revisions | Y | W/O Flight H/W Signature Rigor at CDR |
| 17 | Written Approval | EEE Parts Lists and Analysis Report | If Required for DO See Comments | As Required | Y |  |
| 18 | Mandatory Submittal if Flt H/W | Critical Design Review Data Package | If Required for DO See Comments | Once with Revisions | Y | W/O Flight H/W Signature Rigor at CDR |
| 19 | Mandatory Submittal if Flt H/W | Engineering Drawing Change Proposal | If Required for DO See Comments | As Required | Y |  |
| 20 | Written Approval | GFE Qualification Test Procedure | If Required for DO See Comments | Once with Revisions | Y |  |
| 21 | Written Approval | Flight Product User’s Guide | If Required for DO See Comments | Once with Revisions | Y | W/O Flight H/W Signature Rigor at hardware delivery |
| 22 | Mandatory Submittal if Flt H/W | Software Code | If Required for DO See Comments | As Required | Y |  |
| 23 | Written Approval | Information Technology (IT) Security Program Plan and Reports | (30) days after DO award, and as specified in JPG 2810.1 | JPG 2810.1 | Attachment J-4 Due 30 days after DO award |  |
| 24 | Written Approval | Certification Plan | If Required for DO See Comments | Once with Revisions | N | Included as part of CARD (DRD # 45) |
| 25 | Mandatory Submittal if Flt H/W | Certification Report | If Required for DO See Comments | Once with Revisions | N |  |
| 26 | Mandatory Submittal if Flt H/W | Engineering Analysis | If Required for DO See Comments | As Required | Y | Support of design reviews |
| 27 | Mandatory Submittal if Flt H/W | Acceptance Data Package | If Required for DO See Comments | One Time | Y | Supplied with hardware delivery |
| 28 | Mandatory Submittal | Export Control Audit Results | After award of 1st DO, yearly on Sept. 30 thereafter | Yearly |  |  |
| 29 | Written Approval | Quality Plan | With Proposal | Once with Revisions | Attachment J-11 | Only if contractor is using the R-Quality Plan template instead of ISO, and only if they need to make changes to it |
| 30 | Written Approval | Patent Rights-Retention | As Required | As Required | Y (If Applic’ble) |  |
| 31 | Written Approval | Shuttle/Station Payload Safety Data Package | If Required for DO See Comments | As Required | Y |  |
| 32 | Mandatory Submittal if Flt H/W | Limited Life Systems List | If Required for DO See Comments | As Required | Y (if applicable) |  |
| 33 | Written Approval | Space Station GFE Failure Modes and Effects Analysis and Critical Items List | If Required for DO See Comments | As Required | Y |  |
| 34 | Written Approval | Space Shuttle GFE Safety and Analysis Report &Hazard Report | If Required for DO See Comments | As Required | N |  |
| 35 | Written Approval | Software Quality Assurance Plan Report | 90 Days Prior to Software Development | Once with Revisions | Y (If Applic’ble) |  |
| 36 | Written Approval | ISS Hazard Report | If Required for DO See Comments | As Required | Y |  |
| 37 | Upon Request | Reliability and Maintainability Plan | With Proposal | One Time | Attachment J-9 |  |
| 38 | Written Approval | Government Certification Approval Request (GCAR) | If Required for DO See Comments | As Required | Y |  |
| 39 | Written Approval | Risk Assessment Executive Summary Report (RAESR) | If Required for DO See Comments | As Required | Y | 2 weeks prior to CDR |
| 40 | Written Approval | Problem Reporting and Corrective Action (PRACA) | 2 business days of problem isolation but no later than 10 days after detection | As Required | Y |  |
| 41 | Upon Request | Nonconformance Record | If Required for DO See Comments | As Required | Y |  |
| 42 | Mandatory Submittal | Government Industry Data Exchange Program and NASA Advisory Problem Data | Reported one time when discrepancy occurs | Once with Revisions | Y (if applicable) |  |
| 43 | Written Approval | Electrical, Electronic, and Electromechnical (EEE) Parts Control Plan | If Required for DO See Comments | Once with Revisions | N |  |
| 44 | Mandatory Submittal if Flt H/W | Certification Data Package | If Required for DO See Comments | Once with Revisions | Y |  |
| 45 | Written Approval | Certification and Acceptance Requirements Document | At CDR | Once with Revisions | Y |  |
| 46 | Upon Request | Wage/Salary and Fringe Benefit Data | Thirty (30) days after issuance of each DO | Once | Y |  |
| 47 | Written Approval | GFE Acceptance Test Procedure | If Required for DO See Comments | One Time | Y |  |
| 48 | Mandatory Submittal if Flt H/W | Flight GFE Verification & Validation Report | If Required for DO See Comments | Once with Revisions | N | Included as part of CARD (DRD # 45) |
| 49 | Mandatory Submittal if Flt H/W | Space Shuttle GFE Failure Modes and Effects Analysis (FMEA) and Critical Items List | If Required for DO See Comments | As Required | N |  |
| 50 |  | Reserved | --- | --- | --- | --- |
| 51 | Mandatory Submittal | NASA Contractor Financial Management Reporting | After Issuance of 1st DO | Monthly | Y |  |
| 52 | Written Approval | Government Property Management Plan | With Proposal | Once with Revisions | Attachment J-7 |  |
| 53 | Mandatory Submittal | System Safety Plan | With Proposal | One Time | Attachment J-10 |  |
| 54 | Written Approval | R-Quality Plan Template | With Proposal/ Revisions as Required | Only applicable to B-CRAVE contracts in accordance with the SOW and the DRD |  | Only if contractor is using the R-Quality Plan template instead of ISO, and only if they need to make changes to it |

Type 1 = Written Approval               Type 2 = Mandatory Submittal                Type 3 = Submittal Upon Request

GOVERNMENT FURNISHED PROPERTY  - The list of items below will be provided as Government Furnished Property.

| Item | Part Number | Quantity | Value |
| --- | --- | --- | --- |
| Development TGA | SEG39135052-301, S/N 1001 | 1 | $1,000,000.00 |
| TGA Vacuum/Thermal Test Bed |  | 1 | $300,000.00 |