| 1. DRD Title Financial Management Report | 2. Date of current version OCTOBER 2001 | 3. DRL Line Item No. 08 | RFP/Contract No. (Procurement completes) NAS 9 - 18181 |
| --- | --- | --- | --- |
| Use (Define need for, Intended use of, and/or anticipated results of data) To provide a cost data report on planned and actual costs, labor hours, and estimates over the life of the contract for financial planning and control. | 5. DRD category: (check one) € Technical X Administrative € SR & QA |
| 6. References (Optional) NPG 9501.2C | 7. Interrelationships (e.g., with other DRDs) (Optional) 09, 10, 13 |

8.  Preparation Information (Include complete Instructions for document preparation)

GENERAL:  This document describes the format and content of the NASA Form 533

family of reports required to provide management with the data necessary for:

- Projecting both cost and hours to ensure that dollar and labor

resources realistically support the schedule.

- Evaluating contractor cost performance.

- Planning, monitoring and controlling resources.

- Establishing the basis for NASA’s accrued revenue and expenditure

accounting system.

The formats described in this Data Requirements Description are intended to satisfy the requirements of the Form 533M and the Form 533Q.  The Form 533P (performance Measurement) is not addressed in this description but will be satisfied by performance measurement documents.

NASA is required by law to maintain accrual accounting, which requires cost to be reported in the period in which benefits are received, without regard to time of payment.

The NF533 reports are the official cost documents used at NASA for cost type, price redetermination, and fixed price incentive contracts.  The data contained in the reports must be auditable using Generally Accepted Accounting Principles.  Supplemental cost reports submitted in addition to the NF533 must be reconcilable to the NF533.

The due dates reflect the date the NF533 reports are received by personnel on the distribution list, not the date the reports are generated or mailed by the contractor.  It is critical that the NF533 reports are submitted in a timely manner to ensure adequate time for NASA to analyze and record the cost into the NASA accounting system.

ORGANIZATION:  The reports address costs and direct labor hours with respect to work breakdown structure, cost structure, and time.  Those dimensions are discussed more fully below.

CONTRACT WORK BREAKDOWN STRUCTURE:  The section of these reports organized by contract work breakdown structure (CWBS) shall be consistent with the  CWBS approved by the Contracting Officer’s Technical Representative (COTR).  The data in these reports shall be displayed at the fourth digit level of the CWBS, except PTT/AST and Project Management, which will be reported at the second level.

COST STRUCTURE:  The elements of cost (data) to be included in the reports should be consistent with the latest approved disclosure statement.  Any changes to the cost element detail necessitated by changes in your cost structure or by growth element components will require Contracting Officer direction.  In those cases where inter-organizational or inter-divisional work is required, the total cost of such work should be displayed separately, and not included as a component of material.

The Prime Contractor is responsible for obtaining  533’s from cost-type subcontractors and for providing cost-element-level cost accrual data using the same format and WBS (as it relates to the subcontract) for each of those subcontractors exceeding $500,000 per year as indicated in NPG9501.2C or most current revision.  This requirement shall be satisfied by including the 533’s as a section in the TSC 533.

The required elements of cost include: direct labor hours and costs for the Contractor,  Subcontractor sell price and hours, other direct costs, material including major sub dollars, interdivisional costs, and indirect costs (labor overhead, material overhead, S&A, and cost of money).

Variance explanations are not required in the 533M or 533Q, but will be submitted with the Cost Performance Report (DRD 09).

ADDITIONAL GUIDANCE:

The value of unfilled orders outstanding must be included in the report at the program level in the comments section.

Prime contract award/incentive fee will be reported at the contract level.

Prior period adjustments shall be reflected in Columns 7a and 7c of the 533M and column 7a of the 533Q footnoted at the bottom.

For contracts which have multiple schedules, a summary NF533 is required to provide a cumulative from inception cost for the contract, regardless of schedule.

An initial NF533 Report is required in the NF533Q format to be used as a baseline for the life of the contract.  The initial report shall reflect the original contract value detailed in terms of negotiated reporting categories and shall be the original contract baseline plan.

Cumulative cost reported to NASA should be in full incurred cost.  The prompt payment discount amount taken should be reported as a separate line item on the NF533 below the cumulative cost amounts for the contract.

Short and long-term cost estimates, which include all data entered in columns 8 and 9a on the NF533M and NF533Q reports, shall be based on the most current and reliable information available.

Fee should be accrued as earned using a consistent and auditable method to determine the amount.  For example: an acceptable method would be to use historical data to determine the amount to accrue each month.  Fee should be reported on the NF533 following the “Total Cost” line.  Award fee must be reported by the following categories:  Base Fee, Fee Earned, Interim Fee, Provisional Fee, Potential Additional Fee, and Total Fee.  If any of the above fee categories do not pertain, they should not be included in the NF533.

Monthly NF33 Reporting is no longer required once the contract is physically complete, provided the final cost report includes actual cost only (no estimates or forecasts).  The contractor must continue to submit monthly NF533 reports as long as estimates for the following period are included.  If the final cost of a contract changes after the submission of the “final“ contractor cost report, the contractor must submit a new cost report in the period/month the change is recognized.

The 533 documents shall be assembled with the following sections:

- A comments section consisting of pertinent remarks and clarification

not appropriate for the formats.

- A project section by WBS with all required elements of cost.

Original signed in Mod 100 still in effect

________________________________

Reviewed by:

___ Original signed in Mod 100 still in effect

Chief, Cost Accounting Branch

Financial Management Division

Concurred by:

__ Original signed in Mod 100 still in effect

Chief Financial Officer

# Text boxes

Modification 223

Modification 223

Modification 223