Scope of Work: Learning Laboratory (646 Demos) Meeting

Contractor:

Work Assignment No.:

Work Assignment Title: Learning Laboratory (646 Demos) Meeting

Date Prepared:	May 9, 2006

Project Officer:

Work Assignment Originator and Leader: Michael Harrison

=============================================================

Part I – INITIATOR’S REQUEST

A.  Period of Performance:7/2006-11/2007

B.  Work Assignment Description: Responsible for planning and carrying out the logistics of a one-day user and expert meeting to be held at AHRQ for up to 50 attendees, including  35 attendees and  experts from out of town with expenses paid through this contract.  Approximately 5 attendees will be invited providers, researchers, or stakeholders from the Washington DC metro area and will not require airfare or overnight facilities.  Approximately 10 will be Federal workers. Work will include:

- Meet with Work Assignment Originator (hereafter AHRQ lead) to plan preparations for meeting and develop time line for pre and post meeting tasks including setting date in cooperation with CMS (probably early fall of 2007); planning meeting format; identifying attendees and experts to invite; preparing and sending letters of invitation, hotel arrangements, conference center logistics, meeting synthesis.

- Appoint or hire meeting facilitator and senior writer for synthesis.

- Preparation and sending of invitations to all participants

- Confirmation and provision of logistical information to all participants.

- Contacting up to 35 attendees to make travel arrangements and reimburse for travel accommodations.

- Reserving and making arrangements for meeting room at AHRQ to include necessary audio/visual equipment.

- Food and beverage arrangements at meeting room.

- Preparation and mailing of briefing book. Delivery of additional briefing books and meeting summaries to about 10 federal employees (most of whom will be at AHRQ and CMS).

- Transcription of meeting

- Preparation, editing, and mailing of synthesis (approximately 15 pages) by senior writer, to be approved by AHRQ lead This synthesis must be suitable for web posting on AHRQ and CMS web sites, and suitable for publication as a 1500-2000 word Conference Report for a journal (e.g.,     (e.g. Health Affairs, 24, 1364-1366, 2005). Publication submission subject to review by AHRQ lead and other staff.

- Collect and email power point presentations to all participants who request them. Provide AHRQ and CMS with completed set of power points for subsequent distribution.

- Work Assignment Leader:

Michael I. Harrison, Ph.D.
Senior Research Scientist -- Organizations and Systems

Center for Delivery, Organization, and Markets

Agency for Healthcare Research and Quality
540 Gaither Rd. 
Rockville, MD 20850
Phone: 301-427-1434  Fax: 301-427-1430

Email: Michael.Harrison@ahrq.hhs.gov

D.	Deliverables.

- Meet with AHRQ lead within two weeks of award to plan meeting preparations, agenda development, and activities before during and after meeting.

- Provide AHRQ lead with workplan containing objectives and deadlines for meeting preparation steps and post meeting activities, including dates for deliverables.

- Provide monthly updates to AHRQ lead by email (and as needed by phone) on progress in terms of objectives, budget, and  timeline.

- In coordination with CMS and AHRQ set date for meeting

- Reserve AHRQ conference center facilities

- Secure hotel rooms

- Appoint or hire senior level facilitator subject to approval by AHRQ lead

- Facilitator works with AHRQ and CMS staff to develop agenda

- Appoint or hire senior writer -- to be approved by AHRQ lead -- to prepare meeting synthesis

- Assist in identification/location of appropriate attendees from CMS demonstration sites and experts based on AHRQ and CMS recommendations

- Invite attendees (includes tracking down addresses, handling questions, and confirming attendance)

- Make and pay for all necessary travel and hotel arrangements for up to 35 out-of-town attendee.

- Mail airline/travel tickets, reimbursement claim forms, and instructions to each non-Federal attendee prior to the meeting.  Reimbursement claim forms will be received, and approved expenses for non-Federal participants will be paid no later than 30 days after receipt of forms.

- Other correspondence, e.g., including mailing of agenda, briefing book, and post meeting summary.

- Prepare written synthesis (approximately 15 pages). This synthesis must be suitable for web posting on AHRQ and CMS web sites and suitable for publication as a 1500-2000 word Conference Report for a journal (e.g.,     (e.g. Health Affairs, 24, 1364-1366, 2005).

- Prepare AHRQ meeting rooms, including audio/visual support if needed.  Arrange for afternoon beverage breaks, and lunch for attendees.  Federal participants will pay out-of-pocket for their lunches.

- Prepare and supply binder for meeting participants which includes pre-meeting documents, meeting handouts, discussion questions, list of attendees, and agenda. Binder will have appropriate graphic cover. Binder subject to approval by AHRQ lead.

- Provide all meeting materials and supplies, including name tags, tent cards, and on-site logistical support, agenda, attendee list.

- All materials to be proofed by second staff person prior to their being sent to AHRQ for review.

- During two months prior to meeting update AHRQ lead or other designated staff member with weekly status update on all outstanding matters.

- After meeting compile set of power points and digitalized scans of any short documents handed out by presenters during their presentations (e.g. tables)  – distribute the complete presentation set by email to all attendees requesting this service and provide set to AHRQ lead and CMS contact.

- At conclusion of contract facilitator and other lead staff on project to schedule conference call or meeting with AHRQ lead to debrief on what worked particularly well and what was learned that might be applied to similar future projects.

Estimated Budget (for internal use by AHRQ)

| Budget Estimate for Learning Lab Meeting |  |  |  |
| --- | --- | --- | --- |
|  | Hrs/# | $/hr. or # | Cost |
| Personnel |  |  |  |
| Project director | 48 | $32.7 | $ 1,570 |
| Deputy project director | 18 | $21.65 | $ 390 |
| Meeting planner | 450 | $22 | $ 9,900 |
| Writer – meeting summary | 340 | $30 | $10,200 |
| Meeting specialist- materials editor | 120 | $17 | $ 2,040 |
| IT | 4 | $32 | $ 128 |
| Messenger, reproduction | 20 | $17 | $ 340 |
| Subtotal |  |  | $24,586 |
| Fringe (31%) |  |  | $ 7,616 |
| Subtotal |  |  | $32,184 |
| Overhead (35%) |  |  | $11,264 |
| Total labor |  |  | $43,448 |
| Consultant |  |  |  |
| Facilitator | 15 | $ 287 | $ 4,305 |
| Other direct costs |  |  |  |
| Supplies | 50 | $15 | $ 750 |
| LOCAL TRAVEL – parking and mileage | 10 | $20 | $ 200 |
| POSTAGE, DELIVERY, COMMUNICATION, REPRODUCTION |  |  |  |
| Binders | 50 | $15 | $ 750 |
| Phones and fax |  |  | $ 125 |
| Misc. |  |  | $ 100 |
| TRAVEL AND LODGING |  |  |  |
| Air fare for non-federal participants | 35 | $700 | $24,500 |
| Ground transit for non-federal participants | 35 | $ 50 | $ 1,750 |
| Per diem for non-federal participants | 35 | $51 | $ 1,785 |
| MEETING SERVICES |  |  |  |
| AV (per day) | 1 | $1800 | $ 1,800 |
| Meeting package (breaks, breakfast, room rental, phones) | 50 | $75 | $ 3,750 |
| Subtotal |  |  | $83,263 |
| Fees and handling (about 18%) |  |  | $14,987 |
| TOTAL |  |  | $98,250 |