Summary of the 4th Face-to-face MAQC Project Meeting

February 3-4, 2006, Boston, MA

The MAQC Project: Calibrated RNA Samples, Reference Datasets, and

QC Metrics/Thresholds for Microarray Quality Control

Meeting Date/Place: 	February 3-4, 2006, Boston, MA

Summary Date: 	February 20, 2006

Author: 		Leming Shi, +1-870-543-7387, Leming.Shi@fda.hhs.gov

MAQC Website:	http://edkb.fda.gov/MAQC/

Special thanks to Rick Jensen and his staff at UMass Boston for organizing and sponsoring this great event!

- Overview: The 4th face-to-face MAQC project meeting, “by-invitation-only”, was successfully held at a well-equipped computer laboratory in UMass Boston.  Fifty-one participants attended the meeting, and each participant had access to the internet via a hardwired workstation or a laptop.  Participants were able to share/present their analysis results and presentations in a live mode; such an arrangement was found to be very effective.  Rick Jensen highlighted the specific tasks for the meeting.  Thanks to session chairs for keeping the meeting on schedule: Rick Jensen, Uwe Scherf, Federico Goodsaid, Weida Tong, and Leming Shi.  The most important thing is that our momentum has been maintained (and even accelerated); each manuscript team has been working very hard according to the firm timelines.

- Apparent Lack of Reproducibility of Reported Microarray Results: Leming Shi gave a presentation on “The enigmatic problem in microarray technology: The origin of chaos in data analysis”.  Based on Leming’s analyses, the apparent lack of reproducibility of microarray results (i.e., gene lists) reported in the literature was mainly a result of inappropriate data analysis practices that put statistical significance (P) above scientific common sense (FC).  Leming’s presentation invited lively debates during and after the Boston meeting.  Federico gave a presentation on “Standard requirements in the validation of genomic biomarkers”.

- Specific Issues: During the rest of the 1st day and part of the 2nd day, presentations and discussions were centered around specific issues that must be addressed before data analysis could be finalized.  Such issues included QC metrics/thresholds (Federico Goodsaid, Wendell Jones, et al.), definition of original (non-normalized) data set (Shawn Baker), handling absent calls (Andrew Sun) and offset values (Rich Shippy, Shawn, et al.), identification of differentially expressed genes including normalization and gene ranking methods (Leming Shi, James Chen, Russ Wolfinger, Sue-Jane Wang, et al.), cross-platform probe-sequence mapping and data comparison (Damir Herman and Jean Thierry-Mieg), applications of MAQC outcomes for performance validation (Mike Wilson and Janet Hager).  Consensus and/or convergence was reached for some of these issues.  Each platform provider was given a last chance to provide instructions to analysis sites on handling its data including flags, control probes, offset values, etc..  These instructions will be distributed at the MAQC data download site as soon as possible.

- Manuscript Proposals: The 2nd day of the meeting was focused on the discussion of preparing a set of manuscripts for submission to Nature Biotechnology.  Each team of the proposals was given an opportunity to present the rationale and focus of each manuscript topic, followed by extensive discussions.  Proposals MS-4 (Applications of MAQC outcomes) and MS-10 (Cross-hybridization) were dropped, and the topic of cross-hybridization will be merged into MS-5.  Those manuscripts that do not meet the timelines will be automatically eliminated before submission to NBT.

| No. | Topic | Team Leader |
| --- | --- | --- |
| MS-0 | Editorial | Nature Biotechnology |
| MS-1 | Pharmacogenomics and the U.S. FDA’s Critical Path Initiative | Janet Woodcock and Dan Casciano |
| MS-1A | Data quality in genomics | Ron Davis and Hanlee Ji |
| MS-2 | U.S. FDA’s VGDS and IPRG | Felix Frueh |
| MS-2A | U.S. EPA efforts to develop a framework for the use of genomics data in regulatory and risk assessment applications | David Dix |
| MS-3 | MAQC main manuscript | Leming Shi |
| MS-5 | Sequence mapping | Jean Thierry-Mieg |
| MS-6 | The stability of gene lists from a microarray study | Leming Shi |
| MS-7 | Quantitative technologies for validating microarray results | Federico Goodsaid |
| MS-8 | Titration mixtures for assessing relative accuracy of microarrays | Rich Shippy |
| MS-9 | Modeling technical variation | Walter Liggett |
| MS-11 | One-color versus two-color | Tucker Patterson |
| MS-12 | Spike-ins for array quality assessment | Weida Tong |
| MS-13 | Identification of reproducible gene lists from real-world rat toxicogenomics data sets: a cross-platform study | Lei Guo |
| MS-14 | Reproducibility analysis for microarray experiments | Sheng Zhong |

- Publication Plan with Nature Biotechnology: Dr. Gaspar Taroncher-Oldenburg, representing NBT, attended the Boston meeting and addressed the MAQC team regarding publishing results in a supplemental issue.  There should be a major “Article” that introduces the entire MAQC study and the data sets, followed by several “Analysis” manuscripts, each of which focuses on a specific research topic and gives a clear message (statements and recommendations) to readers.  Each manuscript will be subject to NBT’s routine peer-review process, and NBT makes final decisions regarding the format and contents of the final publications.  It is essential that each manuscript team strictly follow the tight timelines to ensure timely publication of MAQC results.

- Timeline for MAQC Manuscripts:

Feb-28-06:	 Initial draft manuscripts (for circulation within each manuscript team);

Mar-15-06:	 1st draft of manuscripts (for circulation among manuscript teams);

Mar-22-06:	 Discuss 1st version of manuscripts in San Diego (after the MAQC panel discussion at the CHI QPCR meeting) (tentative);

Apr-10-06:	 2nd version for internal review (many organizations);

May-10-06:	 3rd version for internal review (many organizations);

May-31-06:	 Submission of manuscripts;

Jun/Aug-06: Peer review and revision;

Sep-06:	 Publication

- No “Early Access” to MAQC Data Sets: Considering the fact that about 40 organizations have already been given full access to the MAQC data sets and in order to avoid any potential compromises for the MAQC group to have the results published in a timely fashion, the MAQC group decided not to grant additional organizations access to the data sets until the data are formally deposited in public repositories.  Leming Shi acknowledged the interests of the scientific community in the MAQC data sets and felt sorry for being unable to convince the MAQC group to grant permission to those who requested “early access” to the data.

- Presentation at IBC’s Chips to Hits Conference: The MAQC group tentatively agreed to present MAQC results at IBC’s Chips to Hits conference, to be held on Sept. 25-28, 2006, Boston, MA, in the format of a presentation and a panel discussion.  Details will be arranged with IBC.

MAQC-4 Meeting Participants, February 3-4, 2006, Boston, MA

| No. | Name | Organization | No. | Name | Organization |
| --- | --- | --- | --- | --- | --- |
| 1 | Baker, Shawn C. | Illumina | 27 | Mei, Nan | FDA/NCTR |
| 2 | Barbacioru, Catalin | Applied Biosystems | 28 | Papallo, Adam | UMass Boston |
| 3 | Bertholet, Vincent | Eppendorf | 29 | Patterson, Tucker A. | FDA/NCTR |
| 4 | Boysen, Cecilie | ViaLogy | 30 | Peterson, Ron | Novartis |
| 5 | Canales, Roger | Applied Biosystems | 31 | Rowley, Patricia | UMass Boston |
| 6 | Chen, James J. | FDA/NCTR | 32 | Ruppel, Patty | Ianalytics |
| 7 | Chudin, Eugene | Illumina | 33 | Scherf, Uwe | FDA/CDRH |
| 8 | Collins, Jim | Agilent | 34 | Setterquist, Robert A. | Ambion |
| 9 | Croner, Lisa J. | Biogen Idec | 35 | Shchegrova, Svetlana | Agilent |
| 10 | de Longueville, Francoise | Eppendorf | 36 | Shi, Leming | FDA/NCTR |
| 11 | Dix, David J. | EPA | 37 | Shippy, Richard | GE Healthcare |
| 12 | Eklund, Aron | UMass Boston | 38 | Sun, Yongming | Applied Biosystems |
| 13 | Goodsaid, Federico | FDA/CDER | 39 | Szallasi, Zoltan | Harvard/CHIP |
| 14 | Guo, Lei | FDA/NCTR | 40 | Taroncher-Oldenburg, Gaspar | Nature Biotechnology |
| 15 | Guo, Xu | Affymetrix | 41 | Thierry-Mieg, Danielle | NIH/NCBI |
| 16 | Hager, Janet | Yale University | 42 | Thierry-Mieg, Jean | NIH/NCBI |
| 17 | Haje, Paul K. | TeleChem ArrayIt | 43 | Tong, Weida | FDA/NCTR |
| 18 | Herman, Damir | NIH/NCBI | 44 | Walker, Stephen J. | Wake Forest University |
| 19 | Hueter, Irene | CUNY | 45 | Wang, Sue Jane | FDA/CDER |
| 20 | Jensen, Roderick | UMass Boston | 46 | Willey, James C. | Gene Express (Ohio Medical University) |
| 21 | Jones, Wendell | Expression Analysis | 47 | Wilson, Mike | Ambion |
| 22 | Kawasaki, Ernest | NIH/NCI | 48 | Wolber, Paul K. | Agilent |
| 23 | Lee, Kathy Y. | Applied Biosystems | 49 | Wolfinger, Russ | SAS |
| 24 | Liggett, Walter | NIST | 50 | Xiao, Chunlin | Applied Biosystems |
| 25 | Luo, Yuling | Genospectra | 51 | Zhong, Sheng | UIUC |
| 26 | Ma, Yunqing | Genospectra |  |  |  |