MEMORANDUM	P.O. Box 2393

Princeton, NJ 08543-2393

Telephone (609) 799-3535

Fax (609) 799-0005

www.mathematica-mpr.com

TO:	Marsha Silverberg

FROM:	Phil Gleason and Rita Stapulonis	DATE: 11/16/2005

Charter – 156 (revised)

SUBJECT:	Response to OMB on First Year Baseline Data Collection

This memorandum is in response to OMB’s inquiry regarding the first year of baseline data collection for the National Charter School Evaluation. As part of the first round of data collection, a short background information form (BIF) was requested of parents who signed a consent form agreeing that their child could participate in the study.  The consent and baseline forms were administered either at the time parents applied to the charter schools on behalf of their child or after parents applied to the school but before a school lottery was conducted.  In some cases, schools decided to move up the timing of lotteries and baseline data collection had to be after the random assignment.  The schedule of the lotteries and the application process were all determined by the charter schools; evaluation data collection had to be fit into the existing school procedures.

Initial data collection of the BIF was done as a self-administered hard copy questionnaire with either the school distributing the questionnaire along with the consent form to parents applying to the charter school, or by MPR mailing a BIF to parents once a signed affirmative consent was received.  Data collection later moved to telephone interviewing, where interviewers were able to mail a new form to parents or complete the interview over the phone.  For schools where BIF data collection began late in the application process, telephone interviews were the sole form of data collection.

Aside from schools that hosted orientation sessions for interested families and invited staff from MPR to attend and assist with consent and BIF administration, engaging the schools in the baseline data collection process was not an efficient or successful approach. The staff at charter schools typically play multiple roles and are extremely busy;  assisting with the data collection for a national study is not their top priority.  To reduce burden on school staff, much of the activity that was first expected of charter school staff moved to the centralized approach as outlined above, which utilized MPR’s survey operation center (SOC).

Another approach we tested was utilizing field or in-person interviewers to track cases that could not be contacted centrally from MPR’s SOC.  We tested this approach with sample from two schools that were located in different sections of a large city.  We trained two different field interviewers and assigned 52 cases that could not be successfully contacted by telephone through the SOC.  Of the 52 cases assigned, 26 were successfully located and the BIF and consent forms administered by in-person field interviewers.  While in-person efforts are more expensive than phone-only contacts, we felt that the cost was reasonable given the 50 percent rate of return on the attempted cases, and especially since these were cases we had tried unsuccessfully to complete by telephone.

Overall, BIF’s were completed with 95 percent of the parents who signed an affirmative consent form.  Sixty-five percent (65%) of the completed questionnaires were self-administered and the remainder were completed over the phone.  Our plans for the second year of baseline data collection build upon the lessons learned during the first year.  While we will engage the charter schools in collecting consent forms as part of their normal application process, MPR will administer the BIFs as telephone interviews from our SOC.  Additionally, we will utilize the in-person approach with sample from select schools that have lower response rates and seem as though they may benefit from in-person tracking after initial efforts by telephone.