ATTACHMENT J-8

FEE PLAN

1.0	INTRODUCTION

This contract is a cost-plus-incentive-fee/award-fee contract which supports the primary goals of the NASA Space Flight Program: fly safely, accomplish mission success (including meeting the manifest), and reduce cost.  This fee plan includes a combination of award fee, performance incentive and cost incentive designed to emphasize excellence in managerial, technical, schedule and subcontract management (including Small, Small Disadvantaged, and Woman Owned Business performance) and cost performance while providing the Contractor appropriate motivation to achieve Program goals.

2.0	AWARD FEE PROVISIONS

The award fee serves as a tool to measure the Contractor’s performance on the health of the program and motivate continued improvement. The Contractor can earn award fee from a minimum of zero dollars to a maximum stated in Clause B.2 of this contract.  Changes to these award fee provisions will be via bilateral modification, except for internal NASA processes and evaluation factors which are established unilaterally by NASA.

Under Award Fee Provisions, NASA may evaluate the Contractor on any area of performance within the spectrum of the contract.  A significant element of any award fee evaluation shall be the Contractor’s demonstrated performance in meeting or exceeding the SOW performance standards.   Thus, while the award fee process is subjective, these standards may be used in award fee evaluation.

2.1	ORGANIZATIONAL RESPONSIBILITIES

2.1.1	PERFORMANCE EVALUATION BOARD (PEB)

The Performance Evaluation Board (PEB) is comprised of NASA officials who are responsible for establishing specific evaluation criteria and will assess the Contractor’s performance related to the evaluation factors listed in Section 2.3.   At the end of each six-month evaluation period (as identified in the tables in Attachment 1), the PEB will prepare a written report documenting its evaluation which shall include recommendations for an adjective rating and numerical score to be assigned to the Contractor’s performance during the evaluation period. This report as well as a PEB presentation will be provided to the Fee Determination Official (FDO).

2.1.2	Performance Monitors

NASA performance monitors shall evaluate and assess the Contractor’s performance in assigned areas and discuss the evaluation results with Contractor counterparts as appropriate.  Additionally, the performance monitors shall use, at their discretion, evaluations and assessments from NASA officials in preparing their report on assigned areas.  The performance monitors will periodically prepare reports for the PEB.

2.1.3	PEB Chairman

The Manager, Space Shuttle Program will serve as the PEB Chair.  The PEB Chair may reassign performance monitors at any time without advance notice to the contractor.

2.1.4	Fee Determination Official (FDO)

The Deputy Associate Administrator for the International Space Station and Space Shuttle Programs will serve as the FDO.  The FDO, after considering available pertinent information and recommendations, shall make a determination in accordance with the provisions of this plan.

2.2	PERIODIC (SIX MONTH) EVALUATION PROCEDURES

All periodic performance evaluations will be final.  A determination of the performance score and the related dollars earned for each evaluation period will be made by the FDO within 45 days after the end of the period.  Procedures to be followed in monitoring, assessing, and evaluating Contractor performance during each period, are described below.

2.2.1	No later than 45 calendar days prior to the start of each evaluation period, the Contractor may submit to the Contracting Officer recommended areas of emphasis for the ensuing evaluation period that are within the general factors listed in Section 2.3 of this plan.  Consideration will be given to the Contractor’s recommendations; however, it is the Government’s responsibility to establish the specific areas of emphasis for each evaluation period.

2.2.2	No later than 30 days prior to the start of each new six-month evaluation period, the Contractor will be notified by the Contracting Officer of the selected areas of emphasis for that period as well as any weightings NASA wishes to specify.  Emphasis will be directed at particular areas under the contract which appear to the Government to be deserving of special attention and will be used in judging the Contractor’s performance.  These areas of emphasis may not cover the entire spectrum of performance that will be evaluated in determining award fee scores and dollars earned.  Other pertinent factors included under the contract and general factors bearing upon overall performance will be considered.

2.2.3	The COTR shall meet with the Contractor at the mid-point of each evaluation period and at other such times as is deemed appropriate to apprise the Contractor of its performance assessment. These meetings shall address specific areas where Contractor performance requires improvement.  The Contractor will be provided a written assessment.

2.2.4	After the end of each evaluation period, the PEB shall meet to consider all the performance information it has obtained.  At the meeting, the PEB will summarize its preliminary findings and recommendation in the Performance Evaluation Board Report (PEBR).  The contractor shall have the opportunity to make a presentation to the PEB if they so desire. (See 2.2.7)

2.2.5	The Contractor may furnish a self-evaluation report within 10 calendar days after the expiration of each evaluation period.  This self-evaluation report shall not exceed 20 pages in length.  The PEB will not submit its recommendation to the FDO until (1) the Contractor’s self-evaluation report has been received and considered, or (2) the Contractor has provided written notification that a self-evaluation report will not be submitted, or (3) the 10-day period provided for submission of the report has expired.

2.2.6  The PEB Chair is responsible for the preparation of the PEBR and will present the findings and recommendation to the FDO.  The report will include an adjective rating and a recommended overall performance score, upgrades score, and safety score with supporting documentation.  The Contractor will be notified by the Contracting Officer of the PEB evaluation and recommended rating and score, and will be provided a summary of the PEBR.  The Contractor may provide additional information for consideration by the FDO by notifying the Contracting Officer of its desire to do so.  This is an opportunity for the Contractor to provide any information which the Contractor believes is relevant to its performance and which may affect the FDO’s determination.  Any additional information should be provided to the Contracting Officer within 5 calendar days of Contractor receipt of the PEB recommended rating and scores.  This additional Contractor information will be provided to the FDO by the Contracting Officer through the PEB Chair.

2.2.7	In addition to the information cited in Section 2.2.4, the Contractor may choose to make a presentation to the PEB.  If the Contractor chooses to make a presentation, it must notify the Contracting Officer no later than 3 calendar days before the scheduled date of the PEB meeting.  The presentation, if provided, will be limited to 1 hour in length.

2.2.8	The FDO will consider the recommendation of the PEB, the PEBR, information provided by the Contractor, if any, and any other pertinent information in determining the performance scores.  The FDO’s determination of the scores will be stated in a written Award Fee Determination (AFD).

2.2.9	The AFD will be provided to the Contractor by the Contracting Officer.  The Contractor may, after notification of the determination, request, through the Contracting Officer, a briefing by the PEB Chairman.  This briefing shall be conducted no later than 14 days following the written request by the contractor.

2.2.10  The contractor shall provide the Government a Corrective Action Plan or an explanation of why corrective action is not required for each weakness identified in the PEB report.  The Corrective Action Plan should include a description of the non- conformance, determination of the root cause of the non-conformance, action required to correct the weakness and prevent recurrences, and the schedule for completion of the action.  One copy of the report shall be delivered to the Contracting Officer and two copies of the report shall be delivered to the COTR within 30 calendar days after receipt of the PEB report.

2.3	EVALUATION FACTORS

NASA may evaluate the Contractor on any area of performance within the spectrum of the contract (see Section 2.3.8 for specific cost evaluation parameters).  A significant element of any award fee evaluation shall be the Contractor’s demonstrated performance in meeting or exceeding the SOW performance standards.  The following are examples of critical factors which will be included in any evaluation:

2. 3.1	Management Effectiveness

The Contractor will be evaluated based upon management performance in providing a balanced, coordinated and motivated approach to managerial excellence.  This includes an assessment of the Contractor’s performance in the development, analysis and utilization of management data, total available resources, and program controls to effectively accomplish contract requirements.  This will involve the assessment of Contractor performance in planning, controlling, and managing Government facilities and property, as well as contract and subcontract management.  Also included is the Contractor’s track record on the assessment and mitigation of risk. A critical element of this evaluation shall be the effectiveness of the Contractor’s continuous improvement program.

2.3.2	Operational Safety

Operational safety is of supreme importance to NASA.  This includes flight safety issues involving the flight crew, potential risks to flight assets, and ground processing safety affecting personnel or facilities.  Consideration will be given to the maintenance of process and product quality at all levels, and assumes the implementation of performance measures as an indication of quality.  Note:  A specific score will be provided for this factor.

2.3.3	Quality

The Contractor will be evaluated on the maintenance of the program processes with required product quality at all levels, and implementation of performance measures related to quality.

2.3.4	Schedule and Manifest Effectiveness

The Contractor will be evaluated against program schedules and key interim milestones, including non-recurring elements such as performance enhancements.  This evaluation will consider all aspects of planning, processing and operation in support of the NASA manifest, including not only the effectiveness and quality of meeting the manifest, but also the development and demonstration of flexibility and robustness in this capability.  The Contractor will also be evaluated on it's support of long range manifest needs across the life of the Space Shuttle Program through a program of maintenance, repair refurbishment, and logistics planning that assures Program capability.

2.3.5	RESERVED

2.3.6	Supportability

The Contractor will be evaluated on its approach and plans for the long term health and viability of the Program.  This evaluation will assess the Contractor’s performance against the overarching program goals and the ability of the Contractor to balance program health and assure product and process integrity.

2.3.7	Small/Small Disadvantaged/Woman Owned Business (SB/SDB/WOB) Performance

The Contractor will be evaluated on its efforts in achieving contract SB/SDB/WOB goals.  Award fee weighting for SDB performance will be 15 percent.

2.3.8	Cost

Cost evaluation under the award fee procedures will be limited to the evaluation of Level-of-Effort, Program Provisioning, and Upgrades cost performance.  This evaluation will be related to the actual cost performance of individual tasks versus the estimated cost for the tasks, including any task requirement changes.

2.4	EVALUATION PERIODS AND AWARD FEE CALCULATION

2.4.1	Maximum Available Award Fee

The maximum available award fee is identified in Clause B.2.

2.4.2	Evaluation Periods and Award Fee Available

The available award fee dollars for each evaluation period are delineated in Attachment 1, Table A, Operations.  The parties agree that available award fee in award fee period 16 shall be reduced by $6.895 and performance fee shall be increased by $6.895M, should a flight scheduled for launch after 9/30/04 per the NSTS 08178 SSP Schedules updated on 12/9/02 actually be launched prior to 10/01/04.

2.4.3  Dollars Earned

Upon the FDO’s determination of Contractor’s performance for each period, the graded score, as a percentage, will be applied to the dollars available in the period (per the tables in Attachment 1) to determine the dollars earned.

2.4.4	Dollars Not Earned

All award fee dollars available for each evaluation period not earned will not roll forward to subsequent award fee periods.  A unilateral contract modification will be

issued to remove these unearned dollars from maximum award fee available on the contract.  Dollars not earned will also be captured on Attachment 1.

2.5	EVALUATION SCALE AND ADJECTIVE RATING

Award Fee Rating Table, Attachment II, includes adjective ratings as well as a numerical scoring system from 0 - 100.  For this plan, earned award fee dollars are calculated by applying the total numerical score to available dollars.  For example, a numerical score of 85 yields 85 percent of available award fee dollars.  Notwithstanding the preceding, the Contractor will not earn award fee for any evaluation period when the performance score is “poor/unsatisfactory” (less than 61).

2.6	PROVISIONAL PAYMENT OF AWARD FEE

- Pending a determination of the amount of award fee earned for periodic evaluations, a portion of the available award fee for that period will be provisionally paid to the Contractor on a monthly basis.  For the first two evaluation periods for the separate upgrades fee pool, the percentage of the available amount that will be provisionally paid will be equal to the percentage amount to be paid for the operations fee pool during those same periods. For all subsequent evaluation periods, the provisional payment for operations and upgrades will be calculated separately and will be based on an average of the two preceding periods for each of those pools individually.  The provisional payment shall never exceed 80%.  The amount of provisional fee which may be paid monthly in any evaluation period shall be prorated equally to the number of months in that period.

- Should, at any time, the Contracting Officer determine that the Contractor will not achieve a level of performance commensurate with the provisional rate, such rate may be reduced or discontinued.

- The Contracting Officer shall notify the Contractor, in writing, if it’s determined that a reduction or discontinuance is to be made.  This determination is not subject to “Disputes” clause

- All provisional award fee payments will be superseded by the periodic evaluation.  If the FDO’s determination for a period results in earned award fee above that provisionally provided, the Contracting Officer will issue a unilateral modification to recognize such and payment will be made based upon the unilateral modification.  If the amount of award fee earned, as determined by the FDO, is less than the sum of the provisional payments for that period, the Contractor will either credit the next payment voucher for the amount over-paid or refund the difference to the Government, as directed by the Contracting Officer.

- Provisional payment of periodic award fee will be made prior to the first award fee determination by the Government.

2.7	FEE REDUCTION FOR CATASTROPHIC LOSS

Any available award fee for the current six month evaluation period is subject to the section contained hereafter entitled “Fee Reduction for Catastrophic Loss”

3.0	COST INCENTIVE FEE

A cost incentive will motivate the Contractor to control cost.  This incentive fee is based on the Contractor’s performance relative to target cost at the end of the basic contract period.  The Cost Incentive Fee payable under this contract shall be in accordance with the provisions of FAR 52.216-10.  If and when the contractor incurs any costs in any of the categories set forth in paragraph (e)(4) of referenced clause, the contractor shall notify the contracting officer of the amount of such cost together with such supporting detail as the contracting officer may reasonably require.  Upon agreement or determination of the amount of such cost, clause B.2 will be modified by the entry of a new line item titled, “Excluded Costs,” along with the amount of the cost determined or agreed to.  This amount may be increased from time to time in the same manner.  The total resulting amount will be included in the contract total estimated cost, but will not be included in the target cost, nor will it be considered in the determination of the Contractor’s incentive fee earning.  Determinations made related to cost incentive fee are subject to the ”disputes” clause of the contract.

Costs associated with Level-Of-Effort, Program Provisioning, and facilities will not be subject to the cost incentive feature of the contract.  Rather, cost performance for Level-Of-Effort and Program Provisioning will be evaluated under Paragraph 2.0, Award Fee Provisions of this Attachment.  The Contractor is required to account for these costs so as to ensure that no co-mingling of costs subject to incentive provisions versus award fee provisions exists.

- COST INCENTIVE FEE PARAMETERS

3.1.1	Target Cost

The target cost for cost incentive fee purposes is found in Clause B.2.

3.1.2	Maximum Cost Incentive Fee

The maximum fee available on this contract is reflected in Clause B.2.  There is no maximum cost incentive fee identified in Clause B.2 since the maximum cost incentive fee is flexible.  The contract includes a maximum available award fee as well as performance incentive fees.  If such fees are not achieved, there is additional flexibility under the cost incentive provisions for the Contractor to achieve maximum available fee.

Maximum Fee will be increased by an amount equal to 15% of the negotiated Target Cost of fee-bearing changes to this contract.  Maximum Fee for changes to the Program Provisioning or Level-of-Effort portions of the contract will be increased by the amount of fee negotiated for the change.

3.1.3	Cost Incentive fee at Target

The cost incentive fee at target is found in Clause B.2.

3.1.4	Incentive Sharing Arrangement

The Contractor may share in cost overruns/underruns to target cost as follows:

3.1.4.1	Underrun to Target Cost

The Cost Incentive Fee payable under this contract shall be the target fee increased by 35 cents for every dollar that total allowable cost subject to the incentive is less than target cost.

3.1.4.2	Overrun to Target Cost

The Cost Incentive Fee payable under this contract shall be the target fee decreased by 15 cents for every dollar that the total allowable cost subject to the incentive is greater than the target cost for the first $150 million dollars of overrun and then 30 cents for every dollar after that point. This arrangement would exist until all earned target fee and award fee is exhausted.  Overrun fee reductions will not impact earned Objective Performance fees or earned Program Plus fees.

3.1.5		Award Fee Gate

After completion of the basic contract period, not including the options identified in Clause B.6, the parties will negotiate a target cost, and an actual allowable cost pursuant to the incentive fee provisions hereof. In the event the parties are unable to agree on the amounts to be so allocated, the Contracting Officer will determine the amounts.  Such determination will be subject to the "Disputes" clause.

In the event the Contractor has experienced an underrun and has not received a minimum award fee score of 81 for Safety, and a minimum overall award fee score of 71, in a given period, the amount of incentive fee that the contractor would otherwise have earned for that period for such underrun will be forfeited.  The incentive fee dollars applicable to that award fee period will be allocated based on the Percent of Cost Complete (POCC) method.  At contract completion, the amount of the underrun allocated to the specific award fee period will be calculated based on the following formula:

Step 1:	Actual cost for the award fee period in which gate was missed	=	% of cost

Actual total cost, at completion, subject to incentive fee

Step 2:	% of cost X Total Underrun Incentive Fee $* =  Adjustment $ for period

*Underrun $ X 35%

The adjustment $ for the period would then be deducted from the total underrun incentive fee.  If the declaration of an underrun is made prior to contract completion and ESTIMATED forfeiture of the incentive fee is calculated because an award fee gate has been missed, a final forfeiture amount will be determined using ACTUAL costs at contract completion.

3.1.6	Failure to qualify to receive a share of the underrun in a particular period does not prevent the Contractor from achieving a share of the projected underrun in other periods wherein the award fee gate is met.

3.2	PAYMENT OF COST INCENTIVE BASED ON OVERRUN/UNDERRUN

PERFORMANCE

3.2.1	The decision to either allow provisional fee associated with a projected underrun to target cost or to modify fee payments based on an overrun situation is at the discretion of the Contracting Officer.  The development of the incentive fee payment schedule is by mutual agreement of the parties.  The basic tool to be used to determine the payment of provisional incentive fee based on underrun to target cost, or to reduce fees based on overruns to target cost, is the Contractor’s Estimate at Completion (EAC) from the Contractor’s 533 Report, adjusted as necessary by the Contracting Officer.

3.2.2	In the event the Contractor does not meet an award fee gate for an evaluation period, the Contracting Officer shall make an assessment of the amount of provisional fee associated with a projected underrun the Government is willing to pay.  However, in the event of an overrun to target cost, there will be no adjustment for any award fee gate missed when determining the contractor's overrun share per para. 3.1.4.2.

3.2.3	If for any reason, the assessment by the Contacting Officer related to missed award fee gates identifies that the Contractor has been overpaid, the Contractor will repay the Government within 30 days.

- TARGET FEE

- Payment of target fee will begin with the commencement of the contract.

- Provisional payments of target fee will be made to the Contractor on a monthly basis.  The total target fee is delineated in Clause B.2.  If for any reason, the assessment by the Contacting Officer related to missed award fee gates identifies that the Contractor has been overpaid, the Contractor will repay the Government within 30 days.

- In order to qualify to earn target fee in an evaluation period, the Contractor must achieve an overall award fee score of 61.  If such award fee gate is not met, the Contracting Officer will reduce the total target fee by the amounts reflected on Attachment III for each award fee period in which the gate is not achieved.

- Notwithstanding, target fee payment may be reduced during any period in which the Contacting Officer determined that the Contractor will overrun the Target Cost.  The Contracting Officer will notify the Contractor, in writing, if it is determined that such provisional payments will be reduced or discontinued subject to final determination at completion.

3.4	REDUCTION FOR CATASTROPHIC LOSS

All cost incentive fees (target fee and underrun fee) available for a current six month evaluation period are subject to the section contained hereafter entitled “Fee Reduction for Catastrophic Loss.”

4.0	PERFORMANCE INCENTIVE FEE

The Performance Incentive serves an as effective tool to motivate and ensure safe and successful missions utilizing objective, mission specific criteria.  The performance incentive shall be determined in accordance with the following process.

- EVALUATION PROCEDURES

4.1.1	The Contractor will be evaluated for each Space Shuttle Mission in accordance with the Performance Incentive criteria identified in this plan. In a letter to the Contractor three months prior to flight, the Contracting Officer’s Technical Representative (COTR) shall identify, the major mission objectives associated with each mission.

4.1.2	 Within 10 days after the completion of a mission, the Contractor shall submit a written report to the Contracting Officer with its recommendation as to the “successful completion” of each performance incentive criteria.

4.1.3	The Contracting Officer shall, in conjunction with the COTR and Space Shuttle Program Manager, confirm the “successful accomplishment” of each criteria and issue a written determination.   Further, the Contracting Officer will issue a unilateral modification to the Contractor recognizing the earning of the specific performance incentives within 30 days of flight completion.

4.1.4	Payment of the authorized performance incentive fee shall be executed by the NASA Financial Management Office upon receipt of the unilateral contract modification.

4.1.5	 The Contracting Officer’s determination for performance incentive fee is subject to the “Disputes” clause of the contract.

4.2	PERFORMANCE INCENTIVE CRITERIA

4.2.1	The Contractor’s performance in meeting major program objectives will be measured utilizing the objective, predefined criteria established below.  The fee associated with successful completion of these criteria is stated below.  These criteria, as well as the associated fee, will change only through bilateral agreement.  The following criteria are established per flight.  The contract allows for a slight fluctuation in flight rate without contract modification (clause H.33, Launch Schedule Variations).  Therefore, if the Contractor flies eight flights per year, these fees are available for each flight; conversely, if the Contractor flies six flights per year, the fees herein are available for six flights only, for the basic period of performance under the contract.  For Option 1 under the contract, if the Contractor flies five flights per year in Option Year 1, these fees are available for each flight; conversely, if the Contractor flies three flights per year in Option Year 1, the fees herein are available for three flights only.

Performance Criteria for Each Mission	through	after

06/30/98	07/04/98

Delivery of a Flight Ready Integrated Space

Shuttle Vehicle (SSV) and Supporting Systems	$2.5M	$2.870M

Certification of Mission Specific Flight and

Ground Teams	$0.5M	$0.500M

Integrated Mission Performance

- Launch Countdown Start Through Orbit Insertion	$1.0M	$1.290M

- Major Mission Objectives Enabled	$1.0M	$1.120M

- Deorbit Preparation Through Landing/

Recovery - Safe Return	$1.0M	$1.075M

- Launch Delay (Reduction in Fee) Mission

Management Team (MMT) L-2 to SSME Start

- First occurrence per flight	($1.0M)	($1.0M)

- Subsequent occurrence per flight		($0.5M)	($0.5M)

Pad Abort (Reduction in Fee)	($3.0M)	($3.0M)

Intact Abort (Reduction in Fee)	($5.0M)	($5.0M)

Early Mission Termination (Reduction in Fee)   	($1.0M)	($1.0M)

Solid Rocket Booster Recovery	n/a	$0.040M

4.2.2	Objective Criteria and Evidence of “Successful Accomplishment”

4.2.2.1	Delivery of a Flight Ready Integrated Space Shuttle Vehicle (SSV)

and Supporting Systems

SSV requirements will be as defined in the Flight Definition and Requirements Directive (FDRD) and other applicable requirements as defined by the COTR based on the Delta Launch Site Flow Review (LSFR) (approximately launch minus 4 months).  The target date will be to the launch date defined at the Delta LSFR, with adjustments made for changes not resulting from the SFOC Contractor’s performance.  “Successful accomplishment” of this criteria is evidenced by the absence of Contractor induced constraints to continue launch countdown operations at the Prelaunch MMT Review.  Delays to the target Prelaunch MMT Review date greater than 7 calendar days caused by the SFOC Contractor will result in loss of this incentive.  If a launch is delayed due to Contractor induced constraints, subsequent missions for which launch dates had previously been defined may also be impacted as a result of processing flow constraints.  To avoid a “cascading” effect in such instances, the launch dates of impacted subsequent flights will be adjusted without prejudicing the contractor’s opportunity to successfully accomplish this criterion if the subsequent flight delays are due entirely to processing flow constraints and not due to Contractor induced constraints.

4.2.2.2	Certification of Mission Specific Flight and Ground Teams

Certification of Mission Specific Flight and Ground Teams:  The Contractor must prepare and certify the flight and ground operations teams for launch, mission, and recovery operations in support of flight and manifest objectives.  “Successful accomplishment” of this criteria is evidenced by the absence of contractor induced constraints to call to station for launch and mission support as scheduled in support of the launch date set at FRR.

4.2.2.3	Integrated Mission Performance

4.2.2.3.1	Launch Countdown Start Through Orbit Insertion

This criterion focuses on the integrated flight and ground operation of the systems and mission teams to accomplish a safe launch and orbital insertion.  “Successful accomplishment” of this criterion is evidenced by the SSV achieving required orbit insertion.

4.2.2.3.2	Major Mission Objectives Enabled

This criterion focuses on the availability of “system” support required to enable the major mission objectives as defined under section 4.1.1.  “Successful accomplishment” is evidenced by the absence of flight or ground anomalies attributed to the Contractor’s performance which preclude accomplishment of major mission objectives.

4.2.2.3.3	Deorbit Preparation through Landing/Recovery - Safe Return

This criterion focuses on the integrated flight and ground operation of the systems and mission teams to accomplish a safe deorbit, landing, and recovery.  “Successful accomplishment” is evidenced by completion of a safe landing and recovery of the crew, the Orbiter, and payload objectives as defined under section 4.1.1.

4.2.2.3.4	Launch Delay (Reduction of Fee)

If the planned launch of the SSV has to be rescheduled past the date set at the Prelaunch MMT Review, but before Space Shuttle Main Engine (SSME) start due to the performance of the Contractor, the Contractor shall be assessed a reduction in fee as shown in section 4.2.1.

4.2.2.5	Pad Abort (Reduction in Fee)

If a Pad Abort occurs due to Contractor performance, then the contractor shall be assessed a reduction in fee as shown in Section 4.2.1.

4.2.2.6	Intact Abort (Reduction in Fee)

If an Intact Abort occurs due to the Contractor’s performance, then the Contractor shall be assessed a reduction in fee as shown in Section 4.2.1.  Intact Abort is defined as a safe return of the Orbiter to a planned landing site under an intact abort mode: Abort-to-Orbit (ATO), Abort-Once-Around (AOA), Transatlantic Abort Landing (TAL), or Return to Launch Site (RTLS).

4.2.2.7	Early Mission Termination (Reduction in Fee)

If an early mission termination occurs due to the Contractor’s performance which prevents accomplishment of a major mission objective, the Contractor shall be assessed a reduction in fee as shown in Section 4.2.1

4.2.2.8  SRB Recovery

The SRB Recovery Phase begins immediately upon successful booster separation from the Shuttle Orbiter/External Tank and continues through descent and booster splashdowns to the point of stabilized spar buoy positions.  Successful accomplishment of this criterion is when the SRB Recovery System performs in accordance with the requirements of the Part I CEI Specification.”

- PROVISIONAL PAYMENTS

Provisional payments are not available for performance incentive fee.

4.4	FEE REDUCTION FOR CATASTROPHIC LOSS

Any available performance incentive fee for a mission is subject to the section entitled “Fee Reduction for Catastrophic Loss.”

4.5	FEE AVAILABILITY FOR FIRST AND LAST FLIGHTS

The first flight to take place under this contract is subject to the “Performance Criteria for Each Mission” delineated in Section 4.2.1.

The only “Performance Criteria for Each Mission” related to the last flight are those which fall within the completion date of this contract as specified in Clause F.2.

4.6	CONTRACTOR ACCOUNTABILITY

The Parties hereby agree to an affirmation period, for purposes of defining performance fee accountability which will end on June 30, 1998.

During this period:

- The contractor is accountable for its performance as well as the performance of its subcontractors (at any tier) during the term of the contract.

- The contractor shall not be accountable for the first occurrence or discovery of any performance problem that is found to be caused by efforts performed by The Boeing Company or Lockheed Martin Corporation (The Stakeholders).  This shall include any subcontractor at any tier under those subcontracts authorized under contracts awarded to the Stakeholders prior to the SFOC, which contracts or subcontracts have now been consolidated within the SFOC; and

- The contractor is accountable for any subsequent occurrence or discovery of any performance problem found to be caused by either of the Stakeholders or their subcontractors at any tier.

After the affirmation period has ended, the contractor shall remain accountable for its performance as well as its subcontractor's (at any tier) performance under the contract.  Additionally, the contractor shall be held accountable for the performance of the Stakeholders and their subcontractors at any tier, of effort performed previous to [incorporation into], or as part of, the SFOC.

Beginning March 12, 2002, the contractor will continue to be accountable for all performance during the contract period.  Performance problems, which are a result of original defects in design, manufacturing, or workmanship are not accountable to the contractor unless it is determined that an existing defect in design, manufacturing, or workmanship was not discovered due to a lack of reasonable test, inspection, procedures, or processing by the contractor or its subcontractor (at any tier).  In such cases, the contractor shall be accountable for this failure irrespective of when the hardware was built.

- PROGRAM PLUS FEE

As identified in Clause B.2, Program Plus Fee is available under this contract.

The use of this fee is at the discretion of the Space Shuttle Program Manager (SSPM).  For application, the SSPM will identify requirements or performance  parameters and the amount of fee available.  The Contractor will be allowed to provide input as to whether the incentive is commensurate with the delta requirement; however, it is understood that incentive application is a NASA unilateral option.  The Contracting Officer will issue a unilateral administrative modification documenting the available program plus incentive, time frame for completion, and “successful accomplishment” criteria. (See attachment V)  Upon completion of the incentive or time frame, the Contracting Officer shall, in conjunction with the SSPM and COTR, issue a determination.  If program plus fee is earned, the Contracting Officer will issue a unilateral contract payment modification and will forward the modification to the JSC Financial Management Officer for payment.  If the program plus fee is not earned, a modification will be issued removing the program plus fee from the contract value.  The unearned program plus fee may not be used again. At the completion of the entire contract period of performance, any Program Plus Fee that has not been made available to the Contractor for incentive will be paid based on the average overall award fee score for the entire contract period of performance.  The determination by the Contracting Officer is not subject to the “Disputes” clause of the contract.

6.0	FEE REDUCTION FOR CATASTROPHIC LOSS

6.1	A fee reduction will be assessed in the event of loss of an Orbiter and/or individuals associated with Space Flight Operations when such loss is caused by the acts or omissions of the Contractor in performance of effort under this contract.

6.2	For purposes of this article, “loss” means the loss of life which occurs because of an Orbiter mission or total loss, at any time, of an Orbiter vehicle. “Orbiter Mission” commences with fueling of the external tank through actual flight to safe return of the crew.  “Total loss” means that an Orbiter is permanently inoperable.

6.3	In the event of “loss,” the Contractor will forfeit all fee earned or available during the six month award fee evaluation period in which the loss occurs, as well as any performance fee related to that mission earned or available in earlier or later evaluation periods.

6.4	The Contracting Officer in conjunction with a Board of Investigation shall make a determination as to the cause of the loss.  If the loss is determined to be caused by the acts or omissions of the Contractor, the Contracting Officer shall notify the Contractor in writing of such determination.  Repayment of any fee, if required, shall be made within 30 days of notification of a final determination by the Contracting Officer.

6.5	The Contracting Officer’s determination is subject to the “Disputes” clause of the contract.

- VALUE ENGINEERING

VECPs serve as a tool in reducing the overall projected cost to the agency without impairing its essential functions. As identified in Clause H.40, VALUE ENGINEERING, the Contractor is encouraged to develop, prepare, and submit value engineering change proposals (VECPs) voluntarily. The Contractor shall share in any net acquisition savings reductions for each accepted VECP as identified below.

- FLIGHT OPERATIONS REINVENTION

Flight Operations Reinvention is a joint NASA and USA Space Shuttle Program (SSP) initiative that will implement changes to flight operations processes, tools, and work content.  These changes will enable the reduction of the flight operations flight production from 12 months to approximately 7 months and will transform current legacy processes into modern, production-oriented processes.  The exact length of the reduced template depends on resolution of all external template constraints currently being addressed through the SSP Reinvention Process Integration Team.  Improving the flight operations processes and reducing the flight operations flight production template are essential in achieving increased flexibility, both for manifest decisions and responsiveness to customer requirements.

The milestones and required completion dates are established in Table 7.1-1 for accomplishment of the Reinvention VECP and will be used as the basis for establishing the Contractors share of the net acquisition cost savings. Payment of the Contractor’s share of net acquisition savings will be accomplished in lump sum installments that become billable on the noted installment dates.

Timely milestone completion may be impacted by events beyond the control of the contractor.  In such an instance, if it is determined by the Government that the contractor is unable to demonstrate successful completion of one of these identified milestones through no fault of its own, but that the contractor’s performance would have been expected to have successfully met the milestones based on Government evaluation of products and systems performance analysis, the criteria will be considered to have been successfully met and the associated share amount will be considered to have been earned by the Contractor.   The acceptance criteria for each milestone has been partnered and agreed to between the Contractor and the Government and will be documented through the issuance of a joint Memorandum of Understanding.

In the event a milestone that is totally within the control of the contractor is not completed at the noted major milestone date, the contractor shall forfeit amounts as set forth in Table 7.1-1.  Fee associated with each sub-task will be paid upon accomplishment of each subtask. The Contractor shall receive the associated fee for each subtask upon satisfactory completion of the task irrespective of the date accomplished.  In the event the contractor misses one or more sub-task level milestone dates but is still able to meet the required date for the major milestone, the overall technical performance portion for that milestone, including sub-task milestone increments, shall be considered earned.

The three major milestone dates are considered firm requirement dates.  In the event the major milestone date is missed, the overall technical performance share amount shall be forfeited in its entirety.  An apportioned share (1/3) of the $ 750,000 Overall Performance Fee has been applied to each of the major milestone dates; this initial payment is billable by the Contractor on the date the Supplemental Agreement is signed. A contract modification shall be issued to remove each apportioned share of the unearned overall performance fee amounts from the contract, should a major milestone date be missed, and the contractor shall reimburse the Government for that amount.

Table 7.1-1

| Overall Performance | Date 11/1/00 | Share Amount $ 750,000 |
| --- | --- | --- |
| Milestone #1 CPC SAIL System SW Qualification Testing Complete |  |  |
| Subtask #1 - CPC SAIL System SW Development Testing Complete | 2/28/01 | $106,719 |
| Subtask #2 - CPC SAIL System SW Design Review Complete | 5/31/01 | $106,719 |
| Subtask #3 - CPC SAIL System SW Integrated Testing Complete | 7/31/01 | $106,719 |
| Subtask #4 - CPC SAIL System SW Qual. Test Load Delivered | 8/31/01 | $106,718 |
| Subtotal - Milestone sub-tasks | - | $426,875 |
| Overall Technical Performance | 12/31/01 | $676,875* |
| Total for Milestone #1 | - | $1,103,750 |
| Milestone #2 JITFD ORR |  |  |
| Subtask #1 – I-Load Design DCR | 2/28/01 | $213,437 |
| Subtask #2 – Production DCR | 9/30/01 | $213,437 |
| Subtask #3 - I-Load Design ORR | 2/28/02 | $213,438 |
| Subtask #4 – Production ORR | 7/31/02 | $213,438 |
| Subtotal - Milestone sub-tasks | - | $853,750 |
| Overall Technical Performance | 7/31/02 | $1,103,750* |
| Total for Milestone #2 | - | $1,957,500 |
| Milestone #3 POST ORR |  |  |
| Subtask #1 - POST Process Document Published | 1/31/01 | $106,719 |
| Subtask #2 - POST Tools Rel. 1 Delivered | 4/30/01 | $106,719 |
| Subtask #3 - POST Tools Rel. 2 Delivered | 9/30/01 | $106,719 |
| Subtask #4 - POST Tools Rel. 3 Delivered | 1/31/02 | $106,718 |
| Subtotal - Milestone sub-tasks | - | $426,875 |
| Overall Technical Performance | 7/31/02 | $676,875* |
| Total for Milestone #3 | - | $1,103,750 |

* Includes $250,000 initial performance installment payment.

ATTACHMENT I

Table A - Operations

| EVALUATION PERIOD | START DATE | END DATE | AVAILABLE AWARD FEE DOLLARS | DOLLARS EARNED | DOLLARS NOT EARNED |
| --- | --- | --- | --- | --- | --- |
| 1 | 10/1/96 | 3/31/97 | $23,200,000 | $19,488,000 | $3,712,000 |
| 2 | 4/1/97 | 9/30/97 | $26,661,483 | $22,928,875 | $3,732,608 |
| 3 | 10/1/97 | 3/31/98 | $23,788,065 | $19,268,333 | $4,519,732 |
| 4 | 4/1/98 | 9/30/98 | $26,425,761 | $22,197,639 | $4,228,122 |
| 5 | 10/1/98 | 3/31/99 | $30,303,402 | $25,757,894 | $4,545,508 |
| 6 | 4/1/99 | 9/30/99 | $30,971,263 | $26,325,576 | $4,645,687 |
| 7 | 10/1/99 | 3/31/00 | $33,052,574 | $27,433,636 | $5,618,938 |
| 8 | 4/1/00 | 9/30/00 | $34,327,255 | $27,461,804 | $6,865,451 |
| 9 | 10/1/00 | 3/31/01 | $26,917,106 | $23,415,781 | $3,498,910 |
| 10 | 4/1/01 | 9/30/01 | $30,915,116 | $27,205,302 | $3,709,814 |
| 11 | 10/1/01 | 3/30/02 | $31,366,792 | $27,602,777 | $3,764,015 |
| 12 | 4/1/02 | 9/30/02 | $31,071,372 | $28,274,949 | $2,796,423 |
| 13 | 10/1/02 | 3/31/03 | $41,927,394 |  |  |
| 14 | 4/1/03 | 9/30/03 | $42,098,586 |  |  |
| 15 | 10/1/03 | 3/30/04 | $41,826,802 |  |  |
| 16 | 4/1/04 | 9/30/04 | $48,602,350 |  |  |
| 17 | 10/1/04 | 3/30/05 | $550,365 |  |  |
| 18 | 4/1/05 | 9/30/05 | $438,159 |  |  |
| 19 | 10/1/05 | 3/30/06 | $386,510 |  |  |
| 20 | 4/1/06 | 9/30/06 | $367,207 |  |  |
| 21 | 10/1/06 | 3/30/07 | $348,238 |  |  |
| 22 | 4/1/07 | 9/30/07 | $343,043 |  |  |
| 23 |  |  | 7,967 |  |  |
| 24 |  |  |  |  |  |
| 25 |  |  |  |  |  |
| 26 |  |  |  |  |  |
| 27 |  |  |  |  |  |
| 28 |  |  |  |  |  |
| TOTAL |  |  | $525,896,810 | $207,360,566 | $51,637,208 |

# ATTACHMENT I

#### Table B – Upgrades

| EVALUATION PERIOD | START DATE | END DATE | AVAILABLE AWARD FEE DOLLARS | DOLLARS EARNED | DOLLARS NOT EARNED |
| --- | --- | --- | --- | --- | --- |
| 9 | 10/01/00 | 03/31/01 |  |  |  |
| 10 | 04/01/01 | 09/30/01 | $6,360,951 | $5,406,808 | $954,143 |
| 11 | 10/01/01 | 03/30/02 | $6,548,410 | $4,911,307 | $1,637,103 |
| 12 | 04/01/02 | 09/30/02 | $4,377,914 | $3,765,006 | 572,908 |
| 13 | 10/01/02 | 03/30/03 | $4,341,453 |  |  |
| 14 | 04/01/03 | 09/30/03 | $4,009,633 |  |  |
| 15 | 10/01/03 | 03/30/04 | $3,497,207 |  |  |
| 16 | 04/01/04 | 09/30/04 | $1,917,896 |  |  |
| 17 | 10/01/04 | 03/30/05 | $3,495,425 |  |  |
| 18 | 04/01/05 | 09/30/05 | $810,018 |  |  |
| 19 | 10/01/05 | 03/30/06 | $334,963 |  |  |
| 20 | 04/01/06 | 09/30/06 | $263,472 |  |  |
| 21 | 10/01/08 | 03/30/07 | $191,372 |  |  |
| 22 | 04/01/07 | 09/30/08 | $189,945 |  |  |
| 23 | 10/01/07 | 03/30/08 | $85,961 |  |  |
| 24 | 04/01/08 | 09/30/08 | $85,962 |  |  |
| 25 | 10/01/08 | 03/30/09 |  |  |  |
| 26 | 04/01/09 | 09/30/09 |  |  |  |
| 27 | 10/01/09 | 03/30/10 |  |  |  |
| 28 | 04/01/10 | 09/30/10 |  |  |  |
| TOTAL |  |  | $36,510,582 | $14,083,121 | $3,164,154 |

ATTACHMENT II

| ADJECTIVE RATING | RANGE OF POINTS | DESCRIPTION |
| --- | --- | --- |
| Excellent | 100 - 91 | Of exceptional merit; exemplary performance in a timely, efficient manner; performance meets or exceeds contract requirements (e.g., contract standards) ; very minor (if any) deficiencies with no adverse effect on overall performance |
| Very Good | 90 - 81 | Effective performance; requirements accomplished in a timely, efficient manner for the most part; substantially exceeds minimum contract requirements (e.g., Maximum Error Rates) with only minor deficiencies. |
| Good | 80 - 71 | Effective performance; exceeds minimum contract requirements (e.g., Maximum Error Rates); reportable deficiencies, but with little identifiable effect on overall performance. |
| Satisfactory | 70 - 61 | Performance which meets minimum contract requirements (e.g., Maximum Error Rates); reportable deficiencies with identifiable, but not substantial, effects on overall performance. |
| Poor/ Unsatisfactory | 60 - 0 | Overall performance does not meet minimum contract requirements (e.g., Maximum Error Rates); remedial action required in one or more areas; numerous deficiencies which adversely affect performance. |

ATTACHMENT III

| EVALUATION PERIOD | APPLICABLE TARGET FEE DOLLARS TARGET FEE SUBJECT TO SECTION 3.3.3 |
| --- | --- |
| 1 | $9,198,632 |
| 2 | $9,184,301 |
| 3 | $8,859,021 |
| 4 | $10,027,593 |
| 5 | $11,570,722 |
| 6 | $11,440,895 |
| 7 | $11,475,748 |
| 8 | $11,495,540 |
| 9 | $12,121,305 |
| 10 | $12,034,555 |
| 11 | $11,981,699 |
| 12 | $11,814,773 |
| 13 | $11,476,235 |
| 14 | $11,457,954 |
| 15 | $11,981,047 |
| 16 | $11,980,694 |
| 17 | $ 14,000 |
| 18 | $ 14,000 |
| 19 | $ 14,000 |
| 20 | $ 14,000 |
| 21 | $ 14,000 |
| 22 | $ 14,000 |
| TOTAL | $178,184,714 |

##### ATTACHMENT IV

| SHUTTLE | AVAILABLE | DOLLARS | DOLLARS |
| --- | --- | --- | --- |
| MISSION | PERFORMANCE | EARNED | NOT |
|  |  |  | EARNED |
| STS 80 | $6,000,000 | $5,000,000 | $1,000,000 |
| STS 81 | $6,000,000 | $6,000,000 | $0 |
| STS 82 | $6,000,000 | $6,000,000 | $0 |
| STS 83 | $6,000,000 | $6,000,000 | $0 |
| STS 84 | $6,000,000 | $6,000,000 | $0 |
| STS 85 | $6,000,000 | $6,000,000 | $0 |
| STS 94 | $6,000,000 | $6,000,000 | $0 |
| STS 86 | $6,000,000 | $6,000,000 | $0 |
| STS 87 | $6,000,000 | $6,000,000 | $0 |
| STS 89 | $6,000,000 | $6,000,000 | $0 |
| STS 90 | $6,000,000 | $6,000,000 | $0 |
| STS 91 | $6,000,000 | $6,000,000 | $0 |
| STS 95 | $6,895,000 | $6,895,000 | $0 |
| STS 88 | $6,895,000 | $6,895,000 | $0 |
| STS 96 | $6,895,000 | $6,895,000 | $0 |
| STS 93 | $6,895,000 | $6,895,000 | $0 |
| STS-103 | $6,895,000 | $4,025,000 | $2,870,000 |
| STS-99 | $6,895,000 | $4,025,000 | $2,870,000 |
| STS-101 | $6,895,000 | $4,025,000 | $2,870,000 |
| STS-106 | $6,895,000 | $6,895,000 | $0 |
| STS-92 | $6,895,000 | $5,895,000 | $1,000,000 |
| STS-97 | $6,895,000 | $6,895,000 | $0 |
| STS-98 | $6,895,000 | $6,895,000 | $0 |
| STS-102 | $6,895,000 | $6,895,000 | $0 |
| STS-100 | $6,895,000 | $6,895,000 | $0 |
| STS-104 | $6,895,000 | $6,895,000 | $0 |
| STS-105 | $6,895,000 | $6,895,000 | $0 |
| STS-108 | $6,895,000 | $6,895,000 | $0 |
| STS-109 | $6,895,000 | $5,460,000 | $1,435,000 |
| STS-110 | $6,895,000 | $6,895,000 | $0 |
| STS-111 | $6,895,000 | $6,895,000 | $0 |
| STS-112 | $6,895,000 | $6,895,000 | $0 |

###### ATTACHMENT V

| ITEM | Criteria for Successful Accomplishment | Required Date | Available Incentive | Earned (Y/N) |
| --- | --- | --- | --- | --- |
| 1a | AIT (Application Integration Test) and IVT (Independent Verification Test) complete on Delivery 3 content | 06/01/2000 | $500,000 | Yes |
| 1b | AIT and IVT complete on Delivery 4 content | 11/01/2000 | $500,000 | Yes |
| 1c | AIT and IVT complete on Delivery 5 content | 07/02/2001 | $500,000 | Yes |
| 1d | Full TSUP content delivered for operational testing and final certification | 10/01/2001 | $500,000 | Yes |
| 1e * | Achieve demonstrated full capability through “flight following” | 04/30/2002 | $1,000,000 | Yes |
| 1f * | Utilize TSUP as prime system for flight support before mainframe decommission | 09/30/2002 | $2,000,000 | Yes |
| 2* | Completion of the following modifications in the processing flow: 18509 Water Condensation Collection 19029 DDU R&R 19033 Orbiter ET/UMB Plate Gap, Delta P 19400 MMU Upgrade 19484 Cargo PC Wiring 19518 APU R/R Coupling Installation 19527 Critical Wire Separation 19533 Monoball Production Break 19563 Install Micro TAU's/SGU's 19596 AC Bus Separation | 03/27/2002 | $1,000,000 | Yes |

* It is understood that changes in the manifest may preclude the contractor from successfully completing this identified program plus fee objective.  In such an instance, if it is determined by the Government that the contractor is unable to demonstrate successful completion of this identified program plus fee objective through no fault of its own, but that the contractor's performance would have been expected to have successfully met the milestones based on Government evaluation of the completion to date, the criteria will be considered to have been successfully met and the associated program plus fee will be considered to have been earned.