## Project cost est
Cost (Millions
Description | Quantity | of 1999$)
Construction Costs
Site Preparation and Restoration
Utility relocation - meters | 3675 | 13.208
Street restoration - meters | 3675 | 1.8768
Traffic signals - # | 7 | 0.62921
Structure mod. and underpinnings - # | 2 | 2.8764
Environmental mitigations - # | 2 | 0.76404
Maintenance facility and yard | 1 | 25.6
Trackway - meters
At grade - 2 track | 690 | 0.4
Subway - meters
Cut/cover - 1 track | 593 | 16.7
Cut/cover - 2 track | 1230 | 79.1
Mined tunnel - 1 track | 413 | 16.5
Mined tunnel - 2 track | 749 | 42.5
Ventilation (cut/cover + mined tunnel) | 2985 | 5.4831
Stations - number
At grade | 1 | 2.6
Underground | 4 | 79.5473
Trackwork
Ballasted - meters | 690 | 0.35236
Direct fixation - meters | 4964 | 2.7973
Special - turnouts, turnback…etc. - # | 1 | 0.57528
Traction power supply - meters | 5654 | 4.6274
Signaling and train control - meters | 5654 | 7.2
Communications/fire/safety - meters | 5654 | 2.5
Subtotal Construction Costs |  | 305.8372
Non-Construction Costs
Right-of-way
Right-of-way - stations - # | 5 | 4.8
Right-of-way - Maintenance facility - # | 1 | 2.2
New Vehicles - # | 8 | 20.1
Preliminary Engineering |  | 10
Final engineering/management |  | 39.8
Subtotal Non-Construction Costs |  | 76.9
Contingency |  | 45.8756
Total |  | 428.6128

## Baseline cost est
Contract |  | Cost ($Millions)
No. | Description | Escalated*
| Preliminary engineering | 10.3
| Final engineering and project management | 43.7746 |  | 110%
| Real estate | 7.603 |  | 108.6%
| Vehicles | 23.272 |  | 115.8%
| Construction Contracts |  | 23.3
1 | Maintenance facility and yard | 34.7282 |  | 118%
2 | Subway cut/cover | 144.1249 | 0.38986 | 118%
3 | Subway mined tunnel | 90.3449 | 0.24587 | 118%
4 | Trackwork installation | 5.0531 |  | 118%
5 | Construct stations | 121.1992 | 0.36427 | 118%
6 | Install traction power system | 6.2774 |  | 118%
7 | Signalling system | 9.7673 |  | 118%
8 | Communications system | 3.3914 |  | 118%
| Total | 499.836
* May be escalated to either year-of-expenditure or mid-point of construction.

## Cost track sched
|  | Baseline | Contract | Approved | Current | Forecasted | Contract to | Current Budget | Expenditures
No. | Description | Budget | Award | Changes | Contract | Changes | be Awarded | Forecast | To-Date
| Preliminary engineering | 10.3 | 10.3 | 0 | 10.3 |  | 0 | 10.3 | 10.3
| Final eng. and mgmnt | 43.7746 | 42.5 | 0 | 42.5 |  | 0 | 42.5 | 5.5
| Real estate | 7.603 | 7.8 | 0.4 | 8.2 |  | 0 | 8.2 | 4.9
| Vehicles | 23.272 | 22.5 | 0 | 22.5 |  | 0 | 22.5 | 0
Construction Contracts
1 | Maintenance facility | 34.7282 | 32.4 | -0.5 | 31.9 |  | 0 | 31.9 | 0
2 | Subway cut/cover | 144.1249 | 148.8 | 0 | 148.8 |  | 0 | 148.8 | 5.2
3 | Subway mined tunnel | 90.3449 | 94.2 | 0 | 94.2 |  | 0 | 94.2 | 1.5
4 | Trackwork installation | 5.0531 |  | 0 | 0 |  | 5.0531 | 5.0531 | 0
5 | Construct stations | 121.1992 |  | 0 | 0 | -2.5 | 121.1992 | 118.6992 | 0
6 | Traction power system | 6.2774 |  | 0 | 0 |  | 6.2774 | 6.2774 | 0
7 | Signalling system | 9.7673 |  | 0 | 0 |  | 9.7673 | 9.7673 | 0
8 | Communications system | 3.3914 |  | 0 | 0 | -0.2 | 3.3914 | 3.1914 | 0
| Total | 499.836 | 358.5 | -0.1 | 358.4 | -2.7 | 145.6884 | 501.3884 | 27.4