PROJECT MONTHLY STATUS REPORT

| Project Title: | OMBA-123 implementation |
| --- | --- |
| Owner: | Mike Costello |
| Date (MM/DD/YYYY): | 9/25/2006 |
| Reporting Period: | July 1, 2006 through September 15, 2006 |

Project Description: To comply with the 9/15/2006 deadline of Secretary of Energy signing of

The assurance letter on the effectiveness and efficiency of the internal controls over financial reporting.

1. Executive Summary

Overall Status:

Green 1

(Controlled)

Yellow 2

(Caution)

Red 3

| (Critical) | Reason for Deviation |
| --- | --- |
| Deliverable: | [X] | [ ] | [ ] |
|  | Schedule: | [X] | [ ] | [ ] |
|  | Scope: | [X] | [ ] | [ ] |
|  | Budget: | [X] | [ ] | [ ] |

1 Project is within established milestones, scope and on schedule.

2 Project has deviated slightly from the plan.

3 Project has fallen significantly behind schedule, is not tracking to established milestones, or has taken on tasks that are out of scope.

Comments:

|  | Testing for all Entity control subcategories and process cycles was completed on 9/1/2006. The Remediation work was completed by 8/15/2006. All corrective action plans were finalized, approved, and signed off. Implementation project met the overall timelines, milestones, as well as any interim reporting to the Chicago site office. |
| --- | --- |
| 2. Controls |
| Issue Status (Significant issues impacting milestones, schedule or scope) |
| 1. DOE guidelines on the detail steps required continued to be less than clear, this means that future review by |
| any oversight agency may reveal additional required information. |
| 2. Constantly evolving requirements from DOE Chicago prevent planning with a reasonable time horizon. |
| Change Status (Changes raised for consideration that change the approved project baselines. |
| Future review by oversight agency of the implementation process |
| Risk Status (Report on any major project risks) |
| 1. The extensiveness and the depth of the project implementation may be impacted by the overall aggressive timelines. |
| 2. The effort continues to concentrate within the office of the Controller (natural result of the aggressive timelines), therefore the scope of the OMBA-123 implementation, while sufficient, is likely to be less extensive. |

| 3. Budget Report |
| --- |
| Expense | Original Budget | Spent to Date | Variance | Current Budget | Current Forecast | Estimate to Complete |
| Labor |
| External OCFO | 70,000 | 70,000 |
| N/A | N/A | N/A |
| OCFO, Controller’s office | 81,987 | 81,987 |
| Hardware | N/A |
|  | Software | N/A |
|  | Other (Training) | 9,000 | 4,000 |
| Total | 160,987 | 156,987 |
| Link: |
|  | Comments: |

| 4. Scheduled Milestones / Deliverables |
| --- |
| List all Major Project Milestones. Dates should tie to established baseline schedules in the Eroom. |
| Milestone (last revised 7/17/2006) | Approved Schedule | Actual | Current Forecast | Status |
| Final DOE Guidance | 11/15/2005 | 1/17/2006 |
| Complete |
| Software Demo scheduled | 12/22/2005 | 12/22/2005 |
| Complete |
| Project plan finalized and review with sr. mgmt |
| 1/20/2006 |
| Complete |
| Phase I Documentation | 2/17/2006 | 2/17/2006 |
| Complete |
| Phase II Evaluation | 3/29/2006 | 3/29/2006 |
| Complete |
| Test Plan to DOE Chicago | 3/30/2006 | 3/30/2006 |
| Complete |
| 3rd quarter report to DOE Chicago | July 2006 | 7/7/2006 |
| Complete |
| Phase III Testing | 8/1/2006 | 9/1/2006 |
| Complete |
| Phase IV Remediation | 8/15/2006 | 8/15/2006 |
| Complete |

Finalize all OMBA-123 reporting and submission

| To DOE Chicago | 9/15/2006 | 9/6/2006 |
| --- | --- | --- |
| Complete |
| Monthly status report – assessment team | Ongoing |
|  | Open |
| Monthly status report to CFO | Ongoing |
|  | Open |
| Ad Hoc status report to the Steering Committee | Ongoing |
|  | Open |

5. Accomplishments / Plans

Accomplishments during this Reporting Period (Should relate to milestones):

Positive feedback from HQs and Chicago site office on LBNL submission of implementation data,

Statement of material weaknesses to DOE Chicago in August 2006 (none reported).

Successfully met the implementation Remediation, Testing, and Reporting milestones and timelines.

Finalized, approved, and signed off on seven Corrective Action Plans and its CATS reporting.

Plans during the next Reporting Period (Should relate to milestones):

Lessons Learned and 2007 Implementation activities planning.

| 6. Project Monthly Status Report / Signatures |
| --- |
| Project participants: John Chernowski, Michele Mock, Ira Nishibayashi, Kimberly Martens, Grace Huang, Lauretta Corsair, Rosalyn Height, Sallie Frainier, Harry Lorsbach, and Jim Yoshihara, Rich Nosek, and Rose Katsu. |
| Project Owner: Controller, Mike Costello |
| I have reviewed the information contained in this Project Monthly Status Report and agree: |
| Name | Title | Signature |

Date

(MM/DD/YYYY)

The signatures above indicate an understanding of the purpose and content of this document by those signing it. By signing this document, they agree to this as the formal Project Monthly Status Report document.