# Environmental Management

# Committee Meeting Minutes

# Wednesday, December 17 2008, 5:30 p.m.

# DOE Information Center

| Committee Members Present | Others Present |
| --- | --- |
| Darryl Bonner Claire Campbell Miranda Clower Betty Jones Gloria Mei Norman Mulvenon Ron Murphree, Chair Tim Myrick, Vice-chair Bob Olson Kerry Trammell Absent Rhonda Bogard John Coffman Susan Gawarecki Luther Gibson Charles Jensen John Kennerly Lance Mezga Maggie Owen | Dave Adler, Department of Energy (DOE) Dan Jones, ARCADIS John Kubarewicz, Bechtel Jacobs, Co.(BJC) Julie Pfeffer Bill Tewes Kelly Trice (BJC) Russ Vranicar, DOE Ed Walker |

K-25/K-27 Update and ETTP Ponds Remediation Status

The committee received updates on the status of the remediation of the K-1007 Pond and decontamination and decommissioning (D&D) activities at East Tennessee Technology Park (ETTP).

Ms. Pfeffer began by providing the update on the pond remediation project (Attachment 1). Mobilization is scheduled to begin in January with work beginning in February on a project to remediate the K-1007-P1 Pond at ETTP. The fish in the 25-acre pond located on the southwest corner of ETTP are contaminated primarily by PCBs.

The pond is currently the home of grass carp and gizzard shad, which are bottom-feeders and tend to re-suspend contaminated sediment. PCBs accumulate in high levels in the shad, which are a favorite prey of large-mouth bass in the pond. The bass, in turn, could be consumed by humans.

In March 2007 an action memorandum was signed by DOE Oak Ridge to conduct a non-time critical removal action to mitigate PCB contamination in the fish by restoring the pond to a more natural condition.

Other options considered were to remove all of the sediment in the pond or fill in the pond with clean fill. Removal of contaminated sediment would have been a difficult endeavor requiring excavation of about 110,000 cubic yards of sediment and cost about $30 million. Filling in the pond would have required about 150,000 cubic yards of clean fill and cost $11-$12 million.

The selected option is environmental restoration to return the pond to a more natural state. Restoration steps include drawing down the pond, removing the shad and carp and reintroducing blue gill fish, which are not bottom feeders. Some clean fill will be added on top of the contaminated sediment and vegetation will be planted in and around the pond to limit sediment re-suspension and erosion. Higher growing vegetation will be planted to discourage geese from congregating in the area. Geese cause high nutrient loading in the pond that promotes algae growth on the surface water.

Flood controls will be put in place to prevent reintroduction of carp and shad from nearby Poplar Creek. Burchfield Road, which borders the pond, provides some flood protection but additional improvements are needed.

Ms. Pfeffer said the schedule for the work is heavily dependent on the weather. Mobilization to begin the work is scheduled for mid-January through mid-February 2009. The pond will be drawn down from mid-February to about the first of August. Additional fill will be added during the first months of the pond draw down. Ecological enhancement by planting new vegetation and reintroducing blue gill will be from May to about the first of November.

The carp and shad currently in the pond will be killed off using rotenone. While some dead fish will sink to the bottom of the pond, the floaters will be removed and buried in an area across Burchfield Road.

Since no contaminated sediment will be removed, Mr. Myrick asked if hot spots will be sought for placement of clean fill. Ms. Pfeffer said that is not required but most spots should be covered.

Ms. Mei asked if there will be any work to maintain the condition of the pond once the project is complete. Ms. Pfeffer said the area should be self-sustaining, but it will be monitored and results reported in the annual Remediation Effectiveness Report.

Mr. Bonner asked if there will be any recontouring around the pond. Ms. Pfeffer said gravel will be installed for trucks to drive on but that will be removed when the project is finished. Mr. Bonner also asked if there will be any additional barriers for undesirable fish. Ms. Pfeffer said a fencing material is being considered for any 50-100 year flooding event, but details have not been completed. Mr. Adler asked if flooding is a real risk since the nearby Clinch River is controlled by the Tennessee Valley Authority. Ms. Pfeffer said a big storm could cause flooding in the area.

Mr. Trammell asked if fishing will be allowed in the pond after restoration is complete. Ms. Pfeffer said if PCB levels are low enough it should be safe for fishing, but the landlords would have to provide permission to fish.

Mr. Bonner asked about the storm drain exiting the pond. Ms Pfeffer said there are no plans to modify it.

Mr. Vranicar and Mr. Trice provided the update on the K-25/K-27 D&D project (Attachment 2).

The project is a non-time critical removal action to remove high risk process system components from both buildings, establish criticality incredible, and demolish the buildings. Mr. Vranicar repeated the comments by Steve McCracken, the DOE Oak Ridge Assistant Manager for Environmental Management (EM), at the October 2008 Oak Ridge Site Specific Advisory Board (ORSSAB) meeting that he did not believe the North Tower of K-25 was worth saving as had been planned. Mr. Trice said about 200 corbels in K-25 have failed and about 40 of those are in the North Tower.

Debris from the project will be disposed at the waste management facility on Bear Creek Road near Y-12, at Energy Solutions in Utah, and at the Nevada Test Site.

Mr. Vranicar noted major project accomplishments (Attachment 2, pages 9 and 10). All preparation for demolition of the west wing of K-25 has been completed and actual demolition started the day before on December 16. Mr. Vranicar said in order to achieve the criticality incredible status for the operating floor a platform had to be built to access the floor. The operating floor had been closed because it was so degraded.

Full scale deactivation of the east wing is underway including duct cutting, asbestos removal, system draining, transite siding removal, and vent/purge/drain operations.

Demolition of the west wing is scheduled for completion by the end of 2010. Demolition of the east wing is scheduled to begin February 2010.  All demolition work for K-25 is scheduled for completion by March 2011. Demolition of K-27 is scheduled to begin July 2014 and be complete by August 2016.

Mr. Trice said D&D of K-25 is the most complex project underway in the country. He said many of the tasks being done are one of a kind. The expected cost to D&D both K-25 and K-27 is about $850 million. That projection is up from $827 million reported to the committee in July 2008.

Mr. Vranicar said one of the lessons learned in the D&D project is to remove uranium deposits in the equipment while the equipment is still in a functioning condition.

Mr. Tewes said there has not been good documentation of what has taken place in the buildings. He asked if careful records are being kept about where each cell and converter came from in the building. Mr. Vranicar said a tracking device is attached to each large piece of equipment that comes out of the building that notes the waste characterization done on the piece and where it is placed in the waste cell.

Mr. Olson asked how K-27 is being maintained prior to demolition. Mr. Trice said K-27 is in better condition that K-25, although there is some roof leakage. He said the maintenance budget for both buildings is about $10 million a year. He said his job is to get K-27 ready for demolition. He said about 85 percent of the cost of D&D is getting the building ready for demolition.

Mr. Murphree asked what the schedule driver was for K-27. Mr. Trice said the driver is the ability to have the building ready for demolition start in 2014. He said it took 18-20 months to get the west wing of K-25 ready for demolition. He wants to have the east wing ready in 12 months. He said that’s an aggressive schedule but believes it can be done.

Mr. Trammell asked if demolition work is a daytime-only job. Mr. Trice said it was and the work is generally done on four 10-hour work days. He said a lot of the work of demolition is size reduction of large pieces of debris. For each excavator doing demolition there are four doing size reduction. He said about 45 loads of debris will go the waste management facility each day. The hope is to get up to 100 loads a day.

Discussion of possible recommendation or comments on the presentation

Mr. Trice mentioned that the committee could help by recommending stable funding for D&D work.

Mr. Myrick said he didn’t see a need for any comments at this time, but to continue to receive periodic updates on the work at K-25/K-27. Mr. Trammell agreed saying the committee should monitor the work to make sure schedules are being met to ready the east wing for demolition.

Mr. Mulvenon said the reporting of costs needs to be better. No figures were in the presentation and Mr. Trice and Mr. Vranicar provided figures from memory. Mr. Adler said he would bring information to the January meeting clarifying the costs.

Ms. Clower suggested a news item in the next Advocate newsletter about the start of the ponds remediation. She also suggested a more detailed news release on the topic to send to area newspapers.

Staff will work up an item for the newsletter and discuss a more general news release with the Public Outreach Committee.

Committee input on next month’s program: Building 3019 Update

Next month’s presentation is a status update on Building 3019 at Oak Ridge National Laboratory. Ms. Mei asked for input on what the committee would like to receive in the presentation.

Mr. Adler said project manager Gary Riner has a new baseline proposal to report that indicates how costs and schedules have been revised. His new proposal would also include information on the construction of another facility.

Mr. Olson said he would like to hear about any uncertainty related to disposing of the uranium-233 in the building. Mr. Adler said the task is to stabilize the material and get it ready for disposition at the Nevada Test Site. Mr. Olson asked if money has been allocated for the project. Mr. Alder said the 3019 project takes a significant portion of the Oak Ridge EM budget for the next 10 years. He said funding will determine the pace of work.

Develop FY 2010 EM Committee Budget Request

The committee reviewed the FY 2009 committee budget request (Attachment 3). After some discussion about travel and technical assistance the committee agreed on the FY 2010 budget request 
(Attachment 4).

Review Work Plan

In February a joint meeting is scheduled with the Stewardship Committee to receive a report from a technical advisor on the focused feasibility study and proposed plan for the remediation of Bear Creek Burial Grounds. However, the D2 version of the study and plan will not be ready for a report until April.

In April there is another joint meeting scheduled with Stewardship to get a report on exit pathways of groundwater and especially on contaminated groundwater from Melton Valley reaching a line a picket wells southwest of the Oak Ridge Reservation.

The Stewardship Committee said at its December 16 meeting that it is agreeable to simply swap the meeting dates if the EM Committee was agreeable. The EM Committee agreed that topic dates could be swapped. Staff will adjust both work plans accordingly.

Review of Trench 13

ORSSAB received a briefing on Trench 13 in Melton Valley from Mr. Adler at the December meeting. Chair Steve Dixon asked the EM Committee to review the presentation to determine if any comments or recommendations were warranted.

Mr. Olson suggested that the waste in Bear Creek Burial Grounds is similar to that in Trench 13 and perhaps they should be considered together. He suggested that both sites have 'shock sensitive' or pyrophoric materials in them.

Mr. Bonner agreed that discussions on Trench 13 and the Bear Creek Burial Grounds should wait until the April meeting in conjunction with discussions on the focused feasibility study and proposed plan for Bear Creek Burial Grounds.

Mr. Olson suggested holding discussion until DOE submits a proposal to the Tennessee Department of Environment and Conservation on what to do about Trench 13 and then discuss it at the April meeting in

conjunction with the review of the focused feasibility study and proposed plan for Bear Creek Burial Grounds.

Addition to Agenda - Review of K-25 historic preservation

Mr. Murphree said new options for historic commemoration of K-25 has been provided to Steve McCracken. Those options were presented to the Stewardship Committee on December 16.

The preferred option is similar to a suggestion in a minority opinion written in part by Mr. Murphree and Mr. Olson to demolish the North Tower of K-25 and build a separate interpretive center. The new option will be provided to board members Bill Bass and Steve Stow who also signed the minority opinion. The four will consider the new option and determine if their minority opinion will be revised as a full recommendation to put before the board.

Action Items

Open

- Jeff Crane will provide a letter detailing his explanation as to why the state’s water classifications have not been approved by EPA. Carryover from the November meeting.

- A technical advisor scope of work will be completed by Mr. Olson, Ms. Jones, and Mr. Bonner by the end of October. Status. A revised scope of work has been developed in response to some questions raised by the Board Finance & Process Committee.

- Mr. Adler will bring more detailed cost information on K-25/K-27 D&D to the January 2009 committee meeting.

Closed

- Staff will include an item on the ponds remediation in the next Advocate newsletter. A more detailed news release on the subject will be discussed with the Public Outreach Committee. Complete.

- Staff will adjust the EM and Stewardship work plans to reflect swapping the February and April meeting topics. Complete.

# The meeting adjourned at 7:20 p.m.

# Attachments (4) are available on request from the ORSSAB support office.

# rsg