The Dark Energy Camera (DECam) Project

Conceptual Design Report

Version 1.6.2

July 20, 2006

The Dark Energy Survey Collaboration

Table of Contents

Foreword	iv

1	Introduction	1

1.1	The Science Context of the Dark Energy Survey	1

1.2	Overview of the Dark Energy Survey	1

1.3	The Dark Energy Survey Organization	2

1.3.1	Dark Energy Survey Projects	2

1.3.2	Dark Energy Survey Collaboration	3

2	Cerro Tololo Inter-American Observatory	5

2.1	Site Selection	5

2.2	Properties of the CTIO site and the Blanco Telescope	5

3	Science Program and Requirements	6

4	Description of the DECam Project	8

4.1	DECam Conceptual Design	8

4.1.1	CCDs and Focal Plane	9

4.1.2	CCD Characterization	13

4.1.3	CCD Readout Electronics for DES	15

4.1.4	CCD Camera	16

4.1.5	Optical Corrector	17

4.1.6	Prime Focus Cage and Alignment	21

4.1.7	Survey Image System Process Integration (SISPI)	22

4.2	Improvements Planned for the Blanco Telescope and the DECam
                             Instrument	23

4.3	Survey Planning and Simulations	24

4.4	Data Management for the Dark Energy Survey	25

4.5	In-Kind Contributions to the DECam Project	25

4.6	Project Deliverables	26

4.7	Value Engineering for the DECam Project	26

4.7.1	CCDs	26

4.7.2	Optical Design	27

4.7.3	CCD Readout Electronics	27

4.8	Risk Management for the DECam Project	28

4.8.1	Risks in the Optical Manufacture	28

4.8.2	Risks in the CCD Manufacture	29

5	Cost and Schedule for the DECam Project	31

5.1	Work Breakdown Structure for the DECam Project	31

5.2	The Cost Range of the DECam Project	32

5.3	The Schedule Range of the DECam Project	34

6	Justification for the DECam Project	35

6.1	Mission Need for a Ground-Based Dark Energy Experiment	35

6.2	How the DECam Project Satisfies Option 1 in the Mission Need 
                              Statement	36

6.2.1	Forecast Dark Energy Constraints	37

6.2.2	Systematic Errors	40

6.2.3	Combination of results	42

7	Managing the Project Responsibly	42

7.1	Environment, Safety, and Health	42

7.1.1	The National Environmental Policy Act (NEPA)	43

7.1.2	Safety Assessment Documents	43

7.1.3	Integrated Safety Management Plan	43

7.1.4	Waste Minimization/Pollution Identification	44

7.2	Safeguards and Securities Plan and Vulnerability Assessment	45

7.3	Preliminary Plan for Demobilization of Replaced Facilities	45

7.4	Preliminary Plan for Decontamination and Decommissioning	45

7.5	Preliminary Project Execution Plan	46

8	Preliminary Management Control Documents	46

8.1	Memoranda of Understanding	46

8.2	Preliminary Project Management Plan	46

9	Public and Stakeholder Input	47

9.1	Stakeholders in the DECam Project	47

9.2	Community Use of DECam and Access to Data Obtained with DECam	47

10	Project Reviews	48

10.1	Technical Reviews	48

10.2	ES&H Reviews	48

10.3	Director’s Reviews	48

Appendix: Acronyms Used in This Document	49

References	51

# Foreword

This conceptual design report (CDR) was prepared at the request of the Fermilab Associate Director of Research as part of the documentation for the Director’s Review of the DECam Project, which will take place from July 25 to 27, 2006. The writers prepared it to meet the content and format requirements of the conceptual design report specified in DOE Order 413.3 M. While it was written to facilitate the review of the DECam, it provides a brief description of the Dark Energy Survey Data Management System and the Blanco Telescope Improvements, the two other projects in the Dark Energy Survey. The limited descriptions of these projects in this CDR are intended to provide context for the reviewers and to clarify the relationships among the Dark Energy Survey projects in order to allow them to properly evaluate the DECam project. They do not provide reviewable documentation for these projects that meets the requirements of DOE Order 413.3 M. However, it is hoped that if DOE should request Fermilab to submit documentation for Critical Decision 1, this CDR and any revisions that are made as a consequence of the Director’s Review would be a very valuable part of the conceptual design report submitted for the CD-1 documentation.

# Introduction

## The Science Context of the Dark Energy Survey

A critical research problem in cosmology is the drive to understand the observations of an accelerating expansion of the universe.  In 1998 two independent teams studying very distant supernovae observed that Type 1a supernovae appeared dimmer than expected.  This dimness could be explained by either evolution in the intrinsic luminosity of the supernovae or an acceleration of the universal expansion. The gravitational attraction of galaxies and their dark matter halos decelerates the expansion. Because we observe an acceleration instead, something new and strange is required: dark energy.  Since then, independent lines of evidence for dark energy have been found.

The high precision measurements of the temperature fluctuations of the cosmic microwave background (CMB) made with the NASA Wilkinson Microwave Anisotropy Probe (WMAP) mission showed that the geometry of the universe is flat to within the errors of their measurements.  A flat universe requires that the total energy density must be equal to a critical value.  The Sloan Digital Sky Survey and WMAP have determined that the total matter density, the sum of the normal and dark matter densities, is equal to 30% of this critical value. The remaining 70% of the energy density is attributed to the unseen dark energy—in agreement with the supernova studies.

The dark energy could be a simple vacuum energy density (the “cosmological constant”), a new scalar field, a flaw in Einstein’s general relativity or evidence that our world lies embedded in a much higher dimensionality universe. Any of these possibilities represent a major shift in our current understanding of the nature of matter, energy, space and time.  However, to sort out the possibilities and pin down the nature of the dark energy, we will need more precise measurements of the dark energy equation of state parameter, w.  We also need to determine whether the amount of dark energy in the universe has changed with time – that is, whether the equation of state should be described with both a constant and a time-dependent term.  In order to make these measurements, new methods and new instruments are needed.

Our method of choice to begin to pin down the nature of dark energy is an astronomical survey with a new, powerful instrument.

## Overview of the Dark Energy Survey

The goal of the Dark Energy Survey (DES) is to take the next step in unraveling the mystery of dark energy. We will focus on the measurement of w by measuring it to a statistical precision of ~5% through four independent methods: galaxy clusters, weak gravitational lensing tomography, galaxy angular clustering, and supernova distances. These methods are doubly complementary: they constrain different combinations of cosmological model parameters and are subject to different systematic errors. By deriving the four sets of measurements from the same data set with a common analysis framework, we will obtain important cross checks of the systematic errors and thereby make a substantial and robust advance in the precision of dark energy measurements. To make these measurements, we propose an optical-near infrared survey of 5000 sq. deg of the South Galactic Cap to ~24th magnitude in SDSS griz filter bands that will be carried out with a new 3 deg2 CCD camera mounted on the Blanco 4-m telescope at Cerro Tololo Inter-American Observatory (CTIO).

The DES Collaboration proposes to build the Dark Energy Camera (DECam), the new 3 sq. deg. Survey instrument, with the support of Fermilab and the collaborating institutions. The collaboration has requested funding from the U.S. Department of Energy through Fermilab, funding from PPARC through the U. K. DES Consortium, and funding from the Ministerio de Educacion y Ciencia (MEC) through the Spanish DES Consortium in order to build and deploy DECam. The Collaboration also proposes to build and commission a data management system in partnership with NOAO to process the data obtained with DECam. The processed data will be placed in a public archive operated by NOAO. Several of the collaborating institutions have committed to provide additional cash or in-kind contributions in order to partially fund the development phase of the DES.

This conceptual design report (CDR) describes the conceptual design of DECam and the structure of the DECam project. DECam will be built as a DOE project at Fermilab and the collaborating institutions. It includes a large mosaic camera, a five element optical corrector, four filters (g,r,i,z), and the associated infrastructure for operation in the prime focus cage. The focal plane consists of 62 2K x 4K CCD modules (0.27arcsecond/pixel) arranged in a hexagon inscribed within the 2.2 deg. diameter field of view. It has been designed to use the 250-micron-thick fully-depleted CCDs that have been developed at the Lawrence Berkeley National Laboratory (LBNL) in order to obtain the best available quantum efficiency at wavelengths between 700 nm and 1000 nm.  The construction of DECam is scheduled to finish in FY10, and the survey will take data during 2010-2015.

The description of the conceptual design of the data management system and the management of the Data Management Project is described in a separate document, which is in preparation. A very brief description of this part of the DES is presented in this conceptual design report in Section 4.4, solely to show the connection between the projects.

## The Dark Energy Survey Organization

The Dark Energy Survey requires the Blanco telescope, with modest improvements; DECam, the new survey instrument; and the Data Management System. Each of these is treated as a project and each project is carried out under the oversight and direction of one of the principal institutions in accordance with their project management practices. In each case, members of the DES Collaboration will be contributing to all of these projects.

### Dark Energy Survey Projects

Fermilab manages and oversees the DECam project in accordance with DOE management procedures. The Collaboration submitted a proposal to Fermilab for support of the DECam project. As described elsewhere in this CDR, the design, construction, and testing of DECam prior to its delivery to CTIO will be carried out under the direction of Fermilab in accordance with the DECam Project Management Plan (PMP).

The Blanco Telescope is operated by the Cerro Tololo Inter-American Observatory (CTIO) and the improvements to the Blanco will be managed and overseen by the CTIO Director in accordance with the practices developed by NOAO. The integration of DECam with the Blanco and its subsequent operation will also be under the direction and oversight of the CTIO Director.

The Data Management System will be developed and commissioned by the staff of the National Center for Supercomputing Applications (NCSA) in partnership with NOAO Data Products Program. The work at the NCSA will be under the direction of its Director in accordance with their practices. The description of the conceptual design of the Data Management System and the management of the Data Management Project is described in a separate document, which is in preparation. A very brief description of this part of the DES is presented in this conceptual design report in Section 4.4, solely to show the connection between the projects.

Joint oversight of the projects is the responsibility of the Directors of Fermilab, NCSA, and NOAO.  However, each project has been organized to provide close coordination with the others. This coordination is achieved with the assistance of the Dark Energy Survey Collaboration.  The Collaboration requested this natural arrangement because it took advantage of the unique strengths of Fermilab, NCSA and NOAO in building an instrument, building a data management system and operating a large telescope and archive.

### Dark Energy Survey Collaboration

The Dark Energy Survey Collaboration is a collaboration of scientists from Fermilab, the University of Illinois at Urbana-Champaign, the University of Chicago, the Lawrence Berkeley National Laboratory, CTIO, University College London, University of Cambridge, University of Edinburgh, University of Portsmouth, Institut d'Estudis Espacials de Catalunya, Institut de Fisica d'Altes Energies, CIEMAT-Madrid, University of Michigan, and University of Sussex. The DES collaboration developed the scientific objectives for the DES and the concept for the DECam Project, which is being described in this CDR. As shown in Figure 1, the collaboration communicates with the DECam project,  Data Management System, and CTIO through the DES Project Director, the DECam Project Manager, the Data Management System Project Leader, and the CTIO Director.  All are members of the DES Management Committee. It is important to note that the figure shows lines of communication; not lines of authority and responsibility. The DES Project Director serves as the principal point of contact between the DES Collaboration and the Directors of Fermilab, NCSA, and NOAO and represents the Collaboration in interactions with these institutions. The Project Director provides much of the coordination among the three major collaboration efforts: the DECam Project, the Data Management System Project, and the Blanco integration and improvement project. The science working group, which is not shown, reports to the management committee and is responsible for the scientific analysis of the DES data and the publication of result from those analyses.

Figure 1  Lines of Communication for the Dark Energy Survey Organization

1.3.3		DES Project Director and the Management Committee

The DES Project Director serves as the principal point of contact between the DES Collaboration and the Directors of Fermilab, NCSA, and NOAO and represents the Collaboration in interactions with these institutions. The responsibilities of the Collaboration are specified in the DES Memorandum of Understanding (MOU) between these bodies. Overall responsibility for carrying out the DES is vested in the DES Project Director. These responsibilities include the preparation of the Observing Plan, including calibration observations, the coordination of survey observations made by the Collaboration with DECam, including the commissioning of the DECam instrument, the delivery of raw and processed data to NOAO, and the analysis of data and publication of scientific results from those data.

The DES Project Director is advised by the DES Management Committee on all matters relevant to the DES. The DES Project Director and the Management Committee are jointly responsible for obtaining the funds and other resources to mount and operate the DES.

# Cerro Tololo Inter-American Observatory

Prior to the formation of the DES Collaboration, several of the current members were studying how to obtain an extensive set of mass and redshift measurements of a large sample of galaxy clusters in order to measure w.  At the time, the South Pole Telescope (SPT) team was building a millimeter radio telescope at the South Pole to observe clusters of galaxies through the Sunyaev-Zel'dovich Effect (SZE).  This effect is the change in the frequency spectrum of the cosmic microwave background photons when they traverse a galaxy cluster, and it can be used to determine a cluster mass more accurately than the traditional method of counting the number of galaxies in a cluster. However, it does not provide an accurate measure of cluster redshift.  Combining SPT data with the results of an optical-near infrared survey of the same area to the appropriate depth would provide the needed accurate redshifts for the galaxies in the S-Z survey.  This initiated a search for a southern hemisphere site with a telescope capable of carrying out a multi-band wide field survey to the appropriate depth.  Fortunately at the same time, NOAO was looking for a partner who would exploit the wide field survey capability of the Blanco Telescope.

## Site Selection

NOAO issued an announcement of opportunity (AO) in December 2003 for an open competition to partner with NOAO in building an advanced instrument for the Blanco telescope in exchange for awarding the instrument collaboration up to 30% of the observing time over a five-year period for a compelling science project. In response to this AO, the DES Collaboration was formed and submitted a proposal to Fermilab in April 2004 requesting support for the pre-conceptual development phase of DECam and permission to respond to the NOAO AO. This proposal was approved and subsequently the Collaboration submitted a proposal to NOAO in July 2004 requesting observing time to carry out a survey to address the nature of the dark energy with a new instrument, DECam. The proposal included preliminary designs of DECam and the DES Data Management System. The NOAO Director convened the Blanco Instrumentation Review Panel and charged it to review the proposal. The Panel concluded that the DES scientific goals were exciting and timely and recommended that NOAO form a partnership with the DES Collaboration to carry out the proposed survey. Subsequently, the NOAO Director asked the CTIO Director and the DES Project Director to draft an MOU among the Parties that would define the terms of the partnership.

## Properties of the CTIO site and the Blanco Telescope

CTIO is one of the world’s premier observing sites. The Blanco Telescope is a 4 m Ritchey-Chrétien design telescope. The wide field capability of its f/2.7 prime focus has been exploited over the past two decades with a series of ever larger wide field CCD imagers and optical correctors. The telescope and wide field imagers made the facility the southern hemisphere’s (and at times the world’s) leader in optical imaging when gauged by the metric εAΩ (efficiency × aperture × detector area). Together with the prime focus 8K×8K Mosaic II Imager, the latest in the series of imagers, the Blanco has been used to make some of the critical observations of type Ia supernovae that led to the discovery of dark energy.  This combination has also been used for several path breaking surveys including weak lensing surveys, and several surveys are still underway, including one of the major type Ia supernovae searches. All of the surveys that are currently underway are scheduled to be completed by 2008.

At the time of its construction 30 years ago, the quality of the Blanco telescope primary mirror defined the state of the art and the surface quality has only been exceeded in the last decade with the advent of super-polishing. The enclosed energy as a function of diameter as measured during the testing of the Blanco primary at the time of its acceptance is given below:

Enclosed Energy 	Diameter in arcsec

57% 			0.15

80% 			0.25

94% 			0.40

99% 			0.50

The Cerro Tololo observing site has a median image quality of 0.65 arc seconds. The site seeing together with the primary mirror quality will allow the Blanco together with DECam to deliver excellent quality images, limited primarily by atmospheric seeing. No other existing 4m telescope with comparable seeing, and offering the considerable advantage of observing the same survey area as the South Pole Telescope survey, is available for this work.  The CTIO site and the Blanco telescope make it possible for the Collaboration to carry out its science program to make a very precise measurement of dark energy and it was for this reason that the DES Collaboration took the opportunity to respond to the AO.

# Science Program and Requirements

The primary components of the DES scientific program are the four key science projects: galaxy clusters, weak gravitational lensing tomography, galaxy angular clustering, and supernova distances, and these projects determined the science requirements of the survey. Further details of these key science projects can be found in Section 6.2.  The DES observing plan, which was designed to carry out the scientific program with the Blanco telescope, has the following features:

1. An area of 5000 sq-degrees centered roughly at Declination -30 degrees.

2. Wavelength coverage from 390 nm to 1000 nm.

3. Four filter pass bands corresponding to the SDSS g,r,i,z bands.

4. Limiting magnitudes of 24, 24, 24, 23.6 in g,r,i,z, respectively for small galaxies in 1.5” apertures

5.  The instrument plus telescope should deliver images no worse than 0.55” for zenith-corrected images in the r, i, and z bands.

6. Photometric redshifts (photo-z’s) to z = 1, for clusters, red galaxies, and blue galaxies with precisions of (z = 0.1, 0.3, and 0.2 respectively.

7. Observations are made over a 5 year period and are concentrated between September and February, consistent with using only 30% of the available Blanco 4m time.

8. A time domain survey that uses ~10% of the requested observing time and  covers 40 sq-degrees in 13 fields, which are sampled every 3 nights in r and every 6 nights in i and z.

The 5000 sq-degree area is divided into three sub areas as follows: The SPT Area, a nearly 4000 sq-degree area that overlaps the South Pole Telescope Sunyaev-Zeldovich (S-Z) survey; Stripe 82 of the SDSS, a 200 sq-degree area that contains more than one hundred thousand galactic targets with spectroscopic redshifts: and the Connection Area, an 800 sq-degree area that connects the SPT area to Stripe 82. One of the main reasons for selecting the South Galactic Cap for the DES survey area was the opportunity to observe the same area as the SPT S-Z survey, which will begin observations in 2007. Stripe 82 will provide a very large part of the galaxy training set to determine the properties of the DES photo-z’s, an essential requirement for accurate and well understood photo-z’s.

The limiting magnitudes were derived from detailed survey simulations that incorporated weather and seeing data at CTIO over a 30-year baseline. We adopted a median delivered image quality of 0.9” FWHM based on the seeing measured with the Mosaic II Imager on the Blanco over a 5 year baseline. However, with the proposed improvements to the telescope-instrument system that are described in Section 4.2, we expect better image quality.

We have requested 30% of the observing nights on the Blanco telescope over 5 years, concentrated between September and February, to carry out the Dark Energy Survey with DECam. With that time, we expect to reach photometric limits of g=24.6, r=24.1, i=24.3, and z=23.9 over 5000 sq. deg of sky. These are 10( limits in 1.5” apertures assuming 0.9” seeing and are appropriate for faint galaxies; the corresponding 5( limit for point sources is 1.5 magnitudes fainter.

The survey strategy is designed to optimize the photometric calibration by tiling each region of the survey with at least four overlapping pointings in each band. This provides uniformity of coverage and control of systematic photometric errors via relative photometry on scales up to the survey size. This strategy will enable us to determine photometric redshifts (photo-z’s) of galaxies to an accuracy of ((z)~0.07 out to z>1, with some dependence on redshift and galaxy type, cluster photometric redshifts to ((z)~0.02 or better out to z~1.3, and shapes for approximately 200 million galaxies; these measurements will be sufficient to meet the survey science objectives.

The science requirements are presented in the Science Requirements Document.  The required survey area and depth combined with the telescope aperture and time availability directly motivate the design features of the corrector and camera, including the choice of the near-IR sensitive LBNL CCDs.

# Description of the DECam Project

## DECam Conceptual Design

We have developed a conceptual design for DECam that requires only modest development of proven technologies with the goal of minimizing the construction time and costs while maximizing the scientific potential. Table 1 contains a summary of the DES survey parameters and the expected performance of the CTIO site and DECam.  Figure 2 shows a cross section of DECam and a picture of the Blanco telescope.  DECam will replace the entire prime focus cage of the Blanco and attach to the existing spider support fins. The major components of DECam are a 520 megapixel optical CCD camera with vacuum and cryogenic controls, a compact low noise CCD readout system housed in actively cooled crates, a combination shutter-filter system to house the shutter, the four DES filters (g,r,i,z) plus slots for two additional filters that could be provided by the observer community, and a wide-field optical corrector (2.2 deg. field of view). The CCD vessel and corrector are supported as a single unit by a 6x6 hexapod that will provide lateral adjustability as well as focus control. Note that the prime focus cage of the Blanco can flip such that the F/8 mirror that is mounted to the back of the cage, behind the CCD vessel, points towards the primary mirror for Cassegrain observations. DES will maintain this capability by attaching the existing F/8 mirror to the back of the new DES prime focus cage.

The DES survey strategy is based on taking multiple short exposures (100 - 400 sec) and adding them together to reach the required depth in each filter pass-band.  This strategy minimizes the systematic uncertainties resulting from effects such as atmospheric variations.  In the first two years we plan to tile the entire survey area multiple times to enable early scientific results.  To maximize the total time available for exposures, we plan to read out the image CCDs while the telescope is slewing to a new position.  Current measurements indicate that the time it takes for a typical DES slew of 2 deg. is

Table 1  Parameters of DECam, the Blanco Telescope, and the CTIO site

| Blanco Effective Aperture/ f number @ prime focus | 4 m/ 2.7 |
| --- | --- |
| Optical Corrector Field of View | 2.2 deg. |
| Corrector Wavelength Sensitivity | <350-1000 nm |
| Filters | SDSS g, r, i, z (400-1000 nm) |
| Effective Area of CCD Focal Plane | 3.0 sq. deg. |
| Image CCD pixel format/ total # pixels | 2K X 4K/ 520 Mpix |
| Guide, Focus & Alignment Sensor CCD pixel format | 2K X 2K |
| Pixel Size | 0.27 arcsec/ 15 μm |
| Readout Speed/Noise requirement | 250 kpix/sec/ 10 e |
| Median Site Seeing Sept. – Feb. | 0.65 arcsec |
| Delivered Image Quality (DES instrument + telescope) | 0.55 arcsec |
| Limiting Magnitude: 10( in 1.5” aperture assuming 0.9” seeing, AB system | g=24.6, r=24.1, i=24.3, z=23.9 |
| Limiting Magnitude: 5( for point sources assuming 0.9” seeing , AB system | g=26.1,r=25.6, i=25.8, z=25.4 |

Figure 2.  Isometric view of the DECam (the DES prime focus instrument) with a picture of the Blanco telescope

~35 sec.  Upgrades planned by CTIO for the telescope control system as discussed in section 4.2 will likely reduce this to ~ 20 sec.  At the projected CCD readout rate of 250 kpix/sec, the total readout will take 17 sec and will fit within the improved telescope slew time. We plan to read out the alignment and focus CCDs with the image CCDs to allow for image by image corrections.  Currently at the Blanco, observations are interrupted 2-3 times/night to correct the telescope focus and the corrector-primary mirror alignment is checked and adjusted every few months.  Experience with DECam on the Blanco will determine the frequency at which corrections are needed to maintain the best image quality. The guide CCDs need to provide signals to the telescope controls system at a rate of ~ 1 Hz.  To achieve this rate, exposures of ~ 0.5 sec are envisioned and only a small area centered on the guide star will be read out.

### CCDs and Focal Plane

To obtain z-band images efficiently for high-redshift (z~1.3) galaxies, we have selected the fully depleted, high-resistivity, 250 micron thick CCDs that have been designed and developed at the Lawrence Berkeley National Laboratory (LBNL). The thickness of the LBNL design has two important implications for DES: fringing is eliminated, and the quantum efficiency (QE) of these devices is > 50% in the z band, a factor of 5-10 higher than traditional thinned astronomical devices. Figure 3 shows the QE of the LBNL CCDs compared to the CCDs currently in the Mosaic II camera on the Blanco. Several of the LBNL 2k x 4k CCDs of this design have been successfully used on telescopes, including the Mayall 4m at Kitt Peak and the Shane 3m at Lick Observatory.

Figure 3. Quantum Efficiency of the LBNL CCDs and the CCDs in Mosaic II

LBNL developed this CCD design in its MicroSystems Lab processing facility on 4-inch wafers.  For DES we have chosen to follow the CCD acquisition model that has been developed by LBNL for the SNAP devices.  In this model, the wafer vendor performs the first 8 steps in the CCD processing on 650 micron thick 6” diameter wafers.  The wafers are then delivered to LBNL for thinning to 250 microns and the final three process steps.  For DES a new wafer layout, shown in Figure 4, containing four 2kx4k devices on a single 6” wafer was required to keep the processing costs to a minimum (previous wafer layouts had only two 2kx4k devices per wafer).  The DES wafer layout also incorporates a 2kx2k device and eight 0.5x1k devices.   The DES focal plane, also shown in Figure 4,

Table 2  DES CCD Specifications Compared with LBNL CCD Performance

|  | LBNL CCD performance | DECam Requirements |
| --- | --- | --- |
| Pixel array | 2048 ( 4096 pixels | 2048 ( 4096 pixels |
| Pixel size | 15 m ( 15 m | 15 m ( 15 m |
| <QE (400-700 nm)> | ~70% | >60% |
| <QE (700-900 nm)> | ~90% | >80% |
| <QE (900-1000 nm)> | ~60% | >50% at 1000 nm |
| Full well capacity | 170,000 e- | >130,000 e- |
| Dark current | 2 e-/hr/pixel at –150oC | <~25 e-/hr/pixel |
| Persistence | Erase mechanism | Erase mechanism |
| Read noise | 7 e- @ 250 kpixel/s | < 10 e- @ 250kpix/s |
| Charge Transfer Inefficiency | < 10-6 | <10-5 |
| Charge diffusion | 6-7 m | < 7 m |
| Linearity | Better than 1% | 1% |
| Package Flatness | < 10 microns | < 10 microns |

will consist of sixty-two 2K x 4K CCDs (0.27”/pixel) arranged in a hexagon covering an imaging area of 3 sq. degrees.   Smaller format CCDs for guiding (G), focusing (F) and alignment (WF) are located at the edges of the focal plane.

The wafer layout was completed in the spring of 2005 and the first devices from the DES wafers were delivered to LBNL in the summer of 2005. The 2kx4k devices on the fully processed wafers are tested on a cold probe station at LBNL, then shipped out for dicing and delivery to Fermilab.  The first 5 wafers of fully processed 250 micron thick devices arrived at Fermilab in November 2005 and an additional 4 wafers arrived in Feb. 2006. These engineering grade devices are being characterized and used for development of the packaging and testing procedures. They have also proved useful for optimizing the processing procedures at the wafer vendor and LBNL.  Table 2 shows the DES CCD performance requirements along with the results that LBNL achieved using devices of the same design.  The preliminary characterization of the DES CCDs at Fermilab is discussed below and in Reference . The first science grade DES devices are expected in Oct. 2006. The preliminary estimate of the yield for science grade devices is 25% based on an LBNL study of devices procured with this business model for SNAP.

Figure 4 A wafer of DES CCDs showing the 2kx4k, 2kx2k and small test CCDs. The DES Focal plane is shown on the right.

The CCDs will be packaged and tested at Fermilab, utilizing the experience and infrastructure associated with construction of silicon strip detectors for the Fermilab Tevatron program.  Early packaging effort has emphasized construction of simple pictureframe-style modules.  Six different pictureframe types have been assembled, allowing the testing of three different CCD sizes in either front- or back-side illuminated configurations. Figure 5 shows all six pictureframe types.  The window opening sizes and trace layouts correspond to the three different sensor sizes.

Figure 5 Six different pictureframe package types are shown.  The upper row is front side illuminated, the bottom row is backside illuminated.

The CCDs are held in place in the window opening by an aluminum nitride (AlN) ceramic support piece that is epoxied to the pictureframe board.  AlN is a good match to silicon in thermal expansion coefficient and minimizes thermally induced distortions.  As of  June 1, 2006, a total of 68 pictureframe modules have been constructed.  These devices have been extremely useful for gaining experience with CCD handling and packaging and for development of the CCD testing facility.

Figure 6 A complete pedestal package showing the CCD, the AlN readout board, the AlN spacer and the Invar foot.  A 37 pin Nanonics connector is located in the center of the device and is accessed through a hole in the foot. A temporary shorting plug is inserted into the connector.

The CCDs in the DES focal plane will be assembled into a 4-side buttable package, called the pedestal package. The initial version of the pedestal package for the 2k x 4k devices builds on techniques developed by LBNL and Lick Observatory.  Design of the packages for the guide and focus CCDs will follow the 2k x 4k development.

The pedestal package consists of 4 main parts as shown in Figure 6. The CCD itself is oriented with its backside, which has an antireflective coating, towards the incoming light.  This face must be flat and have a uniform height relative to the modules mounting surface. Specifically, the pedestal package specifications are that each CCD module have a flatness on 1 sq. cm scales < 3 microns and adjacent 1 sq. cm areas < 10 microns. All the CCD surfaces are required to be within 25 microns of the mean focal plane. Careful matching of the thermal expansion coefficients is required to achieve this level of flatness when the CCD modules are cooled to an operating temperature between -100 and -150 deg.C.  A confocal chromatic inspection system has been developed to precisely measure flatness over a grid up to 300 x 300mm.  Reference  describes the details of the CCD packaging procedures and flatness measurements.  As of June 1, 2006, 3 pedestal packages have been constructed and one device has been fully measured at -121 deg. C. The fine-grid flatness measurements of this device indicate that it has deviations of ~ 15 microns peak to peak and does not meet the specification. Construction and measurements of additional modules are in progress and improvements to the design are being investigated.

Due to the large number of devices that will need to be packaged and tested, an emphasis on ease of assembly and handling is incorporated into the design. Once a module is complete, it is removed from the gluing fixture and transferred to a storage box as shown in Figure 7.  In order to minimize device handling, the storage box design allows testing without removal of the CCD.  The box interfaces directly with the testing dewar and allows access on the underside to the module’s connector.  After cabling the module and fastening the box to the test dewar coldfinger, the box cover is removed and the vessel is sealed.

Figure 7  Module installation into a storage box.

### CCD Characterization

CCD testing and characterization is currently being performed at Fermilab using the Monsoon readout system developed by NOAO. The characterization of the CCDs at LBNL used a Leach controller and we have also set up a similar system at Fermilab to provide cross checks and comparisons of performance.  In March 2006 we achieved 6.5e noise operations with the Monsoon system and a DES CCD at a readout speed of 160 kpix/sec.   This is currently our default CCD testing readout speed. Modifications of the pixel readout sequence have been studied and the best performance obtained so far was 192kpix/sec with 10e noise. The noise introduced by the Reset pulse into the CCD has been identified as the main limitation in the noise performance at high speed. The next step for improving the noise performance is the installation of active electronics closer to the CCD (i.e., adding a preamplifier mounted in a small board next to the detector).

We have designed and carried out tests on DES CCDs for all of the specifications listed in Table 2. The test equipment includes three small vacuum dewars that allow us to cool CCDs to their operating temperatures; optical equipment including light sources, filters and shutters; and two Monsoon crates and a Leach controller, with controls software for automatic sequencing of test procedures, for readout.  Figure 8 shows the photon light curve: the number of ADC counts versus exposure time using a flat-field white-light source. This test allows us to calculate the CCD linearity and well-depth, and count the number of hot or dead pixels.  Figure 9 shows the photon transfer curve, from which we extract the gain. Figure 10 shows the relative quantum efficiency (QE) for a DES CCD, as measured at Fermilab, in comparison with measurements of a similar 250-micron thick, backside illuminated CCD at LBNL. We see that the key feature, that of high quantum efficiency at 1000 nm, is evident and that the results are in qualitative agreement at all wavelengths. Other tests allow us to optimize the clock and bias voltages, calculate the charge transfer inefficiency (CTI), and measure the charge diffusion.4

Figure 8 The mean number of ADC counts in a DES CCD versus the length of time of a flat field exposure and the deviation from linearity from the same.

Figure 9 Photon Transfer Curve  of a 250 micron, backside illuminated DES CCD. The photon transfer curve shows the variance as a function of the mean, obtained by taking a series of exposures of increasing time length. The slope of this curve is the gain, in units electrons per ADU.

.

Figure 10 Relative Quantum Efficiency vs. wavelength in nm for two DES CCDs. The green circles are the measurements made on a 250 micron thick, backside illuminated CCD similar to the DES type. The blue crosses are measurements, made at Fermilab, at five different sub-surfaces of a DES CCD, normalized at 900 nm.

Before the wafers are diced and shipped to Fermilab, LBNL performs detailed cold probe testing of the 2kx4k devices at a temperature of -65 C.  These tests provide an early indication of the potential yield by finding problems such as inoperative readout channels, as well as blocked, dead and hot areas.  These results are only an estimate of the device performance since some types of defects, such as the blocked or dead columns, may freeze out when the CCDs are operated at -100 C or below. The cold-probe results are also useful for selecting which devices to package.  Thus far, at Fermilab, we have temporarily withheld the best 2k x 4k CCDs (approximately 25%) while we develop our packaging and testing procedures.   Once these have been fully established, these “good” devices will used to establish the packaging and testing yield.

### CCD Readout Electronics for DES

The Monsoon readout system in use for the CCD characterization tests is also the choice of the collaboration as the system to use in the DECam itself.  However, some modifications to the system are required Although the Monsoon architecture was designed to be compact and low power, it is still too large to accommodate the number of channels required by DES at the prime focus and we are investigating a number of options.  A technical review panel commissioned by the collaboration has recommended that we go forward with a compressed design based on Monsoon, but customized to meet the specific needs of the DES.  The purchase of a commercial Leach system, at a density expected to be available soon, was characterized by the panel as a viable fallback solution.

Each DES CCD has two video readout channels (U/L) and requires connection to 15 clock inputs, and 7 bias voltages. In addition, each CCD has a 4-wire temperature sensor on the AlN circuit board that will be used to track the CCD temperature during operation.  The NOAO Monsoon system consists of 3 boards: a Master Control Board (MCB), a Clock and Bias Board (CBB) and an 8-channel video card (ACQ).  The MCB is used to communicate with host computer and control the crate.  The communication link is via Systran FibreXtreme SL100/SL240 Series cards. The CBB produces 32 clocks, 36 bias voltages and 8 fast bias voltages.  The 8-channel card produces 32 Bias voltages and has 8 analog channels.  To fit in the prime focus cage, we have assumed that the CCD performance will not be degraded if 1) the voltage levels of like clock signals are shared on both sides of the CCD are tied together and 2) these clock voltage levels are common to groups of 3 CCDs. With these assumptions and the addition of fanout buffers, each CBB can provide the clock signals for 9 CCDs.  We are also compressing the 8 channel ACQ board design to make room for a total of 12 analog channels.  This 12 channel board will also contain the circuitry to handle the temperature sensors on each device.  With these modifications the readout for the DES focal plane will fit into three 10 slot dual backplane crates.  To provide guide signals to the telescope, the guide CCDs will be operated independently of the image CCDs by locating their readout on a separate backplane. Each 10 slot crate is split into a 4-slot and a 6-slot backplane.   A 4-slot backplane can readout up to 9 CCDs and will contain one MCB, one CBB and two ACQ.  Each 6-slot backplane can read out up to 18 CCDs and will contain one MCB, two CBB and three ACQ.  The guide CCDs will occupy one of the 4-slot backplanes.  The remaining backplanes can accommodate the readout for up to 72 CCDs.  Further options for customization for DES include removing the unused bias circuitry from the CBB and replacing the Systran communications link with an S-LINK system.

The CCD readout crates are estimated to have a power consumption of about 400 watts per crate.  The specification for thermal control requires that the crates will be located in thermally controlled housings.  These housings will maintain the CCD electronics at a constant temperature to ensure constant gain performance.  The outside of the housing will follow the ambient night temperature to avoid creation of thermal plumes in the optical path.  A liquid coolant, likely a water alcohol mixture, will be transported to these housings through insulated lines to remove the heat from the electronics.

### CCD Camera

The camera vessel contains the last element of the optical corrector (C5, see below) and the CCD focal plane array.  The current design uses a Liquid Nitrogen (LN2) dewar that is connected to the focal plane support plate by copper straps.  Each strap will have a temperature monitor and a heater that can tune the temperature of the focal plane support plate. The CCD operating temperature will be between -150 deg. C and -100 deg. C and will be determined by study of the dark current and quantum efficiency as a function of temperature. Finite element models indicate that with 12 straps the focal plane support plate temperature can be uniform to <2 deg. C across the 525 mm diameter focal plane. The C5 lens is athermally constrained within a stainless steel cell using radial High Density Polyethylene (HDPE) spacers that are sized to compensate for the CTE difference between the lens and the cell. The C5 cell mounts to the front flange of the camera vessel with an o-ring seal between the lens and the flange. The CCD array is attached to the vessel using bipod style mounts. The bipods mounts thermally isolate the array from the rest of the vessel and locate the array with respect to C5. The CCD vessel has a 61 cm diameter and is approximately 84 cm in the axial direction.  Figure 11 shows the CCD vessel along with the CCD readout crates that are mounted to the outside of the vessel. The cooling straps, bipods and the feed-thru board for the CCD readout signals are shown on the left side of the figure.   A full sized prototype camera vessel is currently under construction.  It will provide the test bed for multi-CCD readout in an environment very close to what is anticipated for the final CCD vessel design.

Figure 11. Cutaway view of the DES CCD vessel and a view of the internal features

### Optical Corrector

The optical corrector design consists of five fused silica lenses that produce an unvignetted 2.2o diameter image area. The largest element (C1) has an optical clear diameter of 950 mm. The last element (C5) is the window on the CCD vacuum vessel. The shutter and filters will be located in the optical path between C3 and C4. The space is sufficient to allow a stacked filter changer and shutter to be packaged in a single housing to maximize the stiffness of the corrector barrel. The filters will be ~570 mm in diameter.  Studies indicate that an Atmospheric Dispersion Corrector (ADC) is not required to achieve the science goals for DES and thus the DECam optical corrector does not include one.

The optical design of the camera has been carefully considered to optimize performance requirements of the survey as outlined in Reference 2 and to minimize the risks associated with fabrication and assembly.  The camera design is a Wynne-style, 4-element corrector with a field-flattening dewar window and all fused silica elements.  Two of the surfaces are aspheric: the concave surface of C2 and the convex surface of C4.  These are necessary to obtain the high image quality over the full 2.2 deg diameter field of view and wide wavelength range (0.4-1.1microns), as required for the DES science goals, without increasing the mechanical complexity of the camera by adding elements or increasing the length of the camera, and with it, the size of the elements.  The surface characteristics (slope and aspheric deviation) of these aspheres are well within the range which can be easily fabricated by vendors in both the US and Europe.   The largest element, C1, is also well within the demonstrated range of fabrication by our vendors. A schematic of the corrector elements is shown in Figure 12.

Figure 12 The DECam optical corrector.

The most important performance issues for the DES science goals are image quality and scattering characteristics (ghosting) over the full field and wavelength range.  The optical design produces images with an rms radius of 8.5 microns (0.15 asec), averaged over the full field and wavelength range.  This is sufficiently small that it will contribute less than 10% to the median image size resulting from atmospheric effects.  Variations in scattered light will be smaller than 3% across the length of a CCD in the focal plane. This is sufficient to meet the photometric goals of the survey. The anticipated image budget and other details of the design and performance are discussed in Reference 8. Figure 13 shows the spot diagrams for the design.

Figure 13 Spot diagrams for the DES optical design. Configs 1-4 correspond to the g,r,i,z filter band passes.

Coatings for the optics are necessary in order to reduce reflection losses at air-glass interfaces. In the DES optical design, each uncoated surface produces a loss of  ~3.5%. Without coatings, the total loss through the 5-element corrector would be about 30%.  A second reason for minimizing reflection losses is the impact on ghosting. The high reflectivity of CCDs (~ 15%) combined with the large number of surfaces in the design mean that ghost images of single stars and the diffuse night sky from the focal plane deserve attention.

There are two basic options often used in astronomical applications for coating optics this large. The preferred method for the central elements (C2-C4) of the corrector is some form of Sol-Gel coating. This is a semi-hard coating with excellent performance which is relatively easy to deposit on optics this large. The other option is a hard dielectric coating such as a 1/4 wave of MgF2.  This type of coating would be tolerant to moisture (e.g. potential condensation on the dewar window) and could be cleaned if necessary without damaging the coating. The MgF2 coating is the preferred option for the dewar window (C5) and the first element (C1). Typically Sol-Gel coatings reflect ~0.8% of the incident light and MgF2 coatings reflect ~1.5%. These reflectivities and their impact on ghosting have been incorporated into the optimization of the optical design.

The lenses will be mounted into cells and then into the corrector barrel.  Detailed design of the cells and the barrel is in progress. A conceptual design of the corrector barrel is shown in Figure 14.   The corrector barrel will consist of two large pieces that bolt together.  A conical section supports C1. A cylindrical section supports C2, C3, and C4 as well as the combined filter-shutter system.  In earlier designs the shutter was located at the end of the cylindrical section, just in front of C5, at the connection between the corrector and the CCD vessel. The new location, just in front of C4 allows significant improvement to the strength of connection between the corrector and the CCD vessel.

Table 3  Weight of the DES components

| Component | Weight (kgs) |
| --- | --- |
| Barrel | 820 |
| CCD vessel inc. C5 | 590 |
| C1,C2,C3,C4 + cells | 475 |
| Filter+Shutter Cartridge | 390 |
| Total | 2275 |

The material chosen for the corrector barrel is steel and the weights of the various DES components are shown in Table 3.  A preliminary Finite Element Model (FEM) of the barrel and CCD vessel has been used to estimate the deflections of each of the lenses under gravity loading.  Reinforcing tubes have been added around the filter-shutter system with the goal of keeping the deflections of C1 and the focal plane to < 25 microns. The results of the FEM have been fed into a sensitivity analysis of the optics to generate an estimate of the resulting changes to the image quality and the initial indications are that the design is sufficiently stiff.  Future work will include a more detailed FEM and will investigate making the barrel and CCD vessel stiffer and lighter.

Figure 14  Conceptual Design of the DES Corrector Barrel

The leading candidate for the DECam shutter is a design developed by the Hoher List Observatory, at Bonn University. The shutter has sliding blades (a “flying slit”) for fast exposures and to obtain equal exposure times in both directions of travel.  The DES filters will be ~570 mm diameter and 10-30 mm thick.  The main challenge in filter fabrication is expected to be uniformity over this large area.  Other projects such as PanSTARRS, LSST, the WIYN ODI and the Discovery Channel Telescope have similar requirements.  DES has developed a set of detailed filter specifications that has been sent out for budgetary quotes.

The filter cartridge will house the four DES filters and up to two guest filters.  As shown in Figure 15, there are three cassettes in the cartridge. Each cassette houses two filters with one filter at each end of the cassette. It will also be possible to swap in alternative filter cassettes during the day if cassettes are provided by the community users of the camera. The cartridge and the corrector barrel are purged with dry nitrogen to maintain a slight positive pressure and constant dry environment. The cartridge system places the filters at different positions in the optical path. Initial feedback from the filter vendors indicate that the filters may be as thick as 30 mm and with the addition of the mechanical housings this will produce ~ 56 mm offsets between the filters in different cassettes.  The optical beam is roughly a constant diameter in this region and we expect that all the filters will be the same size.  Allowing space for 2 user community filters minimizes the number of times an alternative filter will need to be installed, thus minimizing the risks associated with handling and storage.

Figure 15 Filter and shutter housing conceptual design.

### Prime Focus Cage and Alignment

The current conceptual design for the support and position adjustment of the camera/barrel assembly in the prime focus cage incorporates a hexapod.  As shown in Figure 2, the base of the hexapod would be mounted to a ring built into the prime focus cage.  The corrector would be attached to the top of the hexapod using the front plate of the filter/shutter assembly.  Note that the CCD vessel is aligned and bolted to the corrector and the combination camera/barrel system moves as a single unit. A hexapod system will provide the focus adjustments and has the capability to provide additional degrees of freedom, if it were deemed necessary to keep the corrector aligned to the primary mirror. Serial/stacked adjustable support systems are also being evaluated as an alternative to the hexapod.

The focus and alignment CCDs will be mounted above and below the nominal surface of the focal plane. Comparison of the out-of-focus images above and below the focal plane will indicate the direction of motion needed to bring the image back into focus. The alignment CCDs and a variant of the “donut” method now under development at CTIO for the SOAR telescope will be used to monitor the alignment of the corrector to the primary mirror.  The focus and alignment CCDs will be read out with the image CCDs providing image by image information on the telescope focus and alignment.  An initial study  describes the derivation of alignment and focus corrections from simulations of donut images.

In Oct. 2005, digital micrometers were installed on the primary mirror.  These allow constant monitoring of the mirror position and movements. DES also plans to install a BCAM system which will directly measure the relative positions of the mirror and the corrector without needing to operate the CCDs.  Information from one or both of these systems will be used in conjunction with the alignment CCDs to determine if the corrector needs to be moved laterally in the cage to be better aligned with the primary mirror.

### Survey Image System Process Integration (SISPI)

DES mountain top software is called the Survey Image System Process Integration (SISPI).  SISPI is the set of processes that will coordinate image acquisition and deliver images to the data management system for processing.  Figure 16 shows the top level relationship between the various processes that control CCD readout as well as the other instrument components (such as the shutter and filters).  Telescope and dome control processes are being developed independently by CTIO staff and are indicated by the “TCS” box in the figure.  Similarly, the Sky Camera (SkyCam) and data management (DM) are external to SISPI and are shown as elements with which the SISPI software will interface.  One of the principal SISPI design tasks is the definition and implementation of efficient interfaces between the various software elements.

Figure 16 A Schematic Diagram of the DES SISPI Software

Observation control (OCS) forms the core of SISPI.  It will coordinate the operation of the camera hardware and software.  It will know the state of DECam at all times, in order to be able to respond appropriately to all commands it receives (whether from a human operator or an automatic sequencer).  The structure of DECam operation lends itself to thinking of the OCS as a state machine.  This paradigm applies as well to calibration and diagnostics operation as it does to science data taking.

Command and status communication between SISPI processes and between DECam and the telescope will use a standardized message protocol.  We are considering adopting the system developed by CTIO for use at SOAR, although we are also looking at other solutions, such as EPICS and PVSS II. One advantage of the SOAR system is that, because it is supported by CTIO, it will be more convenient for community use during the 70% of telescope time that is not allocated to DES.

## Improvements Planned for the Blanco Telescope and the DECam Instrument

The median delivered image quality at the Blanco Telescope at present, corrected to V-band and zenith, for long exposures with the prime focus Mosaic Imager is 0.9 – 1.0 arcseconds.  The DECam-Blanco combination should do better from a combination of features of DECam itself, together with a number of additional upgrades and enhancements to the telescope and its environment.  We hope to substantially close the gap between the image quality achieved by the Mosaic Imager, given above, and the median image quality of the Cerro Tololo site itself, 0.65 arc seconds.  However it is important to note that all Dark Energy Survey simulations have conservatively assumed current performance characteristics

The following factors relating to DECam should allow improved optical performance compared to the present Mosaic Imager.

(i) The Blanco telescope primary mirror active-optics control loop will be closed using alignment CCDs integrated into the DECam focal plane. The method used will probably be a variant of curvature sensing (the “donut” method) now under development at CTIO for the SOAR telescope. This will allow DECam focus to be precisely maintained, and thus provide point spread function stability, on an exposure-by-exposure basis.   Small corrections to remove higher-order aberrations such as spherical aberration and astigmatism will likely be made on a slower time-scale (e.g. hours).

(ii) Relative motions of the prime focus cage and primary mirror due to telescope flexure will be measured and checked against an FEA model to estimate the need for active compensation to be built into DECam to maintain alignment and thus eliminate decentering coma.

(iii) The existing Mosaic Imager has no overall thermal control. A full thermal management model for DECam will be developed, and control equipment will be implemented, including liquid coolant lines and air ducts as necessary to make the instrument as thermally neutral as possible. Cooled environments for instrument electronics and for off-telescope equipment such as a cryocooler compressor will be provided.

(iv) The existing prime-focus optical corrector is thought not to achieve its designed optical performance, particularly as one element is damaged. DECam will incorporate a new optical corrector with modern design features not previously available, including SolGel coatings.

The following improvements relate to the existing telescope and its environment.

(i) The environment control system will be evaluated, and options developed for improving the thermal properties of the telescope and dome. A cost-benefit analysis will decide which, if any, of the proposed options will be implemented.

(ii) The telescope control system (TCS) will be upgraded or replaced, prior to the delivery of DECam. This will improve reliability through replacement of aging systems and improve performance in areas critical to the Dark Energy Survey – in particular, investigations have shown that it is feasible to drive the telescope the required 2 degree step between DES fields within the readout time of the camera (~17s) so that telescope slews will not limit survey efficiency.

(iii) Metrology of the prime focus mirror as a function of orientation has shown that the mirror moves in its cell by an amount sufficient to introduce detectable coma. The probable cause has been identified and a definitive fix is in development to be installed during 2007-2008.

## Survey Planning and Simulations

The DECam project will produce both simulated and real data for input into the Data Management system. The catalog and image simulations will help us develop our science analysis codes and data reduction pipelines prior to the start of survey observations. Moreover, the simulations will allow us to validate our analytical forecasts of dark energy parameter constraints, as well as to extend our analyses to comprehensively characterize and incorporate the various sources of statistical and systematic errors inherent in each of our 4 key project techniques. We plan to have yearly cycles of new catalog and image simulations, followed by science analysis and data reduction challenges carried out using the simulation outputs. The level of scale and sophistication involved in each round of simulations will improve, in order to meet the requirements set in conjunction with the science analysis goals of the key project science working groups, and with the data reduction/pipeline development testing goals of the data management project.

In 2004 we produced at Fermilab the Level 0 Image Simulations (ImSim0), where we reformatted existing SDSS images to produce 220 GB of simulated DES images, in order to provide an early jump start for the data management effort to test processing pipelines.  In 2005-6 we produced at Fermilab and the University of Chicago our Level 1 Catalog Simulations (CatSim1), consisting of catalogs of stars and galaxies covering 500 deg2 of sky, based on the parent Hubble Volume N-body simulation, and our Level 1 Image Simulations (ImSim1), consisting of 500 GB of simulated science images, generated using shapelets-based rendering of astronomical objects and incorporating models of DES observing and of DECam optics and detectors.  These simulated data were used successfully to test the data management processing pipelines during the Data Challenge 1 (DC1) effort.  We are currently engaged in producing our Level 2 Simulations (CatSim2/ImSim2), where we will use a higher-resolution parent N-body simulation produced at Barcelona, generate a 5000 deg2 galaxy catalog including more realistic galaxy properties, and produce ~5 TB of simulated images using Fermilab FermiGrid computing resources and adopting improved instrument and atmosphere models.  These simulated data will be used to test recovery of the input cosmology at the catalog level  and to feed the Data Challenge 2 effort.  In 2007-8, for our Level 3 Simulations, we plan to produce suites of DES catalogs with different input cosmologies, along with simulated images corresponding to ~1 year of DES observations; these simulations will be used to test recovery of input cosmologies from both the catalog and image levels using the 4 DES key project techniques, as well to provide data to stress test the full data processing system.

## Data Management for the Dark Energy Survey

The Dark Energy Survey, with a large focal plane array and short readout time, will collect approximately 300 GB of image data per night.  The total raw image data collected by the survey will be about 200TB, and this will grow to approach 1 PB with the addition of processed data sets.  The data management is organized as a separate project, which is managed at NCSA and UIUC, and led by Joe Mohr of UIUC.   We describe it briefly here.

The data management project will take over the data processing once the images have been fully assembled on the mountaintop at CTIO.  Data management is responsible for ingesting the data into an archive located at NCSA, and for the nightly processing pipelines at NCSA which will reduce the data into processed images with calibration and necessary corrections applied.  It will also produce the object catalogs which will be used as a primary source for science analysis.

The data management project has planned a series of data challenges to exercise and inform the software development.   Data Challenges 0 and 1 have been completed, and DC2 is in the planning stage.   These activities have demonstrated prototype pipeline reduction at NCSA, using simulated data produced by the DECam project.

The funding needed for the Data Management project is primarily labor and is estimated to be ~ $5M.  University funding and in-kind contributions of effort have been identified within the DES collaboration for work on the Data Management and proposals for the remaining $1.7 M are in progress.

## In-Kind Contributions to the DECam Project

Contributions from the DES collaborators to the DECam project will be managed as in-kind contributions.

The Spanish Consortium (IFAE and IEEC at the University of Barcelona, and CIEMAT in Madrid), using funds from MEC, will be contributing design and production of the majority of the front end electronics boards needed for the DES CCD readout system.

Procurement of the corrector optics is targeted for non-DOE funds. The procurement of the glass blanks will be covered by university funds from University of Portsmouth in the UK, University of Chicago and University of Michigan. Fabrication and polishing of the lenses, as well as fabrication of the lens cells, and alignment of the lenses into the cell and the cells into the barrel will by managed by the University College London, and funded by PPARC.

An MOU with the University of Illinois was signed in 2004.  They have already made significant contributions to the CCD testing readout electronics and are prepared to lead the development of the SISPI system.

An MOU with the University of Chicago was signed in 2004. Their funds have been used primarily for development of the CCD testing systems, and the construction of a prototype full size camera vessel.

Development of MOUs with the University of Michigan, and the foreign partners are in progress and contingent upon approval and funding from the associated funding agencies.  The University of Michigan has already contributed significantly to the optical design for the corrector lenses, to the design for the filter/shutter mechanism, and to work on a design for the lens mounting.

## Project Deliverables

The final deliverables of the DECam project are:

- Simulation data sets for the data challenges

- Completed camera vessel

- Assembled and tested focal plane of 62 image, 8 alignment/focus and 4 guide  CCDs

- Assembled and tested optical corrector

- Assembled and tested primary cage with associated alignment and cooling systems

- Assembled and tested readout electronics system

- Assembled and tested auxiliary systems (sky camera, cloud camera)

- Completed and tested software and hardware for SISPI

## Value Engineering for the DECam Project

Value Management, also known as Value Engineering, is defined as an organized effort directed at analyzing the functions of systems, equipment, facilities, services, and supplies for the purpose of achieving the essential functions at the lowest life-cycle cost consistent with required performance, quality, reliability and safety.  The DECam project has applied the principles of value engineering during the conceptual design process.   We list here some examples of value engineering decisions taken in the DES design.

### CCDs

A fallback option to the LBNL CCDs  is to use the deep depleted devices that have recently been developed by the British company E2V.  The QE in the near-infrared region is about half that of the thick fully depleted LBNL CCDs.  They could be used for our survey, but the completeness of our galaxy redshift catalogue would suffer. This is a new product for E2V and only a small number of these devices have been produced.  Based on initial discussions with the company, the cost was estimated to be roughly 1.5 million more to procure the CCDs from E2V. The delivery schedule was also significantly slower (~ 3 devices/month, and not demonstrated). We believe the choice of the LBNL CCDs maximizes the science possible with the instrument while minimizing the R&D needed for this project by using CCD design and fabrication processes that have already been proven.

### Optical Design

Fused silica has been chosen as the material for the corrector lenses. There are two possible suppliers of this material and they are Corning (HPFS) and Heraeus (Suprasil). Heraeus are unable to produce a blank over 600mm in size but they are a possible supplier for the smaller lens blanks.  Other material manufacturers were approached when alternative optical designs were being considered, including Schott, Germany (NBK-7) and Ohara, Japan (S-BSL7 and BSL-7Y). Schott said that they could produce a NBK-7 blank of the required C1 size though this would involve a development process and delivery was 12 months. Ohara said that they could produce an S-BSL7 blank for C1 (though not BSL-7Y) with a 13 month delivery.

We have been in discussion with a number of optical fabrication companies in order to discuss the manufacturability, cost and schedule of the proposed design. The companies approached have been SAGEM, SESO and Tinsley. It should be stated that we are not finally committed to using any of these firms and the optics production would need to go out to tender.  Feedback from the vendors has been used in the design optimization.  The goal is to minimize the fabrication difficulty.  Examples of modifications that have been implemented in the current design are limiting the maximum spherical deviation to ~ 1mm, and a maximum slope of 1mm/50mm, and limiting the size of the first element (C1) to less than 1m diameter.

### CCD Readout Electronics

In Early 2006 the DES project director appointed an panel to examine the options for CCD readout in the prime focus cage. Below is the section of their report that addresses alternatives to the modified Monsoon system currently under development:

“Out of the different alternative options examined the conclusions are the following:

- The Leach Controller might provide a viable and commercially available alternative in case an unexpected problem with Monsoon arises.  A Leach Controller system might provide a back-up solution to substitute Monsoon providing a similar performance at an affordable cost in a timely fashion.   Once the production version of its 8-channel Acquisition board -to be released later this year, possibly by August 2006- is proven to work, using a group of Leach controllers in 12 slot housings provides DECAM with an option.  Nevertheless, a disadvantage of Leach is that, unlike Monsoon it does not provide the bias and clock telemetry which might play an important role in the camera commissioning and operation, given the large number of CCDs and the difficulty to access the instrument at the 4m PF location.  In addition, it could be that the use of the Leach controller might require the installation of the power supplies at some distance from the crates (which is the default option for Leach systems). It should be noted that out of the four issues mentioned above that need to be watched out for Monsoon, the last three apply equally to the Leach Controller.

- If the 12 channel board development were not to reach the required performance, we can use the already existing 8-channel acquisition boards as a viable option, provided the power supplies are located remotely.

- The use of the CRIC3 ASIC for the digitization of the CCD signals -using a modified Monsoon system- does not seem at this stage as a realistic option, given the different time scales and time pressures of the different developments needed. In spite of the potential advantages of such a system, the additional work needed would probably stretch the project past its intended completion date.

- The development of a compact system following the design of  MegaCam, seems not viable given the higher integration needed (about twice more CCDs in about the same focal plane surface) and due to the larger complexity required if the same cooling scheme would be used. The development of a compact cryostat allowing short cables a la MegaCam would need a major redesign of the DECam concept, possibly extending the development work beyond the date by which DECAM is supposed to be finalized.”

## Risk Management for the DECam Project

### Risks in the Optical Manufacture

There are four areas of risk for the optical manufacture. These are lens damage, incorrect figuring, material inhomogeneity and schedule overruns.

Incorrect figuring

Once the company is selected to manufacture the lenses, early discussions with the company will be held before the delivery of the blanks to agree on testing plans and documentation to minimise risk of incorrect figuring. Regular visits will be arranged during manufacture to monitor progress. The optical form as produced of the lenses will be monitored and fed back into the optical design for optimisation. The final lens element produced will then be polished to an adjusted specification to optimise the design.

Lens damage

Discussions will be held with the manufacturers to implement handling and shipping procedures to minimise damage risk. Lens cells will be designed with attachment points for protective covers to protect the lens and coating in transit. The lens cells will also be designed to interface with the SolGel coating dipping system. The procurement of spare lens blanks to cover for a breakage is being considered and a decision will be made at a later stage based on a cost/risk assessment.

Material inhomogeneity

For the smaller lenses the blank homogeneity can be measured before shipping to the polishers. In the case of the largest lens, homogeneity tests of the blank after sagging are difficult. It is proposed to test the optic in transmission when the surfaces are being figured so that low order inhomogeneities can be corrected through the polishing process.

Schedule

Contingency is built into the schedule for the optical manufacture of the lenses. The polishing firms have quoted 12 months from the delivery of the optics whilst 15 months are allowed for in the schedule. The fused silica blanks for the smaller C2-C5 lenses will be ready before the C1 blank and these can be shipped out to the polishing firm early. This will allow early delivery of polished optics to UCL for cell mounting and the delivery of the corrector barrel and lens cells to UCL is scheduled to allow for this.

### Risks in the CCD Manufacture

As described in Section 4.1.1, the DES CCDs go through three distinct stages of production during preparation for installation on the focal plane.  Testing is incorporated at the end of each stage to determine the incremental yield.  The total yield for is the number of devices that pass the detailed CCD characterization tests at the expected operating temperature of ~ -100 Deg. C.  The requirements for DES CCDs are shown in Table 2 and detailed in Reference 2.

The three stages of CCD production are processing of the wafers at the foundry (DALSA Semiconductor), processing of the wafers in the Micro Systems Lab (MSL) at LBNL, and packaging of the individual devices at Fermilab.  The first two stages follow the procedures developed for SNAP and thus benefit from the experience and vendor relationships already developed by LBNL. This section will briefly outline the risks in each of these stages and what is being done to mitigate the risks.  As part of the pre-conceptual R&D for DES, a DES wafer design was fabricated and has already been shown to work.  Thus, errors in mask design are not considered a risk to the project.  If design changes are determined to be necessary in the future, this would constitute an additional risk.

Risks associated with processing at the foundry

To keep a low dark current, the first step in the processing is the application of a gettering layer to the backside of the CCDs. A high particulate count during this step has been associated with a high number of blocked columns and occasional shorts which render a device unusable. LBNL is in the process of exploring alternatives which would make the processing less sensitive to the particulate count during this step. One option is to re-polish the wafers after the application of this layer.  This is time consuming, but has already been shown to work during the development of the CCD processing steps at the MSL. A batch of re-polished wafers has been prepared by LBNL and accepted by DALSA for fabrication of the second lot of DES wafers.  Results from this lot will be available by the end of 2006. A second option is to use a different wafer material to which the gettering layer is applied before the wafers are delivered to the foundry.  This is the preferred solution because it is much more efficient and involves many fewer handling steps.  LBNL has fabricated one lot of 18 wafers at their own expense on this wafer material, and results are expected in the next 2-3 months.

Other risks arise due to the fact that the production of CCDs for LBNL is a very small fraction (<0.1%) of DALSA’s business, and DALSA could potentially lose interest in the project or move it to low priority.

DALSA processes the wafers in boats that can hold 24 wafers. Out of each 24 wafer lot, 3 wafers are used as control wafers.  The control wafers are fully processed (all 11 steps) before delivery to LBNL.  Tests on a cold probe station at -45 and -65 deg. C can find non-functional readout channels and provide a first estimate of the cosmetic defects such as the number of blocked, hot and dead columns and pixels.  Some of these cosmetic defects freeze out at lower temperatures so this is only a preliminary estimate.  DALSA also includes test structures on each wafer and the control wafers are used to measure the test structures to determine if the processing of the lot was done correctly.

Risks associated with processing at LBNL

Out of a 24 wafer lot, 21 wafers are sent to LBNL for thinning and processing.  The first step is to send the wafers out for thinning.  Typically 0-3 wafers are broken during this process.  Frequent contacts between LBNL and the vendor are used to mitigate the risk.

Processing at the LBNL MSL has risks associated with handling and control of each processing step.  The wafers are processed in batches of up to 10 wafers at a time.  Close monitoring of each of the settings, in particular the voltages applied during the etching, has led to improvements in yield.

The LBNL MSL consists of a Class-10 clean room, all of the processing equipment necessary for CCD fabrication, and a staff of two full-time engineers and one technician.  There is a risk associated with potential equipment failures in the MSL, as there are no spares.  There is also a risk associated with the small number of personnel, because the departure of any of the staff would greatly reduce the MSL processing capability and necessitate a potentially lengthy delay while new staff is hired and trained.

After the processing is completed the wafers are tested on a cold probe station at -45 and -65 deg. C.  This provides a preliminary estimate of the yield of the thinned devices.  Some of the cosmetic defects will freeze out at lower temperatures.

After the cold probe tests, the wafers are sent out for dicing into the individual die.  Frequent contact between LBNL and the dicing vendor is used to mitigate the risks in this step.

Risks associated with packaging

The primary risk to the CCDs during this stage is damage from electro-static discharge (ESD).  Protective equipment and procedures have been put in place to mitigate this risk.  During packaging, the CCDs are glued and then wirebonded to an Aluminum Nitride circuit board using fixtures that have been developed to minimize the risk of damage from ESD, principally through connection of proper and redundant grounds.   Air-ionizers and humidifiers are used to control the static environment.  ESD field monitors are used to test for the presence of unexpected fields.  All personnel wear grounding straps and ESD-safe gowns during handling.  Once bonded, a grounding bar is inserted into the connector on the CCD package for additional protection.  The process is frequently reviewed to make it safer.

Another risk to the packaging is the loss of trained personnel. CCD Packaging is not labor intensive, but it does require training and expertise.  During the current development stage, one technician and one engineer devote a fraction of their time to the CCD packaging. Once the procedures are well established, additional technical help will be trained and incorporated into the project and sufficient equipment will be procured to support a packaging rate to match or exceed the expected delivery rate from LBNL of 5 CCDs/week.

The most time consuming part of this stage is the testing to confirm that the packaging was successful.  We will establish 5 parallel individual CCD testing setups to match the expected packaging rate.  Initial CCD characterization procedures take ~ 2 days to perform.  The data are then automatically placed in a web-accessible database and analyzed by collaborators at remote institutions.  Results of the tests are captured in standardized reports.  Currently one person on the project is trained to prepare these reports.  Additional personnel will be added as the project progresses to mitigate the risk of delays.

Schedule and Cost

The CCD procurement cost and schedule are driven primarily by the processing at LBNL. Processing at the wafer vendor can also introduce long schedule delays. Contingency is built into the schedule for the delivery of an adequate number of CCDs which meet the performance specifications.  The contingency on the CCD manufacture allows for one complete extra batch of wafers to be procured and processed.  If the projected yield of 25% or better is maintained, this extra batch would be unnecessary, and the savings would be about $1M in MIE funds and 4 months in the schedule.  The inclusion of the additional lot in the contingency allows the project to meet its baseline cost and schedule for a CCD yield as low as 19%.

# Cost and Schedule for the DECam Project

## Work Breakdown Structure for the DECam Project

Table 4 shows the DECam WBS dictionary at Level 2. The project WBS and management structure parallels the project budget structure.

| WBS | Title | Description |
| --- | --- | --- |
| 1.0 | DECAM | Design and construct the DECAM Detector. |
| 1.1 | Management | Management support, (e.g. financial and budget) travel, workshops |
| 1.2 | Focal Plane Detectors | CCDs, CCD Packaging, testing and characterization |
| 1.3 | Front End Electronics | Electronics to readout the Focal Plane |
| 1.4 | Optics | Design, procurement and assembly of the optical corrector |
| 1.5 | Opto-Mechanical System | Mechanical components: Barrel, Camera Vessel, Cooling |
| 1.6 | Survey Image System Process Integration (SISPI) | Software programs and hardware for the acquisition of images |
| 1.7 | Survey Planning | Development and simulation of survey data and the observing plan |
| 1.8 | CTIO Integration | CTIO integration with DECam and shipping management |

Table 4 WBS Structure of the DECam Project

## The Cost Range of the DECam Project

In this section, we describe the costs to the DOE of the DECam project.

After DES received stage 1 approval from Fermilab and was accepted by the NOAO BIRP committee, the DES project director initiated discussions with international partners who had the potential to make significant contributions to both the DES science and construction of DECam. The funding plan is that approximately 1/3 of the equipment costs of DECam will come from non-DOE funds such as the national funding agencies of our international partners and funds from collaborating universities.   While negotiations for this outside funding are well advanced, like the DOE funding, they are not yet certain of approval at this point.

The DECam schedule assumes that construction funding for the DECam project will arrive in FY08 and has a three-year profile through FY10.  The US and international partners are each making in-kind contributions to both the R&D and the project construction. The proposed funding profile, including overheads and using then-year dollars, is shown in Table 5.

As the table shows, the total cost estimated to execute the DECam project is $27.5 M, including all indirect costs and escalations.  We are currently assuming that $4M will be obtained from international partners and universities, and that the cost estimate for the DOE funding will thus be $23.5 M.  The contingency on the total DOE MIE cost is 68%.  We project a cost range for the DOE project of $20.5M - $29.8M, using the following assumptions.

The low end of the range is calculated by assuming a CCD yield of 50%, which would allow the removal of the contingency for the purchase of the fifth lot of CCDs and the contingency providing for its processing, packaging, and testing.   This yields a DOE project cost of $20.5M, still assuming that 4M$ will be provided from the collaboration.

Table 5   Costs in K$ for the DECam Project, including indirect costs and escalation to then-year $

|  | M&S |
| --- | --- |
|  | FY06 | FY07 | FY08 | FY09 | FY10 |
| R&D | 509 | 1,877 | 282 | 0 | 0 |
| MIE |  |  | 3,030 | 1,701 | 272 |
| Contingency | 0 | 0 | 489 | 734 | 1,223 |
|  | Labor |
|  | FY06 | FY07 | FY08 | FY09 | FY10 |
| R&D | 1,792 | 2,755 | 717 | 0 | 0 |
| MIE |  |  | 1,674 | 2,322 | 305 |
| Contingency | 0 | 0 | 733 | 1,144 | 1,982 |
|  | Total |
|  | FY06 | FY07 | FY08 | FY09 | FY10 |
| R&D | 2,302 | 4,631 | 999 | 0 | 0 |
| MIE | 0 | 0 | 4,705 | 4,023 | 577 |
| Contingency | 0 | 0 | 1,222 | 1,878 | 3,206 |
|  | Total DECam Project Costs |  |
|  | M&S | Labor | Total |  |
| R&D | 2,668 | 5,264 | 7,932 |  |
| MIE | 5,003 | 4,301 | 9,304 |  |
| Contingency | 2,446 | 3,859 | 6,305 |  |
| Total | 10,117 | 13,424 | 23,541 |  |
| % Contingency | 49% | 89% | 68% |  |
| In Kind Contributions |  |  | 4,000 |  |
| Total w/ In-Kind |  |  | 27,541 |  |

The high end of the range is calculated by assuming that we will need another full year to complete the project, with spending during that extra year at the same rate as in FY09. This calculation adds $6.0M to the baseline estimate of $23.5M and yields a total DOE project cost of $29.5M.

## The Schedule Range of the DECam Project

A schedule for the DES project was prepared and reviewed in June 2004 as part of both the Fermilab and NOAO project review process.  The procurement of the CCDs and the optical elements were identified as the critical path items for the project. Since those reviews, we have focused our resources on addressing these topics. We are on a schedule for delivery of DECam to CTIO in 2010.

The optics are one of the critical path elements primarily because of the lengthy (2-2.5yr) estimated procurement. We held a Project Director’s Review of the Optical design in February 2006 to obtain early feedback from external reviewers.  Their response to the DES design was positive and they urged us to move forward with the rest of the mechanical design.  We plan to have a review prior to procurement of the glass blanks,

and placing of the polishing contracts.

The CCDs are also on the critical path due to the estimated delivery rate (5 wafers per month plus a 3 month startup) combined with the uncertainty in the CCD yield. The silicon processing for these devices is under development, and it is difficult to estimate the final yield results until all the issues in the processing chain have been understood. Assuming the yield is 25%, production of 70 good devices would require ~ 18 months of

Table 6   Level 1 and Level 2 milestones for the DECam Project.

| Level 1 Milestones | Best Estimate | Base | Contingency |
| --- | --- | --- | --- |
| L1 - Corrector Alignment and Testing Complete | 10/7/09 | 4/14/10 | 26.4 wks |
| L1 - Camera testing complete | 9/9/09 | 3/15/10 | 26 wks |
| L1 - Acceptance Testing Complete | 3/12/10 | 9/30/10 | 28.6 wks |
| Level 2 Milestones |  |  |  |
| L2 - CD1 Directors review | 7/25/06 | 7/25/06 | 0 wks |
| L2 - 30 production wafers delivered to FNAL | 7/22/08 | 11/19/08 | 16.8 wks |
| L2 - CCD Processing and Packaging (v2) Review Complete | 9/5/07 | 1/3/08 | 15 wks |
| L2 - Final CCDs at FNAL | 1/19/09 | 5/19/09 | 17.2 wks |
| L2 - Production CCD testing complete | 4/9/09 | 8/7/09 | 16.8 wks |
| L2 - CCD readout review - go ahead for V2 | 3/2/07 | 6/30/07 | 16.8 wks |
| L2 - Production Electronics Review Complete | 2/26/08 | 6/25/08 | 16.8 wks |
| L2 - DES Front End Electronic Production Complete | 5/26/09 | 9/23/09 | 16.6 wks |
| L2 - Corrector Element Polishing Contract Awarded | 5/18/07 | 9/15/07 | 16 wks |
| L2 - Ready To Install Cells On Lenses at UCL | 5/13/08 | 9/10/08 | 16.2 wks |
| L2 - Barrel and C5 Cell Arrive At UCL From Fermilab | 12/15/08 | 4/14/09 | 15.2 wks |
| L2 - Corrector Alignment and Testing Complete | 10/7/09 | 2/4/10 | 16.8 wks |
| L2 - Design Review of Camera and Cooling Complete | 12/21/07 | 4/19/08 | 15 wks |
| L2 - Camera testing complete | 9/9/09 | 12/8/09 | 12.4 wks |
| L2 - Final SISPI Software Testing Complete | 3/10/09 | 7/8/09 | 16.8 wks |
| L2 - Survey Strategy Complete | 11/20/09 | 3/22/10 | 16.8 wks |
| L2 - Acceptance Testing Ready To Begin | 1/29/10 | 4/29/10 | 12.8 wks |
| L2 - Acceptance Testing Complete | 3/12/10 | 7/10/10 | 17 wks |

processing, packaging and testing.  If the yield is significantly lower than 25%, this would force the purchase and processing of a fifth lot of CCD wafers.  That would result in a schedule delay of about 4 months, and this has been included as contingency on the schedule. By December 2006, we should have more information on the CCD yield.  This will feed directly into the project cost and schedule.   The high level schedule elements of the DECam project are shown in  Table 6. The end of the DECam project is defined by acceptance tests at CTIO, prior to installation on the telescope.   The CTIO director will determine the schedule for installation of DECam on the Blanco.

# Justification for the DECam Project

## Mission Need for a Ground-Based Dark Energy Experiment

The Mission Need Statement for a Ground-Based Dark Energy Experiment, approved in November 2005, discussed the science case for better precision in the measurement of dark energy.  It also noted the support from a recent report from the National Research Council (Connecting Quarks with the Cosmos, April 2002) and from the National Science and Technology Council’s strategic plan to respond to that report (ThePhysics of the Universe, 2004) for a dark energy program using multiple techniques from space and from the ground.   It stated:

“ A project to build a ground-based detector or facility capable of studying dark energy will support the Department of Energy’s Strategic Plan dated September 30, 2003: To protect our national and economic security by providing world-class scientific research capacity and advancing scientific knowledge.  Specifically, it will support the two Science goals: 1) Advance the fields of high-energy and nuclear physics, including the understanding of dark energy… and 7) Provide the Nation’s science community access to world-class research facilities…”

The Mission Need statement then identified three options that could provide complementary ground-based measurements of dark energy as the next steps in a robust dark energy program.  We believe Option 1 offers the fastest approach to make the next step in increasing our understanding of dark energy.  Option 1 was described as:

“Construct a large-scale charged-coupled device (CCD) camera for galaxy cluster counting and other dark energy measurements. The camera could be installed on the Blanco 4m Telescope in Chile. The combination of this telescope and camera with the necessary sensitivity will make it more than 10 times more powerful than any existing facility. In combination with galaxy cluster mass measurements from other telescopes, the data would provide the first high precision (5 – 10% statistical errors) dark energy constraints.”

The National Optical Astronomy Observatory (NOAO) issued an announcement of opportunity (AO) in December 2003 for an open competition to partner with NOAO in building an advanced instrument for the Blanco telescope in exchange for awarding the instrument collaboration up to 30% of the observing time over a five-year period for a compelling science project.  In response to this AO, the Dark Energy Survey (DES) Collaboration was formed and submitted a proposal to NOAO in July 2004 to build DECam, a new wide-field imager for the Blanco, with the goal of carrying out a survey to address the nature of the dark energy using the four primary techniques described below in Sec. 6.2. The Blanco Instrumentation Review Panel convened by NOAO to review the DES proposal in August 2004 concluded that the scientific goals are exciting and timely. Subsequently, the NOAO Director asked the CTIO Director and the DES Project Director to draft an MOU among the Parties that would define the terms of the partnership.  Since that time, the Dark Energy Survey collaboration has further developed the ideas in the proposal and has been strengthened by the addition of strong partners from two international consortia  and from US universities.  The collaboration has conducted R&D to determine more firmly the feasibility of the project, and is now ready to request the next level of approval for the project to construct an instrument which would meet the need expressed in Option 1.

## How the DECam Project Satisfies Option 1 in the Mission Need Statement

Option 1 of the Mission Need statement calls for a new large CCD camera to be installed on the Blanco 4m Telescope.  This describes the core of the DES project.  Option 1 also calls for a project capable of improving the statistical precision of our knowledge of the dark energy equation of state to 5-10%, by the use of multiple, complementary techniques. The four techniques which DES proposes to use for probing dark energy are well-matched to the requirement for better precision in the intermediate time scale.  These techniques are described briefly, below, and in more detail in Reference .

Galaxy clusters: The evolution of the galaxy cluster mass function and cluster spatial correlations provide a sensitive probe of the dark energy; these observables are affected by cosmology through both the growth of density perturbations and the evolution of the volume element,. Clusters make promising cosmological probes, because the formation of these large potential wells involves only the gravitational dynamics of dark matter to good approximation. The primary design driver of the DES is the detailed optical measurement of galaxy clusters, including photometric redshifts, in conjunction with the South Pole Telescope (SPT) Survey. The SPT will use the Sunyaev-Zel’dovich effect (SZE) to detect galaxy clusters out to large distances, providing a census of tens of thousands of clusters over a 4000 square degree region south of declination = (30o. The integrated SZE flux decrement is expected to be a robust indicator of cluster mass, because it is a measure of the total thermal energy of the electrons residing in the gravitational potential well; in particular, it should be insensitive to gas dynamics in the cluster core, . The DES is designed to measure efficiently and accurately photometric redshifts for all SPT clusters to z=1.3. It will also cross-check the completeness of the SPT cluster selection function by optically identifying clusters below the SPT mass threshold and will statistically calibrate SZE cluster mass estimates using the cluster-mass correlation function inferred from weak lensing.

Weak lensing tomography: The DES will measure the weak lensing (WL) shear of galaxies as a function of photometric redshift. The evolution of the statistical pattern of WL distortions—for example, the shear-shear (S-S) angular power spectrum—and of the cross-correlation between foreground galaxies and background galaxy shear (galaxy-shear correlations, G-S), are sensitive to the cosmic expansion history through both geometry and the growth rate of structure, . In the course of surveying 5000 sq. deg. to the depth required for cluster photo-z’s, the DES will measure shapes and photometric redshifts for ~300 million galaxies and, with improved control of the optical image quality, enable accurate measurement of lensing by large-scale structure.

Galaxy angular clustering: The DES will measure the angular clustering of galaxies (denoted G-G in Table 7) in photometric redshift shells out to z~1.1. The matter power spectrum as a function of wave-number shows characteristic features, a broad peak as well as baryon wiggles arising from the same acoustic oscillations that give rise to the Doppler peaks in the CMB power spectrum; these features were recently detected in the SDSS. In combination with CMB observations, they serve as standard rulers for distance measurements, providing a geometric test of cosmological parameters. This approach will provide cosmological information from the shape of the power spectrum transfer function and physically calibrated distance measurements to each redshift shell,,.

Supernova luminosity distances:  In addition to the wide-area survey, the DES will use 10% of its allocated time to discover and measure well-sampled riz light curves for ~1900 Type Ia supernovae in the redshift range 0.3<z<0.75 through repeat imaging of a 40 deg2 region. These SNe will provide relative distance estimates to constrain the properties of the dark energy.

In addition to these methods, cross-correlation of CMB data sets with DES galaxies as tracers of potential wells will probe the dark energy through the integrated Sachs-Wolfe (ISW) effect; this effect is included in the forecast constraints below. Finally, we note that accurate photometric redshifts are critical to the DES science goals; as a relatively shallow survey, a major advantage of the DES will be the availability of spectroscopic redshift calibration (training) samples that extend out to the flux limit of the survey.

### Forecast Dark Energy Constraints

In this section, we quantify how the DES will improve our understanding of dark energy, focusing on the dark energy equation of state parameter w. Such forecasts generally depend upon priors assumed for marginalized parameters and on assumptions about whether w evolves. The marginalized parameters include cosmological parameters other than w, uncertain astrophysical parameters that characterize a particular probe, and possible parameters describing uncorrected systematic errors associated with a particular observational method. As a result, caution must be exercised in comparing the projected dark energy sensitivity of different methods and experiments. For this discussion, we assume constant w and consider 3 cases of cosmological priors: uniform, present CMB (WMAP 1-year), and future CMB (Planck); these priors are specified in Reference 14. While models with constant w ( (1 are not theoretically well motivated, they nevertheless provide a convenient metric for comparison.  A few examples of forecasts with time-varying w are discussed in Reference 14. We also note that for varying w, for the redshift zp at which w(z) is best constrained, the constraints on w(zp) are the same as those on constant w shown below.

Table 7 Example forecast marginalized 68% CL statistical DES constraints on constant equation of state parameter w.

| Method/Prior | Uniform | WMAP | Planck |
| --- | --- | --- | --- |
| Clusters: abundance w/ WL mass calibration | 0.13 0.09 | 0.10 0.08 | 0.04 0.02 |
| Weak Lensing: Shear-shear (S-S) Galaxy-shear(G-S)+G-G S-S+G-S+G-G S-S+bispectrum | 0.15 0.08 0.03 0.07 | 0.05 0.05 0.03 0.03 | 0.04 0.03 0.02 0.03 |
| Galaxy angular clustering | 0.36 | 0.20 | 0.11 |
| Supernovae Ia | 0.34 | 0.15 | 0.04 |

In all cases considered in Table 7, we assume cold dark matter, negligible neutrino masses, adiabatic Gaussian initial perturbations with power-law primordial power spectrum, and a spatially flat Universe. We use a fiducial model with w = (1 and other parameters close to the WMAP concordance values. Further assumptions for each method are given in the remainder of this section.  The numbers in Table 7 can change as those assumptions are varied within reasonable limits and are meant to be representative.  These numbers, based on Fisher matrix and Monte Carlo analyses, indicate that each of the four methods can probe constant w with statistical errors at the 3-20% (2-11%) level for WMAP (Planck) priors, assuming reasonable uncertainties in the appropriate astrophysical parameters as noted below. In fact, we expect these methods will likely be limited by systematic errors; a description of their expected impact on the cosmological parameter error budget is presented in Reference 14.

For the cluster results, we have used the cluster counts above the 5( SPT detection limit (1.9mJy, with a beam of 1’ FWHM) in redshift bins of (z=0.1 out to z=1.5, which results in ~12,000 clusters over 4000 deg2 for the fiducial cosmology and a weakly redshift-dependent mass threshold of ~2(1014Msun. The SZE detection threshold was set this high (as opposed to, say, 3() in order to minimize the effects of sample contamination by radio point sources. We have marginalized over a 3-parameter model for the mass-SZE flux relation that includes power-law evolution with redshift beyond that expected from self-similarity, but no scatter in that relation. While this mass-SZE flux relation is rather simple, there is additional information contained in the cluster angular power spectrum and in the shape of the mass function (rather than just its integral above a threshold) that can be used to help ``self-calibrate” a more complex relation,,. Moreover, the second row of cluster constraints in Table 7 includes the statistical calibration of the mass-observable relation using the weak lensing cluster-shear cross-correlation over the mass range 4(1014 (2(1015 Msun in redshift bins from z=0.4(0.9. Finally, we have assumed that the theoretical uncertainties in the halo mass function, in the halo bias as a function of mass, and in the identification of SZE-detected clusters with dark halos are subdominant compared to the other errors; recent N-body simulations indicate that the first two assumptions are justified and planned future simulations will be needed to ensure the third (see Reference 14 for further discussion).

The forecast weak lensing constraints assume that the shear and galaxy power spectra are each measured in 5 photometric redshift bins out to z=2 (for background galaxy shear) and z=1 (for foreground galaxy positions), with a simplified but reasonable model for the photo-z errors(z)=0.05(1+z). The statistical errors come from cosmic variance and from shot noise (shape noise) corresponding to an effective background density of 10 galaxies/arcmin2 (with shape noise per shear component of 0.16); artificially degrading higher resolution images yields this source density for the DES depth and the 0.9” median seeing delivered by the Mosaic II Camera on the Blanco. If the delivered seeing can be reduced to ~0.7’’, close to the median site seeing for the DES observing months, the effective background density will increase by ~35%, with the shot noise errors in the shear-shear power spectrum correspondingly reduced. The results in Table 7 use angular information and assume Gaussian errors up to multipoles l < 1000, beyond which non-linearities in the density field become important at the typical survey depth; a more conservative (aggressive) limit of l =300 (l =3000) increases (decreases) the w constraints by ~50%. In these forecasts, the non-linear mass power spectrum is modeled by the halo model, which reproduces the results of high-resolution N-body simulations. For constraints that include foreground galaxies (i.e., G-G and G-S), 5 halo occupation parameters per foreground galaxy photo-z bin are marginalized over. These parameterize the bias of galaxies with respect to the dark matter in a manner consistent with high-resolution N-body simulations and with the observed clustering of galaxies at low redshift in the SDSS. For constraints including (G-G), the foreground galaxy power spectrum is only used to provide constraints on these halo occupation parameters.

The galaxy angular clustering constraint assumes measurement of the angular power spectrum for the foreground galaxy sample with photo-z binning and errors as above. However, it uses a more conservative range of angular information, l < 300, since baryon wiggles are washed out in the non-linear regime; compared to the first two methods, this result is more robust to uncertainties in non-linear perturbation evolution. Since this clustering constraint mainly uses the shape of the power spectrum, it is not very sensitive to the galaxy bias model. As a result, its use here is complementary to its use above in constraining galaxy bias for lensing.

The forecast supernova constraints assume SNe Ia are standardizable candles with an intrinsic dispersion in peak luminosity of 0.25 mag; this is larger than the usually adopted value of 0.15 mag and reflects an expected increase in errors due to the fact that only photometric redshifts will be available for the majority of the sample. These constraints also assume an irreducible systematic error floor in peak magnitude dispersion of 0.02(1+z)/1.8 mag in redshift bins of (z=0.1. Under this assumption, the error floor dominates over the intrinsic dispersion in the derived dark energy constraints, so there is little gain from reducing the intrinsic dispersion; with no systematic error floor, the w constraints improve to 0.24, 0.14, and 0.03 for uniform, WMAP, and Planck priors. In all cases, we have also assumed a well-measured set of 300 nearby (z<0.1) SNe Ia (being accumulated by on-going surveys) anchors the low-redshift part of the Hubble diagram.

### Systematic Errors

Table 8 lists the expected dominant systematic error sources for each method, ordered approximately from most to least important, along with the presently envisioned primary methods for controlling them.  A more detailed discussion is presented in Reference 14.

For the cluster technique, the cluster sample must be both complete (above some threshold) and free of contamination, i.e., the cluster selection function must be well understood. For the SZE, cluster selection is complicated by point source confusion, dusty galaxies, radio galaxies, primary CMB anisotropy, and chance projection of clusters at different redshifts. The systematics for DES optical cluster selection are quite different, so the two methods can be compared to understand the selection function. Prior to SPT, the SZA  (now operational) will carry out deep SZE imaging over a smaller area of sky with higher angular resolution; this will provide improved calibration of the mass-SZE flux relation and probe the SZE selection function below the SPT threshold. Prior to DES, members of our collaboration will carry out a 100 sq. deg. multi-band imaging survey with Mosaic II on the Blanco (recently approved as a 3-year survey program beginning in Fall 2005) that overlaps several planned SZE surveys (including APEX, ACT, and SPT); this survey will enable cross-comparison of the SZE and optical cluster selection functions for a fraction of the sample. In addition, we will quantify the SZE cluster selection function through a program of hydrodynamic simulations, and Monte Carlo simulations based on radio source catalogs to evaluate contamination. The cluster technique also relies on an accurate mass-observable relation; as noted above, this will be calibrated by statistical weak lensing, the cluster angular power spectrum, and the shape of the cluster mass function.

For weak lensing, the dominant systematic errors are additive and multiplicative shear systematics, uncorrected biases in photo-z estimates37,, and theoretical uncertainties in the small-scale mass power spectrum,,. Theoretical uncertainties can be controlled by nulling the small-scale information and by using improved high-resolution N-body simulations incorporating baryons.  Photo-z biases will be controlled to an acceptable level by using a pre-existing spectroscopic redshift sample large and deep enough to accurately determine the photo-z error distribution as a function of redshift. The Supplements summarize the acceptable error budget for additive and multiplicative shear systematics37 and the techniques we will pursue to reduce them to acceptable levels.

For angular clustering, the dominant systematic errors are potential inadequacy of the halo occupation description of galaxy bias (affecting the baryon wiggles), photometric calibration errors or uncorrected Galactic dust extinction correlated over large scales (leading to artificial large-scale power), and photo-z biases. Since the angular bispectrum and power spectrum have different dependences on the galaxy bias parameters, combining them will constrain those uncertainties,. In addition, since galaxy bias depends on galaxy type (color and luminosity) measuring angular clustering for different types will constrain the large-scale behavior of the bias. Correlated photometric errors will be controlled by a survey strategy that incorporates multiple visits to each field, by clustering vs. galaxy color, and by checking consistency of results across different angular sub samples.

| Method | Dominant Systematic Errors | Primary Controls |
| --- | --- | --- |
| Clusters | Sample selection Mass-observable relation | SZE + optical cluster selection; simulations Self-calibration; statistical WL masses |
| Weak Lensing | Multiplicative shear Additive shear Photo-z biases Small-scale power spectrum | Measurement algorithm; shear vs. gal. size PCA; active focus; alignment control Spectroscopic calibration sets Null small-scale power; high-res. simulations |
| Angular clustering | Bias prescription errors Large-scale photometric calibration errors Photo-z biases | Angular bispectrum; clustering by type Calibration strategy; clustering by color; angular sub samples Spectroscopic calibration sets |
| Supernovae Ia | SN evolution Photometric errors Extinction Photo-z errors & biases | Low and high z SNe comparison Calibration strategy; artificial SNe SN color and host galaxy information SN spectroscopic calib. sub sample |

Table 8 Dominant sources of systematic error and methods for controlling them

For supernovae, the major systematic errors are evolution of the supernova population, systematic photometric errors, uncorrected host-galaxy extinction, inaccurate K-corrections, and photo-z errors and biases for the part of the sample without spectroscopic redshifts. Evolution is generally controlled by comparing light-curves, colors, and spectra of high- and low-z supernovae and using the fact that the low-z sample, if large enough, should span the range of physical conditions encountered in the sample to z~1. Photometric errors will be minimized by a survey strategy optimized for uniform calibration and cross-checked by overlap with SDSS photometry on the celestial equator. K-correction uncertainties will be mitigated by having a large, nearby comparison SN sample with multi-epoch spectrophotometry. Extinction errors will be addressed by using host galaxy colors to identify a low-extinction subsample of early-type galaxies. The impact of photo-z errors is discussed in Reference 14 and is expected to be small.

Figure 17 DES Constraints on the 2-parameter dark energy equation of state.

### Combination of results

DES is able to acquire the data for the first 3 listed techniques with the same survey strategy on the same instrument.  The fourth technique, the supernova study, requires a separate survey strategy, to which we devote 10% of the observing time. The combined constraints on w0 and wa from the four techniques are shown in Fig. 17.   There are two points to note about this combination of constraints.  Of the four techniques, the BAO and SN measurements are sensitive only to the effect of cosmological parameters on geometry, while the cluster and weak lensing measurements are sensitive to their effects on both geometry and the growth of large scale structure.   Having comparable precision from the full complement of techniques, to the levels DES can achieve, should yield information that will help distinguish between different types of explanation for dark energy.  The other notable point is that the contours shown in Figure 17 are marginalized over other parameters (omega-b, etc.) and the four techniques have different sensitivities to those parameters.  It is that latter point which gives the combination of the four techniques its great power in constraining the dark energy equation of state.

# Managing the Project Responsibly

## Environment, Safety, and Health

The design, construction and testing of DECam at Fermilab will be performed in compliance with the standards in the Fermilab ES&H Manual (FESHM), and all applicable ES&H standards in the Laboratory’s “Work Smart Standards” set. In addition, all related work, including work performed off-site, will be performed in compliance with applicable federal, state and local regulations. All work done at collaborating universities will be performed in accordance with existing university policies and applicable national, state, or local regulations.

The Fermilab ES&H Section provides ES&H support for all activities at Fermilab, including guidance on ES&H issues, environmental monitoring and safety assessments.  The Particle Physics Division ES&H and Building Management Department provides additional support for specific aspects of the camera construction, through the mechanism of standing safety review panels where appropriate.

Fermilab follows the principle of Integrated Safety Management. Each person involved in DECam is responsible for following good ES&H practices in the course of his or her own work. However, in addition to these ordinary responsibilities, the DECam Project has an assigned ES&H Coordinator, who directs the preparation of hazard analyses, ES&H reviews, and associated documentation.

### The National Environmental Policy Act (NEPA)

In compliance with NEPA, the DECam Project submitted an Environmental Evaluation Notification Form, on the basis of which a Categorical Exclusion was granted on July 11, 2006.

### Safety Assessment Documents

A draft DECam Hazard Assessment Document has been prepared for this Project and will serve as the basis for the Preliminary Safety Assessment Document (PSAD) required for CD-2.  A Safety Assessment Document (SAD) will be prepared prior to installation and/or sustained operations of the completed Camera.

Although the installation of the DECam on the telescope is not part of the DECam project, life safety issues pertaining to the installation and operation of DECam have been considered as part of the life cycle assessment. In cooperation with NOAO, Fermilab will perform an assessment of life safety issues for DECam operations at the Cerro Tololo Inter-American Observatory. The assessment will focus on operations at CTIO.  ES&H procedures for installing instruments and operating the Blanco Telescope have already been established by AURA, the contractor for NOAO. A Safety Assessment Document (SAD) will be prepared prior to the delivery of DECam to CTIO.

### Integrated Safety Management Plan

The DECam Project will be executed in accordance with the principles of Integrated Safety Management (ISM) as specified in DOE P 450.4.  While direct implementation of ISM is a line management responsibility, it is also addressed at the project level.  The Project will prepare an ISM Plan, which addresses the following ISM principles.

- Defining the scope of work and identifying hazards.

Subproject managers are responsible for planning work, identifying ES&H concerns and resources needed to support the work.  The DECam Project staff meets regularly with line and safety managers to discuss planned work and establish priorities.  Progress on priority items is tracked and submitted in the monthly report.  

The project has prepared a preliminary Hazard Analysis Document.  This document and additional hazard analyses initiated by line management will be in conformance with the FESHM, Chapter 2060.

- Developing and implementing ES&H controls

Applicable ES&H Standards are integrated into all project planning documents.  Work processes are documented and reviewed. An example of a safety review for DECam construction is the Operational Readiness review conducted by the PPD safety committee for the operations of the automatic LN2 filling apparatus in the CCD testing room. We also anticipate an operational readiness review before authorizing the unattended operation of the multi-CCD test vessel.

Where applicable, the project tasks with identified ES&H hazards will specify appropriately trained workers or else the schedule will allow for adequate training.  Where possible, the project schedule will allow for dry runs of potentially hazardous or complex procedures.

- Assessing performance for continuous improvement

The project will undergo periodic ES&H reviews.  These reviews may be conducted jointly by Fermilab and the DOE, and may be part of technical reviews of subprojects rather than standalone reviews.  Reviews will generate recommendations that will be addressed by the project in a timely manner.  More details on the various reviews DECam will undergo are given in Section 10.

### Waste Minimization/Pollution Identification

Waste Minimization and Pollution Prevention (WM/P2) concepts will be embedded into all aspects of research and operations at Fermilab.  A strong WM/P2 program is an integral part of the Laboratory’s Environmental Management System.  Fermilab’s WM/P2 Program reflects Department of Energy, national and local WM/P2 goals and policies. It represents an ongoing effort to integrate WM/P2 with our research mission.

Fermilab’s WM/P2 program is anchored by three tenets commonly associated with pollution prevention objectives. They are Reduce, Reuse and Recycle.  DECam is doing all of these in the design process and will continue to during the life of the project and on through the operation of the experiment.  Specifically, the materials DECam is recycling include any discarded electronic equipment from the prototyping or production phases, via Fermilab’s lab-wide electronics recycling program.

Fermilab has a comprehensive program for the handling, storage, and disposal of both radioactive wastes and hazardous chemical wastes.  The various waste programs are described in the FESHM, Chapter 802.  DECam construction is not expected to generate any radioactive wastes.  There may be generation of chemical waste, in small amounts, and such waste will be handled according to the relevant sections of the FESHM.

## Safeguards and Securities Plan and Vulnerability Assessment

Safeguards and security will be covered under Fermilab’s existing DOE-approved program. The DECam Project will create no new security issues during design or fabrication. DECam has no special nuclear material (enriched uranium or plutonium) and no nuclear material (natural or depleted uranium). Thus extra protective measures are not required. Access to Fermilab is controlled to ensure worker and public safety and property protection. None of the work on the DES or on the DECam Project is classified. The risk of safeguards and security issues is, therefore, small. DECam is not an attractive target for terrorists, theft, or malicious action. Therefore, due to the 24/7 security force on site, Fermilab’s safeguards and security program, and the non-attractiveness of DECam as a target, the vulnerability assessment is very low.

No laboratory safeguards and security requirements will need to be changed for installation or operations subsequent to project completion

## Preliminary Plan for Demobilization of Replaced Facilities

The only facility to be replaced is the prime focus cage and contents which is currently installed on the Blanco telescope. The responsibility for unmounting and decommissioning the cage rests with CTIO, not with the DECam project.

## Preliminary Plan for Decontamination and Decommissioning

It is the policy of Fermilab to maintain information necessary for future Decontamination and Decommissioning (D&D) of any or all of the facilities at the Laboratory.  The eventual D&D of the beamlines, accelerators and other facilities at Fermilab, will be done in accordance with the provisions of FESHM, Chapter 8070.  The major facility used during DECam construction is the Silicon Detector Facility (SiDet).  The DECam project will comply with any documentation requirements regarding its use of SiDet with regard to eventual D&D for that facility.  The only hazardous material used in the construction of DECam is the black paint used on the camera vessel.  The project plans to use a paint-handling facility at the University of Chicago for the painting operation, which will completely mitigate this hazard.

The decommissioning of the DECam upon completion of the Dark Energy Survey is addressed in the Memorandum of Understanding between NOAO and Fermilab, which states:

“Upon completion of the Dark Energy Survey, the DECam will be transferred from CTIO to Fermilab, at Fermilab’s expense.  Fermilab will return the property contributed by the Collaborating Institutions in accordance with arrangements made with those institutions. AURA will retain title to its contributed equipment.  Other arrangements may be made with the interested parties before the completion of the Dark Energy Survey.

“Return of DECam hardware to Fermilab will be performed in accordance with any applicable US import control laws and regulations.”

Disposal of the DECam after its return to Fermilab will be accomplished with complete adherence to applicable sections of the FESHM.

## Preliminary Project Execution Plan

The DECam Project Execution Plan (PEP) summarizes the mission need and justification of the DECam project, its objective and scope, the Department of Energy (DOE) management structure, the resource plan, and the environmental, safety, and health (ES&H) requirements. In addition, it establishes the technical, cost, and schedule baselines for the project, as well as the DOE Baseline and Change Control thresholds. The DECam Preliminary PEP is being drafted and will be submitted to the DOE as part of the CD1 documentation review.

# Preliminary Management Control Documents

## Memoranda of Understanding

The DECam project is being carried out by the DES Collaboration. The portion of the work carried out a Fermilab is the responsibility of the Universities Research Association, which operates Fermi National Accelerator Laboratory (Fermilab) under Contract DE-AC02-76-CH- 03000. The UK-Consortium, the DES-Spain Consortium, and the US universities in the collaboration have MOUs written or in preparation to provide subsystems for DECam as in-kind contributions.

## Preliminary Project Management Plan

The DECam Project Management Plan (PMP), which is a complementary document to the PEP, describes the organization and systems that the contractor will employ to manage the execution of the project and report to DOE. Subsequent changes to the project scope, cost, or schedule exceeding thresholds defined in the PEP will be traceable, and made in accordance with the Change Control procedures described in the PEP.

# Public and Stakeholder Input

## Stakeholders in the DECam Project

The DECam Project involves the construction of a CCD camera and its associated mechanical infrastructure.  The activity of construction will be carried out at Fermilab and at collaborating institutions, in accordance with established guidelines at these institutions, as well as any applicable local, state, or federal regulations.  We do not anticipate any significant impact on the local community from the DES construction activity, so there should be no stakeholder issues from the general public.

The primary stakeholders for the DECam project are the Dark Energy Survey collaboration, and the broader astronomical community who wish to observe using the DECam instrument, or to utilize the survey data.  The understanding of the DES obligations to the astronomical community is detailed in the Memorandum of Understanding between DES and NOAO, and is excerpted in the following section.

## Community Use of DECam and Access to Data Obtained with DECam

The Memorandum of Understanding between Fermilab and NOAO provides an agreement under which the astronomical community will make use of the DECam instrument during the remaining 70% of observing time when the DES is not observing, and also provides the guidelines for public access to data from the Dark Energy Survey, as follows:

“DECam will be a facility instrument that will be available for use on the Blanco by other observers, who will be selected by NOAO through peer reviewed proposals or through the agreement between the AURA Observatory and the University of Chile. Whenever possible, the policies for the use of DECam on the Blanco Telescope will be consistent with NOAO policy for facility instruments. It is expected that up to 70% of the time could be awarded to observers through the aforementioned processes.

“CTIO, in consultation with the CTIO user community, will develop a priority list of filters in addition to those provided by the Collaboration, to enable additional community science. Purchase of these filters, and fabrication of suitable filter cartridges, will be the responsibility of CTIO. The development of calibration and reduction procedures, if different from those developed by the Collaboration and NOAO DPP for the DES, will be the responsibility of CTIO and NOAO DPP.

“The Collaboration shall deliver the raw DES data obtained with DECam and the calibrated single images produced from this data by the Collaboration to NOAO DPP 12 months after the individual observations have been taken.  The Collaboration and NOAO DPP plan to place the raw data and the calibrated single images in the NOAO Science Archive in order to make them available to the astronomical community.  NCSA and NOAO plan to distribute the raw data and the archive-ready data products through an agreement between NOAO and NCSA, using the same NCSA facilities that will be used to distribute these products to the Collaboration. The Parties agree that this arrangement is in accord with the current AURA/NOAO Data Rights Policy. The AURA/NOAO data rights policies shall also be applied to science data obtained with time awarded to other observers on the Blanco with DECam through peer reviewed proposals to NOAO.

“The final, public DES archive, which will be finished after the 5-year survey is completed, is the final program deliverable of the Dark Energy Survey.  Maintenance of the final, public DES archive, which will be part of the NOAO Science Archive, will be the responsibility of the NOAO DPP after it is delivered to NOAO.”

# Project Reviews

The DECam Project will undergo a series of reviews to monitor the progress of the cost, schedule, technical aspects and safety of the project.

## Technical Reviews

The Dark Energy Survey project, encompassing the DECam project being described here as well as the other major DES components (the telescope improvements and the data management project) will have at least one full-scale technical review annually, once approved.  For all major procurements there will be a final design review before the purchases are initiated in order to ensure that the design and specifications meet the need of the project and that value engineering principles have been applied.

## ES&H Reviews

All technical reviews cover the ES&H aspects of the project and thus the ES&H reviews may be part of the overall technical review, instead of its own standalone review.  Additional ES&H reviews may be scheduled at the discretion of the Project Manager and the PPD Division Head.  The Project Manager will address any findings of noncompliance with ES&H requirements and inform the Division Head in writing of the resolution of those findings.

## Director’s Reviews

The Fermilab Director or his designee will appoint a committee to conduct periodic reviews of the DECam Project to monitor its progress.  Director’s Reviews are held at the Director’s discretion, typically on an annual basis.   The Directors of the two other laboratories which have an oversight interest in the Dark Energy Survey, NOAO and NCSA, will be invited to participate or send representation to these reviews.

# Appendix: Acronyms Used in This Document

ADR:		Fermilab Associate Director for Research

ACQ:		Acquisition Card

AURA:	Association of Universities for Research in Astronomy

BAC:		Budget At Completion

CBB:		Clock and Bias Board

CCB:		Change Control Board

CCD:		Charge-Coupled Device

CDR:		Conceptual Design Report

CTIO: 		Cerro-Tololo Inter-American Observatory

CTIOIC:	CTIO Integration Coordinator

DECam:	Dark Energy Camera

DES:		Dark Energy Survey

DOE:		U.S. Department of Energy

DPM:		Deputy Project Manager

EIC:		Electrical Integration Coordinator

ES&H:		Environment, Safety and Health

ETC		Estimate to Complete

FEM:		Finite Element Model

FMS:		Financial Management System

FPD:		Federal Project Director

HDPE:		High Density Polyethylene

ISM:		Integrated Safety Management

MCB:		Master Control Board

MOU:		Memorandum of Understanding

MIC:		Mechanical Integration Coordinator

NCSA		National Center for Supercomputing Applications

NOAO:	National Optical Astronomy Observatory

NSF:		National Science Foundation

OCS:		Observation Control System

PCR:		Project Change Request

PEP:		Project Execution Plan

PM:		Project Manager

PMG:		Project Management Group

PMP:		Project Management Plan

PSAD:		Preliminary Safety Assessment Document

QE:		Quantum Efficiency

SAD:		Safety Assessment Document

SISPI:		Survey Image System Process Integration

SOW:		Statement of Work

SPT:		South Pole Telescope

SZE:		Sunyaev-Zel’dovich Effect

TCS:		Telescope Control System

TDR:		Technical Design Report

TEC:		Total Estimated Cost

URA:		Universities Research Association

WBS:		Work Breakdown Structure

# References

# Endnotes

DES Proposal to NOAO: https://decam.fnal.gov/NOAO04/A_Proposal_to_NOAO.pdf

DES Science Requirements and Technical Specifications Document, DES Document 20.

Holland, S. et al. IEEE Trans. Elec. Dev., 50, 225 (2003), and Fairfield, J. et al., “Improved spatial resolution in thick, fully depleted CCDs with enhanced red sensitivity,” submitted to IEEE Trans. Nucl. Sci., (April 2006).

“Testing and Characterization of CCDs for the Dark Energy Survey” J. Estrada et al, in the Proceedings of SPIE Astronomical Telescope and Instrumentation Meeting, May 24-31,2006, Orlando, FL.

“0.250mm-Thick CCD Packaging for the Dark Energy Survey Camera Array” G. Derylo et al in the Proceedings of SPIE Astronomical Telescope and Instrumentation Meeting, May 24-31,2006, Orlando, FL.

Information on the Monsoon CCD readout system is available at: http://www.noao.edu/ets/monsoon/

For Information on S-LINK see: http://hsi.web.cern.ch/HSI/s%2Dlink/

“The Dark Energy Survey Optical Corrector Design”, S. Kent, et al. in the Proceedings of SPIE Astronomical Telescope and Instrumentation Meeting, May 24-31,2006, Orlando, FL.

Mike Gladders, DES Document 97.

For information on the BCaMs see http://alignment.hep.brandeis.edu/Devices/BCAM/.

http://www.ctio.noao.edu/new/Telescopes/SOAR/Instruments/SAM/archive/4009-05_SOAR_Controls_Paper.pdf

http://www.aps.anl.gov/epics/

http://www.pvss.com/index_e.asp?id=2&sbl=6

“Cyber-infrastructure to Support Science and Data Management for the Dark Energy Survey,” C. Ngeow et al. in the Proceedings of SPIE Astronomical Telescope and Instrumentation Meeting, May 24-31,2006, Orlando, FL.

Supplements to the DES white paper: https://www.darkenergysurvey.org/the-project/survey_documents/DES-DETF/Supplements_DES-DETF_v1.6.pdf

Haiman, Z.,Mohr, J. J., and Holder, G. P. 2001, ApJ, 553, 545.

Battye, R. A. and Weller, J. 2003, Phys. Rev. D, 68, 083506

Ruhl, J. et al., Astronomical Structures and Mechanisms Technology. Edited by Antebi, Joseph; Lemke, Dietrich. Proceedings of the SPIE, Volume 5498, pp. 11-29 (2004).

Motl, P., et al., 2005, ApJL,623,63.

Nagai, Ph. D. Thesis, University of Chicago, 2005

Johnston et al., 2005, in preparation.

Hu, W.,2002, Phys. Rev. D, 66, 083515.

Huterer, D. 2002, Phys. Rev. D, 65, 063001.

Eisenstein, D. J. et al. 2005, ApJ submitted, astro-ph/0501171.

Hu, W. and Haiman, Z.  2003, Phys. Rev. D, 68, 063004.

Seo, H-J. and Eisenstein, D. J. 2003, ApJ, 598, 720.

Blake, C. and Bridle, S. 2004, MNRAS, submitted, astro-ph/0411713.

Hu, W. and Scranton, R. 2004, Phys. Rev. D, 70, 123002.

Majumdar, S. and Mohr, J. J. 2004,ApJ, 613, 41.

Lima, M. and Hu, W. 2004,Phys. Rev. D, 70, 043504.

Lima, M. and Hu, W.  2005, Phys. Rev. D, submitted, astro-ph/-503363.

Hu, W. and Jain, B.  2004, Phys. Rev. D, 70, 043009.

Kravtsov, A. V. et al., 2004, ApJ, 609, 35.

Zehavi, I. et al., 2004,ApJ, 608,16.

E.g., Frieman, J. A. et al., 2003, Phys. Rev. D,67, 083505.

Melin, J-B. et al., 2005, A&A, 429, 417.

Vale, C. and White, M., 2005, New Astronomy, submitted, astro-ph/0501132.

Huterer, D., Takada, M., Bernstein, G., and Jain, B., 2005,astro-ph/0506030.

Ma, Z.,  Hu, W.,  and Huterer, D., 2005, in preparation.

White, M., 2004, Astropart. Phys., 22, 211.

Zhan, H. and Knox, L.,  2004, apJ, 616, 75.

Huterer, D. and Takada, M., 2005, Astropart. Phys., 23, 369.

Huterer , D. and White, M.,  2005, Phys. Rev. D, submitted, astro-ph/0501451.

Dolney, D., et al.,  2004, astro-ph/0409445.

Gaztanaga, E. and Frieman, J. A., 1994, ApJ, 437, L13.

# Text boxes

Filters

Shutter

Feed-thru

Board

LN2

Dewar

Cooling

Straps

Bipod Supports

Cooling,

Vacuum

Thermally Controlled

CCD readout Crates

Focal Plane

Support Plate

Filter   C4   C5

C2 C3

C1

CCD

Read out

F8 Mirror

Optical

Lenses

Hexapod

1575 mm

3556 mm