NOAA

National Environmental Satellite, Data, and Information Service (NESDIS)

Comprehensive Large Array-data Stewardship System  (CLASS)

Master Project Management Plan

CLASS-1028-CLS-PLN-MPMP

March 15, 2005

Revisions

| Version | Description of Version | Date Completed |
| --- | --- | --- |
| 0.1 | Initial draft | 8/12/02 |
| 0.2 | Incorporated Tino and QA comments | 9/9/02 |
| 0.3 | Incorporated CPMT comments | 11/08/02 |
| 1.0 | Approved by CPMT on 12/03 – removed “draft” | 12/10/02 |
| 1.1 | Update | 4/21/03 |
| 1.2 | Incorporated QA review comments – approved by Tino | 8/12/03 |
| 1.3 | Incorporated Richard Reynolds comments – new organization | 8/24/03 |
| 1.4 | Updated WBS for FY04 | 10/07/03 |
| 1.5 | Incorporated SEPG review comments | 10/15/03 |
| 1.6 | Incorporated SEPG review comments | 09/30/04 |
| 1.7 | Updated to clarify planning, acquisition, stakeholder involvement, measurements, and risk/action tracking. | 01/17/05 |
| 1.8 | Included review comments from Scott McCormick. | 03/09/05 |
| 2.0 | Updated comments showing approval from CPMT. | 03/15/05 |

Review & Approval

Project Plan Review History

| Reviewer | Version Reviewed | Approval Date |
| --- | --- | --- |
| SEPG | 1.7 | 02/09/05 |
| CPMT | 1.8 | 03/15/05 |

Contents

Revisions	i

Review & Approval	ii

Contents	iii

1 Project Definition	1

1.1 Overview	1

1.2 Scope	2

1.2.1 Process	2

1.2.2 Location/Organization	2

1.2.3 Data	3

1.2.4 Application	3

1.2.5 Technology	3

1.3 Deliverables	4

1.4 Assumptions and Constraints	4

1.5 Success and Completion Criteria	5

1.5.1 Acceptance Criteria	5

1.5.2 Critical Success Factors	5

1.6 Reference Materials	5

1.7 Document Maintenance	6

2 Management Structure	8

2.1 Project Lifecycle	8

2.2 Project Organization	9

2.2.1 Project Roles and Responsibilities	9

2.2.2 External Interfaces	11

2.2.3 Internal Coordination	11

2.3 Communication	12

2.4 Risk Management	13

2.4.1 Risks	13

2.4.2 Issues and Action Items	13

3 Planning and Control	14

3.1 Estimation	14

3.2 Resource Identification	14

3.2.1 Staff	14

3.2.2 Time	14

3.2.3 Materials	14

3.3 Resource Allocation	14

3.3.1 Work Breakdown Structure	14

3.3.2 Schedule	16

3.4 Tracking and Control	16

3.4.1 Cost and Schedule Tracking and Control	16

3.4.2 Quality Tracking and Control	16

3.4.3 Functionality Tracking and Control	16

3.4.4 Measurements	16

3.4.5 Stakeholder Involvement	16

4 Technical Process	18

4.1 Engineering	18

4.1.1 Environment	18

4.1.2 Methods, Tools and Techniques	19

4.1.3 Process Training	19

4.2 Technology	19

4.2.1 Environment	19

4.2.2 Methods, Tools, and Techniques	20

4.2.3 Technical Training	21

5 Supporting Plans	22

5.1 Configuration Management	22

5.2 Quality Management	22

5.3 Testing	22

5.4 Software Development	22

5.5 Operations Support	22

5.6 Team Activity Plans	22

6 Definitions and Acronyms	23

List of Tables

Table 1 - CLASS Major Deliverables	4

Table 2 - CLASS Project Management Team Voting Members	9

Table 3 - CLASS Project Roles and Responsibilities	9

Table 4 - CLASS Work Breakdown Structure for FY05	15

Table 5. SEPG Members	17

Table 6. SET Members	18

List of Figures

Figure 1 - CLASS Project Organization	11

# Project Definition

This document describes the overall management approach for work to be performed for the National Oceanic and Atmospheric Administration (NOAA) National Environmental Satellite, Data, and Information Service (NESDIS), on the Comprehensive Large Array-data Stewardship System (CLASS) project.   CLASS is an evolutionary development effort that involves several different government and contractor groups in various geographic locations.  This Master Project Management Plan (MPMP) defines the common principles and guidelines to be followed by all participating groups.  Each group supplements this overall plan with a detailed activity plan with specific information related to management of its component(s) of the system.  The MPMP will be reviewed at the start of each NOAA fiscal year, and updated as necessary.

Section 1 describes the overall scope and objectives for the CLASS project.  It includes the following topics:

- Overview – describes the CLASS project objectives and background

- Scope – defines the work included in the CLASS implementation

- Deliverables – identifies major work products that will be delivered, and an overall timeline for their delivery

- Assumptions and Constraints – identifies the assumptions and constraints that underlie this plan.  Changes to the assumptions or constraints will affect the scope, cost, and/or schedule for this project.

- Success and Completion Criteria – identifies the acceptance criteria for the project and the critical success factors

- Reference Material – refers the reader to additional material for more information on the CLASS project

## Overview

The CLASS project is being conducted in support of the NESDIS mission to acquire, archive, and disseminate environmental data.  NESDIS has been acquiring this data for more than 30 years, from a variety of in situ and remote sensing observing systems throughout the National Oceanic and Atmospheric Administration (NOAA) and from a number of its partners. NESDIS foresees significant growth in both the data volume and the user population for this data, and has therefore initiated this effort to evolve current technologies to meet future needs.

The long-term goal for CLASS is the stewardship of all environmental data archived at the NOAA National Data Centers (NNDC).  The initial objective for CLASS is to support specifically the following campaigns:

- NOAA and Department of Defense (DoD) Polar-orbiting Operational Environmental Satellites (POES) and Defense Meteorological Satellite Program (DMSP)

- NOAA Geostationary Operational Environmental Satellites (GOES)

- National Aeronautics and Space Administration (NASA) Earth Observing System (EOS) Moderate-resolution Imaging Spectroradiometer (MODIS)

- National Polar-orbiting Operational Environmental Satellite System (NPOESS)

- The NPOESS Preparatory Program (NPP)

- EUMETSAT Meteorological Operational Satellite (Metop) Program

- NOAA NEXt generation weather RADAR (NEXRAD) Program

The development of CLASS is expected to be a long-term, evolutionary process, as current and new campaigns are incorporated into the CLASS architecture.  This master project management plan defines project characteristics that are expected to be applicable over the life of the project.  However, as conditions change over time, this plan will be updated as necessary to provide current and relevant project management guidance.

## Scope

This section defines the CLASS scope in terms of both business scope (processes, location, and organization) and technical scope (data, applications, technology).

### Process

The goal of CLASS is to provide a single portal for access to NOAA environmental data, some of which is stored in CLASS and some available from other archives.  The major processes required to meet this goal that are in scope for CLASS are:

- Ingest of environmental data from CLASS data providers

- Extraction and recording of metadata describing the data stored in CLASS

- Archiving data

- Browse and search capability to assist users in finding data

- Distribution of CLASS data in response to user request

- Identification and location of environmental data that is not stored within CLASS, and connection with the owning system

- Charging for data, as appropriate (see out of scope note below)

- Operational support processes: 24x7 availability, disaster recovery, help desk/user support

While the capability of charging for media delivery of data is a requirement for CLASS, the development of an e-Commerce system to support financial transactions is out of scope.  CLASS will interface with another system, NESDIS e-commerce System (NeS), for financial transactions; definition and implementation of the CLASS side of that interface is in scope for this project.

### Location/Organization

CLASS is being developed and operated under the direction of the NESDIS Office of Systems Development, having been under the direction of the NESDIS Chief Information Officer (CIO) during the period 2001 – 2003 (through Release 2.0).

CLASS is being developed by NOAA and contractor personnel associated with the Office of Systems Development (OSD) at the CLASS-MD site in Suitland, MD and at the CLASS_WV site in Fairmont, WV, the National Climatic Data Center (NCDC) in Asheville, NC, and the National Geophysical Data Center (NGDC) in Boulder, CO.

The operational system is currently located at the NOAA facility in Suitland, MD, with a second operational facility at the NCDC facility in Asheville, NC.

The project management is conducted by the CLASS Project Management Team (CPMT), with representatives from each government and contractor team participating in CLASS development and operations and chaired by the OSD Project Manager.  Section 2.2 describes the organizational structure for the CLASS project.

### Data

Data stored in CLASS includes the following categories:

- Environmental data ingested and archived by CLASS.  Currently this includes data for each of the campaigns listed in Section 1.1, and certain product and in situ data

- Descriptive data received with the environmental data, used to support browsing and searching the CLASS archive

- Descriptive data maintained by CLASS to support searching for data maintained in other (non-CLASS) repositories

- Operational data required to support the general operation of the system that is not related to environmental data (e.g., user information, system parameters)

### Application

A goal for CLASS is to reuse existing systems where possible.  Existing systems that have been identified as sources for CLASS functionality include:

- The Satellite Active Archive (SAA) system, which provided the basis for the CLASS Archive and Distribution function

- The Satellite Archive Browse and Retrieval (SABR) system

- The NOAA National Virtual Data System (NVDS)

### Technology

The following technology components are in scope of the CLASS project:

- Application servers

- Data storage and retrieval hardware and system software

- Database management system

- Network connectivity between each of the multiple operational CLASS sites and the NOAA backbone

- Telephone call director for help desk support

Network connectivity between the data providers and the NOAA backbone is out of scope for CLASS.  It is assumed data providers have access to the NOAA backbone, or can stage the data in a location accessible to CLASS via the backbone or via the Internet.

Development, upgrade, or maintenance of the NOAA backbone is out of scope for the CLASS project.

The CLASS customer interface is conducted over the Internet using standard browser technology.  No client software or hardware for interfacing with the customer is in scope.

## Deliverables

The following table identifies the major deliverables for CLASS, and the estimated delivery dates.  These are key high-level support requirements; more detailed interim milestones are defined in the detailed implementation activity plans.  The table shows the updated status for each deliverable since the last version of this document.  Due to budget considerations and revised priorities for NESDIS, some deliverables have been rescheduled or put on indefinite hold, as reflected in the table.

Table 1 - CLASS Major Deliverables

| Deliverable | Date | Update |
| --- | --- | --- |
| CLASS Release 1.0 | December 2002 | Delivered |
| GOES Initial Operating Capability – distribute GOES data | December 2002 | Cancelled |
| GOES Archive and Distribution | June 2003 | December 2003 |
| Creation of Geotiff Images | June 2003 | TBD |
| Geospatial Databases | December 2003 | TBD |
| DMSP Archive and Distribute (SABR) integration | December 2003 | TBD |
| EOS/MODIS Archive and Distribution | December 2003 | June 2005 |
| NPP Archive and Distribution (end-to-end test) | June 2004 | January 2006 |
| Metop Archive and Distribution (end-to-end test) | October 2004 | September 2005 |
| CLASS Release 2.0 |  | Delivered |
| CLASS Release 3.0 |  | Delivered |
| CLASS Release 3.1 |  | Delivered |
| CLASS Release 3.2 |  | March 2005 |
| CLASS Release 3.3 |  | June 2005 |
| CLASS Release 4.0 |  | December 2005 |
| CLASS Release 4.1 |  | January 2006 |
| CLASS Release 4.2 |  | July 2006 |
| CLASS Release 4.3 |  | October 2006 |

## Assumptions and Constraints

The following assumptions and constraints underlie the project plan for CLASS.  Changes to these factors could affect the cost, schedule, or scope of the work included in this plan.

| Assumption | Update |
| --- | --- |
| The communication link between Suitland and Asheville is upgraded and meets the needs for data transfer between the sites. | Link installed and in use |
| The E-Commerce system to be used for managing CLASS financial transactions will be developed and available for use by October 2005, in order to conduct interface testing with CLASS prior to the NPP end-to-end test. The interface between CLASS and the E-Commerce system was defined September 2004 so the CLASS team can begin work on the CLASS interface code in time to meet the October 2005milestone. | E-Commerce requirements changed to only charge for data delivery in physical media. The MD-050 (Interface Control Document) scheduled for completion by April 2005. |
| New Assumptions |
| Schedules for NPP and EOS support are driven by current mission schedules, and are subject to change as priorities of those missions change. NMMR will support CLASS collection-level metadata management requirements. |

## Success and Completion Criteria

### Acceptance Criteria

A system integration and test team, independent of the development teams, conducts testing of all components of CLASS as they are developed and turned over to Configuration Management (CM).  This integration and test is a multi-stage process.  The stages in the acceptance process are:

- Integration – Configuration Management Office (CMO) rebuilds the system in Integration Environment (at the CLASS-MD site in Suitland) and verifies the system builds correctly.

- System Test – CMO builds the system in the Test Environment (at the CLASS-MD site in Suitland), and the system test team validates the system functionality for established data types.

- Deployment Test – CMO builds the system in the Deployment Test Environment, and verifies the system was correctly built.

- Operational Readiness Review – SIT chairs this intergroup meeting confirming the readiness of the system for operations.

Formal acceptance of the system and approval to promote to operations is the responsibility of the NOAA CLASS Technical Lead, Alex Kidd.

### Critical Success Factors

- Each team has a detailed project plan that includes dependencies between teams, and provides sufficient intermediate milestones for tracking.

- Project progress is tracked to provide the CLASS Project Management Team (CPMT) with accurate and current status and forecasts.

- Risks are identified and managed by the CPMT on a regular basis.

- Coordination and collaboration of teams at multiple levels within CLASS.

- Standard development processes are defined and followed by all CLASS development teams.

- Lessons Learned sessions are conducted to support process improvement.

## Reference Materials

CLASS follows policy as directed by NOAA NESDIS OSD Program Office Directives (PODs).  The following documents provide policy direction to CLASS project management:

- OSD POD Technical Management (OSD-1066-NES-DIR-POD)

- OSD POD Project Management (OSD-1067-NES-DIR-POD)

- OSD POD Intergroup Coordination (OSD-1068-NES-DIR-POD)

- OSD POD Change Control (OSD-1069-NES-DIR-POD)

- OSD POD Acquisition (OSD-1094-NES-DIR-POD)

Above documentation is available in the CLASS Document Repository in the Baseline Documentation>Organization>OSD folder.

The following documents supplement this MPMP for CLASS and provide more detail on specific topics related to CLASS project management:

- Quality Management Plan (CLASS-1006-CLS-PLN-QM)

- Configuration Management Plan (CLASS-1001-CLS-PLN-CM)

- Software Development Guide (CLASS-1002-CLS-PRO-Guide)

- Software Development Measurement Plan (CLASS-1054-CLS-PLN-CM)

- Stakeholder Involvement Plan (CLASS-1083-CLS-PLN-SIT)

- Individual team Activity Plans

All above documentation is available in the CLASS Document Repository in Baseline Documentation, stored in appropriate site plans or technical folders.

The following procedures provide additional detail on project management related activities:

- Risk Management (CLASS-1033-CLS-PRO-PM)

- Issues and Action Tracking (CLASS-1034-CLS-PRO-PM)

- Estimation Cycle (CLASS-1035-CLS-PRO-PM)

- Cost and Schedule Tracking (CLASS-1036-CLS-PRO-PM)

- Operational Readiness Review (CLASS-1049-CLS-PRO-SIT)

- Requirements baseline Management (CLASS-1030-CLS-PRO-CM)

- Configuration Change Request (CLASS-1026-CLS-PRO-CM)

All above documentation is available in the CLASS Document Repository in the Baseline Documentation>Procedures folder.

Other CLASS source, process baseline, management and monitoring documentation is contained in the CLASS Document Repository in KnowledgeTree.  Additional detailed technical documentation for CLASS is available online in the CLASS online library: library.class.noaa.gov

Each organization participating in CLASS development and operations can supplement the CLASS guidelines and procedures with their local organization’s policies and procedures to the extent they do not conflict with the CLASS direction.  CLASS standards and procedures take precedence over any local organizational standards and procedures unless the CLASS Technical Area Lead grants a waiver.

## Document Maintenance

This Master Project Management Plan is baselined and approved by both the Software Engineering Process Group (SEPG) and the CLASS Project Management Team (CPMT).  Any proposed changes to this document will be presented to the CLASS Process Manager as a new Work Request (WR), in accordance with the processes defined in the CLASS Work Request (WR) procedure, and Process Baseline Document Management procedure.  During the course of the project, this document will be reviewed for accuracy and updated on a yearly cycle to reflect process improvements.

Additionally, all process baseline documentation for CLASS will fall under the same analysis through the course of this project, be reviewed for accuracy, and updated on a yearly cycle to reflect process improvements.  As needed, process baseline documentation may be updated at any time with the submission and approval of a Work Request (WR).

# Management Structure

This section addresses the overall management approach for the CLASS effort, including

- Project Lifecycle

- Project Organization

- Communication

- Risk Management

## Project Lifecycle

CLASS is being developed based on a currently operational system for data archive and distribution, formerly known as the Satellite Active Archive (SAA).  Additional functionality is being added to CLASS to support new campaigns and expanded data analysis and retrieval capabilities. The new architecture and requirements are being defined while the existing operational system is being supported and upgraded.

The major activities being conducted for CLASS are: research into new technologies, analysis of new requirements, and implementation of new capabilities.  Specific activities are assigned to each of the participating organizations by NESDIS OSD Project Manager (PM).   Planning of these activities is further defined in the CLASS Software Development Guide.

- Research into new technologies:  The PM determines new technologies to be investigated for potential integration into the system.  The assigned organization prepares a plan for the assessment, and reports results to the CPMT for consideration.  If a new technology is to be incorporated into CLASS, a Configuration Change Request (CCR) is submitted to track the change, as described in the CLASS Configuration Management Plan (CMP).

- Analysis of new requirements:  The assigned CLASS organization works with the data supplier organization to evaluate and clarify proposed requirements for CLASS to support new or changed campaign requirements.  New requirements from campaigns, or those derived from the updated architecture, are submitted and processed as CCRs, as defined in the CLASS CMP.  CLASS uses the requirements management tool DOORS to document and track approved requirements, whatever their source.  CCR processing is described in the Requirements Baseline Management Procedure for Level I (system) and Level II (allocated) requirements processing, and in the Configuration Change Request (CCR) procedure for Level III (release) requirements processing.  CCRs are managed in the Remedy tool.

- Implementation of new capabilities: CLASS uses a release-based implementation approach to implement changes to the system, in order to support new campaign requirements while minimizing disruption of the operational system.  All proposed changes are documented as CCRs, assigned to a release, and implemented and tested as part of a scheduled release. The CLASS software lifecycle and associated software engineering processes are defined in the CLASS Software Development Guide. Coding standards are defined in the Software Standards for IPD (June 30, 2001).  Software version control is managed using the Concurrent Versions System (CVS) tool, according to the processes defined in the CLASS CMP and associated procedures.  CLASS documentation is contained in the KnowledgeTree repository, with specific design documentation contained in the intranet CLASS online library.

- Acquisition: Acquisition for CLASS is conducted on a contractual basis as directed and approved by NOAA NESDIS OSD management.  As necessary, CLASS sites will maintain individual acquisition management procedures to identify their process and ensure control throughout the activity.  The NOAA NESDIS OSD POD on Acquisition provides guidance from which to conduct acquisition.

## Project Organization

The CLASS project is a joint effort of various government and contractor organizations, under the direction of the NESDIS OSD.  Each participating government and contractor organization is led by a Technical Area Lead (TAL), who is included as a member in the CLASS Project Management Team (CPMT). Table 2 identifies the voting members of the CPMT.

Table 2 - CLASS Project Management Team Voting Members

| Richard G. Reynolds, OSD Project Manager | Eric A. Kihn, NGDC |
| --- | --- |
| Charles S. Bryant OSD | Alexander W. Kidd, OSD |
| Constantino Cremidis, CLASS-MD (CSDPC) | David P. Bowman, NCDC |
| Ted Habermann, NGDC | Carlos Martinez, CLASS-WV |

### Project Roles and Responsibilities

The responsibilities of each of the governing bodies are defined in the following table:

Table 3 - CLASS Project Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Board of Directors | Provides strategic direction and funding advocacy for CLASS |
| Data Stewardship Committee | Reviews archive and distribution requirements for NOAA and determines role of CLASS in supporting those requirements |
| Archive Requirements Working Group | Develops and recommends requirements for CLASS to the Data Archive Board |
| CLASS Management Oversight Group | Stakeholders providing ongoing review for CLASS through the Data Archive Working Group |
| NESDIS OSD Project Manager | Provides direction and leadership for the CLASS Project. Allocates responsibility and funding for components of CLASS to participating organizations. Assigns Level I – system requirements - responsibility. Defines project goals, plans, and objectives. Manages progress towards project goals. Prepares and manages the Budget. |
| CLASS Project Management Team | Supports NESDIS OSD PM in project planning and tracking activities. Provides leadership for the participating development groups; provides coordination of activities within each participating organization. Assigns Level II – allocated requirements – responsibility. |
| CLASS Project Support | Project Control Office – supports integration of component schedules and plans; collects and processes project status; distributes CLASS project Earned Value reports and assists the CPMT in analysis of the reports Quality Management Office (QMO) – supports the CPMT in the definition and implementation of software development and quality processes; provides independent verification of compliance against CLASS standards and procedures. Measurements Administrator – collects and calculates release measurements showing trends, possible areas for improvements based on measures, and calculated basis of estimate for planning activities. |
| CLASS Development Teams | Develop components of CLASS: conduct analysis, design, code and development testing of new components. The supporting development team organization chart is located in the CLASS Document Repository. This organization chart is dynamic as it reflects current organizational changes for the CLASS Development Teams. |
| CLASS Integration and Test Team | Conduct independent verification of new functionality developed for CLASS |

The chart in Figure 1 shows the governing bodies involved in the management, development, and oversight of the CLASS project.  The corresponding roles and responsibilities of these participants are defined in Section 2.2.1.

Figure 1 - CLASS Project Organization

### External Interfaces

The CPMT provides the point of contact with other CLASS stakeholders, such as the current campaign operations teams for those campaigns planned for integration with CLASS (e.g., NASA IPO), and the operations teams at the CLASS operational sites.  Stakeholders are identified from all phases of the project life cycle by type of resource and function, describing their relevance and degree of interaction for specific project activities.  Refer to the CLASS Stakeholder Involvement Plan for additional information on CLASS stakeholders.

### Internal Coordination

In addition to the CPMT, several other teams have been established to facilitate coordination across the organizations participating in CLASS development:

- The Software Engineering Process Group (SEPG) supports the definition and deployment of processes for use on CLASS, and leads process improvement activities.  The purpose of this group is further defined in Section 4.1.1.

- The Software Engineering Team (SET) provides technical leadership and coordination across CLASS to ensure technical consistency and compatibility among the development groups.  The purpose of this group is further defined in Section 4.1.1.

- The Configuration Control Board (CCB) reviews proposed changes to the system baseline, as defined in the CLASS CMP.

- The CLASS Operations Team (COT) discusses operational capabilities and coordination for all operations sites.

- The System Administration Team (SAT) supports the consistent configuration and operation of CLASS.

- Weekly Developers Meeting is a forum to ensure a common knowledge transfer.

Each of these groups has representation from all participating organizations.  Meetings are regularly scheduled and core participation identified.  Attendance is captured in meeting minutes, as appropriate.  Meeting will continue as scheduled, regardless of participation, unless cancelled in advance.  As necessary, meeting items needing disposition will be carried to the next meeting if the disposing authority is not present.

Additionally, the configuration management and quality management functions are provided by a common CMO and QMO located in the CLASS-MD site in Suitland, MD.

## Communication

In a large, dispersed team such as the CLASS team, facilitating communication is essential to the project success.  The following formal communication within the joint CLASS team is conducted to ensure appropriate coordination of the various organization development teams:

- Weekly CPMT teleconferences, with the following standing agenda items

  - Review of status of inter-group dependencies, including release status

  - Review of selected tasks (identified by the CPMT based on risk, schedule criticality, visibility, etc.)

  - Identify issues and assign action items for their resolution

- Written project schedules from each development team

- Monthly progress reports to include task status and budget information (see Section 3.4 below)

- Monthly video-teleconference meeting of CPMT, with the following standing agenda items

  - Review risks (see Section 2.4 for details of the Risk Management process)

  - Review status of draft documents and planned approval dates

  - Review action items status

  - Review earned value reports

  - Report from technical activities, as necessary

  - Quality activities report, as necessary

- Periodic meeting of full joint development teams to review status, process, and issues

Additionally, special interest groups are formed around major functional capabilities (e.g., user interface, data ingest) to facilitate coordination and knowledge sharing among developers in different organizations who are working on similar or related topics.  An online collaborative environment is used to support communication and teamwork among the project members, and an online library is maintained for project documentation.

## Risk Management

Managing risk is the identification, evaluation, mitigation, and re-evaluation of events that may have an unfavorable impact on the work.

Risk management is a recurring cycle of activities. Major risks are identified when first planning a project; other risks become apparent later. When planning a project, the responsible project team analyzes risks and develops plans to avoid or mitigate them. The CPMT reviews the risks on a regular basis in order to re-evaluate the possibility of risks occurring, to identify new risks, and then to activate plans to prevent their occurrence or to minimize their impact.  The Risk Management Procedure describes further the process for documenting and managing risks for CLASS.

Risks are identified at two levels, with both being managed on CLASS.  The following addresses the management of managing risks and managing issues and action items.

### Risks

Risks will be identified either by an individual project team or by the CPMT itself.  Risks on CLASS are characterized with the following descriptions.  Refer to the Risk Management procedure for further information on documenting and monitoring risks.

- Known Risks: those identified as direct consequences of assumptions about the situation or inadequacies in the information provided.

- Potential/Predictable Risks: those that are known from experience to be encountered in projects of the type being planned.

- Unknown Risks: those that, perhaps suspected, cannot be confirmed with the same degree of confidence as known or predictable risks.

### Issues and Action Items

Project issues and action items that surface during internal technical and management meetings or during client meetings are documented electronically; a closure date is determined; and then they are assigned for analysis and resolution. Issues not resolvable within the project are escalated to successive levels of management as required for resolution. Status of the issues and action are tracked and reported periodically.

The types of meetings or activities that may generate an entry into the CLASS change management tool include process audits, lessons learned sessions, intergroup meetings.  Refer to the Issue and Action Tracking procedure for more information.

# Planning and Control

This section discusses the planned approach for estimating, planning, and controlling the work.

## Estimation

Estimates for CLASS are primarily based on similar experience, i.e., actual effort and duration required for the previous releases, and/or reported effort and duration for development of other existing systems that support the relevant campaigns.  Where previous experience is not available (e.g., new technologies or programming language), the project may conduct prototypes before final estimation of the full system development effort.  The Estimation Cycle Procedure provides a description of the CLASS estimation process.

## Resource Identification

### Staff

As work is allocated to the participating organizations, each affected organization prepares a work plan indicating required staffing and skill levels. The CPMT reviews each work plan as needed, and the OSD PM must approve all plans.  Staffing levels are reviewed at each major milestone to determine if the available staff is adequate to support work planned.

### Time

CLASS is expected to be a continually evolving system, as new campaigns and capabilities are integrated into the base system.  Major milestones that drive the activities in the near-term are defined in Section 1.3.  The system has planned releases based on major functionality, directed from the NOAA NESDIS OSD Project Manager and the CPMT.  Release plans are approved through the CPMT.

### Materials

All materials to be used on the CLASS project will be supplied by NOAA.

A development system will be installed at each major geographic development site, initially to include Suitland, MD, Fairmont, WV, and Boulder, CO.  The integration and test systems are resident at the NOAA Suitland facility and the NCDC facility in Asheville, NC.  The deployment test system resides at the NCDC site in Asheville, NC.  The operational system has been duplicated at Suitland, MD and Asheville, NC.

## Resource Allocation

### Work Breakdown Structure

The following table shows the top levels of the WBS for CLASS.  This provides the level of information required for project planning and tracking at the CPMT level.  Lower levels are defined in the individual MS Project schedules developed by each participating organization.  Changes to the WBS are proposed, reviewed, and conducted on a yearly basis to correlate with the government fiscal year cycle.

Table 4 - CLASS Work Breakdown Structure for FY05

| WBS | Task Name |
| --- | --- |
| CA-1 |  |
|  | Project Management |
|  | Quality Management |
|  | Configuration Management |
|  | Project Control |
| CA-2 |  |
|  | CLASS Architecture and Design |
|  | CLASS Requirements |
|  | Interface Definition |
| CA-3 |  |
|  | Suitland Infrastructure |
|  | Asheville Infrastructure |
|  | NGDC Development System |
|  | COAST Hardware and System Software |
|  | Tool Support |
| CA-4 |  |
|  | Implementation CLASS 3.1 |
|  | Implementation CLASS 3.2 |
|  | Implementation CLASS 3.3 |
|  | Implementation CLASS 4.0 |
|  | Implementation CLASS 4.1 |
|  | Implementation CLASS 4.2 |
|  | Implementation Interim Releases |
| CA-5 |  |
|  | Integration, Test and Deployment CLASS 3.1 |
|  | Integration, Test and Deployment CLASS 3.2 |
|  | Integration, Test and Deployment CLASS 3.3 |
|  | Integration, Test and Deployment CLASS 4.0 |
|  | Integration, Test and Deployment CLASS 4.1 |
|  | Integration, Test and Deployment CLASS 4.2 |
|  | Integration, Test and Deployment Interim Releases |
| CA-6 |  |
|  | Document Maintenance |
|  | Metrics Analysis |
|  | SEPG Activities |
|  | CMMI Evaluation Preparation |
| CA-7 |  |
|  | Unplanned Support |
|  | System Support |
| CA-8 |  |
|  | Suitland Operations |
|  | Asheville Operations |
| CA-9 |  |
|  | Reserved |
| CA-10 |  |
|  | Science Support |

### Schedule

The high-level milestones for deliverables are provided in Section 1.3. The detailed schedule activities are provided in the individual component MS Project files, and rolled up to the CLASS level in the CLASS master schedule.

## Tracking and Control

### Cost and Schedule Tracking and Control

CLASS cost and schedule is managed using an Earned Value measurement system.  The Cost and Schedule Tracking Procedure describes the process and standards for earned value planning and tracking.

### Quality Tracking and Control

Quality of the products produced for CLASS is monitored through peer review, independent testing, and periodic process audits, as defined in the CLASS Quality Management Plan and the CLASS Software Development Guide.  Supporting procedures define individual steps and forms needed.  Procedures are controlled in the CLASS Document Repository under the Baseline Documentation>Procedures folder.

### Functionality Tracking and Control

The CMO manages all proposed changes to the approved system baseline (requirements, software, hardware, etc.), with the review and approval of the CLASS CCB.  For more detail, refer to the CLASS Configuration Management Plan and associated procedures.  CLASS management plans, source documentation, and supporting procedures are controlled through the CMO and retained in the CLASS Document Repository.

### Measurements

The CLASS Measurement Administrator gathers and reports release-based measurements.  Summary contents in the reports include planned versus actual comparisons, trends, summary analysis, and calculated basis of estimate for release planning.  The site Earned Value Administrators at CLASS sites are responsible for collecting, tracking, and reporting progress against cost and schedule.

### Stakeholder Involvement

Coordination and interaction between relevant stakeholders is essential to providing project direction and implementation.  These activities involve Operational Readiness Reviews (ORR), requirements review, and the Configuration Control Board (CCB), and resolution of problems or issues.  Refer to the Stakeholder Involvement Plan for further information.

# Technical Process

This section summarizes the top-level technical approach used on this project.  Details about the technical processes are provided in the Software Development Guide.

## Engineering

This section describes the organizational environment and processes that define the engineering approach for the CLASS project.  The organizations identified meet on a regularly scheduled basis.  Their meetings will continue regardless of participation.  As needed, quorum decisions may be held to a future meeting if adequate participation is lacking.  As needed, other intergroup organizations may be established to discuss and monitor related activities.

### Environment

The Software Development Guide, the CLASS Configuration Management Plan, and the associated procedures provide system and software engineering processes for use throughout the CLASS project for all phases of the development life cycle.  Specifically, the Software Development Guide discusses the CLASS processes for the following activities:

- Release planning

- Estimation

- Peer review

- Design, code, and documentation standards

- Testing

The Configuration Management Plan describes the process for managing changes to requirements or other system baseline elements, and the promotion process for CLASS software.

The CLASS Software Engineering Process Group (SEPG) includes representatives from each organization participating in the CLASS project, and serves as a process advisory council to the CLASS Process Manager.  The SEPG and the CLASS Process Manager provide leadership and expertise in the definition, documentation, and application of processes for the full lifecycle. Table 5, below, identifies the members of the CLASS SEPG.

Table 5. SEPG Members

| Guy Baroni | Mark Ohrenschall |
| --- | --- |
| Michelle Hayes | Doug Zirkle |
| Anita Konzak | Chairie Smith |
| Betty Tilley |  |

The CLASS Systems Engineering Team (SET), following the processes defined in the Software Development Guide, coordinates the engineering functions.  This is a cross-organizational team consisting of technical representatives from each participating organization, government and contractor.  As an advisory group to the CPMT, this team helps assure that all CLASS system-level requirements are defined and allocated to the appropriate organization for analysis and implementation.

Table 6. SET Members

| Barry Wishner | Doug Zirkle |
| --- | --- |
| Amy Drew | Yue Ko |
| Pat Schafer | Tom Lahoda |
| Ken Tanaka | Brian Merandi |
| Chris Wells | Kris Nuttycombe |

### Methods, Tools, and Techniques

The activities of the SET include:

- System definition and design

- Review of functional design and implementation for significant system components

- Review and recommendation on CCRs, including requirements changes and software changes

After requirements have been allocated to a specific development team through approved CCRs, the development team activities include:

- Software and database design

- Software implementation

- Testing

- Configuration Management

- Documentation

- Problem reporting and tracking

Each development group prepares detailed plans for the completion of their assigned activities.

CLASS maintains central CM and system test teams to manage the integration and delivery of the system releases.

CLASS uses the requirements management tool to document requirements and to maintain traceability from requirements to design elements and to test cases.

CLASS uses the CLASS Document Repository as a central repository for the various development teams.

The Issues and Action Tracking Procedure describes the procedure for documenting and tracking issues and action items for CLASS.

### Process Training

Periodic training is conducted for all project personnel to learn, review, and reinforce project standards and procedures.  The CLASS Training Coordinator, and as needed, Process Manager reviews process training needs at least annually, and coordinates the necessary training with the development groups.  Each development group maintains training records for the members of that team.

## Technology

This section describes the physical development environment and the tools and methods used to support development.

### Environment

CLASS software is developed and maintained at several development sites linked to a Central Development Facility (CDF), located at the CLASS-MD site in Suitland, MD.  The development sites are in:

- Suitland, MD

- Asheville, NC

- Fairmont, WV

- Boulder, CO

The CLASS configuration management team establishes and maintains the software repository server at the CDF.  It is the responsibility of each site to setup and maintain their local development environment.  Developers at each site check out software from the central repository, copy it to their local systems, develop and test software locally, and “Commit” finished products to the CDF.

The CLASS configuration management team is responsible for promoting software to the integration and test environments and to operations.   Each release is integrated and independently tested at the CDF, and distributed from there to the operational sites.

The operational system is located at the NOAA facility in Suitland, MD, and the NCDC facility in Asheville, NC.  These two sites archive and access the same data files so that failover can be achieved quickly and either site can fill any order and support all operations.  Test teams at each operational facility will conduct acceptance testing of each software release.

### Methods, Tools, and Techniques

A variety of tools are currently in use to support technical activities.  New tools may be added, upon SET approval, as CLASS evolves.  The CLASS tool set includes the following.

- The Telelogic package Tau-UML (formerly Object Team) supports object-oriented design with the Unified Modeling Language (UML).  It generates various diagrams that are useful for analysis and design (e.g., Use Case, Activity, State, Sequence, Class Association diagrams), verifies design consistency, and generates reports.

- The primary programming languages used are C++, Java, JavaScript, and Perl.

- Off-the-shelf components are used in the Java/XML-based user interface:

  - Apache - HTTP server

  - Cocoon - publishing framework

  - Turbine - database connection pooling

  - Tomcat - servlet engine

  - Log4j  - message logging

  - Informix Java Database Connectivity (JDBC) Driver

- Perl scripts are used to automate testing

- A suite of custom-built Perl programs is used to manage and log software promotions

- Off-the-shelf tools are use to generate on-line software reference documentation in HTML format (e.g., Javadoc, Doxygen)

- The Informix database supports all phases of development, configuration management, and operations

- ERWin is used for database design.

- The CLASS document repository, a KnowledgeTree implementation that is available at https://classlibrary.tmctechnologies.com/, is used as a central repository for the various technical teams.

- The CLASS configuration management tool, a Concurrent Versions System (CVS) implementation, provides software version control in the distributed development environment.

- The CLASS change management tool, a Remedy implementation, is used to create and track Action Items, Configuration Change Requests, Problem Reports, and Work Requests.

- The CLASS requirements management tool, a DOORS implementation, is used to manage CLASS requirements.

- The CLASS library (library.saa.noaa.gov) is used for detailed CLASS design documentation.

- Lotus Notes is used by CLASS-MD personnel as a repository for select quality and site-specific financial and acquisition information.

### Technical Training

The project roles, and the skills required to effectively perform each role for the project, are reviewed on a periodic basis.  Each participating organization is responsible for conducting regular skills assessment for their project personnel, and assessing and addressing training needs.

# Supporting Plans

This section references the detailed supporting plans.

## Configuration Management

CLASS Configuration Management Plan, CLASS-1001-CLS-PLN-CM

## Quality Management

CLASS Quality Management Plan, CLASS-1006-CLS-PLN-QM

## Testing

CLASS System Integration and Test Plan, CLASS-1040-CLS-PLN-SIT

CLASS CSDPC & NCDC Regression Test Plan, CLASS-1053-CLS-PLN-SIT

## Software Development

Software Standards for Information Processing Division (IPD), June 30, 2001

CLASS Software Development Guide, CLASS-1002-CLS-PRO-Guide

## Operations Support

CLASS Operations Support Plan, CLASS-1061-CLS-PLN-OPS

## Team Activity Plans

At the start of new sub-projects of CLASS, the team prepares an activity plan, based on this master plan, and tailored to the specific activities included in the sub-project.  These plans are posted in the CLASS Document Repository.

# Definitions and Acronyms

| CCB | Configuration Control Board |
| --- | --- |
| CCR | Configuration Change Request |
| CDF | Central Development Facility |
| CIO | Chief Information Officer |
| CLASS | Comprehensive Large Array-data Stewardship System |
| CM | Configuration Management |
| CMM | Capability Maturity Model |
| ComMIT | Comprehensive Management Information Tool |
| CMO | Configuration Management Office |
| CMP | Configuration Management Plan |
| COAST | Customer Order Account Software acquisition Team |
| CPMT | CLASS Project Management Team |
| CSC | Computer Sciences Corporation |
| CSDPC | Central Satellite Data Processing Center |
| CVS | Concurrent Versions System |
| DoD | Department of Defense |
| EOS | Earth Observing System |
| EUMETSAT | European Organization for the Exploitation of Meteorological Satellites |
| EV | Earned Value |
| EVM | Earned Value Measurement |
| GAA | GOES Active Archive |
| GOES | Geostationary Operational Environmental Satellite |
| IOC | Initial Operating Capability |
| IPD | Information Processing Division |
| IPO | Integrated Program Office |
| JDBC | Java Database Connectivity |
| Metop | European Meteorological Operational Satellite Program |
| MODIS | Moderate-Resolution Imaging Spectroradiometer |
| MPMP | Master Project Management Plan |
| NASA | National Aeronautics and Space Administration |
| NCAAS | NOAA Coast watch Active Access System |
| NCDC | National Climatic Data Center |
| NeS | NESDIS e-commerce System |
| NESDIS | National Environmental Satellite, Data, and Information Service |
| NEXRAD | NOAA NEXt generation weather RADAR Program |
| NGDC | National Geophysical Data Center |
| NNDC | NOAA National Data Centers |
| NOAA | National Oceanic and Atmospheric Administration |
| NODC | National Oceanographic Data Center |
| NPOESS | National Polar-orbiting Operational Environmental Satellite System |
| NPP | NPOESS Preparatory Program |
| OSD | Office of System Development |
| PCO | Project Control Office |
| POES | NOAA and DoD Polar-orbiting Operational Environmental Satellites |
| QM | Quality Management |
| QMO | Quality Management Office |
| SAA | Satellite Active Archive |
| SABR | Satellite Archive Browse and Retrieval |
| SEI | Software Engineering Institute |
| SEPG | Software Engineering Process Group |
| SET | System Engineering Team |
| TAL | Technical Area Lead |
| TBD | To Be Determined |
| TBW | To Be Written |
| TMC | TMC Technologies |
| UML | Unified Modeling Language |
| WBS | Work Breakdown Structure |
| WP | Work Package |

# Text boxes

CLASS Project Management Team

CSDPC, NCDC(2), NGDC(2), OSD

Data Stewardship Committee

Office and Center Directors

NESDIS OSD Project Manager

Class Management Oversight Group

NCDC, NGDC, NODC, CSDPC, OSD, NASA, CIO, OCIO (representatives of the center directors)

Board of Directors

G. Withee, C. Hartman

CLASS Project Support

CLASS Integration and Test Team

CLASS Development Teams

Archive Requirements Working Group

NCDC, NGDC, NODC, CSDPC, ORA (representatives of the center directors)