Revised 6/29/01, after Cincinnati meeting

TC 4.11, Smart Building Systems

Research Plan and Activities

# June 2001

# Current Research Projects

1043-RP	-	Fault Detection & Diagnostic Requirements & Evaluation Tools for Chillers

1139-RP	-	Development and Comparison of On-line Model Training Techniques for Model-Based FDD Methods Applied to Vapor Compression Equipment

Preliminary 2001-2002 Research Plan

| Priority | Project | Contributors | Status |
| --- | --- | --- | --- |
| 1. | Evaluation and Assessment of Fault Detection and Diagnostic Methods for Centrifugal Chillers – Phase II | John House Srinivas Katipamula Arthur Dexter Osman Ahmed | Approved in Minneapolis 10-0-0 (CNV). Need to submit to RAC AFTER Phase I (1043-RP) is completed. RTAR approved 9/00. No-cost extension to 3/02; however, project expected to be completed by 9/01. Submit WS to Seaton before 9/15/01. |
| 2. | Field Performance Assessment of Package Equipment to Quantify the Need for Monitoring, FDD, and Continuous Commissioning | Todd Rossi Mark Breuker Jim Braun | Draft WS exists. RTAR rejected 9/00. Revised RTAR to be submitted by 8/01/01 as priority 1 RTAR for 2001. Todd Rossi and Dave Shipley will assess number of units necessary for statistical significance and revise WS scope and budget accordingly. |
| 3. | Method of Testing FDD Tools for AHU’s (Was “Benchmarking of FDD Tools for AHUs”) | John House Les Norford Mike Brambley Phil Haves Chariti Young Andrew Price | RTAR to be submitted by 8/01/01 as TC 4.11 priority 2 RTAR for 2001. WS to be prepared for Atlantic City subject to approval of RTAR. |
| 4. | Smart Sensor Systems for Reducing Bias Errors in the Measurement of Air Temperatures and Flows in Air-handling Units (Was “Development of Fault Detection and Diagnostics for Sensor Failures”) | Arthur Dexter Phil Haves | Two page Issues Paper handed out by Phil Haves in Minneapolis. Revised two page write-up distributed by Arthur Dexter in Atlanta. Arthur will revise to focus on a particular application. Arthur has been asked to expand this to a WS for Atlantic City. |
| 5. | Design of Self-Configuration Concepts for an HVAC Control System | Michael Kintner-Meyer | RTAR exists. |
| 6. | Prototyping and Field Testing of Utility – Consumer Information Services | Michael Kintner-Meyer Marty Burns Chuck McParland | SSPC 135 has reviewed the WS and set up a utility/building interface working group. This group will work with TC 4.11 to identify research needs in this area. |
| 7. | Resolving Discrepancies Between Multiple, Hierarchically-Related, Fault Detection and Diagnostic Systems | Mike Brambley Todd Rossi | Mike Brambley scaled back scope and distributed a revised WS in Atlanta. TES thought “looked good”. Need to submit revised RTAR. |