## 1.1 Silicon
U.S. ATLAS COST ESTIMATE (K$ - 2002 prices) COMPARISON TABLE
[5 empty] | U.S. ATLAS (ETC-02) |  |  |  | DOE ESTIMATE |  |  |  | VARIANCE |  | Tech | Cost | Schedule | Design | Tech | Cost | Schedule | Calc
|  |  |  | Actuals | BASE COST | CONTINGENCY |  | TOTAL | BASE COST | CONTINGENCY |  | TOTAL |  |  | Risk | Risk | Risk | Risk | wt | Wt | Wt | Contingency
WBS |  |  | System or Item | @ 9/01 | K$ | % | K$ | K$ | K$ | % | K$ | K$ | K$ | REF.
March 2001 Review (ETC -02)
1.1 |  | Silicon |  | 9437.113 | 9154.4 | 22.84% | 2090.49 | 11409.184 | 16056 | 0.26302 | 4223 | 20279 | 0
* | 1.1.1 | Pixel Syatem |  | 3599.6 | 5451.6 | 38.35% | 2090.49 | 7542.09 | 6758 | 0.30941 | 2091 | 8849 | 0
|  | 1.1.1.1 | Mechanics and Final Assembly | 1672.5 | 2386.8 | 40% | 954.72 | 3341.52 | 1773 | 0.31923 | 566 | 2339 | 0 |  | 10 | 6 | 4 | 4 | 2 | 2 | 1 | 40
|  | 1.1.1.2 | Sensors | 257.7 | 240.8 | 14% | 33.712 | 274.512 | 485 | 0.27216 | 132 | 617 | 0 |  | 1 | 2 | 8 | 0 | 2 | 2 | 1 | 14
|  | 1.1.1.3 | Electronics | 1078.9 | 1227 | 44% | 539.88 | 1766.88 | 2446 | 0.29313 | 717 | 3163 | 0 |  | 10 | 6 | 8 | 4 | 2 | 2 | 1 | 44
|  | 1.1.1.4 | Hybrids, Cables and Optical Components | 179.5 | 543.1 | 32% | 173.792 | 716.892 | 731 | 0.30369 | 222 | 953 | 0 |  | 6 | 4 | 8 | 4 | 2 | 2 | 1 | 32
|  | 1.1.1.5 | Module Assembly/Test | 385.3 | 967.5 | 38% | 367.65 | 1335.15 | 1123 | 0.36866 | 414 | 1537 | 0 |  | 4 | 6 | 8 | 8 | 4 | 1 | 1 | 38
|  | 1.1.1.6 | Pixel Misc Items | 25.7 | 86.4 | 24% | 20.736 | 107.136 | 200 | 0.2 | 40 | 240 | 0 |  | 2 | 4 | 8 | 4 | 2 | 2 | 1 | 24
| 1.1.2 | Silicon Strip System |  | 4330.96 | 2231.6 | 0% | 0 | 2231.6 | 6296 | 0.22824 | 1437 | 7733 | 0
|  | 1.1.2.1 | IC Electronics | 3964.8 | 719.1 | 0% | 0 | 719.1 | 4143 | 0.21072 | 873 | 5016 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.2.2 | Hybrids/Cables/Fanouts | 124 | 797.4 | 0% | 0 | 797.4 | 1089 | 0.21671 | 236 | 1325 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.2.3 | Module Assembly and Test | 242.16 | 715.1 | 0% | 0 | 715.1 | 1064 | 0.30827 | 328 | 1392 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.3 | Read-Out Drivers |  | 1506.553 | 1471.2 | 0% | 0 | 1635.494 | 3002 | 0.23151 | 695 | 3697 | 0
|  | 1.1.3.1 | Test Beam Support | 283.7 | 0 | 0% | 0 | 0 | 287 | 0.11847 | 34 | 321 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.2 | ROD System Design | 191.153 | 0 | 0% | 0 | 0 | 187 | 0.24064 | 45 | 232 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.3 | ROD Design | 886.8 | 16.4 | 0% | 0 | 16.4 | 816 | 0.25123 | 205 | 1021 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.4 | ROD Test Stand | 144.9 | 45.4 | 0% | 0 | 45.4 | 289 | 0.23875 | 69 | 358 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.5 | ROD Prototype Fabrication | 0 | 0 | 0% | 0 | 0 | 1343 | 0.24051 | 323 | 1666 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.6 | ROD Protype evaluated and Debugging | 0 | 44.6 | 0% | 0 | 44.6 | 80 | 0.2375 | 19 | 99 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.7 | ROD Production Model | 0 | 103.3 | 0% | 0 | 103.3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.8 | ROD Fabrication | 0 | 1043.1 | 0% | 0 | 1043.1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.9 | ROD Installation, Repair and Shipping | 0 | 176.3 | 0% | 0 | 250.739 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.1.3.10 | Project Management | 0 | 42.1 | 0% | 0 | 131.955 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0