NAS15-10000

Modification 1081

ATTACHMENT J-1

AWARD FEE PLAN

FOR EXHIBIT A

October 2001

NAS15-10000

Modification 1081

Attachment J-1

Award Fee Plan

(Revision 7)

I.  Introduction

This introduction is for general information; to the extent that it is incomplete or inconsistent with respect to the text of this plan, the latter shall control.

The award fee arrangement outlined in this plan has been established to motivate the Contractor to strive for excellence in managerial, technical, schedule, cost and subcontracting performance.   Through this plan, the Contractor can earn award fee from a minimum as set forth in the base fee to the maximum amounts stated in clause B.1 of this contract.  Effective October 1, 1999 two new award fee pools and a base fee pool are created for Exhibit A contract changes definitized or authorized after October 1, 1999.  The pools are for technical and cost performance and base fee for the period FY 2000 forward entitled FY2000 Forward Technical Performance Pool, FY2000 Forward Cost Performance Pool, and Base Fee, respectively.

This plan calls for a periodic evaluation of Contractor Exhibit A “on-ground” performance in accordance with the factors called out in Section IV beginning in Fiscal Year 1996 and concluding with the final evaluation utilizing the dollars in Table V.B.1 in December 2002, and a final evaluation utilizing the dollars in Tables V.B.2 and V.B.3 in December 2003.  The Exhibit D effort will be evaluated periodically in accordance with the factors called out in Section IV beginning in Fiscal Year 1999 and ending in FY 2001.  The FY 2000 Forward Technical and Cost Performance Pools will be evaluated periodically beginning in fiscal Year 2000.  In addition, separate periodic evaluations of “on-orbit” performance will begin in Fiscal-Year 2000 and conclude in 2004.

Exhibit A and Exhibit D performance evaluations will be performed by a single Performance Evaluation Board (PEB), which will recommend scores to the Fee Determination Official (FDO).  Each periodic decision of the FDO will result in fee dollars earned which are equivalent to the available fee dollars in each pool multiplied by the final score as a percentage, with the exception of Base Fee, which is addressed in paragraph III.G below.

“On-orbit” evaluations will be performed by a “super board” independent from the PEB.  This board will recommend a score to the Performance Incentive Determination Official (PIDO).  Each periodic PIDO determination will be assessed against a percentage of earned Exhibit A “on-ground” performance dollars which are placed at risk.  Any dollars retained during each on-orbit period become final and are no longer subject to be taken back.  Fee earned for the FY2000 Forward Cost and Technical Performance pools, Base Fee, and for Exhibit D effort is not subject to any “take-back” provisions as set forth in Tables V.B2, V.B3, V.B4, and V.B5.

NAS15-10000

Modification 1081

Any changes to this award fee plan will be made via a bilateral contract modification, except for Exhibit A on-ground areas of emphasis and weightings, which are established unilaterally by the Government.

A hypothetical example of how this plan will operate over the lifetime of the contract is shown in Exhibit A of this Award Fee Plan.

- Organizational Structure

A.  Performance Evaluation Board

The PEB will evaluate the Contractor’s performance as related to the factors listed in Section IV.  At the end of each six-month evaluation period (the schedule for the six-month evaluation periods is identified in Tables V.B.1, V.B.2, V.B.3, V.B.4, and V.B.5), the PEB will prepare a written report of its evaluation which shall include recommendations as to the adjective rating and numerical score to be assigned to the Contractor’s performance during that evaluation period for Exhibit A and Exhibit D.

B.  Performance Monitors

1.  NASA performance monitors shall monitor, evaluate and assess Contractor’s performance in assigned areas and discuss the evaluation results with contractor counterparts as appropriate.  Additionally, the performance monitors shall use, at their discretion, evaluations and assessments from NASA officials in preparing reports on assigned areas.  The performance monitor will periodically prepare reports for the PEB.

2.  The PEB Chair may change monitor assignments at any time without advance notice to the Contractor.

C.  Fee Determination Official

1.  All Exhibit A on-ground and Exhibit D performance recommendations made by the PEB will be considered by the Fee Determination Official (FDO).  The Deputy Associate Administrator for the International Space Station Program will serve as the FDO.  The FDO, after considering available pertinent information and recommendations, shall make a determination in accordance with the provisions of this plan.

2.  The FDO shall appoint the PEB Chair and Members.

D.  Super Board

An evaluation “super board,” separate from the PEB described in paragraph II.A above, referred to in the fourth paragraph of the Introduction, shall be appointed for the purpose of evaluating on-orbit performance as related to evaluation milestones.  It is intended that the super board provide an independent assessment of the Contractor’s on-orbit performance.  To this end, the PIDO shall seek to include non-governmental members when appointing the super board (e.g. academia, Vest committee members).  The Performance Incentive Determining Official (PIDO) is the Deputy Associate Administrator for the International Space Station Program.  The super board may be supported in its collection of performance data for evaluation purposes by NASA performance monitors or other individuals at the discretion of the PIDO.

NAS15-10000

Modification 1081

E.  Performance Incentive Determination Official (PIDO)

1.  All on-orbit performance recommendations made by the super board will be considered by the PIDO.  The PIDO, after considering available pertinent information and recommendations, shall make a determination in accordance with the provisions of this plan.

2.  The PIDO shall appoint the super board Chair and Members.  The Contractor will be notified of the appointment and changes to the super board Chair and Membership.

#### III.	Evaluation Procedures

A.  Interim Exhibit A On-Ground, FY 2000 Forward Technical and Cost Performance Pools, and Exhibit D Performance Evaluations

All Exhibit A on-ground (except for the FGB) and FY 2000 Forward Cost Performance Pool evaluations will be interim in nature.  All FY 2000 Forward Technical Performance Pool evaluations, and Base Fee (interim if overall score is 60 or below as set forth in VIII.A) are final in nature in that they are not subject to on-orbit take back provisions.  However, unearned dollars from these pools will be available for final evaluation upward only.   All Exhibit D performance evaluations will be final in nature.  A determination of the dollars earned for each evaluation period will be made by the FDO within 45 days after the end of the period.  Procedures to be followed in monitoring, assessing, and evaluating Contractor performance during each period, are described below.

1.  No later than 45 calendar days prior to the start of each evaluation period, the Contractor may submit to the Contracting Officer recommended areas of emphasis and weightings for the ensuing evaluation period that are within the general factors listed in Section IV of this plan.  Consideration will be given to the Contractor’s recommendations; however, it is the Government’s responsibility to establish the specific areas of emphasis for each evaluation period.

2.  No later than 30 days prior to the start of each new six-month evaluation period, the Contractor will be notified by the Contracting Officer of the selected areas of emphasis and weightings for that period.  Emphasis will be directed at particular areas under the contract which appear to the Government to be deserving of special attention and will be used in judging the Contractor’s performance.  These areas of emphasis will not necessarily cover the entire spectrum of performance that will be evaluated in determining award fee dollars earned.  Other pertinent factors included under the contract and general factors bearing upon overall performance will be considered as the facts and circumstances of each period may require.

3.  The Contractor shall be apprised of a general assessment of his performance at the mid-point of the period, and at such other times as may be deemed appropriate.  It shall be the purpose of these meetings to discuss any specific areas where the Contractor has excelled, and where future Contractor emphasis may be necessary.

NAS15-10000

Modification 1081

4.  Promptly after the end of each six-month evaluation period, the PEB shall meet to consider all the performance information it has obtained.  At the meeting, the PEB will summarize its preliminary findings and recommendations in the Performance Evaluation Board Report (PEBR).

5.  The Contractor may furnish a separate self-evaluation report for Exhibit A and Exhibit D within 10 calendar days after the expiration of each evaluation period.  These self-evaluation reports shall not exceed 20 pages in length each.  The PEB will not submit its recommendation to the FDO until (1) the Contractor’s self-evaluation report has been received and considered, or (2) the Contractor has provided written notification that a self-evaluation report will not be submitted, or (3) the 10-day period provided for submission of the report has expired.

6.  The PEB Chair will prepare the PEBR for the period and present the findings and recommendations to the FDO.  The reports will include an adjective rating and a recommended performance score with supporting documentation.  The Contractor will be notified of the PEB evaluation and recommended ratings and scores, and will be provided copies of the PEBR.  The Contractor may provide additional information for consideration by the FDO by notifying the PEB Chair of its desire to do so.  This is an opportunity for the Contractor to provide any information which the Contractor believes is relevant to its performance and which may affect the FDO’s determination.  Any additional information should be provided to the PEB Chair within five (5) calendar days of Contractor notification of the PEB recommended rating and score.  This additional Contractor information will be provided to the FDO by the PEB Chair.

7.  The FDO will consider the recommendations of the PEB, the PEBR, information provided by the Contractor, if any, and any other pertinent information in determining the Exhibit A and Exhibit D performance scores.  The FDO’s determination of the scores will be stated in a written Award Fee Determination.

8.  The Award Fee Determination will be provided to the Contractor by the Contracting Officer.  The Contractor may, after notification of the FDO’s determination, request, through the Contracting Officer, a briefing by the FDO.  This briefing should be conducted no later than 45 days following the conclusion of the award fee period.  Award fee determinations made by the FDO may be appealed by the Contractor to the NASA Associate Administrator of Space Flight.

NAS15-10000

Modification 1081

B.  Final Exhibit A Performance Evaluation

After the final on-ground evaluation specified in Table V.B.1, the Contractor’s performance for the Exhibit A on-ground effort (except for the FGB), will be evaluated to determine whether the Contractor’s performance warrants the award of any remaining unearned fee dollars in Table V.B.1, in addition to the total amount previously earned as a result of the periodic evaluations.  After the final on-ground evaluation specified in Table V.B.2, the Contractor’s performance on the remaining Exhibit A on-ground effort will be evaluated to determine whether the Contractor’s performance warrants the award of any remaining unearned fee dollars in Table V.B.2, in addition to the total amount previously earned as a result of periodic evaluations These final evaluations will not result in the reduction in the amount of award fee previously earned.  The process used to determine the final dollars earned for Exhibit A on-ground performance and the FY 2000 Forward Technical Performance and unearned Base Fee will be the same as that cited in A. above.

The Contractor’s performance for FGB effort will be evaluated to coincide with the final acceptance of the FGB.  The award fee determination for this effort will be final and not subject to potential “take back” from subsequent On-Orbit performance evaluations as provided for in this attachment, J-1 Award Fee Plan.  Additionally, any fee not earned by the Contractor shall not be rolled forward to the final on-ground evaluation described above.  Available dollars are set forth in Table V.B1.

- On-Orbit Performance

1.  The on-orbit performance provisions of this plan have been established to recognize on-orbit performance of Contractor products.  With discrete amounts of fee allocated to specific evaluation milestones, the Contractor will have the opportunity to retain 100% of the award fee dollars earned under the Exhibit A on-ground evaluation procedures (Table.V. B.1).  Earnings from Exhibit D, Exhibit A, FY 2000 Forward Technical and Cost pools, and Base fee are excluded from the on-orbit performance evaluation take-back provisions.  Six (6) annual evaluation milestones are established in the Addendum 1, On-Orbit Award Fee Plan, attached.   The contractor’s annual on orbit assessment will evaluate the hardware/software through the period ending October 31st of the respective year.

2.  Areas of emphasis are established as stated in the Addendum 1, On-Orbit Award Fee Plan and the On-Orbit Award Fee Plan. These areas of emphasis do not necessarily cover the entire spectrum of milestone performance that will be evaluated in determining on-orbit performance fee retained.  Other pertinent factors included under the contract, and general factors bearing upon overall milestone performance will be considered as the facts and circumstances may require.

3.  In the event that a mutual agreement on areas of emphasis and milestone pool weightings cannot be reached, the Contracting Officer may resolve areas of disagreement by unilateral determination.

NAS15-10000

Modification 1081

4.  The maximum potential fee retained through on-orbit performance shall be equal to the total earned Exhibit A on-ground performance dollars in Table V. B.1, which excludes Exhibit D earnings and the FY 2000 Forward Technical and Cost Performance and Base Fee dollars set forth in Tables V. B.2., V. B.3., V. B.4.,and  V. B.5.  Each on-orbit performance incentive period evaluation shall be considered final.  Award fee retained for the period will not be subject to “take back.”

5.  Promptly after the end of each on-orbit evaluation milestone, the super board shall meet to consider all the performance information it has obtained.  The board will summarize its findings and recommendations in a Milestone Evaluation Report (MSER).

6.  The Contractor may furnish a self-evaluation report within 10 calendar days of milestone completion.  The board will not submit its recommendation to the PIDO until (1) the Contractor’s self-evaluation report has been received and considered, or (2) the Contractor has provided written notification that a self-evaluation report will not be submitted, or (3) the 10-day period provided for submission of the report has expired.

7.  The super board’s Chair will prepare the MSER and present the findings and recommendations to the PIDO.  The report will include an adjective rating and a recommended performance score with supporting documentation.  The supporting documentation will reflect the rationale of the super board in arriving at their score.  The Contractor will be notified of the board’s performance evaluation and recommended rating and score.  This notification will include the MSER with its supporting documentation.  The Contractor may provide additional information for consideration by the PIDO by notifying the Chair of its desire to do so.  This is an opportunity for the Contractor to provide any information which the Contractor believes is relevant to its performance and which may affect the PIDO’s determination.  Any additional information should be provided to the board Chair within five (5) calendar days of Contractor notification of the board’s evaluation.  This additional Contractor information will be provided to the PIDO by the super board Chair.

8.  The PIDO will consider the recommendations of the super board, the information provided by the Contractor, if any, and any other pertinent information in determining the amount of performance incentive earned.  The PIDO’s determination will be stated in a written Performance Incentive Determination.

9.  The Performance Incentive Determination will be provided to the Contractor by the Contracting Officer no later than 45 days after the end of the evaluation period.  The Contractor may, after notification of the PIDO’s determination, request, through the Contracting Officer, a briefing by the PIDO.  This briefing should be conducted no later than 45 days following the conclusion of the milestone evaluation.  PIDO determinations may be appealed by the Contractor to the NASA Administrator.

NAS15-10000

Modification 1081

- Provisional Payments

1.  Provisional payments will be made to the Contractor on a monthly basis after receipt of the Contractor’s first voucher, in accordance with contract provision G.1.  The amount of award fee which may be provisionally billed each period is 80 percent of the maximum award fee available for that period (see tables V. B.1, V. B. 2., V. B.3., V. B.4., and V. B.5).  The amount of provisional fee which can be paid monthly in any evaluation period shall be prorated equally to the number of months in that period.  The Contractor will submit a separate voucher for provisional fee payments and show Exhibit D fee separately.

2.  All Exhibit A provisional award fee payments will be superseded by the Exhibit A performance evaluation and determinations at the conclusion of each performance period.  All Exhibit D provisional award fee payments will be superseded by the performance evaluations and determinations at the conclusion of each performance period.  The Government will then pay the Contractor, or the Contractor will refund to the Government, the difference between the final fee determination and the cumulative provisional fee payments.  Any additional payment will be made via unilateral modification.  The Contracting Officer will issue a unilateral modification to the contract that will recognize any provisional award fee payments.  Payments will be made based upon the unilateral modification.

3.  Provisional payments are discontinued during any period in which the Government determines that the total provisional payments made during that period will substantially exceed the amount which would be paid based upon the anticipated score for the period.

### E.  FY 2000 Forward Technical Performance Pool

For contract changes definitized after October 1, 1999, and contract changes authorized after October 1, 1999, the Contractor may earn award fee dollars for technical performance. The Contractor’s Technical Performance will be evaluated during the periods as specified in Table V. B.2.  Performance will be evaluated to determine whether the Contractor’s performance warrants the award of dollars for accomplishment in Program Management and Technical Performance, including Schedule, Quality and Safety.  The final evaluation will not result in the reduction in amount of award fee previously earned.  However, any unearned award fee during the stated evaluation periods will be carried forward and made available to the Contractor for a final “look-back” award fee evaluation in addition to the Final Exhibit A On-Ground performance evaluation as stated in paragraph III.B. above.

NAS15-10000

Modification 1081

### F.  FY 2000 Forward Cost Performance Pool

### For contract changes definitized after October 1, 1999, and contract changes authorized after October 1, 1999, the Contractor may earn award fee dollars for cost performance. The Contractor’s Cost Performance will be evaluated during periods as specified in Table V. B.3.  The cost evaluation will focus only on the Contractor’s estimate to complete the contract effective October 1, 1999 through the end of the Contract for Exhibit A effort.  The cost evaluation will take into consideration the contractor’s ability to control, adjust, and accurately project contract costs.

### Base Fee

### The available base fee is set forth in Table V. B.4, entitled “Base Fee”.  The Contractor earns the entire available amount in each period if the overall award fee score is 61 or above.  In the event the contractor fails to obtain an overall score of at least 61 in the applicable award fee period, the base fee for the instant period shall be available as part of the final on-ground look back as set forth in III.B. above.

IV.  Evaluation Factors and Weightings for Exhibit A On-Ground Performance

A.  Weightings for Exhibit A Evaluation Factors

Weightings for each Exhibit A evaluation factor shall be established as set forth in paragraph III.A; however, the factors for the FGB procurement shall not be weighted so as to exceed the proportion of FGB award fee negotiated ($839,000) to the total available award fee for the evaluation period.  Weightings for SDB performance shall never exceed 15 percent.

B.  Exhibit A Performance

1.  Program Management

This factor measures Contractor performance in the overall management of the program, including support to International Partners.  Evaluation will be made of Contractor performance in providing a balanced, coordinated and motivated approach to management of technical and programmatic matters.  Such evaluation will include an assessment of the Contractor performance in the development, analysis, and utilization of management data, total available resources, and program controls to effectively manage the project.  This will involve assessment of contractor activities in planning and control, Government Furnished Property management, contract and subcontract management.  Implementation of adjustments to the project baseline in an efficient manner will be measured and evaluated.

NAS15-10000

Modification 1081

2.  Technical Performance, including Schedule, Quality and Safety

This factor will measure:

a)  The effectiveness and quality of the overall design, development, manufacturing, assembly, and test and checkout activities of the contract, including the overall program technical planning, integration, technical resource allocation, and accomplishment of contract requirements.

b)  Safety and mission assurance (S&MA) performance, taking into consideration quality control, safety, reliability, software product assurance, and maintainability, and the effectiveness with which the Contractor plans and assures that these are considered in engineering and design activities.

c)  Compliance to program schedules, particularly hardware and software delivery schedules and the response to schedule problems, including problems associated with International Partner products and Government Furnished Product.

3.  SDB Performance

This factor will measure the efforts expended by the contractor in achieving the NASA/Contractor team goal of 8 percent SDB participation for total contract effort.  The Contractor commits to expend its best efforts on this contract to achieve the NASA/Contractor team goal of 8 percent SDB participation for the total contract effort, including Exhibit D.

V.  Evaluation Factors and Weightings for Exhibit D

A.  The following factors and weightings will be used for Exhibit D:

| EVALUATION CRITERIA | WEIGHT PERCENTAGE |
| --- | --- |
| I. TECHNICAL PERFORMANCE | 40 |
| a. Technical Performance |  |
| -- Quality of Work |  |
| -- Program Management |  |
| -- Timeliness |  |
| b. Efficiency of Performance of Technical Work |  |
| -- Task Efficiency |  |
| -- Productivity/Quantity of Work |  |
| II. MANAGEMENT | 20 |
| a. Contract Administration |  |
| b. Program/Project Control |  |
| III. SDB PERFORMANCE | 15 |
| IV. COST PERFORMANCE | 25 |

NAS15-10000

Modification 1158

##### VI.  On-Orbit Performance

On-Orbit performance milestone evaluations shall be conducted in accordance with the On-Orbit Award Fee Plan, Addendum 1 to this Plan.  This plan is not applicable to Exhibit D.

VII.  Evaluation Periods and Award Fee Calculation

A.  Maximum Award Fee

The maximum available award fee for this contract is identified in contract clause B.1.

B.  Evaluation Periods and Dollars Available

- The maximum number of award fee dollars available by performance period is provided in Table V. B.1 for DDT&E as of Modification 862:

TABLE V.B.1.

On-Ground Award Fee

| PERIOD | START | END | MAXIMUM |  | MAXIMUM | DOLLARS |
| --- | --- | --- | --- | --- | --- | --- |
| NUMBER | DATE | DATE | AVAILABLE MOD 1024 | CHANGE | AVAILABLE MOD 1030 | EARNED |
| 1 | 4/1/96 | 9/30/96 | 30,616,000 | - 0 - | 30,616,000 | $21,431,200 |
| 2 | 10/1/96 | 3/31/97 | 33,748,833 | - 0 - | 33,748,833 | $0 |
| 3 | 4/1/97 | 9/30/97 | 28,150,368 | - 0 - | 28,150,368 | 19,705,258 |
| 4 | 10/1/97 | 3/31/98 | 24,772,365 | - 0 - | 24,772,365 | 18,083,826 |
| 5 | 4/1/98 | 9/30/98 | 29,031,884 | - 0 - | 29,031,884 | 23,515,826 |
| 6 | 10/1/98 | 3/31/99 | 18,393,506 | - 0 - | 18,393,506 | 14,898,740 |
| 7 | 4/1/99 | 9/30/99 | 11,123,161 | - 0 - | 11,123,161 | 8,564,834 |
| 8 | 10/1/99 | 3/31/00 | 8,727,533 | - 0 - | 8,727,533 | $6,545,650 |
| 9 | 4/1/00 | 9/30/00 | 7,023,351 | - 0 - | 7,023,351 | $5,759,148 |
| 10 | 10/1/00 | 3/31/01 | 3,557,716 | - 0 - | 3,557,716 | $3,024,059 |
| 11 | 4/1/01 | 9/30/01 | 4,071,805 | - 0 - | 4,071,805 | $3,705,343 |
| 12 | 10/1/01 | 3/31/02 | 2,953,753 | - 0 - | 2,953,753 | $2,687,915 |
| 13 | 4/1/02 | 9/30/02 | 351,924 | - 0 - | 351,924 | $327,289 |
| Totals |  |  | 202,522,199 | - 0 - | 202,522,199 | $128,249,088 |
| FGB |  |  | 839,000 |  | 839,000 | $797,050 |
| Total Dollars Earned |  |  |  |  |  | $129,046,138 |

Final		4/1/96		9/30/02					74,273,111*

*Unearned award fee through Period 13 available for final lookback.  Will be updated after end of each period.  In accordance with Section III.B of Attachment J-1, “The Award Fee Plan,” FGB unearned shall not be rolled forward to the final on-ground evaluation.	      .

NAS15-10000

MOD 1171(S/A)

2.  The maximum number of award fee dollars available by performance period is provided in Table V. B.2 for FY 2000 Forward Technical Performance Award Fee:

TABLE V. B.2.

## FY 2000 Forward Technical Performance Award Fee

| PERIOD | START | END | MAXIMUM | CHANGE | MAXIMUM | DOLLARS |
| --- | --- | --- | --- | --- | --- | --- |
| NUMBER | DATE | DATE | AVAILABLE MOD 1167 |  | AVAILABLE MOD 1171 | EARNED |
| 8 | 10/1/99 | 3/31/00 | 3,929,528 |  | 3,929,528 | 2,947,145 |
| 9 | 4/1/00 | 9/30/00 | 7,420,414 |  | 7,420,414 | 6,084,739 |
| 10 | 10/1/00 | 3/31/01 | 8,925,787 |  | 8,925,787 | 7,586,919 |
| 11 | 4/1/01 | 9/30/01 | 9,420,431 |  | 9,420,431 | 8,572,592 |
| 12 | 10/1/01 | 3/31/02 | 16,963,302 |  | 16,963,302 | 15,436,605 |
| 13 | 4/1/02 | 9/30/02 | 15,341,585 |  | 15,341,585 | 14,267,674 |
| 14 | 10/01/02 | 3/31/03 | 13,514,957 | 348,470 | 13,863,427 | TBD |
| 15 | 4/1/03 | 12/31/03 | 18,890,617 | 560,662 | 19,451,279 | TBD |
| Totals |  |  | 94,406,621 | 909,132 | 95,316,753 |  |
| Total Dollars Earned |  |  |  |  |  | TBD |
| Final |  | 12/31/03 | TBD | TBD | TBD | TBD |

NAS15-10000

MOD 1171 (S/A)

3.  The maximum number of award fee dollars available by performance period is provided in Table V. B.3 for FY 2000 Forward Cost Performance Award Fee:

TABLE V. B.3.

FY 2000 Forward Cost Performance Award Fee

| PERIOD | START | END | MAXIMUM | CHANGE | MAXIMUM | DOLLARS |
| --- | --- | --- | --- | --- | --- | --- |
| NUMBER | DATE | DATE | AVAILABLE MOD 1167 |  | AVAILABLE MOD 1171 | EARNED |
| 8 | 10/1/99 | 3/31/00 | 2,365,407 |  | 2,365,407 | 1,655,785 |
| 9 | 4/1/00 | 9/30/00 | 4,712,422 |  | 4,712,422 | 3,298,695 |
| 10 | 10/1/00 | 3/31/01 | 6,682,021 |  | 6,682,021 | 4,811,055 |
| 11 | 4/1/01 | 9/30/01 | 7,069,185 |  | 7,069,185 | 5,867,424 |
| 12 | 10/1/01 | 3/31/02 | 13,552,773 |  | 13,552,773 | 10,571,163 |
| 13 | 4/1/02 | 9/30/02 | 12,578,340 |  | 12,578,340 | 10,691,589 |
| 14 | 10/1/02 | 3/31/03 | 11,146,216 | 282,842 | 11,429,058 | TBD |
| 15 | 4/1/03 | 12/31/03 | 15,601,869 | 455,070 | 16,056,939 | TBD |
| Totals |  |  | 73,708,233 | 737,912 | 74,446,145 |  |
| Total Dollars Earned |  |  |  |  |  | TBD |
| Final |  | 12/31/03 | TBD | TBD | TBD | TBD |

*Spread based on cost dollar profile

All dollars unearned will be subject to a final assessment in conjunction with the final Exhibit A on-ground performance evaluation.  The final look-back shall be subject to an upward or downward adjustment.

The base fee dollars available by performance period is provided in Table V. B.4 for Base Fee:

TABLE V. B.4.

Base Fee

| PERIOD | START | END | DOLLARS | CHANGE | DOLLARS | DOLLARS |
| --- | --- | --- | --- | --- | --- | --- |
| NUMBER | DATE | DATE | MOD 1157 |  | MOD 1171 | EARNED |
| 8 | 10/1/99 | 3/31/00 | 1,558,625 |  | 1,558,625 | 1,558,625 |
| 9 | 4/1/00 | 9/30/00 | 2,272,155 |  | 2,272,155 | 2,272,155 |
| 10 | 10/1/00 | 3/31/01 | 1,508,348 |  | 1,508,348 | 1,508,348 |
| 11 | 4/1/01 | 9/30/01 | 1,551,268 |  | 1,551,268 | 1,551,268 |
| 12 | 10/1/01 | 3/31/02 | 67,970 |  | 67,970 | 67,970 |
| 13 | 4/1/02 | 9/30/02 | 124,963 |  | 124,963 | 124,963 |
| 14 | 10/1/02 | 3/31/03 | 132,791 | 12,944 | 145,735 | TBD |
| 15 | 4/1/03 | 12/31/03 | 158,617 | 20,826 | 179,443 | TBD |
| Totals |  |  | 7,374,737 | 33,770 | 7,408,507 | TBD |
| Total Dollars Earned |  |  |  |  |  | TBD |

NAS15-10000

Modification 1105

All dollars unearned will be subject to a final assessment in conjunction with the final Exhibit A on-ground performance evaluation.  The final look-back shall be subject to an upward adjustment only.

- The maximum number of award fee dollars available by performance period is provided in Table V.B.5 for Exhibit D:

TABLE V.B.5

Exhibit D - LOE

| Period Number | Start Date | End Date | Maximum $ Available | Dollars Earned |
| --- | --- | --- | --- | --- |
| 1 | 10/1/98 | 3/31/99 | $ 5,145,500 | $ 4,425,130 |
| 2 | 4/1/99 | 9/30/99 | $ 5,145,500 | $ 4,270,765 |
| 3 | 10/1/99 | 3/31/00 | $ 8,037,301 | $ 6,510,214 |
| 4 | 4/1/00 | 9/30/00 | $ 8,037,300 | $6,992,451 |
| 5 | 10/1/00 | 3/31/01 | $ 6,105,674 | $5,189,823 |
| 6 | 4/1/01 | 9/30/01 | $ 6,105,673 | $5,617,219 |
| Total |  |  | $38,576,948 | $33,005,602 |

The above estimated hours differ from target hours in Clause B.11, LOE due to the exclusion of the 212,978 actual hours worked in FY 98 under a fixed fee arrangement.

The maximum available award fee in the above table is based on the assumption that the hours worked will correspond with the hours in Table V. B 5.  Should the hours worked represent a variation of +/- 20 percent from those in the table, then the table will be modified to re-phase the total hours and the available award fee to the appropriate award fee period.  Neither the total hours nor the total maximum available award fee shall change as a result of re-phasing.

C.  Dollars Earned

Upon evaluation of the Contractor’s performance for each period, the graded score as a percentage will be applied to the dollars available per tables V.B.1, V.B.2, V.B.3, and V.B.5 to determine the dollars earned.

For example:

Period 1 = $28.40M available dollars with a score of 85% assessed

by the FDO:

$28.40M X 85% = $24.14M earned.

For base fee dollars per Table V.B.4, upon evaluation of the Contractor’s performance for each period, the Contractor earns the total dollars available for each period if the award fee score is 61 or above.

NAS15-10000

Modification 1105

D.  Dollars Not Earned

1.  All Exhibit A dollars in Tables V. B.1., V. B.2., V.B.3 and dollars in Table V. B.4. not earned will be subject to a final assessment at the final on-ground performance evaluation (ref. paragraph III.B).  This will be the numeric difference between the total dollars earned and the total award fee pool.  Any unearned dollars may be available for the lookback.  For the FY2000 Technical pool any unearned award fee shall be available for final upward lookback evaluation.  In addition any unearned base fee not earned in accordance with Section III.G shall be earned if the average award fee score is greater than 60.

2.  All Exhibit D dollars not earned will not be rolled forward and will not become available for future period assessments.

E.  On-Orbit Performance

1. In each performance milestone evaluation, the PIDO will determine a numeric score based on assessment of on-orbit performance.  That numeric score (expressed as a percentage) will be applied to the cumulative on-ground dollars earned (which excludes FY 2000 Forward Technical and Cost Performance pools, base fee, and Exhibit D) as of the end of the on-ground evaluation period immediately preceding the determination of such numeric score.  The calculation of dollars shall always be expressed to the nearest one thousand

.

For example:  Milestone B provides 60% of the total award fee pool dollars available.  Assume the cumulative Exhibit A on-ground performance dollars earned is $97.045M (out of a total possible of $120.0M) and the numeric score as determined by the PIDO is 80%.

$97.045M x 60% = $58,227M available to be retained for this milestone.

$38.818M x .80 (grade) = $46.582M retained.

TABLE V.E

On-Orbit Award Fee

Milestone         	         Milestone     	        Weight        $ Available       	   $ Retained

(Date)                                            for Retention

___A		March 2000	15%		$17,775,672	$17,775,672

###### B		Oct 2001	60%		$57,364,658	$57,364,658

###### C		Oct 2002	75%		TBD		TBD

###### D		Oct 2003	85%		TBD		TBD

###### E		Oct 2004	100%		TBD		TBD

###### Final		Residual Dec 2004	  		TBD		TBD

Total Dollars Retained                        	                          			TBD

NAS15-10000

Modification 1081

*Note:  This table will be updated through contract modification.

F.  Award Fee

1.  Once the determination has been made of the dollars retained, the resulting amounts will be recorded in Table V.E above.

2.  All on-orbit dollars not retained from milestones A through F along with all remaining earned Exhibit A on-ground dollars which have yet to be made available,

will be subject to a final assessment.

3.  Once the determination of final dollars has been made for the final milestone, any fee to be refunded to the Government will be calculated by subtracting the total dollars retained on-orbit as stated in Table V.E from the total dollars earned on-ground as stated in Table V. B.1.

For example:  $147.071M - $141.633M = $5.438M

VIII.  Evaluation Scale

A.  Award Fee Curve

The award fee rating Table VI.B below includes adjectival ratings as well as a numerical scoring system of 0-100.  For this plan, earned award fee dollars and dollars to be retained as a result of on-orbit performance are calculated by applying the total numerical score to available dollars.  For example, a numerical score of 85 yields 85 percent of available award fee dollars.  Notwithstanding the preceding, the contractor will not earn Exhibit A on-ground performance dollars (or retain any earned dollars through the on-orbit evaluation process for Exhibit A on-ground), FY 2000 Forward Technical and Cost Performance, Base fee, or Exhibit D award fee dollars for any evaluation period when the interim score is “poor/unsatisfactory” (less than 61).  Further, any Exhibit A on-ground, FY 2000 Forward Technical and Cost Performance or Exhibit D performance factor receiving a grade of “poor/unsatisfactory” (less than 61) will be assigned zero dollars for the period.  On-orbit performance factors (assembly, operation, and science) will be scored on a scale of 0-100% in accordance with the on-orbit scoring guidelines described in Tables V. B.A., V. B.B., and V. B.C of the On-Orbit Award Fee Plan, Addendum to Attachment J-1.

NAS15-10000

Modification 1081

- Exhibit A On-Ground Dollars Scoring for Technical and Project Management, FY 2000 Forward Technical and Cost Performance Pools and Exhibit D Dollars Scoring for Technical, Program Management, and Cost Performance:

TABLE VI.B

Adjective	 Range of

Rating		   Points                                            Description

_____________________________________________________________________

Excellent	        (100 - 91)    Of exceptional merit; exemplary performance in a timely, efficient manner; very minor (if any) deficiencies with no adverse effect on overall performance.

Very Good         (90 - 81)    Very effective performance, fully responsive to contract; contract requirements accomplished in a timely, efficient manner for the most part; only minor deficiencies.

_____________________________________________________________________

Good	         (80 - 71)     Effective performance; fully responsive to contract requirements; reportable deficiencies, but with little identifiable effect on overall performance.

Satisfactory       (70 - 61)    Meets or slightly exceeds minimum acceptable standards;  adequate results; reportable deficiencies with identifiable, but not substantial, effects on overall performance.

Poor / Unsat.      (0 - 60)     Overall performance does not meet minimum acceptable standards; remedial action required in one or more areas; numerous deficiencies which adversely affect overall performance.

C.  On-Orbit Performance Scoring

On-orbit scoring guidelines are contained in the On-Orbit Award Fee Plan Addendum 1, Tables V. B.A., - V. B.C.

IX.  Disputes

Award fee determinations made by the Government are subject to the Disputes clause.

NAS15-10000

Modification 1081

(THIS PAGE DELIBERATELY LEFT BLANK)

NAS15-10000

Modification 1081

Addendum to Attachment  J-1

(Award Fee Plan)

On-Orbit Award Fee Plan

October 2001

NAS15-10000

Modification 1081

Table of Contents

| I. | Introduction | 16 |
| --- | --- | --- |
| II. | Approach/Objectives | 16 |
| III. | Evaluation Procedures | 16 |
| 1V. | Evaluation Milestones, Factors, and Weightings | 17 |
| V. | Evaluation Scale | 18 |
| VI. | Scoring Methodology and Fee Calculation | 20 |
| VII. | Contingency Provisions | 20 |
| VIII. | Changes | 21 |
| IX. | Precedence | 21 |
| X. | Denied Opportunity | 21 |
| XI | Performance During Sustaining Engineering | 22 |

Exhibits -

Exhibit 1 -- Areas of Emphasis, Performance Evaluation - Period A

Exhibit 2 -- Areas of Emphasis, Performance Evaluation - Period B through Final Evaluation

NAS15-10000

Modification 1081

I.  Introduction

A.  The on-orbit incentive outlined in this plan has been established to motivate the Contractor to strive for excellence in all aspects of performance leading to successful on-orbit operations of the space station.  This plan is intended to supplement and amplify the award fee provisions as stipulated in Attachment J-1, regarding on-orbit performance.  In the event of a conflict, the provisions of the Attachment J-1, Award Fee Plan shall prevail.

B.  This plan provides the identification of, the number of, the timing of, and the weighting of the evaluation milestones.  It further defines the “Areas of Emphasis” that are associated with each of the evaluation periods.

II.  Approach/Objectives

Achieving satisfactory on-orbit performance is absolutely essential.  The approach used in this plan is to provide a simple and easy to understand set of Areas of Emphasis, which define the critical performance parameters at selected milestones, as well as the corresponding criteria by which the contractor’s performance will be scored.  The objective is to promote quality by clearly identifying the primary Program goals in a manner which may be easily understood by the contractor personnel charged with doing a quality job.

III.  Evaluation Procedures

A.  The methodology for on-orbit performance evaluation is per Attachment J-1, Paragraph III.C.  Paragraph IV. B, below, further describes three areas of emphasis against which on-orbit performance will be evaluated.  Within each of the three areas of emphasis, critical parameters and specific criteria have been identified to serve as the focus of attention and the basis for evaluating performance.  The Exhibits provide the detailed listing of areas of emphasis, the relative importance of these three areas of emphasis, as well as the corresponding on-orbit performance criteria for each of the evaluation periods.

B.  Award fee performance assessments of station systems and components are against planned station operation for each individual evaluation period.  Station level specification requirements are not fully imposed until Assembly Complete.

C.  The NASA evaluation process will be a qualitative assessment of how well the Contractor performed to the areas of emphasis, critical parameters and specific criteria for the period being evaluated.  If the systems and components are found to be performing outside of specified requirements or planned operational capability, there is valid cause for adjusting the Contractor’s score.  Conversely, earned on-ground award fee shall not be subject to reduction in the on-orbit process if specified requirements or planned operational capabilities are met.

NAS15-10000

Modification 1081

IV.  Evaluation Milestones, Factors, and Weighting

A.  Evaluation Milestones:  (Reference Attachment J-1, paragraph III. C. 1.)

There will be 6 evaluation milestones, including the Final evaluation, as delineated herein.  Milestones are defined below:

| MILESTONE |  | DATE |
| --- | --- | --- |
| Milestone A (2R) |  | Mar 2000 |
| Milestone B |  | October 31, 2001 |
| Milestone C |  | October 31, 2002 |
| Milestone D |  | October 31, 2003 |
| Milestone E |  | October 31, 2004 |
| Final Evaluation |  | December 31, 2004 |

Milestone completion for Milestone A is defined as  “the docking event.”  Milestone completion for milestones B through Final are defined by the date.

B.  Evaluation Factors: (Reference Attachment J-1, paragraph IV. C.)

The areas of emphasis that will form the basis for the critical parameters against which on-orbit performance will be judged are:

Assembly configuration completed as planned, within mission limitations (Table V. B.A)

Station systems and components operating according to design specification and according to planned stage capabilities (Table V. B.B)

Science capabilities and timelines supported as specified/planned (Table V. B.C)

NAS15-10000

Modification 1081

C.  Evaluation Weighting:  (Reference Attachment J-1, paragraph V. E.)

For the 6 milestones, the percentage of cum-to-date on-ground award fee dollars earned that are subject to on-orbit performance evaluation are:

Milestone A   15%

Milestone B   60%

Milestone C   75%

Milestone D   85%

Milestone E   100%

Residual

Final On-Orbit Evaluation -- all remaining on-ground award fee dollars earned as set forth in Table V. B.1 of Attachment J-1, but not previously subjected to on-orbit performance evaluation, plus all remaining on-orbit performance fee dollars that were not retained.

V.  Evaluation Scale

A.  The award fee curve for on-orbit performance evaluations is specified in the Award Fee Plan, Section VI. Evaluation Scale, paragraph A. Award Fee Curve.

B.  Scoring guidelines for each of the areas of emphasis are:

Table V. B.A

| Assembly configuration completed as planned | Score |
| --- | --- |
| Stage/element assembly completed as planned, with only minor difficulties | 91-100% |
| Stage/element assembly completed as planned, with some difficulties; unplanned crew intervention | 71 - 90% |
| Stage/element assembly completed with significant difficulty; unplanned re-supply required | 51 - 70% |
| Assembly operations severely impaired; next assembly sequence not precluded | 1 - 50% |
| Stage/element lost, non-recoverable, or must be returned; next assembly sequence precluded | 0% |

NAS15-10000

Modification 1081

Table V. B.B

| Station systems operating to plan | Score |
| --- | --- |
| Full functionality, with only minor deficiencies; meets specification/ supports expectations | 91-100% |
| Functionality limited, with some deficiencies; supports basic expectations | 71 - 90% |
| Functionality limited; significant work-arounds required; supports minimal expectations | 51 - 70% |
| Functionality severely limited; re-design required and/or highly constrained operations result | 1 - 50% |
| Total system failure; i.e., it is unable to perform to any degree | 0% |

Table V. B.C

| Science capabilities and timelines supported | Score |
| --- | --- |
| All significant science objectives supported successfully by vehicle performance | 91 - 100% |
| Science objectives moderately degraded due to vehicle performance | 71 - 90% |
| Significant science objectives partially supported by vehicle performance | 51 - 70% |
| Science objectives severely degraded due to vehicle performance | 1 - 50% |
| Science objectives not supported to any degree, due to vehicle performance | 0% |

NAS15-10000

Modification 1081

VI. Scoring Methodology and Fee Calculation

A.  The score for each milestone is calculated by multiplying the weighting for each area of emphasis (assembly, operation, or science) by its individual score (ranging from 0 - 100%), then adding the 3 results.  The result of adding the 3 results together is the total score for that milestone.  The score is than applied to the Award Fee Curve in Attachment J-1, Section VI.A.

The following example depicts the scoring method:

| An Assembly weighting of 40% multiplied by a score of 78% ------ | .40 X .78 = .31 |  |
| --- | --- | --- |
| An Operation weighting of 50% multiplied by a score of 87% ------ | .50 X .87 = .43 |  |
| A Science weighting of 10% multiplied by a score of 60% ---------- | .10 X .60 = .06 |  |
|  | Total Score = .80* |  |

*This score is then applied to the Award Fee Curve.

VII.  Contingency Provisions

A.  Failures/problems that would have been discovered prior to flight through more extensive environmental testing or interface testing that was eliminated or excluded because of Program cost/schedule constraints will be mitigating factors when evaluating scores.  The unavailability of adequate spares will also be considered a mitigating factor when evaluating any resulting failures/problems.  The Contractor’s evaluation score will not be reduced for problems caused by the Government, International Partners, acts-of-God, or for problems where the Contractor is not the source of the problem.

B. Exceedences, anomalies, discrepancies or failures induced by external interfaces, e.g. crew, shuttle, ground systems, or external communications operating outside of specified requirements, interface limits or related operational constraints shall not be cause for reduced evaluation scores, except in the case where an out-of-specification operation was necessitated by a prior failure of a contractor provided item.

C.  Evaluation scores shall not be reduced as a result of the failure of Government or International Partner hardware/software/services to perform as specified or intended.  Hardware/software built and previously delivered by the Contractor under this contract shall be excluded from the definition of “Government hardware” for purposes of the Contractor’s performance evaluation.  Hardware/spares not built and delivered under this Prime contract shall be included in the definition of “Government hardware” for purposes of Contractor’s performance.  For spares that were qualified under the Prime contract but not purchased under the Prime contract, the Contractor will be responsible for deficiencies related to design, but not responsible for deficiencies related to materials or workmanship.

NAS15-10000

Modification 1081

D.  If, prior to provisional DD250, during on-ground processing for launch, the Contractor has reason to believe that an item of hardware/software has failed or is not in a flight ready condition, then the Contractor shall give immediate notice to NASA.  If NASA elects to continue, and degraded performance results from the identified condition, NASA shall not reduce the Contractor's on-orbit evaluation score for the subject hardware/software item.

E.  Failures beyond the reliability and maintainability limits of the system shall not be cause for lowered evaluation scores.

VIII.  Changes

Any changes to this plan will be made via bilateral contract modification

IX.  Precedence

This plan is intended to supplement and amplify the award fee provisions as stipulated in Attachment J-1.  In the event of a conflict, the provisions of the Award Fee Plan shall prevail.

X.  Denied Opportunity

If, through no fault of the Contractor, any flight is delayed beyond its estimated (contract assembly sequence) date plus 3 months OR beyond the estimated date of the performance milestone (paragraph IV, above), whichever date occurs first, the Contractor will be evaluated on the performance of the flights accomplished before the delay resulting in the incomplete milestone.  The amount of fee subject to retention through the on-orbit evaluation process will be that percentage equivalent to the percentage of the milestone completed OR 100% of the available fee if the estimated date of the end of the performance milestone occurred first.  The interim amount available for retention will be determined by multiplying the percentage of flights completed by the cumulative on-ground performance dollars earned to date.  The result is then multiplied by the weighting designated for the milestone.  The evaluation of any interim milestone which is a result of the operation of the clause will be in accordance with this on-orbit award fee addendum.  Deferred fee, if any, will be made available for a final milestone performance evaluation of the segment on-orbit after an additional 3 months (for a total of 6 months delay) OR the estimated date of the performance milestone, whichever date occurs first.  For example:

f flight 4R.1 were delayed 3 months, the percentage of the completed milestone subject to evaluation would be 3 completed flights out of a total of 11 (27.3%).

(27.3% X 88.565M Cum earned*) X 20% milestone weighting = $4.836M

The fee deferred from the above interim evaluation (72.7%) would be evaluated for retention 3 months later, applied against the milestone weighting.

(72.7% X 88.565M Cum earned*) X 20% milestone weighting = $12.877M

* Cum dollars taken from Exhibit ‘A’ of Attachment J-1

The following graph and examples depict the operation of the above paragraph:

NAS15-10000

Modification 1081

Further, Boeing and NASA will enter into negotiations of a revised flight/assembly schedule and associated on-orbit milestones which will be added to the contract through a bilateral modification.

XI.  Performance During Sustaining Engineering

In the event that NASA fails to contract for sustaining engineering (for the period of performance that is the concurrent period of performance for the delivery of the ISS assembly complete plus 12 months) from the Contractor (reference the SE definition, below,) the Contractor’s award fee earned on-ground but not retained through on-orbit evaluation will not be subject to further evaluation or take back after the date that sustaining engineering is ended.

For purposes of this clause, sustaining engineering applies to Contractor-provided hardware and software items and to the system analysis to facilitate anomaly isolation and system performance assessments which includes non-contractor provided hardware and software.  Sustaining engineering is defined as the engineering responsibility for flight hardware and software after delivery to the launch site.  This is limited to launch processing support; analysis of vehicle performance; maintenance of system analytical models; and development of software modifications.

NAS15-10000

Modification 1081

On-Orbit Award Fee Plan

Exhibits 1 and 2

NAS15-10000

Modification 1081

Exhibit 1  Areas of Emphasis, Performance Evaluation - Period A

MILESTONE COMPLETION:  Element 2R delivered on-orbit

ESTIMATED COMPLETION DATE:  ’ March 2000

PERIOD WEIGHTING: 15%

PROJECTED ASSEMBLY SEQUENCE THIS PERIOD:

| Flight | Delivered Elements |
| --- | --- |
| 1A/R | FGB |
| 2A | Node 1 |
| 2A.1 | Spacehab Double Cargo Module |
| 1R | Service Module |
| 2A.2 | Spacehab Double Cargo Module; Strela Components |
| 3A | Z1Truss, CMGs, Ku-band, S-band Equipment |
| 2R | Soyuz |

AREAS OF EMPHASIS: (Reference Attachment J-1, paragraph IV. C.)

The relative importance of the 3 top level areas of emphasis for this period are:

| Assembly configuration completed as planned, within mission limitations | 70% |
| --- | --- |
| Station systems and components operating according to design specification and according to planned stage capabilities | 30% |
| Science capabilities and timelines supported as specified/planned | 0% |

CRITICAL PARAMETERS/ SPECIFIC CRITERIA:

The critical parameters and specific criteria to serve as the focus of attention and the basis for judging performance as follows:

1)	The elements to be assembled on-orbit are listed in the first column in the table below.  Emphasis is placed on the ability for each successive arriving launch package to be successfully mated and integrated with the previous stage.  Each stage on-orbit is ready to accept the next assembly with respect to physical and functional configuration.

2)	The systems/subsystems/components planned to operate are listed in the second column. Emphasis is placed on the ability for each stage to be successfully activated, with its systems operating as planned for this stage of assembly.  Each stage on-orbit will operate and survive until the next launch package or re-supply mission is successfully integrated.

NAS15-10000

Modification 1081

3)	The science capabilities planned to be supported are listed in the third column. Emphasis is placed on the ability to provide power, data handling, and overall environment necessary to conduct science.  The Contractor will not be judged for the success/failure of the science itself.

Exhibit 1:  Areas of Emphasis, Performance Evaluation - Period A (Continued)

| Elements: | Capabilities: | Science Capabilities: |
| --- | --- | --- |
| 1A/R -- FGB 2A -- Node 1, PMA-1 & PMA-2 2A.1 – Spacehab Double Cargo Module 1R – Service Module 2A.2 – Spacehab Double Cargo Module; Strela Components 3A – Z1 Truss, CMGs, Ku-band, S-band Equip., PMA3, EVAS 2R -- Soyuz | Interface between U.S. and Russian elements using PMA-1 Shuttle docking location using PMA-2. Re-boost & attitude control (SM & FGB) Power generation (SM &FGB) Progress refueling/resupply Life support for crew of 3 (SM) Crew transportation & Lifeboat (Soyuz) Russian Orlan EVA Capability | None |

NAS15-10000

Modification 1081

Exhibit 2  Areas of Emphasis, Performance Evaluation - Period B through Final Evaluation Period

AREAS OF EMPHASIS: The Areas of emphasis for the Periods B through the final period are set forth herein.

The relative importance of the 3 top level areas of emphasis for this period are:

| Assembly configuration completed as planned, within mission limitations | 40% |
| --- | --- |
| Station systems and components operating according to design specification and according to planned stage capabilities | 50% |
| Science capabilities and timelines supported as specified/planned | 10% |

CRITICAL PARAMETERS/ SPECIFIC CRITERIA:

The critical parameters and specific criteria to serve as the focus of attention and the basis for judging performance as follows:

- The elements to be assembled on-orbit are listed in the first column in the table below.  Emphasis is placed on the ability for each successive arriving launch package to be successfully mated and integrated with the previous stage.  Each stage on-orbit is ready to accept the next assembly with respect to physical and functional configuration.

2)	The systems/subsystems/components planned to operate are listed in the second column. Emphasis is placed on the ability for each stage to be successfully activated, with its systems operating as planned for this stage of assembly.  Each stage on-orbit will operate and survive until the next launch package or re-supply mission is successfully integrated.

- The science capabilities planned to be supported are listed in the third column. Emphasis is placed on the ability to provide power, data handling, and overall environment necessary to conduct science.  The Contractor will not be judged for the success/failure of the science itself.

NAS15-10000

Modification 1081

| Mission Assembly Elements | Performance Capabilities | Science Capabilities |
| --- | --- | --- |
| 2P | Progress-M1 | SM Outfitting, Refueling and Resupply | None |
| 4A | P6 Truss, PV Module S4 and P6 Truss Radiators, and S-Band Equipment | US power generation and S-band (low rate) |  |
| 5A | U.S. Laboratory and PDGF | Active thermal control, US life support, on-board command and control, high rate S-band, non-propulsive attitude control, and interior audio |  |
| 3P | Progress-M | Refueling and Resupply |  |
| 5A.1 | Lab System Racks, RSR, and RSPs | Interior Video | Initial Payload utilization and Ku-band operational to support early science capability |
| 6A | Lab Payload Racks, RSRs, RSPs, UHF and SSRMS | Robotic capability and exterior communication via UHF |  |
| 2S | Soyuz-TM | Crew Lifeboat Exchange |  |
| 4P | Progress-M1 | Refueling and Resupply |  |
| 7A | Joint Airlock and High Pressure Gas Tanks | Airlock operational to provide US based EVA and HP Gas to augment Russian gas re supply system | N2 for Science Payloads |
| 7A.1 | RSRs, RSPs, ISPRs, and Early Ammonia Servicer | Ammonia Resupply for Thermal Control and Crew Rotation |  |
| 5P | Progress-M | Refueling and Resupply |  |
| 4R | Docking Compartment 1 (Strela 2) | Transfer equipment and supplies to ISS and install Cargo Cranes RS Airlock, 3rd RS Docking Port |  |
| 3S | Soyuz-TM | Crew Lifeboat Exchange |  |
| 6P | Progress-M1 | Refueling and Resupply |  |
| UF 1 | RSRs, RSP-2, ISPRs, and ORUs | Transfer equipment and supplies to ISS and Crew Rotation |  |
| 7P | Progress-M1 | Refueling and Resupply |  |

NAS15-10000

Modification 1081

| Mission Assembly Elements | Performance Capabilities | Science Capabilities |
| --- | --- | --- |
| 8A | S0 Truss, MT, GPS, Lab and Node 3 Umbilicals, and Airlock Spur | US GN&C attitude and state determination | Automated Procedure Processing |
| 4S | Soyuz-TM | Crew Lifeboat Exchange |  |
| UF 2 | RSRs, RSP-2, ISPRs, MBS, PDGF, and SMDP | Mobile Robotics, and transfer equipment and supplies to ISS and Crew Rotation |  |
| 9A | S1 Truss, CETA Cart A, Starboard Central Radiator Panels and Boom, and S-band Equipment | S-Band redundancy, exterior video, and non-robotic translation |  |
| 11A | P1 Truss, CETA Cart B, Port Central Radiator Panels and Boom, and UHF | Expanded UHF coverage and non-robotic translation |  |
| 5S | Soyuz-TMA | Crew Rotation |  |
| ULF 1 | ISPRs and ESP-2 with ORUs | Crew Rotation |  |
| 12A | P3 Truss and PV Module P4 with UCLAS and Battery Sets, Radiator and Port Inboard SA 4A and 2A | Install truss segments, and deploy Solar Arrays/PV Radiator | Unpressurized payload utilization sites |
| 6S | Soyuz-TMA | Crew Lifeboat Exchange |  |
| 12A.1 | Space Hab Single Cargo Module, P5 Truss, ESP-2 ORU, and PVRGF OSE | Additional power (alpha tracking), flexibility (MBSU), and thermal control |  |
| 13A | S3 Truss and PV Module S4 with PAS and Battery Sets, and Starboard Inboard SA 3A and 1A | Additional power | Unpressurized payload utilization sites and increased power resources available for utilization |
| 13A.1 | Space Hab Single Cargo Module, S5 Truss, and PVRGF OSE | Additional Power (P6 relocation) |  |
| 7S | Soyuz-TMA | Crew Lifeboat Exchange |  |
| 15A | S6 Truss with Battery Sets and PV Module S6 Truss Radiator and Starboard Outboard SA 1B and 2B | Additional power | Increased power resources available for utilization |
| 10A | Node 2 (DDCU Racks and Zero-g Stowage Racks) and PDGF | Additional power distribution, berthing docking ports |  |
| 8S | Soyuz-TMA | Crew Lifeboat Exchange |  |
| 1J/A | JEM ELM-PS Module Core with System Racks, Stowage Rack and ISPRs, SPP SA Truss, and SM M/OD Shields, NTA and ATA | Transfer equipment and supplies to ISS, install ELM-PS/SM M/OD Shields, and deploy Solar Array |  |
| ATV 1 | Automated Transfer Vehicle | Alternate Logistics Carrier, Refueling and Resupply |  |
| 1J | JEM PM Core, System Racks and RMS | Additional Robotics capability | International utilization volume provided by JEM pressurised module |
| 3R | Universal Docking Mechanism with LSS | Redundant non-propulsive attitude control |  |
| 9S | Soyuz-TMA | Crew Lifeboat Exchange |  |
| UF 3 | RSPs, RSR, ISPRs, JEM Proximity/ICS Rack with SIGI Antenna, EXPRESS Pallet 1 and Cross Bay Carrier | Expanded GPS coverage and transfer equipment and supplies to ISS | Express Pallet 1 provides first significant unpressurized payload utilization availability |
| 1E | Columbus Module Core with Integrated System Racks and ISPRs | Transfer equipment and supplies to ISS and install Columbus Module Core | Increased utilization volume provided by COF pressurized module |

# Text boxes

Appendix A