# Clinical Investigator Student Trainee (CIST) Forum

### November 1-3, 2006

# Contractual Services:  Scope of Work

- Invitations

  - Develop preliminary announcement of event for approval, coordinate printing, and mail to all attendees (from up to six programs)

  - Develop formal event invitation for approval, coordinate printing, and mail to attendees and guests

  - Develop invitation to Wednesday evening welcome event and Thursday evening dinner, coordinate printing, and mail

- Preliminary Arrangements and Agenda Preparation

  - Develop agenda in consultation with NIH contacts

  - Once speakers are confirmed, communicate with them about audiovisual needs and confirm times and locations

  - Obtain handouts in advance from speakers for inclusion in participant packets and provide extra copies at the meeting site

  - Remind speakers two weeks prior to event and again on the day before; ensure that a positive response is received

- Travel Arrangements:  Hotel, Air, Local Transport

  - Book hotel rooms (at either Bethesda Sheraton Four Points or Bethesda Holiday Inn.  Two students per room; maximum 70 rooms.  Once head count is confirmed, may need to decrease room allocation)

  - Hotel reservations needed for two nights 11/1 and 11/2

  - Communicate regularly with hotel on numbers, to avoid cancellation charges

  - Communicate with all hotel registrants regarding travel arrangements, allowable hotel charges; provide maps, local travel information

  - Book round trip air travel for up to 160 U.S. participants (Doris Duke, Fogarty International Center-Ellison, Sarnoff, NCRR), make changes as necessary (contingent upon cost, and according to predetermined guidelines), and confirm arrangements with travelers

  - Arrange for shuttles, and ensure all passengers accounted for on Wednesday evening, Thursday morning to NIH, Thursday evening, and Friday morning to NIH

- Registration

  - Maintain list of confirmed participants and communicate RSVPs and regrets to NIH contacts twice monthly and then on a daily basis in the two weeks prior to the event

- Budget

  - Communicate with NIH contact on a monthly basis prior to event, and on a weekly basis for the month prior to the event, about costs and projections

  - Provide detailed budget breakdowns, including projected staff charges

- Development of Forum Materials

  - Create name badges for all attendees and speakers

  - Prepare folders of materials for all participants to include agendas, maps, schedule of events and speakers

  - Develop placecards and signage for Thursday luncheon and dinner and ensure correct seating for each event

  - Print copies of CIST Forum Booklet for all attendees and speakers

- On-Site Logistical Arrangements

  - Greet guests upon arrival at hotel, within a specified time frame of up to five hours

  - Provide support staff member to serve as point of contact to trouble-shoot and ensure smooth functioning of all events in the agenda

- Communications

  - Maintain regular communication, by e-mail, with designated NIH contacts and obtain approvals as required

  - Send personalized thank-you letters and follow-up materials to speakers

Direct Costs:

- Airline tickets, round trip to DC:

Up to 160 participants (range of U.S. destinations @ range of contract fares)

- Subsistence – all meals to be provided; coffee and soft drink breaks on Thursday

- Ground transportation:  shuttles as needed

- Meeting supplies

- Invitations

- Conference materials

- Post-conference mailing

- Courier/freight

- Postage

- Out-of-pocket

Labor:

For pre-conference, on-site and post-conference efforts:

Hourly Rates: Program Manager, Asst. Program Manager and Support staff

NIH project officers to provide:

- Mailing lists of invitees (including complete addresses and contact information)

- Invitation copy, agenda