ASHRAE TC 7.6 System Energy Utilization

RESEARCH PLAN

February 6, 2005

RESEARCH TOPICS (listed by priority)

- Methods and tools that use data normally collected with energy management systems and O&M procedures to identify energy efficiency retrofit opportunities.

- Compare of buildings created under LEED-NC to actual performance and to LEED-EB ratings (ASHRAE 90.1 vs. Energy Star)

- Determine the technologies available for demand response and characterize what is available and how well they work.

- Develop specifications and protocols for monitoring the energy performance of buildings and their end uses.

- Provide guidance on establishing and implementing an effective, ongoing energy management program, as documented in Chapter 35 of the ASHRAE Applications Handbook.

- Update and improve the recommended methodologies and procedures for planning and completing projects to monitor energy use in buildings, as documented in Chapter 40 of the ASHRAE Applications Handbook.

RESEARCH TOPIC ACCEPTANCE REQUESTS (RTAR) Under Development

- Development of methodologies and tools to mine building data for energy efficiency opportunities.

- Research the energy performance predicted by methods in LEED-NC to actual performance and to the performance rating from Energy Star.

- Research the technologies available for demand response and characterize what is available and how well they work.

CURRENT PROJECT STATUS

- 1092-RP  Development of procedures to determine in-situ performance of commonly used HVAC systems.

- Status report delivered at review meeting.  The number of buildings used for the verification of the methods was reduced from six to five and potentially four.  There is a request for a change in scope to reduce the buildings from six to four and to expand the calculation methods.   The PI has asked for a one year no cost extension.

- 1286-TRP Evaluation of Building Energy Performance Rating Protocols.

  - Task 2 report draft completed, which reviews and compares five rating protocols.

  - contract ends 8/05.